## Milestone Status
UBS Warburg Energy LLC - "Go Live" Status Report
Date: 1/29/02
Function | Milestone | % Complete | Day Req'd | Date Sched. | Status
Legal | Hart Scott Rodino Approval Status |  | Day 0 | 2002-02-06
| Obtain 3rd party consents for Software license |  | Day 0 | 2002-02-06
| Finalize Canadian Legal Structure |  | Day 0 | 2002-02-06
HR | Finalize Offer Letter Acceptance - Houston | 90% | Day 0 | 2002-02-06
| Finalize Offer Letter Acceptance - Canada |  | Day 0 | 2002-02-06
CRE | Finalize Real Estate Lease Agreements - Houston |  | Day 0 | 2002-02-01
| Finalize Real Estate Lease Agreements - Canada |  | Day 0 | 2002-02-01
Credit Risk | Agree initial Counterparty List |  | Day 0 | 2002-01-29
| Set Credit Limits for initial Client List |  | Day 1 | 2002-02-07
FCD | Finalize Canadian Capital, Funding, and Guarantees |  | Day 0 | 2002-02-06
| Test and Validate internal infrastructure |  | Day 1 | 2002-02-08
Market Risk | EBK review of VaR models |  | Day 1 | 2002-02-07
| Define Global VaR, Stress (establish scenarios), and operational limits. |  | Day 1 | 2002-02-11
Business | Test and Validate internal infrastructure |  | Day 1 | 2002-02-08
IT | Test and Validate internal infrastructure |  | Day 1 | 2002-02-08
Operations | Test and Validate internal infrastructure |  | Day1 | 2002-02-08
Corp Comms | Send Client Notifications |  | Day 1 | 2002-02-08
On target for required completion date
At risk of missing required completion date
Will miss required completion date

## Add'l Status
Additional UBS Warburg Energy LLC Integration Status Information
Corporate Admin Services
- Temporary process in place to order office supplies
- Process in place to order Corp Amex Cards, Business Cards and Mobile phones
Security
- Access Control Process developed
- Temporary access to Enron building for UBSW employees process in place.
IT
- Conf room established with additional access lines. Conf room phone number on the web under contacts
Prog Office
- Web access available in both UBSW and UBSW Energy LLC employees
http://energy
http://ubsintegration.corp.enron.com
- Established weekly Integration team meeting Thurs 10:00 EST for both UBSW and UBSW Energy LLC
team members.
Corp Comms
- Finalizing Letter Head for initial Client Communications