## Milestone Status
UBS Warburg Energy LLC - "Go Live" Status Report
Date: 02/05/02
Function | Milestone | % Complete | Day Req'd | Date Sched. | Status
Legal | Hart Scott Rodino Approval Status |  | Day 0 | 2002-02-08 | Completed
| Obtain 3rd party consents for Software license |  | Day 0 | 2002-02-08
| Finalize Canadian Legal Structure |  | Day 0 | 2002-02-08 | Completed
HR | Finalize Offer Letter Acceptance - Houston | 100% | Day 0 | 2002-02-08 | Completed
| Finalize Offer Letter Acceptance - Canada |  | Day 0 | 2002-02-08
CRE | Finalize Real Estate Lease Agreements - Houston/ Portland |  | Day 0 | 2002-02-08
| Finalize Real Estate Lease Agreements - Canada |  | Day 0 | 2002-02-08
Credit Risk | Agree initial Counterparty List |  | Day 0 | 2002-01-29 | Completed
| Set Credit Limits for initial Client List |  | Day 1 | 2002-02-08
FCD | Finalize Canadian Capital, Funding, and Guarantees |  | Day 1 | 2002-02-08
| Test and Validate internal infrastructure |  | Day 1 | 2002-02-08
Market Risk | EBK review of VaR models |  | Day 1 | 2002-02-07
| Define Global VaR, Stress (establish scenarios), and operational limits. |  | Day 1 | 2002-02-11
Business | Complete Mock Trading |  | Day 1 | 2002-02-07
| Test and Validate internal infrastructure |  | Day 1 | 2002-02-08
IT | Test and Validate internal infrastructure |  | Day 1 | 2002-02-08
Operations | Test and Validate internal infrastructure |  | Day1 | 2002-02-08
Corp Comms | Send Client Notifications |  | Day 1 | 2002-02-08
On target for required completion date
At risk of missing required completion date
Will miss required completion date