## Graph Data Sep 24
SUMMARY BY WEEK OF | [5 empty] | 4/05-4/11 | 4/12-4/18 | 4/19-4/25 | 04/26-05/01 | 5/2/-5/9 | 5/10-5/17 | 5/18-5/25 | 5/28-6/1 | 06/04-06/08 | 06/11-06/15 | 06/18-06/22 | 06/25-06/29 | 07/02-07/05 | 07/09-07/13 | 07/16-07/20 | 07/23-07/27 | 07/30-08/03 | 08/06-08/10 | 08/13-08/17 | 8/20-8/24 | 08/27-8/31 | 09/04/-09/07 | 09/10-09/14 | 09/17-09/21 | 09/24-09/28
Deal Capture | [6 empty] | 2 |  | 1 | [5 empty] | 1 | [12 empty] | 1 | 2 | 2
Deal Valuation | [12 empty] | 1 |  | 1 |  | 2 |  | 1 | [10 empty] | 1
Breakdown in Officializing Process- Human | [5 empty] | 30 | 6 | 10 | 19 | 13 | 7 | 2 | 8 | 5 | 6 | 6 | 9 | 5 |  |  |  | 17 | 12 | 5 | 4 | 8 | 11 | 4 | 6 | 4
Breakdown in Officializing Process- IT(UK) | [5 empty] | 5 | 3 | 3 | 2 | 6 | 5 | 6 | 4 | 5 | 2 | 4 | 3 | 1 | 12 | 9 | 9 | 4 | 5 | 5 | 3 | 6 | 4 | 3 | 6 | 4
Breakdown in Officializing Process- IT (US) | [5 empty] | 2 | 4 | 1 | 3 |  |  | 1 |  | 1 | 3 |  |  |  | 5 | 5 | 5 | 1 | 1 | 2 |  | 1 |  | 2
Curve Issues | [5 empty] | 3 | [5 empty] | 1 | 1 | 3 |  | 1 | 5 | 1 | 3 |  |  | 2 | 1 | 2 |  | 3 | 1 | 1
Uncontrollable-System Needs to Change | [5 empty] | 4 | 1 | 5 | 1 | 2 | 1 |  | 3 |  | 3 | 1 |  |  | 2 |  | 2 |  | 1 | 1 | 3 | 2
Miscellaneous | [9 empty] | 1 |  | 1 |  | 2 |  | 4 | 7 |  |  |  | 2 | 3 | 3 | 2 | 3 | 2 | 1 |  | 1 | 3
Not identified | [17 empty] | 1 |  | 1 | 1 | 2 | 1 |  | 1 | 1 | 1 |  | 1
Total Errors for the Week | [5 empty] | 44 | 16 | 19 | 26 | 22 | 13 | 11 | 17 | 16 | 16 | 16 | 26 | 8 | 23 | 15 | 19 | 29 | 24 | 17 | 14 | 23 | 18 | 11 | 16 | 14
SUMMARY BY WEEK OF | [5 empty] | 2001-04-05 | 2001-04-12 | 2001-04-19 | 2001-04-26 | 2001-05-02 | 2001-05-10 | 2001-05-18 | 2001-05-28 | 2001-06-04 | 2001-06-11 | 2001-06-18 | 2001-06-25 | 2001-07-02 | 2001-07-09 | 2001-07-16 | 2001-07-23 | 2001-07-30 | 2001-08-06 | 2001-08-13 | 2001-08-20 | 2001-08-27 | 2001-09-04 | 2001-09-10 | 2001-09-17 | 2001-09-24
EIM | [5 empty] | 2001-08-13: 3; 2001-08-20: 1; 2001-09-04: 3; 2001-09-10: 2; 2001-09-17: 3; 2001-09-24: 8 | EIM
EGM | [5 empty] | 2001-08-06: 14; 2001-08-13: 3; 2001-08-20: 8; 2001-08-27: 2; 2001-09-04: 9; 2001-09-10: 17; 2001-09-17: 57; 2001-09-24: 16 | EGM
EBS | [30 empty] | EBS
EEL | [30 empty] | EEL
EES | [30 empty] | EES
EAM | [5 empty] | 2001-08-06: 6; 2001-08-13: 7; 2001-08-20: 3; 2001-08-27: 11; 2001-09-04: 1; 2001-09-10: 17; 2001-09-17: 6; 2001-09-24: 5 | EAM
Book creation | [5 empty] | 2001-08-06: 20; 2001-08-13: 13; 2001-08-20: 12; 2001-08-27: 13; 2001-09-04: 13; 2001-09-10: 36; 2001-09-17: 66; 2001-09-24: 29 | Total Books Created
Curve Creation | [30 empty] | Curve Creation
LOG OF WEEKLY VALUATION ISSUES
CLASS
A - Deal Capture
B - Deal Valuation
C - Breakdown in transfer of data to RiskTrac (Officializing Process) - Human
D1 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (UK)
D2 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (US)
E - Curve Issues
F - No ones fault. System needs to change.
G - Other
H - Not identified.
|  |  |  | RESPONSIBLE |  | 2001-04-19: VAR; 2001-04-26: CREDIT; 2001-05-02: IMPACT CASH; 2001-05-10: STATUS
DATE | BOOK/AREA | Group | COMMODITY/OFFICE | PARTY | CLASS | 2001-04-05: PROBLEM; 2001-04-12: ACTION PLAN; 2001-04-19: RERUN?; 2001-04-26: AFFECTED?; 2001-05-02: FLOWS?; 2001-05-10: (DATE)
2001-09-28 | Paper VaR | EIM | US PAPER | Kristen Hanson | A | 2001-04-05: Positions were incorrect. Data was updated and VaR rerun.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-28 | Power VaR | EA | Power East | Stacey White | A | 2001-04-05: Canada Alberta GAS Positions were incorrect. Data updated and VaR rerun.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-28 | EAF-AUS-SRA-PRC | EEL | AUSTRALIA POWER | HEIDI MASON | C | 2001-04-05: Book was not officialized for COB Sep 28; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-09-28 | UK-EBS Credit file | EEL | UK EBS | Niel Tarling | G | 2001-04-05: Credit file not transmitted within schedule.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-28 | UK POWER | EEL | UK Power | James New | D1 | 2001-04-05: Due to increased volumes associated with Month End the book finished processing into RisktRAC late.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-27 | Unify Gas Credit Feed |  |  |  | G | 2001-04-05: Credit feed not received as schedule. Data provided later.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-26 | EPMI-W-BIO-INV-PRC; EPMI-W-BIO-PRC; EPMI-W-GEO-INV-PRC; WPMI-W-GEO-PRC; EPMI-W-WIND-INV-PRC | EA | US POWER WEST | Stacey White | C | 2001-04-05: Due to an attribute change in region codes data was not captured by RisktRAC. Working to resolve.; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: Y; 2001-05-10: Done
2001-09-26 | OPTIONS-EXOTIC-PRC | EA | US GAS FIN | Jeff Gossett | C | 2001-04-05: Book was not officialized. No impact on VaR as book only contains premium related to options reported on XL sheet upload.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-25 | Lisa Lumber Settlements feed | EIM | US Lumber | Mike Moscoso | G | 2001-04-05: Credit feed file not transmitted. Data provided late.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-25 | Continental Power | EEL | UK Power | James New | D1 | 2001-04-05: Due to improper documentation used to schedule Dove calc MTM process resulted in data for incorrect COB data. Code correct and MtM rerun for COB 25. Data loaded late into RisktRAC.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-25 | UK Power; Eastern SS 1&2; UKPWRSWAP1 | EEL | UK Power | James New | D1 | 2001-04-05: Due to improper documentation used to schedule Dove calc MTM process resulted in data for incorrect COB data. No COB 25 data positions and values rolled from COB Sep 24th.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-24 | NG-PRICE-GDL | EA | US GAS FIN | Jeff Gossett | C | 2001-04-05: Due to attribute mismatch the book data was not captured by RisktRAC. VaR was rerun once data loaded into RisktRAC.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-24 | Continental Power | EEL | Continental Power | James New | B | 2001-04-05: Due to an upstream change in Continental Power the Price curve is based on COB Sep 21. Downstream users not advised; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-24 | UK POWER, Eastern Spreadsheets 1 & 2 | EEL | UK Power | James New | D1 | 2001-04-05: UK Power was officialized late due to code change for server that was inconsistent with Dove calc. Process corrected. Spreadsheets data rolled from COB Sep 20th due to dependence on UK Power.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
SUMMARY FOR 05/28 - 06/01 BY GROUP | % of Total Errors for the Week | # of errors | # Active books by group | Ratio of Errors to Active Books
EIM | 14.29% | 2 | 70 | 2.8571
EGM | 0% | 0 | 730 | 0
EEL | 57.14% | 8 | 42 | 19.0476
EA-CAN | 0% | 0 | 40 | 0
EA - GAS | 14.29% | 2 | 466 | 0.42918
EA - POWER | 7.143% | 1 | 173 | 0.57803
EES | 0% | 0 | 9 | 0
EBS | 0% | 0 | 17 | 0
OTHER | 7.143% | 1
TOTAL | 100% | 14 | 1547
Qtr end reporting

## summary 0924
SUMMARY BY WEEK FOR 09/04-09/07
TOTAL ISSUES |  |  | 14
Category | Description
A | Deal Capture |  | 2
B | Deal Valuation |  | 1
C | Breakdown in Officializing Process- Human |  | 4
D1 | Breakdown in Officializing Process- IT (UK) |  | 4
D2 | Breakdown in Officializing Process- IT (US)
E | Curve Issues
F | Uncontrollable-System Needs to Change
G | Miscellaneous |  | 3
H | Not identified
Breakdown By Group |  | # of Issues | Biggest Problem
EIM |  | 2
EGM
EEL |  | 8
EA-CAN
EA - GAS |  | 2
EA - POWER |  | 1
EES
EBS
Other |  | 1
TOTAL ISSUES |  | 14

## Graph Data Sep 17
SUMMARY BY WEEK OF | [5 empty] | 4/05-4/11 | 4/12-4/18 | 4/19-4/25 | 04/26-05/01 | 5/2/-5/9 | 5/10-5/17 | 5/18-5/25 | 5/28-6/1 | 06/04-06/08 | 06/11-06/15 | 06/18-06/22 | 06/25-06/29 | 07/02-07/05 | 07/09-07/13 | 07/16-07/20 | 07/23-07/27 | 07/30-08/03 | 08/06-08/10 | 08/13-08/17 | 8/20-8/24 | 08/27-8/31 | 09/04/-09/07 | 09/10-09/14 | 09/17-09/21
Deal Capture | [6 empty] | 2 |  | 1 | [5 empty] | 1 | [12 empty] | 1 | 2
Deal Valuation | [12 empty] | 1 |  | 1 |  | 2 |  | 1
Breakdown in Officializing Process- Human | [5 empty] | 30 | 6 | 10 | 19 | 13 | 7 | 2 | 8 | 5 | 6 | 6 | 9 | 5 |  |  |  | 17 | 12 | 5 | 4 | 8 | 11 | 4 | 6
Breakdown in Officializing Process- IT(UK) | [5 empty] | 5 | 3 | 3 | 2 | 6 | 5 | 6 | 4 | 5 | 2 | 4 | 3 | 1 | 12 | 9 | 9 | 4 | 5 | 5 | 3 | 6 | 4 | 3 | 6
Breakdown in Officializing Process- IT (US) | [5 empty] | 2 | 4 | 1 | 3 |  |  | 1 |  | 1 | 3 |  |  |  | 5 | 5 | 5 | 1 | 1 | 2 |  | 1 |  | 2
Curve Issues | [5 empty] | 3 | [5 empty] | 1 | 1 | 3 |  | 1 | 5 | 1 | 3 |  |  | 2 | 1 | 2 |  | 3 | 1 | 1
Uncontrollable-System Needs to Change | [5 empty] | 4 | 1 | 5 | 1 | 2 | 1 |  | 3 |  | 3 | 1 |  |  | 2 |  | 2 |  | 1 | 1 | 3 | 2
Miscellaneous | [9 empty] | 1 |  | 1 |  | 2 |  | 4 | 7 |  |  |  | 2 | 3 | 3 | 2 | 3 | 2 | 1 |  | 1
Not identified | [17 empty] | 1 |  | 1 | 1 | 2 | 1 |  | 1 | 1 | 1 |  | 1
Total Errors for the Week | [5 empty] | 44 | 16 | 19 | 26 | 22 | 13 | 11 | 17 | 16 | 16 | 16 | 26 | 8 | 23 | 15 | 19 | 29 | 24 | 17 | 14 | 23 | 18 | 11 | 16
SUMMARY BY WEEK OF | [5 empty] | 2001-04-05 | 2001-04-12 | 2001-04-19 | 2001-04-26 | 2001-05-02 | 2001-05-10 | 2001-05-18 | 2001-05-28 | 2001-06-04 | 2001-06-11 | 2001-06-18 | 2001-06-25 | 2001-07-02 | 2001-07-09 | 2001-07-16 | 2001-07-23 | 2001-07-30 | 2001-08-06 | 2001-08-13 | 2001-08-20 | 2001-08-27 | 2001-09-04 | 2001-09-10 | 2001-09-17
EIM | [5 empty] | 2001-08-13: 3; 2001-08-20: 1; 2001-09-04: 3; 2001-09-10: 2; 2001-09-17: 3 | EIM
EGM | [5 empty] | 2001-08-06: 14; 2001-08-13: 3; 2001-08-20: 8; 2001-08-27: 2; 2001-09-04: 9; 2001-09-10: 17; 2001-09-17: 57 | EGM
EBS | [29 empty] | EBS
EEL | [29 empty] | EEL
EES | [29 empty] | EES
EAM | [5 empty] | 2001-08-06: 6; 2001-08-13: 7; 2001-08-20: 3; 2001-08-27: 11; 2001-09-04: 1; 2001-09-10: 17; 2001-09-17: 6 | EAM
Book creation | [5 empty] | 2001-08-06: 20; 2001-08-13: 13; 2001-08-20: 12; 2001-08-27: 13; 2001-09-04: 13; 2001-09-10: 36; 2001-09-17: 66 | Total Books Created
Curve Creation | [29 empty] | Curve Creation
LOG OF WEEKLY VALUATION ISSUES
CLASS
A - Deal Capture
B - Deal Valuation
C - Breakdown in transfer of data to RiskTrac (Officializing Process) - Human
D1 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (UK)
D2 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (US)
E - Curve Issues
F - No ones fault. System needs to change.
G - Other
H - Not identified.
|  |  |  | RESPONSIBLE |  | 2001-04-19: VAR; 2001-04-26: CREDIT; 2001-05-02: IMPACT CASH; 2001-05-10: STATUS
DATE | BOOK/AREA | Group | COMMODITY/OFFICE | PARTY | CLASS | 2001-04-05: PROBLEM; 2001-04-12: ACTION PLAN; 2001-04-19: RERUN?; 2001-04-26: AFFECTED?; 2001-05-02: FLOWS?; 2001-05-10: (DATE)
2001-09-21 | EBS-BWT-PRC | EEL | UK EBS | Niel Tarling | G | 2001-04-05: Credit file was not appropriately saved for processing. .; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-21 | UK Gas/ Eastern SS 1 &2 | EEL | UK Power | James New | D1 | 2001-04-05: Reran MTM process as original process generated inconsistent numbers. However, change was due to change in deals. Eastern SS rolled due to dependence on UK GAS mtm values.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-21 | Uk Power | EEL | UK Power | James New | D1 | 2001-04-05: Book was officialized twice as initial process feed data to incorrect books. Issue was caused to temporary rename of portfolios.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-21 | FRT-DIESEL-PRC; FRT-FWD-TXFR-PRC; FRT-HO-PRC; FRT-LC-PRC; FRT-MIDWEST-BAS; FRT-MIDWEST-PRC; FRT-MOUNTAIN-BAS; FRT-MOUNTAIN-PRC; FRT-NORTHEAST-BAS; FRT-NORTHEAST-PRC; FRT-NORTHWEST-BAS; FRT-NORTHWEST-PRC; FRT-OHIO-BAS; FRT-OHIO-PRC; FRT-SOUTHCENT-BAS;FRT-SOUTHCENT-PRC; FRT-SOUTHEAST-BAS; FRT-SOUTHEAST-PRC; FRT-UCF-PRC; FRT-WEST-BAS; FRT-WEST-PRC; FRT-WTI-PRC | EGM | US Freight | Sheri Thompson | C | 2001-04-05: Books were not officialized.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-20 | UK Gas | EEL | UK Gas | James New | H | 2001-04-05: During officialization process system generated an error message so process was reinitiated.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-20 | Nordic Power | EEL | Nordic Power | James New | A | 2001-04-05: Book was officialized late due to incorrect deal entry. Data was reentered and book was reofficialized.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-20 | UK Power/ Spreadsheet and Eastern Spreadsheets 1 & 2 | EEL | UK Power | James New | D1 | 2001-04-05: The Dove calc process failed due to a virus detected by systems. Manual process reinitiated and data updated. Spreadsheets late due to reliance on Dove Calc.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-19 | UK Power/Spreadsheet | EEL | UK Power | James New | D1 | 2001-04-05: The Dove calc process failed due to unsynchronized clocks. This caused delay in MTM process for spreadsheets and UK Power. Process was reinitiated and books officilized; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-19 | Continental Power | EEL | Continental Power | James New | D1 | 2001-04-05: Book was officialized late due to simultaneous running; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-18 | PWR-NG-ST-NENG-GDI;GDL | EA | US Power East | Stacey White | C | 2001-04-05: The book attributes did not agree with book request. This prevented capture of data. Attributes have been resolved. Due to the immaterial values contained within the book VaR and Credit not rerun.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: Y; 2001-05-10: Done
2001-09-18 | FRT-SPOT-BAS; FRT-SPOT-PRC | EGM | US Freight | Todd Hall | C | 2001-04-05: Books not officialized until AM; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-18 | LNG-PRICE-BAS; IDX;PRC | EGM | US LNG |  | C | 2001-04-05: Books not officialed until AM; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-18 | Zinc Deal Between EM-ENA-Galvak(Mex) | EGM |  | Todd Hall | A | 2001-04-05: Deal was completed on Aug 31st, but not entered into RisktRAC until Sep 17th.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-17 | FRT-EXOTIC-PRC | EGM | US Freight | Todd Hall | C | 2001-04-05: Spreadsheet was not loaded into RisktRAC. Uploaded in the AM and VaR; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-17 | UK Credit Trading | EEL |  | James New | C | 2001-04-05: Credit spreadsheet was not completed by deadline.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-17 | Continental Power | EEL | Continental Power | James New | D1 | 2001-04-05: The MTM process failed due to unsynchronized time clocks. This prevented curve load process. Problem resolved and process reinitiated.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
SUMMARY FOR 05/28 - 06/01 BY GROUP | % of Total Errors for the Week | # of errors | # Active books by group | Ratio of Errors to Active Books
EIM | 0% | 0 | 62 | 0
EGM | 31.25% | 5 | 714 | 0.70028
EEL | 62.5% | 10 | 42 | 23.8095
EA-CAN | 0% | 0 | 40 | 0
EA - GAS | 0% | 0 | 466 | 0
EA - POWER | 6.25% | 1 | 168 | 0.59524
EES | 0% | 0 | 9 | 0
EBS | 0% | 0 | 17 | 0
OTHER | 0% | 0
TOTAL | 100% | 16 | 1518
Qtr end reporting

## summary 0917
SUMMARY BY WEEK FOR 09/04-09/07
TOTAL ISSUES |  |  | 16
Category | Description
A | Deal Capture |  | 2
B | Deal Valuation
C | Breakdown in Officializing Process- Human |  | 6
D1 | Breakdown in Officializing Process- IT (UK) |  | 6
D2 | Breakdown in Officializing Process- IT (US)
E | Curve Issues
F | Uncontrollable-System Needs to Change
G | Miscellaneous |  | 1
H | Not identified |  | 1
Breakdown By Group |  | # of Issues | Biggest Problem
EIM
EGM |  | 5
EEL |  | 10
EA-CAN
EA - GAS
EA - POWER |  | 1
EES
EBS
Other
TOTAL ISSUES |  | 16

## Graph Data Sep 10
SUMMARY BY WEEK OF | [5 empty] | 4/05-4/11 | 4/12-4/18 | 4/19-4/25 | 04/26-05/01 | 5/2/-5/9 | 5/10-5/17 | 5/18-5/25 | 5/28-6/1 | 06/04-06/08 | 06/11-06/15 | 06/18-06/22 | 06/25-06/29 | 07/02-07/05 | 07/09-07/13 | 07/16-07/20 | 07/23-07/27 | 07/30-08/03 | 08/06-08/10 | 08/13-08/17 | 8/20-8/24 | 08/27-8/31 | 09/04/-09/07 | 09/10-09/14
Deal Capture | [6 empty] | 2 |  | 1 | [5 empty] | 1 | [12 empty] | 1
Deal Valuation | [12 empty] | 1 |  | 1 |  | 2 |  | 1
Breakdown in Officializing Process- Human | [5 empty] | 30 | 6 | 10 | 19 | 13 | 7 | 2 | 8 | 5 | 6 | 6 | 9 | 5 |  |  |  | 17 | 12 | 5 | 4 | 8 | 11 | 4
Breakdown in Officializing Process- IT(UK) | [5 empty] | 5 | 3 | 3 | 2 | 6 | 5 | 6 | 4 | 5 | 2 | 4 | 3 | 1 | 12 | 9 | 9 | 4 | 5 | 5 | 3 | 6 | 4 | 3
Breakdown in Officializing Process- IT (US) | [5 empty] | 2 | 4 | 1 | 3 |  |  | 1 |  | 1 | 3 |  |  |  | 5 | 5 | 5 | 1 | 1 | 2 |  | 1 |  | 2
Curve Issues | [5 empty] | 3 | [5 empty] | 1 | 1 | 3 |  | 1 | 5 | 1 | 3 |  |  | 2 | 1 | 2 |  | 3 | 1 | 1
Uncontrollable-System Needs to Change | [5 empty] | 4 | 1 | 5 | 1 | 2 | 1 |  | 3 |  | 3 | 1 |  |  | 2 |  | 2 |  | 1 | 1 | 3 | 2
Miscellaneous | [9 empty] | 1 |  | 1 |  | 2 |  | 4 | 7 |  |  |  | 2 | 3 | 3 | 2 | 3 | 2 | 1
Not identified | [17 empty] | 1 |  | 1 | 1 | 2 | 1 |  | 1 | 1 | 1
Total Errors for the Week | [5 empty] | 44 | 16 | 19 | 26 | 22 | 13 | 11 | 17 | 16 | 16 | 16 | 26 | 8 | 23 | 15 | 19 | 29 | 24 | 17 | 14 | 23 | 18 | 11
SUMMARY BY WEEK OF | [5 empty] | 2001-04-05 | 2001-04-12 | 2001-04-19 | 2001-04-26 | 2001-05-02 | 2001-05-10 | 2001-05-18 | 2001-05-28 | 2001-06-04 | 2001-06-11 | 2001-06-18 | 2001-06-25 | 2001-07-02 | 2001-07-09 | 2001-07-16 | 2001-07-23 | 2001-07-30 | 2001-08-06 | 2001-08-13 | 2001-08-20 | 2001-08-27 | 2001-09-04 | 2001-09-10
EIM | [5 empty] | 2001-08-13: 3; 2001-08-20: 1; 2001-09-04: 3; 2001-09-10: 2 | EIM
EGM | [5 empty] | 2001-08-06: 14; 2001-08-13: 3; 2001-08-20: 8; 2001-08-27: 2; 2001-09-04: 9; 2001-09-10: 17 | EGM
EBS | [28 empty] | EBS
EEL | [28 empty] | EEL
EES | [28 empty] | EES
EAM | [5 empty] | 2001-08-06: 6; 2001-08-13: 7; 2001-08-20: 3; 2001-08-27: 11; 2001-09-04: 1; 2001-09-10: 17 | EAM
Book creation | [5 empty] | 2001-08-06: 20; 2001-08-13: 13; 2001-08-20: 12; 2001-08-27: 13; 2001-09-04: 13; 2001-09-10: 36 | Total Books Created
Curve Creation | [28 empty] | Curve Creation
LOG OF WEEKLY VALUATION ISSUES
CLASS
A - Deal Capture
B - Deal Valuation
C - Breakdown in transfer of data to RiskTrac (Officializing Process) - Human
D1 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (UK)
D2 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (US)
E - Curve Issues
F - No ones fault. System needs to change.
G - Other
H - Not identified.
|  |  |  | RESPONSIBLE |  | 2001-04-19: VAR; 2001-04-26: CREDIT; 2001-05-02: IMPACT CASH; 2001-05-10: STATUS
DATE | BOOK/AREA | Group | COMMODITY/OFFICE | PARTY | CLASS | 2001-04-05: PROBLEM; 2001-04-12: ACTION PLAN; 2001-04-19: RERUN?; 2001-04-26: AFFECTED?; 2001-05-02: FLOWS?; 2001-05-10: (DATE)
2001-09-14 | PHYSOIL-EVERGREE-PRC;EGLI-C2MW-PRC; EGLI-C3MW-PRC; EGLI-C5MW-PRC; EGLI-NC4NW-PRC; EGLI-FEES-PRC; C3-PRC; C5+-BRNT-HEDGE-PRC; NAPTHA-UR-PRC; C3-CAND-EGSC-PRC; C3-UR-PRC;EGLI-C2GC-PRC; PHYSOIL2-IDX; PHYSOIL-PRICE-PRC;C2-PRC | EGM | US Global Products | Todd Hall | E | 2001-04-05: Due to curve data update, books were reofficialized. Due to the immaterial change in P&L, VaR was not rerun. Change in P&L will be captured in COB S EP 17 DPR. Credit was notified.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-14 | Lisa Lumber Settlements feed | EIM | US Lumber | Mike Moscoso | C | 2001-04-05: Prior responsible party out of office and backup did not follow instructions for file feed. Data was uploaded late into CAS.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-14 | STEEL VaR | EIM | Steel | Shelly Wood | A | 2001-04-05: Due to incorrect deal capture positions were incorrect. Data was corrected and VaR rerun.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-14 | DUB-EESEAM-XL-BAS, DUB-EESEAM-XL-PRC, DUB-ERMS-XL-BAS, DUB-ERMS-XL-PRC, DUB-INT-PHY, DUB-OPT-BAS , DUB-OPT-PRC | EES | US EES GAS | Scott Mills | C | 2001-04-05: Books were not officialized. Books were officialized in the AM. Credit not impacted as they receive a separate credit file.; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-09-14 | UK 4 File Feeds |  |  | RisktRAC IT | D2 | 2001-04-05: While the File was sent on time by London, it was not processed until after 6 am VaR run. Due to certain systems upgrades, RistRAC database was brought down. Files were processed from the que and captured by 8 am VaR run.; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-09-14 | LNG-PRICE-PRC. LNG-PRICE-BAS, LNG-PRICE-IDX | EGM | LNG | John Swinney | C | 2001-04-05: Book was not officialized. Process completed in the AM and VaR Rerun.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-13 | EPMI-LT-NAMGMT-PRC; EPMI-LT-WNAMGMT-PRC | EA | US GAS FIN | KLOIBL | C | 2001-04-05: BA forgot to officialize. Books were officialized in the AM; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-09-13 | EAF-AUS-SRA-PRC | EEL | AUSTRALIA POWER | HEIDI MASON | D1 | 2001-04-05: BA initiated uploaded process and received no error message. Assumed data had been captured. Due to process of upload, through terminal server, connection may have been lost which prevented deal capture.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-09-13 | Continental Power | EEL | Continental Power | James New | A | 2001-04-05: 4 Deals were entered incorrectly, which caused a 14 twh discrepancy. 1 new curve was not properly set up, which caused mtm to fail. Data was corrected and process reiniated. File was subsequently retransmitted to R isktRAC.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-12 | Continental Power | EEL | Continental Power | James New | D1 | 2001-04-05: Continental Power MTM process failed due to an inability of process to access curver server. Issue identified to be curve server had not finished processing when MTM process is requesting data. To prevent further problems pushed back MTM process 30 minutes.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-09-10 | UK Power; Eastern Spreadsheets; UK Power SS | EEL | UK Power | James New | D1 | 2001-04-05: Due to bad data that corrupted the valuation process the MTM failed. Data was corrected and process re-initated for all books.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
SUMMARY FOR 05/28 - 06/01 BY GROUP | % of Total Errors for the Week | # of errors | # Active books by group | Ratio of Errors to Active Books
EIM | 18.18% | 2 | 59 | 3.3898
EGM | 18.18% | 2 | 657 | 0.30441
EEL | 36.36% | 4 | 42 | 9.5238
EA-CAN | 0% | 0 | 38 | 0
EA - GAS | 9.091% | 1 | 466 | 0.21459
EA - POWER | 0% | 0 | 164 | 0
EES | 9.091% | 1 | 9 | 11.1111
EBS | 0% | 0 | 17 | 0
OTHER | 9.091% | 1
TOTAL | 100% | 11 | 1452
Qtr end reporting

## summary 0910
SUMMARY BY WEEK FOR 09/04-09/07
TOTAL ISSUES |  |  | 11
Category | Description
A | Deal Capture |  | 1
B | Deal Valuation
C | Breakdown in Officializing Process- Human |  | 4
D1 | Breakdown in Officializing Process- IT (UK) |  | 3
D2 | Breakdown in Officializing Process- IT (US) |  | 2
E | Curve Issues |  | 1
F | Uncontrollable-System Needs to Change
G | Miscellaneous
H | Not identified
Breakdown By Group |  | # of Issues | Biggest Problem
EIM |  | 2
EGM |  | 2
EEL |  | 4
EA-CAN
EA - GAS |  | 1
EA - POWER
EES |  | 1
EBS
Other |  | 1
TOTAL ISSUES |  | 11

## Graph Data Sep 04
SUMMARY BY WEEK OF | [5 empty] | 4/05-4/11 | 4/12-4/18 | 4/19-4/25 | 04/26-05/01 | 5/2/-5/9 | 5/10-5/17 | 5/18-5/25 | 5/28-6/1 | 06/04-06/08 | 06/11-06/15 | 06/18-06/22 | 06/25-06/29 | 07/02-07/05 | 07/09-07/13 | 07/16-07/20 | 07/23-07/27 | 07/30-08/03 | 08/06-08/10 | 08/13-08/17 | 8/20-8/24 | 08/27-8/31 | 09/04/-09/07
Deal Capture | [6 empty] | 2 |  | 1 | [5 empty] | 1
Deal Valuation | [12 empty] | 1 |  | 1 |  | 2 |  | 1
Breakdown in Officializing Process- Human | [5 empty] | 30 | 6 | 10 | 19 | 13 | 7 | 2 | 8 | 5 | 6 | 6 | 9 | 5 |  |  |  | 17 | 12 | 5 | 4 | 8 | 11
Breakdown in Officializing Process- IT(UK) | [5 empty] | 5 | 3 | 3 | 2 | 6 | 5 | 6 | 4 | 5 | 2 | 4 | 3 | 1 | 12 | 9 | 9 | 4 | 5 | 5 | 3 | 6 | 4
Breakdown in Officializing Process- IT (US) | [5 empty] | 2 | 4 | 1 | 3 |  |  | 1 |  | 1 | 3 |  |  |  | 5 | 5 | 5 | 1 | 1 | 2 |  | 1
Curve Issues | [5 empty] | 3 | [5 empty] | 1 | 1 | 3 |  | 1 | 5 | 1 | 3 |  |  | 2 | 1 | 2 |  | 3 | 1
Uncontrollable-System Needs to Change | [5 empty] | 4 | 1 | 5 | 1 | 2 | 1 |  | 3 |  | 3 | 1 |  |  | 2 |  | 2 |  | 1 | 1 | 3 | 2
Miscellaneous | [9 empty] | 1 |  | 1 |  | 2 |  | 4 | 7 |  |  |  | 2 | 3 | 3 | 2 | 3 | 2 | 1
Not identified | [17 empty] | 1 |  | 1 | 1 | 2 | 1 |  | 1 | 1 | 1
Total Errors for the Week | [5 empty] | 44 | 16 | 19 | 26 | 22 | 13 | 11 | 17 | 16 | 16 | 16 | 26 | 8 | 23 | 15 | 19 | 29 | 24 | 17 | 14 | 23 | 18
SUMMARY BY WEEK OF | [5 empty] | 2001-04-05 | 2001-04-12 | 2001-04-19 | 2001-04-26 | 2001-05-02 | 2001-05-10 | 2001-05-18 | 2001-05-28 | 2001-06-04 | 2001-06-11 | 2001-06-18 | 2001-06-25 | 2001-07-02 | 2001-07-09 | 2001-07-16 | 2001-07-23 | 2001-07-30 | 2001-08-06 | 2001-08-13 | 2001-08-20 | 2001-08-27 | 2001-09-04
EIM | [5 empty] | 2001-08-13: 3; 2001-08-20: 1; 2001-09-04: 3 | EIM
EGM | [5 empty] | 2001-08-06: 14; 2001-08-13: 3; 2001-08-20: 8; 2001-08-27: 2; 2001-09-04: 9 | EGM
EBS | [27 empty] | EBS
EEL | [27 empty] | EEL
EES | [27 empty] | EES
EAM | [5 empty] | 2001-08-06: 6; 2001-08-13: 7; 2001-08-20: 3; 2001-08-27: 11; 2001-09-04: 1 | EAM
Book creation | [5 empty] | 2001-08-06: 20; 2001-08-13: 13; 2001-08-20: 12; 2001-08-27: 13; 2001-09-04: 13 | Total Books Created
Curve Creation | [27 empty] | Curve Creation
LOG OF WEEKLY VALUATION ISSUES
CLASS
A - Deal Capture
B - Deal Valuation
C - Breakdown in transfer of data to RiskTrac (Officializing Process) - Human
D1 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (UK)
D2 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (US)
E - Curve Issues
F - No ones fault. System needs to change.
G - Other
H - Not identified.
|  |  |  | RESPONSIBLE |  | 2001-04-19: VAR; 2001-04-26: CREDIT; 2001-05-02: IMPACT CASH; 2001-05-10: STATUS
DATE | BOOK/AREA | Group | COMMODITY/OFFICE | PARTY | CLASS | 2001-04-05: PROBLEM; 2001-04-12: ACTION PLAN; 2001-04-19: RERUN?; 2001-04-26: AFFECTED?; 2001-05-02: FLOWS?; 2001-05-10: (DATE)
2001-09-07 | Advertising VaR | EBS | US EBS | Kristin Albrecht | C | 2001-04-05: Due to incorrect positions, data was reloaded. VaR and CAS rerun.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-07 | FREIGHT-IDX; FREIGHT-VS1-PRC | EGM | US Global Products | Todd Hall | C | 2001-04-05: Books wer e not officialized during end of day process. Officialized in the AM.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-07 | FRT-EXOTIC-PRC | EGM | US Freight | Todd Hall | C | 2001-04-05: Book was not officed during end of day process. Uploaded in the AM.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-07 | Continental Power | EEL | Continental Power | James New | D1 | 2001-04-05: Due to weekend power outage and continuing server issues, the server was unable to connect to the enPower curver FTP Server. Server efforts to reconnect failed, which caused the late officialization and upload of book into RisktRAC.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-07 | EAF-AUS-SRA-PRC | EEL | Australia Power | Heidi Mason | D1 | 2001-04-05: Book was officialized with effective date of Sep 9 for COB Sep 7. IT moved data to appropriate date. As VaR calculated by local office there was no impact on VaR. Credit exposure is managed at local office.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-09-06 | UK Gas/ Nordic Power | EEL | UK Gas | James New | D1 | 2001-04-05: Due to incorrect curve data, which had to be updated, mtm process had to be rerun. Books loaded late and VaR was rerun.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-06 | FT-REGS-GDI | EA | US Gas West | Jeff Gossett | C | 2001-04-05: Book was officialized with an incorrect effective date. Book was reofficialized. Book has no 3rd party credit exposure.; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: Y; 2001-05-10: Done
2001-09-06 | FT-IM-ENOV-GDL; INTRA-EMWNSS2-GDL | EA | US Ennovate |  | C | 2001-04-05: Books were not officialized.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-06 | STEEL-HUNTCO-SG-PRC | EIM | US STEEL | Shelly Wood | C | 2001-04-05: Book had flat positions, so there was no impact on VaR, however there was credit exposure.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-06 | EAF-AUS-SRA-PRC | EEL | Australia Power | James New | H | 2001-04-05: Due to IT issues the spreadsheet could not be uploaded correctly. Issue was identified and resolved subsequently. As the book currently has no positions or 3rd party exposure VaR or CAS were not rerun; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-09-05 | CR-AGG-EES-RPS-PRC | EES | EES Power | Scott Mills | C | 2001-04-05: Credit file not transmitted within schedule.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-05 | UK Power & Continental Power | EEL | UK Power | James New | D1 | 2001-04-05: Due to IT issues associated with Outlook the Extract process had to be kicked off Manually.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-04 | PAPER-AFF-PRC; PAPER-CAND-NWSP-PRC; PAPER-CONSOL-PRC; PAPER-IDX | EIM | US PAPER | Kristen Hanson | C | 2001-04-05: Books were not officialized during end of day process.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-04 | EIM-US-PAPER-PRC | EIM | US PAPER | Kristen Hanson | C | 2001-04-05: Books were not officialized during end of day process.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-09-04 | DUB-OPT-BAS; DUB-OPT-PRC; DUB-EESEAM-XL-BAS; DUB-EESEAM-XL-PRC; | EES | US EES GAS | Scott Mills | C | 2001-04-05: Books were not officialized during end of day process.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-04 | FRT-EXOTIC-PRC | EGM | US Freight | Brent Price | C | 2001-04-05: Spreadsheet was not loaded into RisktRAC. Uploaded in the AM and VaR; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-04 | UK Power & Eastern SS | EEL | UK Power | James New | E | 2001-04-05: EnPower curves were not saved out properly, which caused the MtM process to fail. Data was corrected and process reiniated. Due to the UK Power failure the Eastern SS process, which is dependent on UK Power process, did not function properly. Eastern SS was rerun and uploaded later in the day.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-09-04 | UK Coal Positions |  |  |  | G | 2001-04-05: Coal Positions were doubled due to a duplicate child portfolio within Hierarchy structure. There was no impact for credit as the positions mtm was only brought in once.; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
SUMMARY FOR 05/28 - 06/01 BY GROUP | % of Total Errors for the Week | # of errors | # Active books by group | Ratio of Errors to Active Books
EIM | 16.67% | 3 | 57 | 5.2632
EGM | 16.67% | 3 | 640 | 0.46875
EEL | 33.33% | 6 | 42 | 14.2857
EA-CAN | 0% | 0 | 38 | 0
EA - GAS | 11.11% | 2 | 452 | 0.44248
EA - POWER | 0% | 0 | 161 | 0
EES | 11.11% | 2 | 9 | 22.2222
EBS | 5.556% | 1 | 17 | 5.8824
OTHER | 5.556% | 1
TOTAL | 100% | 18 | 1416
Qtr end reporting

## summary 0904
SUMMARY BY WEEK FOR 09/04-09/07
TOTAL ISSUES |  |  | 18
Category | Description
A | Deal Capture
B | Deal Valuation
C | Breakdown in Officializing Process- Human |  | 11
D1 | Breakdown in Officializing Process- IT (UK) |  | 4
D2 | Breakdown in Officializing Process- IT (US)
E | Curve Issues |  | 1
F | Uncontrollable-System Needs to Change
G | Miscellaneous |  | 1
H | Not identified |  | 1
Breakdown By Group |  | # of Issues | Biggest Problem
EIM |  | 3
EGM |  | 3
EEL |  | 6
EA-CAN
EA - GAS |  | 2
EA - POWER
EES |  | 2
EBS |  | 1
Other |  | 1
TOTAL ISSUES |  | 18

## Graph Data Aug 27
SUMMARY BY WEEK OF | [5 empty] | 4/05-4/11 | 4/12-4/18 | 4/19-4/25 | 04/26-05/01 | 5/2/-5/9 | 5/10-5/17 | 5/18-5/25 | 5/28-6/1 | 06/04-06/08 | 06/11-06/15 | 06/18-06/22 | 06/25-06/29 | 07/02-07/05 | 07/09-07/13 | 07/16-07/20 | 07/23-07/27 | 07/30-08/03 | 08/06-08/10 | 08/13-08/17 | 8/20-8/24 | 08/27-8/31
Deal Capture | [6 empty] | 2 |  | 1 | [5 empty] | 1
Deal Valuation | [12 empty] | 1 |  | 1 |  | 2 |  | 1
Breakdown in Officializing Process- Human | [5 empty] | 30 | 6 | 10 | 19 | 13 | 7 | 2 | 8 | 5 | 6 | 6 | 9 | 5 |  |  |  | 17 | 12 | 5 | 4 | 8
Breakdown in Officializing Process- IT(UK) | [5 empty] | 5 | 3 | 3 | 2 | 6 | 5 | 6 | 4 | 5 | 2 | 4 | 3 | 1 | 12 | 9 | 9 | 4 | 5 | 5 | 3 | 6
Breakdown in Officializing Process- IT (US) | [5 empty] | 2 | 4 | 1 | 3 |  |  | 1 |  | 1 | 3 |  |  |  | 5 | 5 | 5 | 1 | 1 | 2 |  | 1
Curve Issues | [5 empty] | 3 | [5 empty] | 1 | 1 | 3 |  | 1 | 5 | 1 | 3 |  |  | 2 | 1 | 2 |  | 3
Uncontrollable-System Needs to Change | [5 empty] | 4 | 1 | 5 | 1 | 2 | 1 |  | 3 |  | 3 | 1 |  |  | 2 |  | 2 |  | 1 | 1 | 3 | 2
Miscellaneous | [9 empty] | 1 |  | 1 |  | 2 |  | 4 | 7 |  |  |  | 2 | 3 | 3 | 2 | 3 | 2
Not identified | [17 empty] | 1 |  | 1 | 1 | 2 | 1 |  | 1 | 1
Total Errors for the Week | [5 empty] | 44 | 16 | 19 | 26 | 22 | 13 | 11 | 17 | 16 | 16 | 16 | 26 | 8 | 23 | 15 | 19 | 29 | 24 | 17 | 14 | 23
SUMMARY BY WEEK OF | [5 empty] | 2001-04-05 | 2001-04-12 | 2001-04-19 | 2001-04-26 | 2001-05-02 | 2001-05-10 | 2001-05-18 | 2001-05-28 | 2001-06-04 | 2001-06-11 | 2001-06-18 | 2001-06-25 | 2001-07-02 | 2001-07-09 | 2001-07-16 | 2001-07-23 | 2001-07-30 | 2001-08-06 | 2001-08-13 | 2001-08-20 | 2001-08-27
LOG OF WEEKLY VALUATION ISSUES
CLASS
A - Deal Capture
B - Deal Valuation
C - Breakdown in transfer of data to RiskTrac (Officializing Process) - Human
D1 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (UK)
D2 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (US)
E - Curve Issues
F - No ones fault. System needs to change.
G - Other
H - Not identified.
|  |  |  | RESPONSIBLE |  | 2001-04-19: VAR; 2001-04-26: CREDIT; 2001-05-02: IMPACT CASH; 2001-05-10: STATUS
DATE | BOOK/AREA | Group | COMMODITY/OFFICE | PARTY | CLASS | 2001-04-05: PROBLEM; 2001-04-12: ACTION PLAN; 2001-04-19: RERUN?; 2001-04-26: AFFECTED?; 2001-05-02: FLOWS?; 2001-05-10: (DATE)
2001-08-31 | Nordic Power | EEL | Nordic Power | James New | D1 | 2001-04-05: MTM failed due to unknown IT issue. Process failed to generate error message. Book was rerun and loaded into RisktRAC; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-31 | UK Power; Eastern Spreadsheets | EEL | UK Power | James New | E | 2001-04-05: Books loaded late into RisktRAC due to missing curve data which prevented completion of MTM process and feed. Due to immaterial curves shift between prior day data, used prior day curve data to rerun MTM process. Due to US Holiday data was captured in VaR run.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-31 | TOLUENE-DISTR-PRC | EGM | US Global Products | Todd Hall | C | 2001-04-05: Attribute mismatch. Book was officialized using risk type of basis.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-31 | OIL-CAND2-EGSC-PRC | EGM | US Global Products | Todd Hall | C | 2001-04-05: Book was not officialized as part of end of day process. Book was officialized in the AM.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-30 | CR-AG-EES-RG-XL-PRC; CR-AGG-EES-RPS-PRC | EES | EES | Scott Mills | C | 2001-04-05: MTM credit files at counterparty level were not updated for COB Aug 29; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-30 | EAF-AUS-SRA-PRC | EEL | Australia Power | James New | D1 | 2001-04-05: Positions are held in spreadsheets due to enPower limitations. RM are experiencing problems uploading data into RisktRAC. Working with IT to resolve and upload data.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-08-30 | STEEL VaR | EIM | Steel | Shelly Wood | E | 2001-04-05: VaR had to be rerun because BLCR & BLCRFH steel curves not loaded. VaR reverted to prior day, however uploated new curve data and Reran VaR.; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-08-30 | FT-CAND-EGSC-BC-IDX; FT-CAND-EGSC-BC-PRC; FT-CAND-EGSC-IDX; FT-CAND-EGSC-PRC; FT-CAND-EGSC-A-BAS; FT-CAND-EGSC-PRC; FT-CAND-EGSC-BO-PRC; FT-CAND-ROLLOFF-PRC | EA | Canada Gas | Peggy Hedstrom | F | 2001-04-05: Due to the volume of deals and month end process books were officialized past 3 am. This caused the books to miss the Credit process. Additionally, certain books were officialized for current day and prior day, which caused manual processing for IR/FX group.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-08-30 | UK Power | EEL | UK Power | James New | D1 | 2001-04-05: Book loaded late into RisktRAC due to slightly late officialization; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-30 | GD-TEXAS-GDL & ST-BAMMEL-FNCL-GDL | EA | US GAS TEXAS | Jeff Gossett | C | 2001-04-05: Books were not officialized during end of day process.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-08-30 | EBS-BWT-PRC | EEL | UK EBS | Niel Tarling | G | 2001-04-05: Credit file was not appropriately saved for processing. .; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N
2001-08-29 | EAF-AUS-SRA-PRC | EEL | Australia Power | James New | D1 | 2001-04-05: Positions are held in spreadsheets due to enPower limitations. RM are experiencing problems uploading data into RisktRAC. Working with IT to resolve and upload data.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-08-29 | NG-X-OPT-HO-PRC | EA | US Gas Financial | Jeff Gossett | D2 | 2001-04-05: Book was officialized, however due to attribute issues not captured by RisktRAC.; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Done
2001-08-29 | FT-KATY-GDI | EA | US GAS TEXAS | Jeff Gossett | C | 2001-04-05: Book was not officialized; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-08-29 | UK Credit Trading | EEL |  | James New | G | 2001-04-05: Due to problems with DPR process file was not completed in time.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-29 | Nordic Power | EEL | Nordic Power | James New | F | 2001-04-05: Book is encountering delays during upload due to systems performance issues. IT is working to identify issue and resolve; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-28 | FRT-DIESEL-PRC; FRT-FWD-TXFR-PRC; FRT-HO-PRC; FRT-LC-PRC; FRT-MIDWEST-BAS; FRT-MIDWEST-PRC; FRT-MOUNTAIN-BAS; FRT-MOUNTAIN-PRC; FRT-NORTHEAST-BAS; FRT-NORTHEAST-PRC; FRT-NORTHWEST-BAS; FRT-NORTHWEST-PRC; FRT-OHIO-BAS; FRT-OHIO-PRC; FRT-SOUTHCENT-BAS; FRT-SOUTHCENT-PRC; FRT-SOUTHEAST-PRC; FRT-SOUTHEAST-BAS;FRT-UCF-PRC;FRT-WEST-PRC; FRT-WEST-PRC;FRT-WTI-PRC | EGM | US Freight | Todd Hall | C | 2001-04-05: Books were not officialized. Done in the AM and VaR rerun.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Done
2001-08-28 | UKPWRSWAP1, UK Term | EEL | UK POWER | James New | D1 | 2001-04-05: Uk Pwr Swap :Only 1 of the 4 files was transmitted. Issue identified and file resent. UK TERM: File not received by 6:15, but did make the VaR Run.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-28 | Nordic Power | EEL | Nordic Power | James New | E | 2001-04-05: Due to an incorrect interest rate curve mapping in Energydesk, the book was late. The Curve was corrected and the MTM rerun.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-27 | EES AR File | EES |  |  | H | 2001-04-05: Due to systems issues the file received contained data for COB 08/27 and COB 08/26. Corrected file was subsequently remitted.
2001-08-27 | DUB-INT-PHY | EES | US EES GAS | Scott Mills | C | 2001-04-05: Book was not officialized.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-27 | COAL-SYN-XL-BAS | EGM | US COAL | Frank Prejean | C | 2001-04-05: Book was not officialized; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Done
2001-08-27 | UK-POWER; CONTINENTAL POWER; EASTERN SPREADSHEETS | EEL | UK Power | James New | D1 | 2001-04-05: Continental power was officialized late for COB 27 due to overnight MTM failure. Process was subsequently rerun and officialized, VaR was Rerun. UK Power was officialized late due to an unnecessary MTM process, that was halted by IT/Risk and officialized. Eastern SS officialized late due to issues with UK Power, which is a precursor to Eastern SS officialization.
SUMMARY FOR 05/28 - 06/01 BY GROUP | % of Total Errors for the Week | # of errors | # Active books by group | Ratio of Errors to Active Books
EIM | 4.348% | 1 | 57 | 1.7544
EGM | 17.39% | 4 | 638 | 0.62696
EEL | 47.83% | 11 | 32 | 34.375
EA-CAN | 4.348% | 1 | 38 | 2.6316
EA - GAS | 13.04% | 3 | 452 | 0.66372
EA - POWER | 0% |  | 160 | 0
EES | 13.04% | 3 | 9 | 33.3333
EBS | 0% |  | 17 | 0
OTHER | 0%
TOTAL | 100% | 23 | 1403
Qtr end reporting

## summary 0827
SUMMARY BY WEEK FOR 08/13-08/20
TOTAL ISSUES |  |  | 23
Category | Description
A | Deal Capture
B | Deal Valuation
C | Breakdown in Officializing Process- Human |  | 8
D1 | Breakdown in Officializing Process- IT (UK) |  | 6
D2 | Breakdown in Officializing Process- IT (US) |  | 1
E | Curve Issues |  | 3
F | Uncontrollable-System Needs to Change |  | 2
G | Miscellaneous |  | 2
H | Not identified |  | 1
Breakdown By Group |  | # of Issues | Biggest Problem
EIM |  | 1
EGM |  | 4
EEL |  | 11
EA-CAN |  | 1
EA - GAS |  | 3
EA - POWER
EES |  | 3
EBS
Other
TOTAL ISSUES |  | 23

## Graph Data Aug 20
SUMMARY BY WEEK OF | [5 empty] | 4/05-4/11 | 4/12-4/18 | 4/19-4/25 | 04/26-05/01 | 5/2/-5/9 | 5/10-5/17 | 5/18-5/25 | 5/28-6/1 | 06/04-06/08 | 06/11-06/15 | 06/18-06/22 | 06/25-06/29 | 07/02-07/05 | 07/09-07/13 | 07/16-07/20 | 07/23-07/27 | 07/30-08/03 | 08/06-08/10 | 08/13-08/17 | 8/20-8/24
Deal Capture | [6 empty] | 2 |  | 1 | [5 empty] | 1
Deal Valuation | [12 empty] | 1 |  | 1 |  | 2 |  | 1
Breakdown in Officializing Process- Human | [5 empty] | 30 | 6 | 10 | 19 | 13 | 7 | 2 | 8 | 5 | 6 | 6 | 9 | 5 |  |  |  | 17 | 12 | 5 | 4
Breakdown in Officializing Process- IT(UK) | [5 empty] | 5 | 3 | 3 | 2 | 6 | 5 | 6 | 4 | 5 | 2 | 4 | 3 | 1 | 12 | 9 | 9 | 4 | 5 | 5 | 3
Breakdown in Officializing Process- IT (US) | [5 empty] | 2 | 4 | 1 | 3 |  |  | 1 |  | 1 | 3 |  |  |  | 5 | 5 | 5 | 1 | 1 | 2
Curve Issues | [5 empty] | 3 | [5 empty] | 1 | 1 | 3 |  | 1 | 5 | 1 | 3 |  |  | 2 | 1 | 2
Uncontrollable-System Needs to Change | [5 empty] | 4 | 1 | 5 | 1 | 2 | 1 |  | 3 |  | 3 | 1 |  |  | 2 |  | 2 |  | 1 | 1 | 3
Miscellaneous | [9 empty] | 1 |  | 1 |  | 2 |  | 4 | 7 |  |  |  | 2 | 3 | 3 | 2 | 3
Not identified | [17 empty] | 1 |  | 1 | 1 | 2 | 1 |  | 1
Total Errors for the Week | [5 empty] | 44 | 16 | 19 | 26 | 22 | 13 | 11 | 17 | 16 | 16 | 16 | 26 | 8 | 23 | 15 | 19 | 29 | 24 | 17 | 14
SUMMARY BY WEEK OF | [5 empty] | 2001-04-05 | 2001-04-12 | 2001-04-19 | 2001-04-26 | 2001-05-02 | 2001-05-10 | 2001-05-18 | 2001-05-28 | 2001-06-04 | 2001-06-11 | 2001-06-18 | 2001-06-25 | 2001-07-02 | 2001-07-09 | 2001-07-16 | 2001-07-23 | 2001-07-30 | 2001-08-06 | 2001-08-13 | 2001-08-20
LOG OF PENDING VALUATION ISSUES
CLASS
A - Deal Capture
B - Deal Valuation
C - Breakdown in transfer of data to RiskTrac (Officializing Process) - Human
D1 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (UK)
D2 - Breakdown in transfer of data to RiskTrac (Officializing Process) - IT (US)
E - Curve Issues
F - No ones fault. System needs to change.
G - Other
H - Not identified.
|  |  |  | RESPONSIBLE |  | 2001-04-19: VAR; 2001-04-26: CREDIT; 2001-05-02: IMPACT CASH; 2001-05-10: STATUS
DATE | BOOK/AREA | Group | COMMODITY/OFFICE | PARTY | CLASS | 2001-04-05: PROBLEM; 2001-04-12: ACTION PLAN; 2001-04-19: RERUN?; 2001-04-26: AFFECTED?; 2001-05-02: FLOWS?; 2001-05-10: (DATE)
2001-08-16 | UKPWRSWAP1 | EEL | UK Power | James New | D1 | 2001-04-05: Book was officialized, however only 1 of 4 files were received in feed.; 2001-04-12: RM and IT researching to determine what is causing error and provide update.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-08-13 | Power R3 Vol Curve | EA | US Power | Stacey White | E | 2001-04-05: R3 curve was marked the related books calc'd appropriately. Subsequently, the trader went in and changed Peak vol data which caused the off peak data to zero out. The zero values caused the VaR to crash and prevented the aggregation of AGG-ECT. Data was corrected and VaR rerun.; 2001-04-12: RM has communicated with Trader that once a curve is marked final no changes should be made as it may impact downstream systems. Additionally, IT investigating as why the off-peak data was zeroed out when only peak data was amended.; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
2001-08-13 | UKPWRSWAP1 | EEL | UK Power | James New | D1 | 2001-04-05: Book was officialized, but was not picked up by RisktRAC until after 9 am.; 2001-04-12: Only one of 4 required files were transmitted in file feed process. Working with IT and RM to identify issue.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-08-13 | Freight VaR rerun | EGM | US Freight | Todd Hall | E | 2001-04-05: Freight VaR was significantly greater than prior day. Change was caused by BA's request to change the Primary/Secondary factor. Additionally, the the vol curves were marked as zero which caused the VaR calc to revert to NG vol which further exaggerated problem.; 2001-04-12: Action plan pending.; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
2001-08-10 | UKPWRSWAP1 | EEL | UK Power | James New | D1 | 2001-04-05: Book was officialized, but was not picked up by RisktRAC until after 9 am.; 2001-04-12: Only one of 4 required files were transmitted in file feed process. Working with IT and RM to identify issue.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-08-06 | Nordic Weather Credit File | EEL | Nordic Weather | Didrik Thraner Nielsen | C | 2001-04-05: Due to Human error the file was not processed in time. It was subsequently sent.; 2001-04-12: Recommunicated deadline; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-08-06 | Unify Power | EGM | Unify Power |  | G | 2001-04-05: File was not transmitted as scheduled run. CAS IT had to pull data in manually. File impacts the Margin position for ENRON; 2001-04-12: Update pending; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-08-02 | PWR-NG-TEXAS-GDI; PWR-NG-ST-HEDGE-GDI;PWR-MG-GAS-MTM-GDI; PWR-NE-GAS-MTM-GDI; PWR-MW-GAS-MTM-GDI; PWR-NG-ERCT0-AST-GDI | EA | US Power EAST | IT | H | 2001-04-05: Books were officialized, however the data was not captured by RisktRAC. No problem noted during end of day procedures or with data attributes. IT could not resolve the issue.; 2001-04-12: IT and RM will monitor GDI books to identify any future problems. Subsequent review of Postids noted that positions were captured later in the day.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-08-02 | UK Power | EEL | UK Power | James New | H | 2001-04-05: Net Open positions reported by RisktRAC for UK power missing approximately 5 terrawatts compared to data transmitted.; 2001-04-12: RM researching issue.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-07-30 | Power VaR | EA | Power East | Stacey White | E | 2001-04-05: Volatilty for R1B curve was marked incorrectly by trader, which materially overstated VaR for positions against the curve. Curve data was corrected, reloaded and VaR rerun.; 2001-04-12: Update Pending; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
2001-07-27 | Eastern 1 & 2 spreadsheets | EEL | Eastern Spreadsheets | James New | D1 | 2001-04-05: Positions in spreadsheets were rolled from COB Jul 26. The data was rolled due to an error in the overnight MtM run of the Excel based models. Data being rerun and will be feed to RisktRAC later.; 2001-04-12: Update pending.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-07-27 | FIN-AGRI-GRAINS-PRC; UK-COFFEE-PRC;FIN-AGRI-SOFT-PRC;UK-COCOA-PROP-PRC;UK-SUGAR-NYBO-P-PRC | EGM | US Financial | Sheila Glover | H | 2001-04-05: Books had liquidated, but were still reporting deal legs with zero volumes and mtm value. Book has been officialized to zero, however due to deal leg table it appears as though it has Credit and VaR exposure, when non appears to exist.; 2001-04-12: BA and ERMS IT working to identify issue and correct to insure proper data capture by RisktRAC and CAS.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-07-23 | FT-IM-ENOV-GDL | EA | US Ennovate | Kevin Radous | C | 2001-04-05: Book was officialized, however due to an attribute mismatch the book was not captured by RisktRAC.; 2001-04-12: Issue was identified on 07/25. Proper procedures for changing attributes communicated to BA.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-07-20 | FT-IM-ENOV-GDL | EA | US Ennovate | Kevin Radous | C | 2001-04-05: Book was officialized, however due to an attribute mismatch the book was not captured by RisktRAC.; 2001-04-12: BA is working with ERMS IT to determine issue and resolution.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-07-20 | EES-MTM Power at Coutnerparty level | EES | EES Power | Scott Mills | C | 2001-04-05: EES Power MTM at counterparty level feed for Credit not received for COB 07/19. Per Scott Mills this is due to IT issues.; 2001-04-12: Update pending; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-07-18 | Nordic Power | EEL | Nordic Power | James New | D1 | 2001-04-05: Nordic Power was loaded late into RisktRAC due required rerun of MTM due to omission of Nordic futures and options.; 2001-04-12: Update Pending; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-07-09 | INTRA-EMWNSS2-GDL | EA | US GAS | Jeff Gossett | C | 2001-04-05: Book was officialized, but due to an attribute mismatch the data was not captured by RisktRac. Problem was resolved and data pulled in and VaR rerun.; 2001-04-12: Working to identify issue and resolve.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-07-09 | Eastern Spreadsheets 1&2 | EEL | European | James New | E | 2001-04-05: Trader failed to load needed curve data, which prevented calcing of book during overnight run. Therefore, data was rolled from 07/06/01. Curve data has was updated in the AM, however due to the time required to run the Eastern sheets the positions and values were not updated.; 2001-04-12: Implementation of Energydesk.com will allow for an table to track curves that are saved.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-07-02 | EAF-AUS-PRC | Australia | Australia Power | Justin Den Hertog | H | 2001-04-05: Update pending; 2001-05-10: Pending
2001-07-02 | NBP Curve | EEL | UK Gas | James New | E | 2001-04-05: Curve data after Sept 2003 is zeroed out on the RisktRAC side, while data is valid on UK side. Zero values can cause VaR to crash as it is a primary curve.; 2001-04-12: RM and IT researching to determine what is causing error and provide update.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
2001-06-29 | UK EBS | EEL | UK EBS | James New | G | 2001-04-05: EBS credit file not transmitted for 06/29/01.; 2001-04-12: Will discuss importance of completing end of day process with RM; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-06-27 | FT-CAND-EGSC-BC-PRC;FT-CAND-EGSC-PRC; FT-CAND-EGSC-OPT IDX & PRC | EA | Canada Gas | Peggy Hedstrom | G | 2001-04-05: Books were officialized late, but before VaR deadline. However, the data was not captured for credit reporting purposes since credit report runs at 1:30am.; 2001-04-12: Will discuss potential to change timing of credit process with Debbie Brackett and John Powell.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-06-27 | UK-EBS | EEL | UK-EBS | James New | G | 2001-04-05: The credit file was not processed since there were no new deals or curve shift. RM felt that processing was not necessary since there was no change in prior day data and given that the Credit system reverts to prior day data if current day is not available.; 2001-04-12: Discuss process given circumstance with Debbie Brackett and UK RM; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-06-27 | EES-CANADA-PRC | EES | EES-GAS | Scott Mills | E | 2001-04-05: Trader failed to load needed curve data, which prevented calcing of book. Curve data was loaded and books were officialized; 2001-04-12: RM needs to develop procedures to identify when needed data is not loaded; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-27 | Solarc Europe |  |  |  |  | 2001-04-05: The Solarc Europe file was not trasmitted to Credit, which understates credit exposure for physical nominations that have not been billed.; 2001-04-12: Application recently went to a new server which may have caused change. Working to identify issues and correct. Fix expect 06/28; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-06-26 | VaR failure |  |  |  | E | 2001-04-05: B33 & B11 primary power curves have not been marked for the past 15 days, which caused the VaR run to fail. The curves have not been marked because their use has been discontinued. RisktRAC requires that all primary curves be marked or VaR will fail to run completely.; 2001-04-12: Power RM notified users and RAC that the curves would be not be marked going forward and that they should be deleted during factor loading to prevent VaR failure. Latest factor loading has not been approved, which prevented the deletion of the discontinued curves. Need to approve latest factor loading or develop alternate process to add and delete curves.; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
2001-06-22 | Eastern Spreadsheets 1&2 | EEL | European | James New | D1 | 2001-04-05: Original file feed size noted to be extremely small. London RM reviewed and transmitted larger file.; 2001-04-12: Waiting on update related to issue and action plan.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-22 | Nordic Power | EEL | Nordic Power | James New | D1 | 2001-04-05: Book was officialized late because the server that holds relevant price curve data was down, which prevented completion of MTM process. Server was rebooted in the AM and MTM completed.; 2001-04-12: RM is currently developing a replacement systems called Energydesk.com, which is currently in TEST. This system will replace the current MTM system. ETA for go live is during 3q 2001; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-06-22 | DUB-ERMS-XL-PRC; DUB-ERMS-XL-BAS; DUB-INT-PHY | EES | EES-GAS | Scott Mills | H | 2001-04-05: Book Admin states that normal procedures were followed and file was uploaded into RisktRAC with no error messages noted, however positions were not noted in RisktRAC. As file was reloaded in the AM IT could not determine the problem. VaR was rerun.; 2001-04-12: Follow up to try and ID issue.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-21 | Eastern 1&2 Spreadsheets | EEL | European | James New | G | 2001-04-05: Spreadsheets officialized late to due file format incompatability with gas hedge files. Due to a systems upgrade the file format was altered.; 2001-04-12: Currently there is no TEST server available to test system upgrades prior to placing into production. RM working with IT to secure a test server to prevent future occurance.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-21 | Nordic Power | EEL | Nordic Power | James New | E | 2001-04-05: Spreadsheets officialized late due to Overnight MTM failure caused by missing curve data. The needed gas price curve was not saved.; 2001-04-12: Risk Management is working to develop a process to monitor the price curve saving process. Expect to have process in production in about 2 weeks.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-21 | EES Credit File | EES |  | Scott Mills | G | 2001-04-05: Due to problems with source system upgrade, the EES MTM credit file has not been received in a timely manner.; 2001-04-12: Risk Management working to identify problem and resolving issue.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-21 | SAP FILE |  |  |  | G | 2001-04-05: Due to a change in the feed process, which was not communicated to downstream users, the data was not properly captured by Credit. This change in feed caused an overstatement of Credit Risk by $500 million; 2001-04-12: Communicate the importance of discussing any changes in current procedures, feeds or formats with all impacted downstream users to minimize potential impact to systems and users.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-06-20 | Eastern 1&2 Spreadsheets | EEL | European | James New | D1 | 2001-04-05: Eastern spreadsheets were officialized late, around 6:38 am, due to technical problems with the workstation which runs the Eastern Model. The PC shut down during the night which prevented completion of MTM process.; 2001-04-12: Risk Management with IT are prioritizing the purchase of a new server for the Eastern Spreadsheets which will give the model 24 hr support and also give the model a more stable environment.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-19 | Nordic Power | EEL | Nordic Power | James New | G | 2001-04-05: Overnight MTM failed due to lack of disk space. DBA is working to allocate additional space to process.; 2001-04-12: Working to allocate additional disk space to insure process does not fail.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-18 | Eastern1&2 Spreadsheets | EEL | European | James New | D1 | 2001-04-05: Spreadsheets were officialized late due to the failure of the overnight MTM process.; 2001-04-12: Risk Management working on 24 hr support to monitor overnight process. Additionally, the implementation of the Socrates valuation engine will remove the inherent instability in using Excel.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-15 | Heat Rate Swaps | EA | US-POWER |  | D2 | 2001-04-05: Positions related to Heat Rate Swaps are being captured for Benchmark purposes, however data is not automatically captured for RisktRAC VaR calculation due to the problems associated with index issues noted below; 2001-04-12: EnPower needs to be updated to recognize basis legs and RisktRAC needs to be updated to recognize change in source system. Changed in systems is estimated to complete by 06/30/01; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-15 | UK Power | EEL | UK-Power | James New | D1 | 2001-04-05: Due to maintenance error over the weekend, the Unix server did not receive needed data, which resulted in MTM failure. MTM reperformed in AM and data submitted.; 2001-04-12: IT working to implement procedures at close of business that would allow time to identify errors prior to Houston deadline.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-15 | Eastern 1 & 2 spreadsheets | EEL | UK-Power | James New | D1 | 2001-04-05: Due to Maintenance error the 06/15 MTM failed. Rolled positions for 06/14; 2001-04-12: IT working to implement procedures at close of business that would allow time to identify errors prior to Houston deadline.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-15 | DBL-XL-TRIGGER-PRC |  | US-GRM | John Best | C | 2001-04-05: Assigned staff believed they had loaded sheet successfully, however data not captured.; 2001-04-12: Will Communicate use of Active/Inactive Website to RM to ensure any data transfer issues are properly identified.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-14 | UK POWER Options | EEL | UK Power | James New | A | 2001-04-05: 1.4 Terrawatt position is not being reported and therefore is not being captured for VaR purposes.; 2001-04-12: Risk management is working to identify why the positions are not being captured. An amendment to Dove Calc will take place in 2-3 weeks in an attempt to captured positions. In the mean time RM should run and AD-HOC VaR and transmit data for DPR purposes.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-11 | Heat Rate Swaps | EA | US Power EAST | Stacey White | C, D2 | 2001-04-05: Heat rate swaps were not captured in RisktRAC, due to the lack of an appropriate book within RisktRAC and that the appropriate commodity NG was not set up in EnPower. These two factors prevented the capture of the Heat Swap positions.; 2001-04-12: The Needed book was created within RisktRAC and the commodities were updated within EnPower. The books were reofficialized and the VaR was rerun for Commodity VaR, AGG_ECT and AGG Power IV. W orking to develop procedures to insure reconcile positions between source and reporting systems.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-08 | EAF-AUS-PRC | EEL | Australian Power | Justin Den Hertog | C | 2001-04-05: Due to Australian Holiday book was not officialized. However, the holiday procedures were not followed.; 2001-04-12: Need to recommunicate holiday officialization procedures to Risk Management team.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-07 | Eastern Spreadsheets 1&2 | EEL | UK Power | James New | E | 2001-04-05: Since a Power Curve for Jun 7th was not saved, the spreadsheets were unable to run a valuation and report MTM & Risk exposures for Jun 7th. Therefore data reported is as of Jun 6.; 2001-04-12: Risk Management is working to develop process to insure that all needed curve data is saved for each day. Additionally, need to establish procedures for reporting MTM and P&L when process fails.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-07 | UK Power | EEL | UK Power | James New | E | 2001-04-05: Traders failed to save Power Curves for June 7th. Therefore, no P&L Curve shift available. All positions were properly loaded into RisktRAC; 2001-04-12: Risk Management is working to develop process to insure that all needed curve data is saved for each day.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
2001-06-04 | Factor Loading/Primary Curves |  |  | RAC | G | 2001-04-05: Due to current processes and procedures in place, factor loadings have not been approved since April 17, 2001. This lack of factor loading prevents the addition of new primary curves in RisktRAC. Therefore certain secondary curves are not mapped to the appropriate primary curves. The addition of the new primary curves could impact VaR.; 2001-04-12: Coordinate with various groups to identify improved process for approving factor loadings and primary curves into system.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
2001-06-01 | Bandwidth Curve | EBS | Bandwidth | Gary Stadler | E | 2001-04-05: Volatilty Curve Data not Captured in RisktRAC.; 2001-04-12: Following up with IT to determine issue and resolution; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
2001-06-01 | EBS-BWT | EEL | EBS-BWT | James New | C | 2001-04-05: Risk Management advised that file is late because of month-end issues and a larger than normal number of deals to be input.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-06-01 | Nordic Power | EEL | Nordic Power | James New | C | 2001-04-05: Business holiday for 06/04/01, however appropriate holiday schedule not followed. Communicated procedures required that 06/01/01 data be officialized prior to holiday.; 2001-04-12: Recommunicate holiday procedures with appropriate Business Risk Managers to insure that data is appropriatesly reported.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-05-29 | Nordic Power | EEL | Nordic Power | James New | D1 | 2001-04-05: Experienced problems sending their feed to RisktRac due to a failure in the overnight Nordic MTM system run.; 2001-04-12: IT is working on this issue.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
2001-05-24 | Eastern Books | EEL | UK Eastern | James New | D1 | 2001-04-05: Problems loading current day spreadsheet as a result, 70 Bcf of hedges did not make it to RisktRac.; 2001-04-12: IT is working on this issue.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-05-24 | UK Power | EEL | UK Power | James New | D1 | 2001-04-05: Database is not functioning properly. (IT issues); 2001-04-12: Houston IT working on fixing this problem.; 2001-05-10: Pending
2001-05-22 | Nordic Power | EEL | Nordic Power | James New | D1 | 2001-04-05: File had to be re-send because of a deal that was doubled up. File was re-sent before the first file sent completed reconciling deal and position table.; 2001-04-12: Houston IT suggested when having to re-send file, develop a test to check if first file was completed and wait 10 mins before sending the second one.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
2001-05-22 | UK Gas | EEL | UK Gas | James New | E | 2001-04-05: PPP power curve was loaded into the curve file thus causing incorrect valuation and problems with the position files.; 2001-04-12: Waiting for an Action Plan from UK.; 2001-04-19: Y; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
2001-05-21 | Unified Power | EA | Power | Leslie Reeves | D1 | 2001-04-05: Unified power system failed and had to be re-run.; 2001-04-12: Unified system personnel are monitoring the system to determine cause of the problem.; 2001-04-19: N; 2001-04-26: Y; 2001-05-02: N; 2001-05-10: Pending
2001-05-08 | Continental Power | EEL | Continental Power | James New | D1 | 2001-04-05: Monday was a bank holiday and IT switched Portcalc off as they did not want the systems to run overnight. However, it was not turned on by IT for Tuesday 8 May close of business overnight run. Consequently, Portcalc mtm did not run and there was no data for 8 May to be officialized by risk management. The Portcalc mtm had to be subsequently re-run by IT during the current day and was then officialized and loaded into Risktrac at 7:35 am Houston time.; 2001-04-12: Procedure to be put in place so that the dates for running of the mtm are clearly stated and defined for the benefit of IT. This will ensure that any confusion is removed as to the dates for the mtm run.; 2001-04-19: Y; 2001-04-26: Y; 2001-05-02: Y; 2001-05-10: Pending
2001-05-08 | Nordic Power | EEL | Nordic Power | James New | D1 | 2001-04-05: Nordic Power data for 8 May did not load into Risktrac until 6:13 am Houston time. This was due to a random IT error in that some options failed to be calculated in the overnight mtm run. Nordic risk management had to manually determine which of the book's option positions failed to be calculated and then had to manually recalculate these options before officialization could be initiated.; 2001-04-12: Waiting for an Action Plan from Michael Kass.; 2001-04-19: N; 2001-04-26: N; 2001-05-02: N; 2001-05-10: Pending
SUMMARY FOR 05/28 - 06/01 BY GROUP | % of Total Errors for the Week | # of errors | # Active books by group | Ratio of Errors to Active Books
EIM | 0% |  | 56 | 0
EGM | 14.29% | 2 | 628 | 0.31847
EEL | 35.71% | 5 | 32 | 15.625
EA-CAN | 7.143% | 1 | 38 | 2.6316
EA - GAS | 21.43% | 3 | 447 | 0.67114
EA - POWER | 0% |  | 151 | 0
EES | 7.143% | 1 | 9 | 11.1111
EBS | 14.29% | 2 | 17 | 11.7647
OTHER | 0%
TOTAL | 100% | 14 | 1378
Active/Inactive Website go Live
Qtr end reporting

## summary 0820
SUMMARY BY WEEK FOR 08/13-08/20
TOTAL ISSUES |  |  | 14
Category | Description
A | Deal Capture
B | Deal Valuation
C | Breakdown in Officializing Process- Human |  | 4
D1 | Breakdown in Officializing Process- IT (UK) |  | 3
D2 | Breakdown in Officializing Process- IT (US)
E | Curve Issues
F | Uncontrollable-System Needs to Change |  | 3
G | Miscellaneous |  | 3
H | Not identified |  | 1
Breakdown By Group |  | # of Issues | Biggest Problem
EIM
EGM |  | 2
EEL |  | 5
EA-CAN |  | 1
EA - GAS |  | 3
EA - POWER
EES |  | 1
EBS |  | 2
Other
TOTAL ISSUES |  | 14