## Sundevil by Task by Month
|  |  |  | PROJECT SUNDEVIL TASK LIST AND CASH FLOW ESTIMATE FOR ENVIRONMENTAL PROGRAMS | [15 empty] | PROJECT SUNDEVIL TASK LIST AND CASH FLOW ESTIMATE FOR ENVIRONMENTAL PROGRAMS
6792-162 | [14 empty] | 6792-162
| TOTAL | 2001 |  |  |  | 2002 | [11 empty] | 2003
| COSTS | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC
Task
Data Collection & Review | TOTAL COSTS: 30000; 2001 SEP: 5000; 2001 OCT: 20000; 2001 NOV: 5000
Agency Consultation | 60000 | 5000 | 10000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Route Selection | TOTAL COSTS: 30000; 2001 SEP: 5000; 2001 OCT: 20000; 2001 NOV: 5000
Habitat/Land Use Surveys | TOTAL COSTS: 30000; 2001 OCT: 15000; 2001 NOV: 15000
T&E Species Surveys | TOTAL COSTS: 160000; 2002 MAR: 32000; 2002 APR: 32000; 2002 MAY: 32000; 2002 JUN: 32000; 2002 JUL: 32000
Wetland Delineation & Report | TOTAL COSTS: 120000; 2002 MAR: 10000; 2002 APR: 20000; 2002 MAY: 60000; 2002 JUN: 30000
Cult. Res. Survey/Report | TOTAL COSTS: 500000; 2001 OCT: 25000; 2001 NOV: 200000; 2001 DEC: 100000; 2002 JAN: 25000; 2002 FEB: 25000; 2002 MAR: 25000; 2002 APR: 25000; 2002 MAY: 25000; 2002 JUN: 25000; 2002 JUL: 25000
Cult. Res. Testing/Mitigation | TOTAL COSTS: 800000; 2002 MAY: 100000; 2002 JUN: 200000; 2002 JUL: 200000; 2002 AUG: 100000; 2002 SEP: 100000; 2002 OCT: 50000; 2002 NOV: 50000
Cultural Resources Mgt. | 135000 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | 7500
FERC Resource Reports | TOTAL COSTS: 100000; 2001 SEP: 5000; 2001 OCT: 16000; 2001 NOV: 16000; 2001 DEC: 16000; 2002 JAN: 16000; 2002 FEB: 16000; 2002 MAR: 15000
FERC Data Requests | TOTAL COSTS: 20000; 2002 MAY: 10000; 2002 JUN: 10000
Biological Assessment | TOTAL COSTS: 30000; 2001 OCT: 5000; 2001 NOV: 5000; 2001 DEC: 5000; 2002 JAN: 5000; 2002 FEB: 5000; 2002 MAR: 5000
Map/Alig. Sheet Review | TOTAL COSTS: 15000; 2001 OCT: 2500; 2001 NOV: 2500; 2001 DEC: 2500; 2002 JAN: 2500; 2002 FEB: 2500; 2002 MAR: 2500
Section 404 Permits | TOTAL COSTS: 25000; 2002 JUN: 5000; 2002 JUL: 5000; 2002 AUG: 10000; 2002 SEP: 5000
404 Conditions Follow-up | TOTAL COSTS: 11000; 2002 OCT: 1000; 2002 NOV: 5000; 2002 DEC: 5000
Air Quality Permits | TOTAL COSTS: 40000; 2002 JAN: 5000; 2002 FEB: 5000; 2002 MAR: 5000; 2002 APR: 5000; 2002 MAY: 5000; 2002 JUN: 5000; 2002 JUL: 5000; 2002 AUG: 5000
Withdrawal/Discharge Permits | TOTAL COSTS: 25000; 2002 APR: 5000; 2002 MAY: 5000; 2002 JUN: 5000; 2002 JUL: 5000; 2002 AUG: 5000
Agency/Public Meetings | TOTAL COSTS: 70000; 2001 SEP: 5000; 2001 OCT: 10000; 2001 NOV: 10000; 2001 DEC: 5000; 2002 JAN: 5000; 2002 FEB: 5000; 2002 MAR: 5000; 2002 JUN: 5000; 2002 JUL: 5000; 2003 MAY: 5000; 2003 JUL: 5000; 2003 SEP: 5000
Coordination Meetings | 90000 | 5000 | 5000 | 5000 | 5000 | 5000 |  | 5000 | 5000 | 5000 |  | 5000 |  | 5000 |  | 5000 | 5000 |  | 5000 |  | 5000 |  | 5000 |  | 5000 |  | 5000 |  | 5000
Project Management | 275000 | 10000 | 20000 | 10000 | 10000 | 6250 | 6250 | 6250 | 6250 | 6250 | 6250 | 6250 | 6250 | 6250 | 6250 | 6250 | 6250 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500 | 12500
GIS Web Page Mgt. | 70000 | 2500 | 5000 | 7500 | 5000 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000
Env. Compliance Plan Prep. | TOTAL COSTS: 50000; 2002 OCT: 10000; 2002 NOV: 20000; 2002 DEC: 20000
EIS Review and Input | TOTAL COSTS: 10000; 2002 NOV: 5000; 2002 DEC: 5000
Implementation Plan Prep. | TOTAL COSTS: 10000; 2002 NOV: 5000; 2002 DEC: 5000
Permit Book Preparation | TOTAL COSTS: 15000; 2002 NOV: 5000; 2002 DEC: 5000; 2003 JAN: 5000
Permit Compliance Tracking | TOTAL COSTS: 35000; 2002 NOV: 2500; 2002 DEC: 2500; 2003 JAN: 2500; 2003 FEB: 2500; 2003 MAR: 2500; 2003 APR: 2500; 2003 MAY: 2500; 2003 JUN: 2500; 2003 JUL: 2500; 2003 AUG: 2500; 2003 SEP: 2500; 2003 OCT: 2500; 2003 NOV: 2500; 2003 DEC: 2500
Env. Inspector Mgt. | TOTAL COSTS: 30000; 2003 JAN: 2500; 2003 FEB: 2500; 2003 MAR: 2500; 2003 APR: 2500; 2003 MAY: 2500; 2003 JUN: 2500; 2003 JUL: 2500; 2003 AUG: 2500; 2003 SEP: 2500; 2003 OCT: 2500; 2003 NOV: 2500; 2003 DEC: 2500
Env. Inspector Subcontract | TOTAL COSTS: 1584000; 2002 DEC: 66000; 2003 JAN: 132000; 2003 FEB: 132000; 2003 MAR: 132000; 2003 APR: 132000; 2003 MAY: 132000; 2003 JUN: 132000; 2003 JUL: 132000; 2003 AUG: 132000; 2003 SEP: 132000; 2003 OCT: 132000; 2003 NOV: 132000; 2003 DEC: 66000
Discharge Water Analysis | TOTAL COSTS: 15000; 2003 OCT: 5000; 2003 NOV: 5000; 2003 DEC: 5000
Env. Training Support | TOTAL COSTS: 15000; 2002 NOV: 4000; 2002 DEC: 4000; 2003 JAN: 4000; 2003 FEB: 2000; 2003 MAR: 1000
Field Support | TOTAL COSTS: 35000; 2002 NOV: 2500; 2002 DEC: 2500; 2003 JAN: 2500; 2003 FEB: 2500; 2003 MAR: 2500; 2003 APR: 2500; 2003 MAY: 2500; 2003 JUN: 2500; 2003 JUL: 2500; 2003 AUG: 2500; 2003 SEP: 2500; 2003 OCT: 2500; 2003 NOV: 2500; 2003 DEC: 2500
Restoration Support | TOTAL COSTS: 15000; 2003 SEP: 2500; 2003 OCT: 2500; 2003 NOV: 5000; 2003 DEC: 5000
Third Party Contractor | 550000 |  | 10000 | 28000 | 28000 | 28000 | 28000 | 28000 | 32000 | 38000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | 25000 | 25000
Total For Month |  | 50000 | 171000 | 319500 | 187000 | 110750 | 105750 | 151750 | 143250 | 299250 | 376250 | 341250 | 179250 | 169250 | 119250 | 162250 | 178250 | 197500 | 195500 | 157000 | 159000 | 159000 | 159000 | 159000 | 159000 | 161500 | 166500 | 162000 | 101000
Grand Total to Date |  | 50000 | 221000 | 540500 | 727500 | 838250 | 944000 | 1095750 | 1239000 | 1538250 | 1914500 | 2255750 | 2435000 | 2604250 | 2723500 | 2885750 | 3064000 | 3261500 | 3457000 | 3614000 | 3773000 | 3932000 | 4091000 | 4250000 | 4409000 | 4570500 | 4737000 | 4899000 | 5000000
Grand Total | TOTAL COSTS: 5000000; 2002 AUG: Revised 09/25/01; 2003 NOV: Revised 09/25/01