## Sheet1
|  |  | Approved | Work Orders | Work Orders | Work Orders | Work Orders Estimate |  | Work Orders
System Name | Account Number | System Number | Capital Cost | Capital Cost | Capital Cost | Capital Cost | Accrual for Mat.&Labor |  | Estimate at
|  |  | RAROC | Approved | Thru 8-31-00 | 9-01 to 9-14 | 9-01Thru 9-22 |  | Completion
House Creek | 11025 | 100 | 11944234 | 5151501 | 2933154 | 1000 | 4000 | 2938154 | 11944234
Caballo Lateral | 11026 | 200 | See Note 2 | 2511400 | 2762885 | 0 | 10000 | 2772885 | 2800000
Caballo Compression | 11026 | 200 | 8062497 | 5740000 | 7329075 | 29755.53 | 550000 | 7908830.53 | 8100000
Clydesdale | 11027 |  | 3254256 | 3370675 | 1841961 | 31608.66 | 720000 | 2593569.66 | 3254256
South Kitty | 11028 |  | 7462998 | 9413156 | 3134393 | 99427.73 | 1500000 | 4733820.73 | 7462998
Hoe Creek | 11029 |  | 6735882 | 4661220 | 786642 | 1514.45 | 350000 | 1138156.45 | 6735882
Box Draw | 11030 | 400 | 6707026 | 7053775 | 7609828 | 3403 | 90000 | 7703231 | 8000000
Maverick | 11030 | 300 | 1650000 | See Note 1 | See Note 1 | See Note 1 | See Note 1 | 0 | See Note 1
Kudzu |  |  | 4729128 | 0 | 0 | 0 | 0 | 0 | 7153363
Fort Union Receipt Points |  |  | 676713 | 1194000 | 1233726 | 1882.94 | 12000 | 1247608.94 | 1325000
|  | Grand Total = | 51222734 | 39095727 | 27631665 | 168592.31 | 3236000 | 31036257.31 | 56775733
Note 1: All of Maverick's Capital cost is included in the Box Draw work order.
Note 2: This cost was included in the Caballo Compression RAROC number.