## Project Listing
Project Name | Enron Business Unit | Project Type I | Project Type/Description | Originator(s) | Responsible Tech Services | Technical Support | Location | $$ Exposure | Assessment of Risk | Updated | Update/Comments | EBU | PT1
AMPS | North America - Principal Investing |  | Generation Technology - mobile power units | M. Miller/K. Kitagawa | Bob Virgo | Grigory Zelondzhev | Various |  |  | 2001-03-13 | Waiting in AMPS to finalize Marketing Director hire. Will do a turnover at that time.
Austin | North America - East |  | Development/Construction - Simple Cycle Project (~180 MW) | Jeff Keenan | Bob Virgo | Eric Booth | Austin, TX |  |  | 2001-05-15 | Construction nearly complete. Estimated completion = May 31, 2001.
Electrobolt | South America | Greenfield | Development/Construction - Simple Cycle Project (386 MW) | Brett Wiggs | Rob Blackham | EEOS | Rio de Janeiro |  |  | 2001-05-15 | Site is under development - initial foundations and temporary facilities. 2 of 6 gas turbines to be shipped today to site. EEOS/NEPCO are primary parties in construction. Target Operation date = November 1, 2001.
Fort Pierce | North America - East |  | Repower Steam Plant using MHI 501D turbine | Dave Fairley | Bob Virgo/M. Coleman | Darrell Stovall | Ft. Pierce, FL |  |  | 2001-04-30 | Team working last revision on FPUA agreements. Engineering on hold waiting on DASH. Looking for final negotiation.
Las Vegas Cogen | North America - West |  | Development/Construction - 4 @2x1 LM6000's combined cycle plant | Ed Clark | Wayne Mays | Bob Williams, Bob Chmielewski, Ed Dannhaus | Las Vegas, NV |  |  | 2001-05-15 | DASH executed. EPC contractor has been selected (Modern Continental). NTP early next week
Columbia (Longview) | North America - West |  | Development/Construction 2 7FAs combined cycle. Permitting underway | Jake Thomas | Wayne Mays | Don Hammond, Mark Mullen, Bill Williams | Port of Longview, WA |  |  | 2001-05-15 | Currently reviewing EPC contractor financial risk and execution risk. Scott is current contractor being considered
Roseville | North America - West |  | Site acquisition underway. Seeking to secure emission credits | Mike McDonald | Wayne Mays | Don Hammond | No. California - near Sacramento |  |  | 2001-05-15 | I-DASH for early development work and purchase of emission credits
TexMex | North America - East |  | Development/Construction - Installation of AC/DC tie, power export to Mexico | Ozzie Pagan | Bob Virgo | Walter Coffer, Scott Laidlaw | Brownsville, TX |  |  | 2001-04-23 | Interface with Brownsville public utility and ABB Engineering. Currently on hold
Vitro | Mexico | Greenfield | Development/Construction - Combined Cycle Cogen Project (245 MW) | Steve Irvin, Marc Sabine, Max Yzaguire | Bob Virgo | Ed Elam | Monterrey, Mexico |  |  | 2001-05-15 | Engaged EPC Contractor (Mitsui). Now in the early stage of construction.
EPC Negotiaion Team | Enron Americas | Greenfield | Lead EPC and turbine purchase contract discussions. | R. Tapscott, L. Bills, J. Schwartzberg | Bob Virgo | M. Coleman | ENA |  |  | 2001-05-15 | Now focused on Ft. Pierce

## COPY
Enron Business Unit | Project Name | Project Type I | Project Type II | Originator(s) | Responsible Party | Technical Support | $$ Exposure | Assessment of Risk | Updated | Update/Comments
OEC | New Albany | Other | Operation |  | Virgo / Dobler |  | >$500K | AMPS testing received verbal approval from state DEQ for allowance of the test. Completed combustor testing with Power Systems on Unit 6. Completed testing on phase one of AMPS unit. | 2001-01-29 | High commercial risk should equipment damage occur. No risk preceived
OEC | Caledonia | Other | Operation |  | Virgo / Dobler |  |  | None present, impending sale to CINERGY | 2001-01-29
OEC | Brownsville | Other | Operation |  | Virgo / Dobler |  |  | None present, impending sale to CINERGY. Preparing resolutions to outstanding items as presented by Enron audit. Scheduled Pro Mod 99-3440 for generator bearing clearance. Scheduling upgrades on steam silencers on units 1 & 2. | 2001-01-29 | Scheduled outage to begin week of November 8. Low risk to component repairs and replacements in combustion system and turbine bearings.
OEC | Gleason | Other | Operation |  | Virgo / Dobler |  | >$2MM | 1. Low frequency noise resolution. 2. Plant availability impacts due to exhaust plenum design/construction. 3. Miscellaneous warranty clean-up. Compeleted required stackwork for Seimens Westinghouse. Impending sale, OEC will lead the transistion to Alleghany Power. | 2001-01-29 | 1. Medium risk to offer price, discounting effects of noise on local properties. 2. Medium risk on NEPCO/EECC direction to review plenum construction and design. 3. Low risk on miscellaneous warranty clean-up. SWPC has agreed to consolidated listing of concerns.
OEC | Wheatland | Other | Operation |  | Virgo / Dobler |  |  | None present, Impending sale, OEC will lead the transisiton to Alleghany Power. CEMS Re-Certification with stack stratification on units 1-4. | 2001-01-29 | Scheduled outage is on schedule. No major findings. CEM testing could impact sale.
OEC | Lincoln | Other | Operation |  | Virgo / Dobler |  | ? | 1. Combustor design retrofit. 2. Unit 6 compressor failure. Impending sale OEC will lead transition to Alleghany Power. Compressor failure on seventeen stage, repaired and completed. Thirteen open warranty issues open due to retesting of combustor systems to verify CO outstanding. | 2001-01-29 | 1. Medium risk, GE has replaced 4 of 8 combustion systems. One system failed shortly after replacement. RCA due out within 4 weeks. 2. RCA on compressor failure due out by November 3rd. OEC lloking for potential casting problem, as root cause. GE has issued a TIL for the compressor failure, no RCA has been issued from GE.completed
OEC | Doyle | Other | Operation |  | Virgo / Dobler |  | $ 1 - $ 2 MM | H2 cooled generator leakage rates. Mist eliminator opacity issues Still an issue with Unit 1. Units 2&3 within limits. High seal air flows to #2 bearing, unit 1. Compressor failure seventeen stage. Compressor Rotor and turbine at GE shops for repair. Estimated repair time 4-6 weeks. Generator unit 1 repair being completed by RTA. RTA is replacing the H2 seal along with strip heater installation. Found seals severely damaged because of Furminite repair performed during construction. Estimate the repair to be competed by 1/12/01. Also found Bearing damage in generator. GE continues to work on unit five expected completion 3/01. Unit 4 failed on 1/4/01 similar to unit five failure. Rotor and turbine shipped to GE Cincinatti on 1/24/01. | 2001-01-29 | Turbine inspections to begin week of 9/18/00. Owner decision to not install H2 seals and leave unit off line for remainder of off-peak season. Mist eliminator replacement has mitigated the opacity levels, however, seal replacement is required to eliminate both opacity issue and high seal air flows to bearing cavity. TIL issued by GE for compressor repair -need resolution to TIL and RCA for 17th stage failures.
West | Alpine Natural Gas | Other | Operation | Vicky Ha / Carlos Gorricho | Don Hammond/Vicky Ha |  |  | Approximately $500,000 of invoices from the principal construction contractor are outstanding for installation of mainline piping and service lines during 2000. $225 to 250,000 in charges are contested by Alpine NG. Construction costs will be $200 to 400,000 over budget depending on the outcome of disputed charges. | 2001-04-23 | Just discovered outstanding invoices to digging contractor of about $500K. February 7th meeting with Loy Clark and Alpine to resolve outstanding invoices. Third party investors being sought for the project. Deal is being transferred to the Special Assets Group.
West | Bighorn (Colstrip) | Other | Operational Review |  | Chuck Ward |  |  | No current Risk | 2000-10-26 | Big Horn's historic availability exceeds 92%.
West | Cactus Black Mtn Power/Saguaro | Other | Operational Review |  | Chuck Ward |  |  | No current Risk | 2000-10-26 | The facility is currently over 95% available and ENA's ownership is 15%. The plant availability has to fall below 90% for capacity payments to decrease substantially.
West | Columbia (Port of Longview, WA) | Other | Development/Construction |  | Bill Williams/ Mark Mullen/ Don Hammond |  | Development Budget Amount | 1) Water Supply 2) Interconnection 3) Fuel Supply 4) Waste Water Discharge | 1/29/2001, 4/30/2001 | 1) Securing water rights. 2) Power Engineers submitting feasibility engineering and RFP preparation 3) Met with Cascade Natural Gas on fuel supply alternatives - direct connections to Cascade or bypass pipeline. 4) Met with Cowlitz County on use of their outfall for wastewater discharge on 1/24. County is very agreeable and is drafting terms of agreement. 5) Air permit application has been filed. Response to request for additional information to be submitted the week of 1/29. 6) Draft design basis document from Power Engineers - will coordinate review with EE&CC. Notional bids dur from EPC players next Friday. Expect to enter discussion with two - Scott Company (Turner Power Engineering and Modern Continental),(Harris Group Engineering). Site visit by Scott next Thursday.
West | Elvis (LVCLP) | Other | O&M |  | J. Blackburn |  |  | 1) Warranty on Gas Turbine expired. Not enrolled in leased engine program. | 2001-01-29 | Warranty issue with engine that occurred prior to expiration - HPT blade coating. Resolving with GE.
West | Priscilla (LVCII) | Other | Development/Construction |  | Bill Williams/ Mark Mullen/ Don Hammond |  |  | 1) Finalizing EPC Contract 2) Equipment long lead items 3) Water supply 4) Wastewater discharge | 2001-01-29 | Lauren terminated as constructor as of 1/31. Going to two other EPC contractors for price and schedule. COD moving to 9/1/02. Will evaluate present engineering contractor over next two weeks. Day by day slip on OTSG and steam turbine. 1) EPC contractor will get contractor's license issued 1/9. 2) Long lead material contracts and delivery dates are now in place to support construction schedule. 3) Informed on 1/25 by City that offsite submittal has been signed off and Will Serve Letter will be issued upon payment of fees. 4) Continuing negotiations with City on reduction of wastewater connection fees.
West | Pastoria | Other | Development/Construction |  | Wehn/Russell/ Calger |  |  | No current Risk | 2001-01-30 | CEC permit was officially issued on 1/22/01 with no comments, Biological opinion has been recieved and the Prevention of Significant Deterioration (PSD) is expected this week from the EPA. No issues outstanding. NEPCO has submitted a bid in the event counterparty would like to proceed or ENA chooses to build the project they are available.
West | PSCo (Zebulon) | Other | Development/Construction |  | Mark Mullen/Don Hammond |  | $.5MM | 1) Signed EPC COD dates are later than PPA requirements. 2) No full-time ENA site construction representation at this time | 2001-01-29 | 1) CIG to provide gas line extension turnkey basis. 2) EPC contract with NEPCO signed 1/19. 3) Working to have onsite construction Representative by week of 1/29. 4) Interconnect agreement with PSCo is essentially complete.
East | Austin | Other | Development/Construction |  | Virgo |  |  | Normal Construction Risk | 2001-01-30 | Schedule is verty tight, however low LD's if COD is not met.
East | Project Neptune (LIPA) | Other | Development/Construction |  | Virgo |  |  | Project Pending, no deal at end of last week | 2001-01-30
East | TexMex | Other | Development/Construction | Ozzie Pagan | Virgo/Coffer |  |  | 1) Transmission line siting 2) Converter station siting 3) Converter/Inverter station | 2001-04-30 | Proceeding fine, no current risk perceived. Project on hold.
East | Ada Cogeneration | Other | O&M |  | Mike Mazowita White Pine 248-442-4823 |  |  | None currently present. | 2001-01-25 | None
East | Michigan Power | Other | O&M |  | Mike Mazowita White Pine 248-442-4823 |  |  | None present | 2001-01-25 | The plant is running very well with Annual Availability exceeding 97%. The Partners discussed a possible 2055 Gas Turbine Uprate in December, but they did not approve the proposal. The plant is gearing up for their first major overhaul in September.
East | Tenaska IV Texas Partners (Cleburne) | Other | O&M |  | Mike Mazowita White Pine 248-442-4823 Virgo |  |  | Inherent risk exposure to Westinghouse 501 F technology machines and the transition/transition seal design deficiencies. | 2001-01-25 | The plant returned to service on November 25, 2000 and so far has acheived 100% availability. An investigation is still underway to determine the root cause failure of the row 1 blades. The new thin seal has been re-installed in the machine and will be checked during the week of February 5, 2001 for any performance degradation. Power Sytems is still proceeding with their work.
Mexico | Vitro | Other | Development/Construction | Max Yzaguire / Steve Irvin / Marc Sabine | Rimbau/Virgo |  |  | Inherent exposure to change orders due to the fast track schedule. Changes resulting from lender requirements, permits, turbine storage and intereconnection are now included in the EPC agreement to mitigate the risk to potential change orders. | 1/30/2001, 03/26/01 | Project is off to a good start. Auth $1,606,262 Pen $409,359 (Oct) OE Proj $3,500,000. Project Kickoff Mtg on 01/18/00. Working on the OE and in the transition from development to execution.
Upstream | Nautilus | Other | EPC |  | Cocavessis |  |  | Exceeded project estimated cost by about $500,000 to cover additional environmental mitigation costs. Hurricane off Yucatan caused several days of demob for offshore work at our cost. | 2001-01-29 | Project is complete. Negotiating change orders with contractor.
Upstream | Spinnaker Liquids Handling | Other | EPC |  | Kuehler |  |  | Not established yet. | 2001-01-29 | The project is to enable HPL to handle condensate associated with the increased throughput of the Spinnaker Project. Currently evaluating the environmental impact and of using the existing slug catcher at Vector versus a grass-roots installation at Lehman. Cost will vary from $4 - $6 MM.
Upstream | Ballard Well Connect and Pipeline | Other | EPC |  | Kuehler |  |  | In construction. No risk; project is reimburseable by the producer. | 2001-01-29 | Contruction complete except for connection to producer which is pending the condemnation hearing the week of 1/29.
Upstream | Ship Channel Crossing Pipeline Removal | Other | EPC |  | Kuehler |  |  | Risk associated with the level of cleanliness required to prevent contaminating the Ship Channel once the pipe is cut. Have mitigated the risk by using robust chemical cleaning. | 2001-01-29 | Phase I construction (cleaning of the pipeline)was completed on January 10. Phase II construction (removal of the pipelines) started January 15. Estimated project cost is $1,300,000 (includes an allowance of $200,000 to remove piping currently on Exxon property if forced by Exxon).
Upstream | Constellation Power - Rio Nogales Plant | Other | EPC |  | Cocavessis |  |  | No Risk. | 2001-01-29 | Scope reduced - No ENA involvement. Constellation Power is assuming all risk associated with the EPC of this project including the pipelines and meter stations. Reduced the scope of work to HPL providing a tap into its line to be reimbursed by CP.
Upstream | Constellation Power - Gateway Plant | Other | EPC |  | Cocavessis |  |  | Risk mitigation was based proposal on several material and construction bids and a detailed scope provided by the client. | 2001-01-29 | This is an EPC opportunity through HPL. ENA is negotiating a construction contract. The value of the project is $9,600,000 with about 13% in construction profit. HPL has proposed a gas supply contract. LOW PROBABILITY PROJECT
Upstream | ANP Chambers County Plant | Other | EPC |  | Cocavessis |  |  | Risk mitigation was based proposal on several material and construction bids and a detailed scope provided by the client. | 2001-01-29 | This is an EPC opportunity through HPL. ENA appears to be the chosen contractor. The value of the project is $3,000,000 with about 12% in construction profit. ANP still determining the viability of project.
Upstream | Crescendo (NG Resources) | Other | EPC |  | Cocavessis |  |  | Exposure is approximately $1MM for the process plant. The contractor has a limited overrun liability because of the way the contract was negotiated. There may be additional exposure in the event discussions between ENA and the gas gathering company collapse and ENA is required to provide its own gas gathering system (cost is about $4,000,000) | 2001-01-29 | Contractor's current cost estimate is about $9.5MM for the process plant vs. the $8.65 budgeted. The cost increase accounts for increasing the plant throughput from 20mmscfd to 24mmscfd. A $9MM cost is targeted.
Upstream | Crescendo (NG Resources) - Wildhorse Gathering System | Other | EPC |  | Cocavessis |  |  | To conduct full due diligence prior to a binding offer. | 2001-01-29 | Crescendo considering the purchase of Tom Brown's Wildhorse Gas Gathering assets associated with the Nitrogen Rejection plant. Total asset cost estimated to be around $5MM.
Upstream | South Albuquerque N. M. Power Plant and LDC Gas SupplyProposal | Other | EPC |  | Cocavessis |  |  | Risk mitigation was based on material and construction bids and a preliminary scope developed internally. | 2001-01-29 | ENA will be proposing a gas supply contract to this power plant. The pipeline has been oversized to allow for other area customers. Project cost is estimated at $15MM
Upstream | Silas Ray Power Plant and Brownville, Tx Gas Supply Proposal | Other | EPC |  | Cocavessis |  |  | Risk mitigation was based on material and construction bids and a preliminary scope developed internally. | 2001-01-29 | ENA will be proposing a gas supply contract to this power plant. The pipeline has been oversized to allow for other area customers. Project cost is estimated at $16MM
Energy Capital Resources | Bonne Terre Exploration | Other | Exploration Program |  | Pruett / Fox |  |  | Exploration Risk | 2001-01-26 | Dissolution negotiations with SGA proceeding. Expect spud of Wedge (Manti Operated) and Pines Ridge Prospects (Manti) within 30 days. Recently re-processed 3-D data very encouraging with respect to Hackberry amplitude prospects. Mayne & Mertz has drilled 2 successful Hackberry wells immediately to the north of the Bonne Terre prospective area. Working to promote prospects to industry.
Energy Capital Resources | CGAS | Other | Exploration Program |  | Pruett / Fox |  |  | Exploration Risk | 2000-12-19 | Exploration strategy working according to business plan. F&D for 2000 projected at $.89/Mcfe all-in. $10.4 MM capital budget presented 12/14/00.
Energy Capital Resources | Cypress Exploration | Other | Exploration Program |  | Pruett / Fox |  |  | Exploration Risk | 2001-01-26 | Riceville Miogyp Prospect drilling below 14,100' to 16,500' target. Partners are Tri-C(Operator) and Preston Exploration. ENA paying 14% WIBCP to earn 42% WIACP (with $650 M cost reimbursement). Additional prospects under review by Rozel (Bill Rogers) . Expect activity at Lakeside (S. of Thornwell) based on latest seismic processing.
Energy Capital Resources | Hanson | Other | Development Drilling |  | Fox |  |  | Exploration Risk | 2001-01-26 | TP Ranch #3 on production at 3.5 MMcfd + 230 Bopd. Negotiating buyout of creditor interests, evaluating options for additional drilling.
Energy Capital Resources | Vastar Onshore | Other | Operational Review |  | Pruett / Fox |  |  | Exploration Risk | 2000-12-19 | Bluewater Prospect preparing to spud. 15-20 Bcf potential in Marg Tex Sand. Partners are Samedan, Operator, (50% WIBCP/35% WIACP), and Andex (30% WIBCP/25% WIACP). Vastar carried by Samedan for 15% WIACP. ENA paying 20% WIBCP for 25% WIACP. This well is probably final exploratory test in program.
Energy Capital Resources | Preston VPP (St. Mary's Production Co.) | Other | Production Payment |  | Fox |  |  | Reserves and production profile | 2001-01-26 | 2 deals combined into $70 MM transaction. Reserves located in NW Myette Point, St. Mary Ph., La. Term of VPP is 3.5 years
Portfolio Management | Anson VPP | Other | Production Risk |  | Neyman |  |  | VPP ending, no technical risk | 2000-10-26 | Some potential for reservoir and mechanical risk on any production payment but we're collateralized such that risk is minimal
Portfolio Management | EnSerCo | Other | Other |  | Lydecker |  |  | Sale in progress | 2001-01-26 | Potential sale in Q1
Portfolio Management | Hanover Compressor | Other | Operational Review |  | Lydecker |  |  | Minority Public, no technical risk | 2001-01-26 | Hanover is a natural gas compressor service outsourcing company, there is no technical risk. The value is strictly driven by the market. Attempting to sell by end of 2001
Portfolio Management | Inland Resources | Other | Operational Review |  | Lydecker |  |  | Preferred minority interest, no technical risk | 2001-01-26 | Company has risk in exploitation of reserve base. ENA bears no direct technical risk. Currently working to dispose of the asset.
Portfolio Management | Linder Petroleum | Other | Operational Review |  | Lydecker |  |  | Ltd Partnership, production/development risk. | 2000-10-26 | Potential buyout of interest by Roger Linder (principal), bid/offer spread defined, working to expedite a transaction.
Portfolio Management | Mariner Energy | Other | Operational Review |  | Melendrez/ Bowen/Fox |  |  | Private - Development risk, most of the company's activity is in deep water Gulf of Mexico. | 2000-10-30 | Jeff Sherrick (ENE) sits on the BOD, outside engineering is performed by Ryder Scott and technical risk is reviewed by Craig Fox. On Oct. 18, approved Key West prospect (100% WI), King Kong development project, and 3 short cycle development projects that should add to 2001 reserves and cash flow.
Portfolio Management | Masada | Other | Operational Review |  | Lydecker |  |  | Equity position; Solid Waste Conversion that extracts enthanol from garbage. Pre-development phase, no financing and no EPC. | 2000-10-26 | Masada has obtained insurance coverage from Hartford Steam Boiler for construction and threshold performance criteria. No direct technical risk to ENA at this time. Projected revenue will come from "tipping". Currently working to dispose of the asset, however a challenge due to the venture capital nature of the project.
Principal Investing | AMPS | Other | Generation Technology | Bob Virgo | M. L. Miller/Virgo |  |  | Advanced Mobile Power Systems - Jet engine technology PSM lacks a track record for reverse engineering complete power gen systems (but has reverse engineered turbine parts for ENE) PSM expects to hire ex-Pratt & Whitney engineers who worked on the original mobile design. | 2001-03-13 | Desk indicates an interest in purchasing the first 2 units for installation in Jacksonville. Waiting on AMPS to finalize Marketing Director hire. Will do a turnover at that time.
Principal Investing | DAC | Other | Generation Technology |  | Vetters |  |  | Testing to begin shortly on HVAC polymer technology. Will update as results become known. | 2000-10-26 | Option on Public Markets
Principal Investing | Destec | Other | Coal Reserves |  | Kuykendall |  |  | Coal Position - Contract monetization: no technical risk | 2000-10-26 | Only thing remaining is the reserves. Destec no longer exists.
Principal Investing | Encorp | Other | Generation Technology |  | Vetters |  |  | Private Minority Interest, no technical risk. Leading edge technology for controls communictions and grid interconnection for auxilary and emergency power generators. | 2000-10-26 | Outperforming original expectations. Market is lagging behind their technology and not expected to catch up before a potential IPO in Q1 or Q2 of '01. Beginning to raise last round of private equity.
Principal Investing | First World | Other | Operational Review |  | Kuykendall |  |  | Basis is $0, currently own 3MM warrants, slightly above water. | 2000-10-26 | Service provider, only market risk, no technical issues.
Principal Investing | Fuel Cell Technology | Other | Green Power |  | Vetters |  |  | Technologically sound. | 2000-10-26 | Cost must be reduced to make technology competitive,
Principal Investing | Metering Technology Corp | Other | Operational Review |  | Kuykendall |  |  | U.S. Private; no technical risk. | 2000-10-26 | ENA offering market introductions for Metering Technology. The meters are standardized and as they are launched into a new Market (for example India) they are configured to meet "market standards" and have to receive approvals (timing only, not technical)
Principal Investing | Solo | Other | Generation Technology |  | Vetters |  |  | Micro turbine technology | 2000-12-15 | Finalizing field test; next phase beta test at SCANA to run 5/01 - 9/01. Chase has been hire to raise private funds.
Principal Investing | Syntroleum | Other | Technological Review |  | Vetters |  |  | Australian Synfuels project | 2000-12-15 | Stone & Webster retained for technical due diligence, report has been forwarded to Syntroleum for comment and then ENA will assess potential LOI for incremental $20MM in capital.
Principal Investing | Tridium | Other | Technological Review |  | Kuykendall |  |  | Java based remote control of distributed hardware. Risks related to customer acceptance and competition on the technology front. | 2000-10-26 | Currently the only company offering open system capability which is increasingly in demand; and is negotiating with industry leaders that currently offer closed system configuration. Company has a 12-18 month lead on competitors.
Principal Investing | Utiliquest | Other | Operational Review |  | Kuykendall |  |  | Locates pipe & wires subsurface, no technical risk | 2000-10-26 | Low tech service business. Strictly operational review.
East | Georgia Peakers: Sites at Hartwell and Athens under Review | Other | Development/Construction | [5 empty] | 2001-01-05 | Air Permit in Progress, E&S plan in progress.
East | Fuel Cells | Other | Development/Construction | [5 empty] | 2001-01-05 | Waiting on final PO with FCE
East | Cogentrix Coal Plants (Alamac) - Performance Test Protocol | Other | Development/Construction | Ozzie Pagan/Dwight Beach |  |  |  |  | 2001-02-26 | D. Williams sent Rich Kottke to plants to find a way to parrallel BFPs.
West | Cleburne Review | Other | Other | [5 empty] | 2001-01-05
West | GE 7FA for Longview, Washington | Other | Other | Jake Thomas/Bill Williams |  |  |  |  | 2001-05-07
East | Alcoa - Lead Shedding | Other | Development/Construction |  | Virgo |  |  |  | 2001-03-13 | Sponsored by: Bob Virgo. Waiting on Alcoa - Hoppe has left Enron. Don't know effect on project.
East | Trona Plant Investigation | Other | Development/Construction | Dean Russell |  |  |  |  | 2001-03-13 | Visited IMC facility at Trona, CA with Rod Griscom. Looking at some possible ways to reduce fuel/steam consumption and use the reduction to generate emission credits
West | Golden Dale | Other | Other | [5 empty] | 2001-04-09 | Meetings scheduled in Portland 10-13 April to perform due diligence.
West | LVC II | Other | Other | Ed Clark, Bill Williams |  |  |  |  | 2001-04-09 | EPC contract signed 3/30/01. Tech review with Desser Rand on 4/10/01.
West | PSCo, Colorado 6x LM6000 simple cycle peaker | Other | Other | Jake Thomas |  |  |  |  | 2001-04-30 | Project has been sold.
East | Ft. Pierce, FL Repowering of existing steam plant | Other | Other | Dave Fairley |  |  |  |  | 2001-04-30 | TL's approved up to $1,700,000 - waiting management approval of additional funds. Team working last revision of FPUA agreements. Engineering onhold waiting on DASH. Looking for final negotiation.
West | Coal Intiative, Southwest US, Texas, and Western US | Other | Other | Mitch Robinson |  |  |  |  | 2001-04-30 | TL approved up to $85,000. Seminole Tribe incorporating comments into LOI. Tech visit in three weeks. Seminole Electric Cooperative - draft LOI to be sent this week. Conceptual layout in preparation. Ormet - identifying local culm piles and preparing site layout. TMPA - preparing possible layout and beginning to identify possible common facilities. Ft. Mohave Tribe - contacts regards possible site.
East | FL Greenfield Projects: including Pompano and Deerfield Beach, Midway, South Dade, Medley & Corbett | Other | Other | Steve Krimsky / Greg Krause |  |  |  |  | 2001-04-23 | Preparing FPL submittals, SwYd layouts and One Line Diagrams. Pompano Beach: White paper to be released w/o 2/12/01. P&Z hearing 2/28/01. ERP, WUP & PSD filed. Deerfield Beach: White paper targeted w/o 2/26. Draft ERP application under review. Public hearing in March. Midway: ERP & PSD applications filed. Open house 2/13/01, P&Z hearing 2/15/01. South Dade (Certosa): ERP & PSD applications filed. Public hearings March & April. Apparent goal is to permit & bank the sites, then flip. Need turbines & long-lead BOP on order ASAP if we expect to hit Summer '02 on any of these sites. Silent participation in MHI weekly conference calls. Submitting data requests to MHI as ReoGEN questions. Establishing MHI scope of supply for units 3 & 4. Reviewing PBPower drawings submitted.
East | TexMex, TX: Installation of AC/DC tie, power export to Mexico | Other | Other | Ozzie Pagan |  |  |  |  | 2001-04-23 | Interface with Bpub and ABB.
East | Mexico Projects: Copamex Fersinsa, FAPSA, Arancia Corn Products, Willamette de Mexico, CIPSA | Other | Other | Matt Duffy |  |  |  |  | 2001-04-23 | Project proposal input. Preparing electrical tie-in estimated and SwYd equipment layout.
Other | Virtual Power - Disbributed Generation, West TX | Other | Other | [5 empty] | 2001-04-23 | Investigate/Proposal - ABB/Encorp convert gas compressors to TG's.
Other | CanFibre/Kafus - MDF plant startup | Other | Other | John Enerson |  |  |  |  | 2001-04-30 | Developing plans for Lackawanna performance test which will occur in May or June.
Other | Papier Masson - startup of TMP | Other | Other | Paul Devries |  |  |  |  | 2001-04-30 | Passed 72 hour performance test. Final completion signoff in next two months.
Other | Stockton Generation - RFP process for acquisition from Air Products | Other | Other | Mike Etringer |  |  |  |  | 2001-04-30 | Project now on hold pending resolution of some uncertainties (!) in CA energy market.
Other | Ramgen | Other | Technological Review | Kyle Kettler |  |  |  |  | 2001-04-30 | Review of technology.
Other | Fapsa: 12MW Cogen, Mexicali | Other | Other | [5 empty] | 2001-03-26 | Provided EPC quote, waiting on PPA, preparing the DASH for management approval.
Other | Doyle Ins. Claims | Other | Other
Other | Project Dodger: York Research Assets: 1) Trinidad, 2) Big Springs, 3) Brooklyn Navy Yard, 4) Coney Island | Other | Other | David Marks |  |  |  |  | 2001-05-07 | Site survey of Trinidad last week. Big Spring wind farm this week. Visit to Brooklyn Navy Yard data room next week.
Other | Baja Coal Project, La Jovita, Rosarita, Baja California | Other | Other | Matt Duffy, Naveed Ahmed, and Jaime Alatorre (Mexico) |  |  |  |  | 2001-05-07 | Site surveys on 4/3/01 completed at Rosarita and La Jovita. Bruce Golden is developing.
East | Orlando Cogen | Other | Other | George Schaeffer |  |  |  |  | 2001-05-07 | Due diligence report issued 3/23/01. Bid made on 3/27/01. Notified that bid was lost.
Other | Las Vegas Cogen II (Priscilla) | Other | Other | Jim Gilbert |  |  |  |  | 2001-04-30 | Working tolling agreement. Final documents and reviews working for Bridge Load Extension to the Development DASH. Site introduction to Ray Campbell next week. Turnoer to Ed Dannhaus following Full NTP - anticipated 05/01/01.