## Sheet2 (hidden)
TVA Peaking Plant
Issues/Savings
Issue
EECC increased current estimate
Fuel cost during start up not included
Tax Handling Fee to LLC for arms length transaction .25% not included in plan
Savings Recognized
| New Albany | Caledonia | Brownsville | Total
Decrease Environmental permitting | -310000 | -300000 | -233000 | -843000
Decrease Legal expense | -550000 | -550000 | -350000 | -1450000
Decrease Development | -200000 | -200000 | -200000 | -600000
Total Savings | -1060000 | -1050000 | -783000 | -2893000

## NA Mquip (hidden)
New Albany
Major Equipment Detail
Refurbishment with DLN Units 1-6
(includes commission) |  | 26785396
| Spare Parts | 5214604
32000000
Dow Unit
| Purchase & spares | 1347000
| Dissassembly | 500000
| Commission 10% | 134700
1981700
4 Kepco Units (original)
| Purchase | 27502700
| Commission IBC(10%) | 2700000
| Commission Natole | 900000
| Less Steam Turbine | -700000 | Allocate to 2000
| Disassemble & move to Kunsan Port | 1307660
| Less Steam Turbine | -200500 | Allocate to 2000
| Freight Reimbursement to IBC | 1274025
| Less Steam Turbine | -100000 | Allocate to 2000
| Commission (7%) | 89181.75
32773066.75
1 Kepco Unit (new set)
| 1 of 4 Purchase price | 6875000
| Disassembly & shipping | 500000
| Commission | 0
7375000
Unidentified |  | 0 | Spare parts to be reconciled per Miller
Total IBC items |  | 74129766.75
Transformers etc |  | 10870000
Grand Total Major Equipment |  | 84999766.75

## EECC (hidden)
EECC RECONCILIATION
| Control | Current
| Budget | Estimate |  | Net Increase
Brownsville | 395276 | 587051 |  | 191775
0
Caledonia | 395276 | 620100 |  | 224824
New Albany | 395276 | 641831 |  | 246555
Fulton | 395276 | 225000 | a | -170276
Total | 1581104 | 2073982 |  | 492878
a) Sunk Cost

## To Update (hidden)
To Update:
1 | Save file as new name
2 | Go to Summary tab
in cell "O3" drop in date of Project Tracking report used as backup
3 | Go to LLC tab
unhide all columns
update actuals for applicable month
check totals
tie budget and current estimate to report from week before
make sure that sum of Actuals to Date Total Project + Estimate to Complete + variance = Current Estimate amount
4 | Go to Summary tab
update variance explanations to current estimate

## Summary
ENRON CAPITAL & TRADE RESOURCES
1999 TVA PEAKING PLANTS | [5 empty] | Report Date: |  |  | 2025-09-26 22:33
COST SUMMARY ($ thousands) | [5 empty] | Expenditures to date: |  |  | as of 12/10/99
Revision # 56
Actuals
|  |  | Current Estimate | Actuals to Date | Estimate to Complete |  | Total to Complete | Variance | %
Project |  | MW | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 |  | as of 12/10/99 | from CE | Complete
BROWNSVILLE, TN |  | 458 | 123741.9855 | 125266.8015 | 2972.8762 |  | 128239.6777 | -4497.6922 | 97.68%
CALEDONIA, MS |  | 442 | 148897.9926 | 151635.291 | 3009.368 |  | 154644.659 | -5746.6663 | 98.05%
NEW ALBANY,MS |  | 360 | 128386.3001 | 144071.4588 | 4185.7383 |  | 148257.1971 | -19870.897 | 97.18%
Less: Depreciation |  |  |  | -4589.7058 | 0 |  | -4589.7058 | 0 | -
(thru 11/99)
TOTAL PROGRAM |  | 1260 | 401026.2782 | 416383.8455 | 10167.9824 |  | 426551.828 | -30115.2556 | 97.64%
Target $$/MW
(without Debt Res) |  |  | 318.2748 |  |  |  | 338.5332
Changes to Current Estimate Explanations
All Plants | 11/10 | Decrease costs due to reduced interest expectation and reduced financing fees.
| 11/16 | Decrease costs due to reduced spare part expense.
Increased costs related to increased O&M/Startup costs
| 12/09 | Recognition of Switchyard increase (NEPCO)
| 1/26 | Decrease estimated Interest Charges for Interest Rate Swap (7.5% Cap Chg vs. 5.75% swap)
Increase for Startup fuel not in original Budget
| 1999-04-27 | Increased Insurance costs to carry additional 30-60 days of Builder's Risk insurance.
Weekly Beginning | 3/30 | Updated IDC, commitment fee and swap gain / (loss) based on actual draws to date and current interest rates.
New Albany | 11/16 | Increased cost related to $7.5 MM for DLN equipment
| 2/2 | Final approved New Albany NEPCO/EECC budget presented in 1/99 (excludes turbine switch)-incr of $483k
Caledonia | 1/26 | Remove cost associated with dedicated train
Current Estimate vs Actual Variance Explanations (000s)
Brownsville: |  | -2073.1009 | Major Equipment variance (include change orders and circuit breaker installation)
|  | -147.6717 | EECC Program Management
|  | -1069.0377 | NEPCO (primarily major mechanical, Above and Underground Electrical, and Startup, Training, Manauals)
|  | -13.7504 | Increased EI Startup primarily for augmenting O&M staffing during the startup and commissioning due to the compressed commissioning
and turnover schedule.
|  | -1051.1119 | ECT development / land acquisition / permitting cost overages
|  | -3.1374 | Electrical Interconnection
|  | -1.725 | Interest credit on unused cash
|  | -103.7697 | Financing fees more than expected-ECT
|  | 771.9489 | Startup fuel
|  | -4.386 | Insurance during construction
|  | -19.3253 | Commitment fee (trueup to actuals)
|  | -284 | NEPCO Interest Charges
|  | -497.6268 | Spare Parts
-4497.694
Caledonia: |  | -2416.8989 | Major Equipment (progress pymts to ABB for transformers and circuit breakers, change orders and circuit breaker installation)
|  | -165.8542 | EECC Program Management
|  | -3704.6391 | Construction variance-NEPCO (primarily major mechanical, startup, training, manuals, above and below ground electrical)
|  | 115.9596 | Increased EI Startup primarily for augmenting O&M staffing during the startup and commissioning due to the compressed commissioning
and turnover schedule.
|  | -668.7868 | ECT development / land acquisition / permitting cost overages / legal / insurance
|  | -125.1123 | Electrical interconnection
|  | 117.884 | Interest credit on unused cash
|  | 805.317 | Sales tax savings
|  | 863.9639 | Startup fuel
|  | -283 | NEPCO Interest Charges
|  | -285.0197 | Financing fees more than expected-ECT
-5747.1865
New Albany: |  | 100.6774 | Dow 7B removal/shipping cost savings
|  | -1931.9509 | Major equipment variance (incl change orders and circuit breaker installation & transformer repair)
|  | -2968.9787 | Cost overrun on Korean (Kunsan) units deconstruction/move/transport
(incl cost of moving #1-4 from Korea to Pensacola and #1-6 from Pensacola to New Albany)
|  | -17.179 | Circuit Breakers - movement of actuals from transformers
|  | -964.413 | KEPCO Youngwol units (incl cost of trans one unit from Korea to Pensacola)
|  | -8506.6375 | Overrun on Refurbishment of KEPCO units (estimated costs NOT FINAL)
|  | -2526.1565 | Cost overrun on Spare Parts
|  | -557.848 | Estimated overrun on EECC Program Mgmt. based on EECC's revised budget captions
|  | -93.6086 | Increased EI Startup primarily for augmenting O&M staffing during the startup and commissioning due to the compressed commissioning
and turnover schedule.
|  | -2158.5542 | NEPCO - (primarily construction - maj. mech. equip, above ground electrical, TTS Scope)
|  | -716.9249 | ECT development / land acquisition / permitting cost overages / insurance
|  | -153.7697 | Financing fees more than expected
|  | 64.384 | Interest credit on unused cash
|  | 263 | Sales tax savings
|  | 624.9843 | Startup fuel
|  | -260 | NEPCO Interest Charges
|  | -68.9732 | Electrical Interconnection
-19870.9485
-30115.8291
NOTE: | This summary includes updates reported in the September Detailed Cost Status Report received from EE&CC.
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/TVA_Wkly_Anal___121499.xls'#$Summary

## Brownsville
ENRON CAPITAL & TRADE RESOURCES
COST SUMMARY ($ thousands)
BROWNSVILLE (458 MW) | [5 empty] | 458 | MW | [22 empty] | 2025-09-26 22:33 |  | Revision # 56
[12 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals |  | Anticipated
[6 empty] | ECT |  |  | ECT | Actuals to Date | Actuals to Date | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | Actuals to Date | Increase / | ESTIMATE | TOTAL
|  |  | Responsibility | Enron Contact | Certainty | CONTROL BUDGET |  | Increase/(Savings) | CURRENT ESTIMATE | 1998-12-21 | 12/21-12/31/98 | 1999-01-31 |  | 1999-02-28 |  | 1999-03-31 |  | 1999-04-30 |  | 1999-05-31 | 1999-06-30 | 1999-07-31 | 1999-08-31 | 1999-09-30 | 1999-10-31 | 1999-11-30 | 1999-12-31 | Total Project | (Savings) | TO COMPLETE | PROJECT | VARIANCE | Comments
[10 empty] | as of 10/1/99 | as of 10/1/99 | as of 12/10/99 |  | as of 12/10/99 |  | as of 12/10/99 |  | as of 12/10/99 |  | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99
MAJOR EQUIPMENT
| TURBINE UNITS - 5D'S (4ea) | WH | MM | Bob Emerson | Vendor Quote | 68797500 |  | 0 | 68797500 | 55432001 | 3467538 | 48600 |  | 3705425.2 |  | 3342087.7 | [6 empty] | 3337740.9 |  |  |  |  | 69333392.8 | 532936 | 0 | 69333392.8 | -535892.8
| TD OF 1 | WH | SG | Bob Emerson | estimate | 1397500 |  | 0 | 1397500 | 0 | 0 | [6 empty] | 338722 |  | 840995 | 276019 | 136426 |  | 172832 | 16019 |  |  | 1781013 |  | 0 | 1781013 | -383513
| REDUNDANT DPU'S | WH | SG | Bob Emerson | Vendor Quote | 97872 |  | 0 | 97872 | 0 | 0 | [16 empty] | 0 | -97872 | 0 | 0 | 97872
| LADDERS & PLATFORMS | WH | SG | Bob Emerson | Vendor Quote | 33132 |  | 0 | 33132 | 0 | 0 | [16 empty] | 0 | -33132 | 0 | 0 | 33132
| LIGHT KITS | WH | SG | Bob Emerson | Vendor Quote | 5504 |  | 0 | 5504 | 0 | 0 | [16 empty] | 0 | -5504 | 0 | 0 | 5504
| FUEL METERING | WH | SG | Bob Emerson | Vendor Quote | 85744 |  | 0 | 85744 | 0 | 0 | [16 empty] | 0 | -85744 | 0 | 0 | 85744
| WATT/VAR METERING | WH | SG | Bob Emerson | Vendor Quote | 40000 |  | 0 | 40000 | 0 | 0 | [16 empty] | 0 | -40000 | 0 | 0 | 40000
| CAPITAL SPARES | [26 empty] | 0 | 1500000 | 1500000 | 1500000 | -1500000
| 85 dBa ATTENUATION | WH | SG | Bob Emerson | Vendor Quote | 210000 |  | 0 | 210000 | 0 | 0 | [16 empty] | 0 | -210000 | 0 | 0 | 210000
| TOTAL WH EQUIP |  |  |  |  | 70667252 |  | 0 | 70667252 | 55432001 | 3467538 | 48600 |  | 3705425.2 |  | 3342087.7 |  | 338722 |  | 840995 | 276019 | 136426 | 3337740.9 | 172832 | 16019 | 0 | 0 | 71114405.8 | 1560684 | 1500000 | 72614405.8 | -1947153.8
| POWER TRANSFORMERS | ABB | SG | Bob Emerson | Vendor Quote | 5300000 |  | 0 | 5300000 | 1929482 | 0 | 1590000 | [5 empty] | 1060000 |  | 265000 | 692015.89 |  |  | -236497.89 |  |  |  | 5300000 |  | 0 | 5300000 | 0
| AUX TRANSFORMERS | ABB | SG | Bob Emerson | Vendor Quote | 162480 |  | 0 | 162480 | 24815 | 0 | [6 empty] | 115801 | [5 empty] | 24814.5 |  |  |  | 165430.5 | 0 | -0.5 | 165430 | -2950
| LOAD CENTER TRANSFORMERS | ABB | SG | Bob Emerson | Vendor Quote | 59780 |  | 0 | 59780 | 11303 | 0 | [6 empty] | 52749.2 | [5 empty] | -5875.06 |  |  |  | 58177.14 | 0 | 0 | 58177.14 | 1602.86
| CIRCUIT BREAKERS | ABB | SG | Bob Emerson | Vendor Quote | 2968940 |  | 0 | 2968940 | 1032970 | 0 | 1361629 | [7 empty] | 129000 |  |  |  | 445341.46 |  |  |  | 2968940.46 | 0 | -0.46 | 2968940 | 0
| MISC CHANGE ORDERS | [6 empty] | 0 | 0 | [18 empty] | 0 | 0 | 0 | 0 | 0
| INSTALLATION OF CIRCUIT BREAKERS | [6 empty] | 0 | 0 | [10 empty] | 213100 |  | 174000 | [5 empty] | 387100 | 0 | 0 | 387100 | -387100
| TD OF I-ABB | ABB | SG | Bob Emerson | estimate | 25000 |  | 0 | 25000 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | 25000
| FREIGHT - TRANSFORMERS | ABB | SG | Bob Emerson | Vendor Quote | 107600 |  | 0 | 107600 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | 107600
| TRANSFORMER INSTALLATION | ABB | SG | Bob Emerson | Vendor Quote | 105500 |  | 0 | 105500 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | 105500
| OFF LOAD CIRCUIT BREAKERS | ABB | SG | Bob Emerson | estimate | 10000 |  | 0 | 10000 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | 10000
| MISC TVA REQUIREMENTS | ABB | SG | Bob Emerson | estimate | 20000 |  | 0 | 20000 | 0 | 0 | [6 empty] | 1200 |  | 4400 | [7 empty] | 5600 | 0 | 0 | 5600 | 14400
| TOTAL ABB EQUIP |  |  |  |  | 8759300 |  | 0 | 8759300 | 2998570 | 0 | 2951629 |  | 0 |  | 0 |  | 1229750.2 |  | 611500 | 692015.89 | 174000 | 0 | 227783.01 | 0 | 0 | 0 | 8885248.1 | 0 | -0.96 | 8885247.14 | -125947.14
| TOTAL MAJOR EQUIPMENT |  |  |  |  | 79426552 |  | 0 | 79426552 | 58430571 | 3467538 | 3000229 |  | 3705425.2 |  | 3342087.7 |  | 1568472.2 |  | 1452495 | 968034.89 | 310426 | 3337740.9 | 400615.01 | 16019 | 0 | 0 | 79999653.9 | 1560684 | 1499999.04 | 81499652.94 | -2073100.94
EECC PROGRAM MGT
| HOME OFFICE | EECC | SG | Bob Emerson | estimate | 251225 |  | 146275 | 397500 | 0 | 132437.87 | [9 empty] | 245110.72 | 97452.72 | -22914.74 |  | 17268.41 | 5054.93 | 7051.9 | 481461.81 | 85481 | 1519.19 | 482981 | -85481
| FIELD COORDINATION | EECC | SG | Bob Emerson | estimate | 6500 |  | 5700 | 12200 | 0 | 0 | [16 empty] | 0 | -12200 | 0 | 0 | 12200
| TVA INTERFACE COORDINATION | EECC | SG | Bob Emerson | estimate | 24500 |  | 0 | 24500 | 0 | 0 | [9 empty] | 23705.98 |  | 157.26 |  | -1665 |  |  | 22198.24 | -2302 | 0 | 22198.24 | 2301.76
| EXPENSES | EECC | SG | Bob Emerson | estimate | 113050 |  | 2250 | 115300 | 0 | 12386.94 | [9 empty] | 20278.74 | 27882.71 | 53401.94 |  | 5500 | 37400.15 |  | 156850.48 | 26700 | 0 | 156850.48 | -41550.48
| DEVELOPMENT AND PERMIT SPPT | EECC | SG | Bob Emerson |  | 0 |  | 37551 | 37551 | 0 | 37550.69 | [9 empty] | 35142.12 | [6 empty] | 72692.81 | 35142 | 0.19 | 72693 | -35142
| TOTAL EECC PROGRAM MGT |  |  |  |  | 395275 |  | 191776 | 587051 | 0 | 182375.5 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 324237.56 | 125335.43 | 30644.46 | 0 | 21103.41 | 42455.08 | 7051.9 | 733203.34 | 132821 | 1519.38 | 734722.72 | -147671.72
ENGINEERED BOP EQUIPMENT
| VALVES/PIPE SPECIALTIES | NEPCO | SG | David Lundquist |  | 53528 |  | 0 | 53528 | 0 | 0 | [8 empty] | 91897.14 |  | -91897 | [5 empty] | 0.14 | -53528 | 0 | 0.14 | 53527.86
| BUS DUCT |  | SG | David Lundquist |  | 1228835 |  | 0 | 1228835 | 0 | 82024 | 220594 | [5 empty] | 386895.9 |  | 39621 | 149.25 | -729283.9 | [5 empty] | 0.25 | -1228835 | 0 | 0.25 | 1228834.75
| DRY XMFERS & PANEL |  | SG | David Lundquist |  | 18358 |  | 0 | 18358 | 0 | 0 | [8 empty] | 7453 |  | -7453 | [5 empty] | 0 | -18358 | 0 | 0 | 18358
| 5KV & 480 V SWITCHGEAR & MCCS |  | SG | David Lundquist |  | 337106 |  | 0 | 337106 | 0 | 0 | 53.62 |  | 91706.12 |  | 309600 |  |  |  | 39789 |  | -441149 | [5 empty] | -0.26 | -337106 | 0.26 | 0 | 337106
| 15 KV SWITCHGEAR |  | SG | David Lundquist |  | 95368 |  | 0 | 95368 | 0 | 0 | [16 empty] | 0 | -95368 | 0 | 0 | 95368
| CONTROL PANEL/TERM BOXES |  | SG | David Lundquist |  | 2765 |  | 0 | 2765 | 0 | 0 | 0 | [5 empty] | 66392 |  | 23359.43 | 4163 | -93914 | [5 empty] | 0.43 | -2765 | 0 | 0.43 | 2764.57
| HIGH VOLTAGE DEVICES |  | SG | David Lundquist |  | 0 |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 530.66 |  | -531 | [5 empty] | -0.34 | 0 | 0.34 | 0 | 0
| DCS |  | SG | David Lundquist |  | 188829 |  | 0 | 188829 | 0 | 0 |  |  |  |  | 56700 |  |  |  |  | 144164 | -200864 | [5 empty] | 0 | -188829 | 0 | 0 | 188829
| UPS SYSTEM |  | SG | David Lundquist |  | 44266 |  | 0 | 44266 | 0 | 0 | [16 empty] | 0 | -44266 | 0 | 0 | 44266
| DC SYSTEM |  | SG | David Lundquist |  | 63897 |  | 0 | 63897 | 0 | 0 | [16 empty] | 0 | -63897 | 0 | 0 | 63897
| FIELD MOUNTED INSTRUMENTS |  | SG | David Lundquist |  | 61269 |  | 0 | 61269 | 0 | 0 |  |  |  |  | 1870.42 |  | 0 |  |  |  | -1870 | [5 empty] | 0.42 | -61269 | 0 | 0.42 | 61268.58
| STACK MONITORING |  | SG | David Lundquist |  | 424721 |  | 0 | 424721 | 0 | 0 | [8 empty] | 42687.75 |  | -42688 | [5 empty] | -0.25 | -424721 | 0.25 | 0 | 424721
| CONTROL VALVES |  | SG | David Lundquist |  | 65690 |  | 0 | 65690 | 0 | 0 | [8 empty] | 10031.06 |  | -10031 | [5 empty] | 0.06 | -65690 | 0 | 0.06 | 65689.94
| OTSG (Once-through Steam Generator) |  | SG | David Lundquist |  | 3447600 |  | 0 | 3447600 | 1136784 | -123504 | 507739.2 |  | 675520 |  | 928840 |  |  |  | 50000 |  | -3175379 | [5 empty] | 0.2 | -3447600 | 0 | 0.2 | 3447599.8
| PUMPS |  | SG | David Lundquist |  | 137799 |  | 0 | 137799 | 0 | 0 | [8 empty] | 170983.47 | 19420.12 | -190404 | [5 empty] | -0.41 | -137799 | 0.41 | 0 | 137799
| BRIDGE CRANE |  | SG | David Lundquist |  | 8023 |  | 0 | 8023 | 0 | 0 | [16 empty] | 0 | -8023 | 0 | 0 | 8023
| MINOR MECH EQUIP |  | SG | David Lundquist |  | 16989 |  | 0 | 16989 | 0 | 25612.65 | [8 empty] | 102683.87 | 13421.95 | -141718.2 | [5 empty] | 0.27 | -16989 | 0 | 0.27 | 16988.73
| PRESSURE REDUCING STATIONS |  | SG | David Lundquist |  | 549000 |  | 0 | 549000 | 0 | 0 |  |  |  |  | 112350.68 |  |  |  | 2278.54 |  | -114629 | [5 empty] | 0.22 | -549000 | 0 | 0.22 | 548999.78
| GAS FILTER |  | SG | David Lundquist |  | 134000 |  | 0 | 134000 | 18058 | -18058 |  |  |  |  | 21067.2 |  |  |  | 21067.2 |  | -42134 | [5 empty] | 0.4 | -467000 | 0 | 0.4 | 133999.6
| Steam/WATER SEPARATOR |  | SG | David Lundquist |  | 0 |  | 0 | 0 | 0 | 0 | [16 empty] | 0 | 0 | 0 | 0 | 0
| FIELD/SHOP FAB VESSELS |  | SG | David Lundquist |  | 389130 |  | 0 | 389130 | 0 | 141561.2 | [6 empty] | 62864.1 |  |  |  | -204425 | [5 empty] | 0.3 | -389130 | 0 | 0.3 | 389129.7
| OIL/WATER SEPARATOR |  | SG | David Lundquist |  | 23596 |  | 0 | 23596 | 0 | 0 | [16 empty] | 0 | -23596 | 0 | 0 | 23596
| TOTAL ENGINEERED BOP EQUIP |  |  |  |  | 7290769 |  | 0 | 7290769 | 1154842 | 107635.85 | 728386.82 |  | 767226.12 |  | 1430428.3 |  | 516152 |  | 602382.12 | 181318.32 | -5488370.1 | 0 | 0 | 0 | 0 | 0 | 1.43 | -7623769 | 1.26 | 2.69 | 7290766.31
CONSTRUCTION
| SITE PREPARATION | NEPCO | SG | David Lundquist | estimate | 215657 |  | 0 | 215657 | 0 | 0 | 260283 |  | -69761 | [5 empty] | 0 | -2237 | 0 | [5 empty] | 188285 | -27372 | 0 | 188285 | 27372
| SITE IMPROVEMENTS |  |  | David Lundquist |  | 728097 |  | 0 | 728097 | 0 | 0 | 225000 |  | 97000 |  | 22906 |  |  |  | 2634 | 3790 | 93762 | 115343 |  | 26637 |  |  | 587072 | -141025 | 0 | 587072 | 141025
| UNDERGROUND ELECTRICAL (LAB & MAT) |  |  | David Lundquist |  | 216167 |  | 0 | 216167 | 0 | 0 | 130466 |  | 69885 |  | 93842 |  |  |  | 111933 | 38279 | 134817 | 47964 |  | 37098 |  |  | 664284 | 416081 | 0 | 664284 | -448117
| UNDERGROUND PIPING (LAB & MAT) |  |  | David Lundquist |  | 365324 |  | 0 | 365324 | 0 | 0 | 6887 |  | 24435 |  | 127949 |  |  |  | 87618 | 94201 | 69728 | 2294 | 129 |  |  |  | 413241 | 47788 | 0 | 413241 | -47917
| CONCRETE |  |  | David Lundquist |  | 1364088 |  | 0 | 1364088 | 0 | 0 | 410522 |  | 226458 |  | 174859 |  |  |  | 119588 | 84286 | 123276 | 23822 | 1295 | 4108 | 1842 |  | 1170056 | -201045 | 0 | 1170056 | 194032
| GROUT & SPECIAL COATINGS |  |  | David Lundquist |  | 75872 |  | 0 | 75872 | 0 | 0 | 0 |  |  |  | 7606 |  |  |  |  | 12593 | 20526 | 2412 |  |  |  |  | 43137 | -32735 | 0 | 43137 | 32735
| STRUCTURAL STEEL (LAB & MAT) |  |  | David Lundquist |  | 50931 |  | 0 | 50931 | 0 | 0 |  |  |  |  | 617 |  |  |  | 2982 | 13928 | 81336 | [5 empty] | 98863 | 43987 | 0 | 98863 | -47932
| ARCHECTURAL |  |  | David Lundquist |  | 19817 |  | 0 | 19817 | 0 | 0 | [8 empty] | 47192 |  | 1064 |  |  |  | 575 |  | 48831 | 29014 | 0 | 48831 | -29014
| SUBCONTRACT ERECTED BLDG'S |  |  | David Lundquist |  | 262088 |  | 0 | 262088 | 0 | 0 |  |  |  |  | 25522 |  |  |  | 103810 | 54933 | 145632 | 3170 | 873 |  |  |  | 333940 | 71852 | 0 | 333940 | -71852
| ABOVE GROUND PIPING |  |  | David Lundquist | [24 empty] | 0 | 0 | 0 | 0
| MATERIAL |  |  | David Lundquist |  | 187673 |  | 0 | 187673 | 0 | 0 |  |  |  |  | 2816 |  |  |  | 41140.58 | 199342 | 173856 | 28454 |  |  | 1865 |  | 447473.58 | 259801 | 0.42 | 447474 | -259801
| SUBCONTRACT |  |  | David Lundquist |  | 0 |  | 0 | 0 | 0 | 0 | [10 empty] | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0
| LABOR |  |  | David Lundquist |  | 148167 |  | 0 | 148167 | 0 | 0 |  |  |  |  | 1230 |  |  |  | 19155 | 75682 | 204199 |  | 194 |  |  |  | 300460 | 152099 | 0 | 300460 | -152293
| ABOVE GROUND ELECTRICAL |  |  | David Lundquist | [24 empty] | 0 | 0 | 0 | 0
| MATERIAL |  |  | David Lundquist |  | 516773 |  | 0 | 516773 | 0 | 0 | 0 |  | 6361 |  | 2837 |  | 336964.1 |  | 95774.76 | 91219.34 | 1724866.58 | 86929.72 | 56730 | 13514 | -1375 |  | 2413821.5 | 1132572 | 0 | 2413821.5 | -1897048.5
| SUBCONTRACT |  |  | David Lundquist |  | 119562 |  | 0 | 119562 | 0 | 0 | [10 empty] | 0 | [5 empty] | 0 | -119562 | 0 | 0 | 119562
| LABOR |  |  | David Lundquist |  | 546363 |  | 0 | 546363 | 0 | 0 | 0 |  |  |  | 3598 |  |  |  | 66600 | 226484 | 567335 | 192691 |  |  |  |  | 1056708 | 510345 | 0 | 1056708 | -510345
| INSTRUMENTATION |  |  | David Lundquist |  | 189969 |  | 0 | 189969 | 0 | 0 | [8 empty] | 111943.16 | 56074 | 213877 | 22635 |  | 6187 | 4440 |  | 415156.16 | 225187 | 0 | 415156.16 | -225187.16
| INSULATION |  |  | David Lundquist |  | 447894 |  | 0 | 447894 | 0 | 0 | [10 empty] | 74986.2 | 295693 | -55315 | 12549 |  |  | 327913.2 | -148290 | 0 | 327913.2 | 119980.8
| PAINTING |  |  | David Lundquist |  | 160658 |  | 0 | 160658 | 0 | 0 | [11 empty] | 54000 |  | 201988 | 7500 |  | 263488 | 102830 | 0 | 263488 | -102830
| OTSG'S |  |  | David Lundquist |  | 184852 |  | 0 | 184852 | 0 | 0 | 0 |  | 990 |  | 24155 |  |  |  | 61326 | 74313 | 3198313 | 1853 | 568639.67 |  | -18 |  | 3929571.67 | 3695120 | 0 | 3929571.67 | -3744719.67
| MINOR MECHANICAL EQUIP |  |  | David Lundquist |  | 2065720 |  | 0 | 2065720 | 0 | 0 | 4366 |  | 9118 |  | 328138 |  |  |  | 357359.93 | 451601 | 1726704.06 | 461180 | 119422 | 5572 | 21654 |  | 3485114.99 | 1389659 | 0 | 3485114.99 | -1419394.99 | Per Suzie G, put Backcharges & Changeorders here
| SWITCHYARD |  |  | David Lundquist |  | 3895281 |  | 3307345 | 7202626 | 0 | 153327 | 152376 |  | 96630 |  | 778248 |  | 628779.68 |  | 1693431.68 | 1713121.39 | 825495.44 | 323295.71 | -63445 | 71376 | 6922 |  | 6379557.9 | -823069 | 0 | 6379557.9 | 823068.1
| Third Party | [22 empty] | 26625.07 | 53590.28 | 47704.55 |  | 127919.9 | 0 | 0 | 127919.9 | -127919.9
| TOTAL CONSTRUCTION |  |  |  |  | 11760953 |  | 3307345 | 15068298 | 0 | 153327 | 1189900 |  | 461116 |  | 1594323 |  | 965743.78 |  | 2922488.11 | 3187609.73 | 9379773.28 | 1661736.43 | 655147.74 | 432619.28 | 91109.55 | 0 | 22694893.9 | 6583237 | 0.42 | 22694894.32 | -7626596.32
INDIRECTS
| ENGINEERING DIRECT LABOR | NEPCO | SG | David Lundquist | estimate | 561095 |  | 0 | 561095 | 0 | 0 | 122479 |  | 32686 |  | 37074 |  |  |  | 54446 | 45324.69 | 46854 | 2052 |  | 231 |  |  | 341146.69 | -432948 | 822996 | 1164142.69 | -603047.69
| ENGINEERING CONTRACT LABOR |  |  | David Lundquist |  | 69206 |  | 0 | 69206 | 0 | 0 | 6806 |  | 6554 |  | 24343 |  |  |  |  | 27624 | 7500 | 12600 | 152 |  |  |  | 85579 | 16373 | 0 | 85579 | -16373
| EQUIPMENT RENTAL , FUEL SMALL TOOLS |  |  | David Lundquist |  | 887183 |  | 0 | 887183 | 0 | 0 | 34493 |  | 107452 |  | 67926 |  |  |  | 135400 | 197804 | 287422 | 227079 | 22112 | 45004 | 14298 |  | 1138990 | 251807 | 0 | 1138990 | -251807
| GENERAL PROVISIONS, OVERHEAD, IND CON LABOR |  | SG | David Lundquist | estimate | 6477468 |  | 0 | 6477468 | 0 | 0 | 910946 |  | 398385 |  | 718647 |  |  |  | 505070 | 767510 | 89424 | 1933067 |  |  |  |  | 5323049 | -1154419 | 0 | 5323049 | 1154419
| STARTUP, TRAINING, MANUALS, CONTING, PRO ALLOW |  |  |  |  | 815943 |  | 0 | 815943 | 0 | 0 | 11418 |  | 60048 |  | 48858 |  |  |  | 120993 | 220735 | 324273 | 601116 | 299255 | 284632 | 177738 |  | 2149066 | 1099913 | 0 | 2149066 | -1333123
| TOTAL INDIRECTS |  |  |  |  | 8810895 |  | 0 | 8810895 | 0 | 0 | 1086142 |  | 605125 |  | 896848 |  | 0 |  | 815909 | 1258997.69 | 755473 | 2775914 | 321519 | 329867 | 192036 | 0 | 9037830.69 | -219274 | 822996 | 9860826.69 | -1049931.69
INTEREST CHARGES | [27 empty] | 0 | 284000 | 284000 | 284000 | -284000
OTHER COSTS - G&A |  | NEPCO | SG | David Lundquist | estimate | 726500 |  | 0 | 726500 | 0 | 0 | 38226 |  | 17728 |  | 44812.58 |  |  |  | 54996 | 73759 | 115901 | 40490 | 6865 | 12760 | 4237.94 |  | 409775.52 | 4238 | 0.48 | 409776 | 316724
TOTAL NEPCO SCOPE |  | NEPCO | SG | David Lundquist | estimate | 28589117 |  | 3307345 | 31896462 | 1154842 | 260962.85 | 3042654.82 |  | 1851195.12 |  | 3966411.88 |  | 1481895.78 |  | 4395775.23 | 4701684.74 | 4762777.18 | 4478140.43 | 983531.74 | 775246.28 | 287383.49 | 0 | 32142501.54 | -1255568 | 1106998.16 | 33249499.7 | -1353037.7
| TOTAL EECC & NEPCO SCOPE |  |  |  |  | 108410944 |  | 3499121 | 111910065 | 59585413 | 3910876.35 | 6042883.82 |  | 5556620.32 |  | 7308499.58 |  | 3050367.98 |  | 5848270.23 | 5993957.19 | 5198538.61 | 7846525.79 | 1384146.75 | 812368.69 | 329838.57 | 7051.9 | 112875358.78 | 437937 | 1108517.54 | 113983876.32 | -2073811.32
STARTUP & COMMISSIONING |  | EI | D. Regan | Noles |  | 600000 |  | 59539 | 659539 | 6110.75 | 0 | 25336.96 | [5 empty] | 74417 |  | 173681 | 225874 | 95731.61 | 68947.09 | 26336.93 | 1079.27 | 774.79 | 0 | 698289.4 | 30115.33 | 0 | 698289.4 | -38750.4
| EI Hourly billing | EI | D. Regan | Noles |  | 25000 |  | 0 | 25000 | 0 | 0 | [16 empty] | 0 | -25000 | 0 | 0 | 25000
[6 empty] | 625000 |  | 59539 | 684539 | 6110.75 | 0 | 25336.96 |  | 0 |  | 0 |  | 74417 |  | 173681 | 225874 | 95731.61 | 68947.09 | 26336.93 | 1079.27 | 774.79 | 0 | 698289.4 | 5115.33 | 0 | 698289.4 | -13750.4
SPARE PARTS |  | ECT | BV | Bob Virgo |  | 2000000 |  | -1179880 | 820120 | 0 | 0 |  |  | 0 | [8 empty] | 238231.22 | 16621.03 | 1062894.56 | 0 | 0 | 1317746.81 |  | 0 | 1317746.81 | -497626.81
LAND ACQUISITION |  | ECT | BV/MJG | Clay Spears |  | 446907 |  | 0 | 446907 | 446907 | 0 | [8 empty] | 3333.33 | [7 empty] | 450240.33 |  | 0 | 450240.33 | -3333.33 | Title Charges and Option Payment
| Additional fee paid for loss of crops | ECT | MJG |  |  | 7700 |  | 0 | 7700 | 7700 | 0 | [16 empty] | 7700 |  | 0 | 7700 | 0
| Right of Way Easement-Todd Chilcutt |  |  |  |  | 0 |  | 0 | 0 | 0 | 3500 | [16 empty] | 3500 |  | 0 | 3500 | -3500
[6 empty] | 454607 |  | 0 | 454607 | 454607 | 3500 | 0 |  | 0 |  | 0 |  | 0 |  | 3333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 461440.33 | 0 | 0 | 461440.33 | -6833.33
ENVIRONMENTAL PERMITTING |  | ECT | BV/MJG | Clay Spears | [26 empty] | 0
| Neel-Schaffer | [6 empty] | 0 |  | 148172.8 | 0 | 59941.69 |  | 0 |  | 0 |  | 0 |  | 66861.36 | 7106.38 | [5 empty] | 12247.95 | 294330.18 |  |  | 294330.18 | -294330.18
| TN. Department of Environment & Conservation | [6 empty] | 0 |  | 2100 | 0 | [16 empty] | 2100 |  |  | 2100 | -2100
| Walter Powell Surveying | [6 empty] | 0 |  | 4200 | 0 | [16 empty] | 4200 |  |  | 4200 | -4200
| Spencer Martin Surveying | [6 empty] | 0 |  | 41000 | 0 | [16 empty] | 41000 |  |  | 41000 | -41000
| Health Department | [6 empty] | 0 |  | 100 | 0 | [10 empty] | 298 | [5 empty] | 398 |  |  | 398 | -398
| Layne Christensen (Water Wells) | [6 empty] | 0 |  | 25237 | 0 |  |  | 30440.7 |  | 125057.7 |  | 24442.2 |  |  | 196903.8 | 83901.6 | [5 empty] | 485983 |  |  | 485983 | -485983
| KVB Entertec |  |  |  |  | 500000 |  | -233000 | 267000 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 37358.1 |  |  | 37358.1 |  |  | 37358.1 | 229641.9
| TOTAL ENVIRONMENTAL PERMITTING |  |  |  |  | 500000 |  | -233000 | 267000 | 220809.8 | 0 | 59941.69 |  | 30440.7 |  | 125057.7 |  | 24442.2 |  | 66861.36 | 204010.18 | 84199.6 | 0 | 0 | 37358.1 | 0 | 12247.95 | 865369.28 | 0 | 0 | 865369.28 | -598369.28
GAS INTERCONNECTION |  | ECT | BV/MJG | Chris Meyer |  | 0 |  | 0 | 0 | 0 | 0 | [16 empty] | 0 |  | 0 | 0 | 0
ELECTRICAL INTERCONNECTION |  | ECT | BV/MJG | Larry Soderquist
| W.O. Cost |  |  |  |  | 1543817 |  | 0 | 1543817 | 0 | 0 | 73861.53 | [5 empty] | 646527.34 |  |  | 379197.17 | 353835.71 | 91393.38 |  |  |  |  | 1544815.13 |  | 0 | 1544815.13 | -998.13
| O.H Cost (21.6%) |  |  |  |  | 333464.472 |  | 0 | 333464.472 | 0 | 0 | [12 empty] | 52976.2 | 5187.94 | 133605 | 3347.28 | 195116.42 |  | 138348.052 | 333464.472 | 0
| System Impact Study |  |  |  |  | 0 |  | 35152 | 35152 | 0 | 0 | [6 empty] | 11826.01 | [9 empty] | 11826.01 |  | 23325.99 | 35152 | 0
| Facilities Study |  |  |  |  | 0 |  | 55920 | 55920 | 0 | 0 | [6 empty] | 59057.41 | [9 empty] | 59057.41 |  | 0 | 59057.41 | -3137.41
[6 empty] | 1877281.472 |  | 91072 | 1968353.472 | 0 | 0 | 73861.53 |  | 0 |  | 0 |  | 717410.76 |  | 0 | 379197.17 | 353835.71 | 91393.38 | 52976.2 | 5187.94 | 133605 | 3347.28 | 1810814.97 | 0 | 161674.042 | 1972489.012 | -4135.54
SALES TAX ON EQUIPMENT |  | ECT | SG/MG | Pat Maloy |  | 225949 |  | 0 | 225949 | 0 | 0 |  |  | 5852.62 |  |  |  | 27412.47 | [9 empty] | 33265.09 |  | 192683.91 | 225949 | 0
INSURANCE DURING CONSTR |  | ECT | BV/MJG | David Marshall |  | 145263 |  | 14699 | 159962 | 0 | 0 | 117600 | [9 empty] | 14699 |  | 22048 |  |  |  | 154347 | 4386 | 10001 | 164348 | -4386
CAPITALIZED SALARIES |  | ECT | TS | Mike Miller |  | 113333 |  | 0 | 113333 | 0 | 0 |  |  | 5868.98 |  |  |  | 4276.09 |  | 14353.06 | 6433.81 | 4128.48 | [5 empty] | 35060.42 | -20000 | 0 | 35060.42 | 78272.58
INTEREST DURING CONSTRUCTION |  | ECT | TS | Mike Miller |  | 6718835 |  | -2310788 | 4408047 | 806147 | 1278602 | 440999.51 |  | 374381.83 |  | 391590.46 |  | 467674.29 |  | 256005.28 | 683274 | 598297 | -598297 | -290628 |  |  |  | 4408046.37 | 0 | 0.63 | 4408047 | 0
| Interest Credit on Unused Cash | [6 empty] | -125689 | -125689 | [8 empty] | -123964 | [9 empty] | -123964 |  | 0 | -123964 | -1725
COMMITMENT FEE | [5 empty] | 0 |  | 3880 | 3880 | 0 | 0 | 6251.01 |  | 5254.99 |  | 4060.88 |  | 3911.42 |  | 3727 | [7 empty] | 23205.3 |  | 0 | 23205.3 | -19325.3
SWAP GAIN/LOSS | [5 empty] | 0 |  | -15668 | -15668 | 0 | 0 | 0 |  | 0 |  | 0 |  | 2666 |  | -18333.94 | [7 empty] | -15667.94 | 0 | 0 | -15667.94 | -0.06
| Subtotal - CapX |  |  |  |  | 121071212.472 |  | -196714 | 120874498.472 | 61073087.55 | 5192978.35 | 6766874.52 |  | 5978419.44 |  | 7829208.62 |  | 4248614.21 | 0 | 6347897.32 | 7492746.35 | 6349430.01 | 7646800.48 | 1211500.91 | 1918888.56 | 464218.36 | 22647.13 | 122543311.81 | 427438.33 | 1472877.122 | 124016188.932 | -3141690.46
FINANCING FEE |  | ECT | RM | R. Malcolm |  | 1500000 |  | -500000 | 1000000 | 0 | 0 | 756250 | [7 empty] | 83333.34 | [7 empty] | 839583.34 | -243750 | 0 | 839583.34 | 160416.66
| Escrow | [8 empty] | 0 | 55979.1667 | [16 empty] | 55979.1667 |  | 0 | 55979.1667 | -55979.1667
| Legal Fees | [8 empty] | 0 | 2533.3333 | [14 empty] | 83333.33 |  | 85866.6633 | 352817 | 0 | 85866.6633 | -85866.6633
| Insurance | [8 empty] | 0 | 3333.3333 | [16 empty] | 3333.3333 |  | 0 | 3333.3333 | -3333.3333
| Other (RW Beck) | [8 empty] | 0 | 6540.11 | 4787.55 | [14 empty] | 107679.56 | 119007.22 | 33995 | 0 | 119007.22 | -119007.22
[6 empty] | 1500000 |  | -500000 | 1000000 | 0 | 68385.9433 | 761037.55 |  | 0 |  | 0 |  | 0 |  | 83333.34 | 0 | 0 | 0 | 0 | 0 | 83333.33 | 107679.56 | 1103769.7233 | 143062 | 0 | 1103769.7233 | -103769.7233
RESALE HANDLING FEES (.25%) |  | ECT |  | Pat Maloy |  | 0 |  | 67487 | 67487 | 67487 | 2450 | [16 empty] | 69937 |  | 0 | 69937 | -2450
DEVELOPMENT EXPENSES |  | ECT | SG/MM/MJG | Mike Miller
| Travel Expenses | [6 empty] | 0 |  | 20888 | 4649 |  |  | 1054.91 |  | 188 |  | 3513.88 |  | 24447.34 | 3535.23 | 3238.47 | 3519.89 | 1417.15 |  |  |  | 66451.87 |  |  | 66451.87
| Deloitte & Touche | [6 empty] | 0 |  | 5024 | 0 | [16 empty] | 5024 |  |  | 5024
| Utility Consulting Services (Infinergy) | [6 empty] | 0 |  | 19407 | 0 | 3386.49 |  | 3356.81 | [5 empty] | 14074.27 | 3359.47 |  | 3385.34 | 6729.58 |  | 3362.57 |  | 57061.53 |  |  | 57061.53
| GLC Consulting | [8 empty] | 0 | 0 | [8 empty] | 103082.3 | 30238.8 | 51396.11 | [5 empty] | 184717.21 |  |  | 184717.21
| Haywood County Trustee (re-zonimg) | [6 empty] | 0 |  | 135 | 0 |  |  |  |  | 1925.14 | [11 empty] | 2060.14 |  |  | 2060.14
| HARC Development Service- Tom Young | [6 empty] | 0 |  | 21650 | 833 |  |  |  |  | -22066.22 | [11 empty] | 416.78 |  |  | 416.78
| Harry Leather and Ron Anderson | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0 |  |  | 0
| Wilson Well | [6 empty] | 0 |  | 4055.15 | 0 | [16 empty] | 4055.15 |  |  | 4055.15
| Engineering Assessment | [6 empty] | 0 |  | 16217.88 | 0 | [8 empty] | 1785.83 | [7 empty] | 18003.71 |  |  | 18003.71
| Maps | [6 empty] | 0 |  | 307.09 | 0 | [16 empty] | 307.09 |  |  | 307.09
| Southwest Tennessee Electric Membership Corp. | [6 empty] | 0 |  | 91000 | 0 | [16 empty] | 91000 |  |  | 91000
| ICF - Studies | [6 empty] | 0 |  | 15287.16 | 0 | [9 empty] | 4449.95 |  | 19502.67 | 15230.31 | 3271.03 |  |  | 57741.12 |  |  | 57741.12
| Southern Rents & Sales | [6 empty] | 0 |  | 651 | 0 | [16 empty] | 651 |  |  | 651
| D'Lomar Media | [6 empty] | 0 |  | 52.5 | 0 | [16 empty] | 52.5 |  |  | 52.5
| Other | [8 empty] | 0 | 0 | [8 empty] | 4576.25 |  | 9949.48 | 50818.27 | 2329.04 |  | 100 |  | 67773.04 |  |  | 67773.04
| TOTAL DEVELOPMENT COST |  |  |  |  | 500000 |  | -200000 | 300000 | 194674.78 | 5482 | 3386.49 |  | 4411.72 |  | -19953.08 |  | 3513.88 |  | 147965.99 | 41583.45 | 64584.06 | 77226.17 | 25706.08 | 3271.03 | 3462.57 | 0 | 555315.14 | 0 | 0 | 555315.14 | -255315.14
LEGAL EXPENSES |  | ECT | TS/MM | Doug Pedigo
| Waring Cox PLC | [6 empty] | 0 |  | 4742.72 | 0 | [16 empty] | 4742.72 |  |  | 4742.72
| Goodin, Macbride | [6 empty] | 0 |  | 0 | 0 | [16 empty] | 0 |  |  | 0
| Andrews & Kurth | [6 empty] | 0 | 190000 | 83518.93 | 0 | 2085.5 | [7 empty] | 45832.64 |  | 23282.45 |  | 25078.88 |  |  |  | 179798.4 |  |  | 179798.4
| Stokes & Bartholomew | [6 empty] | 0 |  | 63461.66 | 0 | 3168.32 | [7 empty] | 86683.03 |  | 869.46 |  | 118370.99 | 5463.38 |  |  | 278016.84 |  |  | 278016.84
| Vinson & Elkins | [6 empty] | 0 |  | 5126.21 | 0 | [16 empty] | 5126.21 |  |  | 5126.21
| Gerald & Brand | [6 empty] | 0 | 45000 | 11164.84 | 0 | [16 empty] | 11164.84 |  |  | 11164.84
| Hale Headrick | [8 empty] | 0 | 0 |  |  | 2145 |  |  |  | 3489.5 |  | 3387.1 | [7 empty] | 9021.6 |  |  | 9021.6
| Pat Mann | [8 empty] | 0 | 0 | [8 empty] | 2750 | [7 empty] | 2750 |  |  | 2750
| McCutcheon, Doyle, Brown & Emersen | [6 empty] | 0 |  | 13500.54 | 0 | [12 empty] | 316.3 |  |  |  | 13816.84 |  |  | 13816.84
| Other | [12 empty] | 126458.5 | [5 empty] | 126643.02 |  | 3689.01 |  | 2747.72 | 2441.05 |  |  | 261979.3 |  |  | 261979.3
| TOTAL LEGAL EXPENSE |  |  |  |  | 850000 |  | -350000 | 500000 | 181514.9 | 0 | 5253.82 |  | 128603.5 |  | 0 |  | 3489.5 |  | 265295.79 | 0 | 27840.92 | 0 | 146513.89 | 7904.43 | 0 | 0 | 766416.75 | 0 | 0 | 766416.75 | -266416.75
START-UP FUEL |  | ECT |  | K Presto |  | 0 |  | 1000000 | 1000000 | 0 | 0 | 0 | [7 empty] | 121527.11 | 58914 | 47610 | [5 empty] | 228051.11 | -771949 | 0 | 228051.11 | 771948.89
| Subtotal - Expense |  |  |  |  | 2850000 |  | 17487 | 2867487 | 443676.68 | 76317.9433 | 769677.86 |  | 133015.22 |  | -19953.08 |  | 7003.38 |  | 618122.23 | 100497.45 | 140034.98 | 77226.17 | 172219.97 | 11175.46 | 86795.9 | 107679.56 | 2723489.7233 | -628887 | 0 | 2723489.7233 | 143997.2767
TOTAL BROWNSVILLE | [5 empty] | 123921212.472 |  | -179227 | 123741985.472 | 61516764.23 | 5269296.2933 | 7536552.38 |  | 6111434.66 |  | 7809255.54 |  | 4255617.59 |  | 6966019.55 | 7593243.8 | 6489464.99 | 7724026.65 | 1383720.88 | 1930064.02 | 551014.26 | 130326.69 | 125266801.5333 | -201448.67 | 2972876.162 | 128239676.6953 | -4497691.2233
TARGET $$/MW (without Debt Reserve) | [5 empty] | 269393.9402 |  |  | 269004.3162 | [21 empty] | 278781.9059
DEBT RESERVE | [5 empty] | 0 |  |  | 0 |  |  | 0 | [15 empty] | 0 | 0 | 0 | 0 | 0
LESS: DEPRECIATION (BEG 6/99) | [27 empty] | -1412567.868 |  |  | -1412567.868
TOTAL BROWNSVILLE (with Debt Reserve | [5 empty] | 123921212.472 |  | -179227 | 123741985.472 | [18 empty] | 123854233.6653 |  | 2972876.162 | 126827108.8273 | -4497691.2233
TARGET $$/MW (without Debt Reserve) | [5 empty] | 270570.3329 |  |  | 270179.0076 | [21 empty] | 276915.0848
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/TVA_Wkly_Anal___121499.xls'#$Brownsville
Reconciliation to Work Order:
| Balance per Work Order | [7 empty] | 87222214.36 |  |  | 0 |  | 68142828.45 | [16 empty] | 122815224.2
| Balance per Weekly Summary (less mobil exp and spare parts) | [7 empty] | 87222214.36 |  |  | 7536552.38 | 0 | 6111434.66 | 0 | 7809255.54 | 0 | [13 empty] | 123282213.0333
| Difference | [7 empty] | 87222214.36 |  |  | -7536552.38 | 0 | 62031393.79 | 0 | -7809255.54 | 0 | [13 empty] | -466988.8333
Note on K141: Stacey Aune: New estimate 10/26/98 per MJ Glasscock
Note on K147: tshepperd: 98 capital 7.5% 99 capital 7.0% Off balance sheet in 99 Not based on current cash flow
Note on W123: Stacey Aune: Payment made to Layne Central . Invoiced by Neel-Schaffer
Note on Y123: Stacey Aune: Payment made to Layne Central . Invoiced by Neel-Schaffer
Note on AC191: apearce: includes $119K reclass from Faith Killen for project Cheetah erroneously booked to her RC
Note on AU111: apearce: $250K / 3 projects for incr in O&M manpower req's.
Note on AW143: apearce: $22,049 plus possible trueup of $10K per David Marshall thru 7/15

## Caledonia
ENRON CAPITAL & TRADE RESOURCES
1999 TVA PEAKING PLANTS
CALEDONIA (442 MW) | [5 empty] | 442 | MW | [24 empty] | 2025-09-26 22:33 |  |  | Revision # 56
[12 empty] | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals |  | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals |  |  | Anticipated
[6 empty] | ECT |  |  | ECT | Actuals to Date | Actuals to Date | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) |  | Actuals to Date | Increase / | ESTIMATE |  | TOTAL
|  |  | Responsibility | Enron Contact |  | CONTROL BUDGET |  | Increase/(Savings) | CURRENT ESTIMATE | 1998-12-21 | 12/21-12/31/98 | 1999-01-31 |  | 1999-02-28 |  | 1999-03-31 |  | 1999-04-30 |  | 1999-05-31 |  | 1999-06-30 | 1999-07-31 | 1999-08-31 | 1999-09-30 | 1999-10-31 | 1999-11-30 | 1999-12-31 |  | Total Project | (Savings) | TO COMPLETE |  | PROJECT | VARIANCE |  | Comments
[10 empty] | as of 10/1/99 | as of 10/1/99 | as of 12/10/99 |  | as of 12/10/99 |  | as of 12/10/99 |  | as of 12/10/99 |  | as of 12/10/99 |  | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 |  | as of 12/10/99 | as of 12/10/99
MAJOR EQUIPMENT
| TURBINE UNITS - 7EA'S (6 ea) | GE-7B | MM | Bob Emerson | Vendor quote | 99408000 |  | -408000 | 99000000 | 37377776.48 |  | 6859219.62 |  | 6859219.62 |  | 12326713.52 |  | 12919709.86 |  | 15213391.9 |  |  |  | 3280101 |  |  | 4852795.92 |  |  | 99688927.92 | 0 | 0 |  | 99688927.92 | -688927.92 |  | EECC missing 10/15 pmt. of $6,831,000;
| HMI CONTROLS | GE | SG | Bob Emerson | Vendor quote | 160800 |  |  | 160800 | [20 empty] | 0 | 0 | 160800 |  | 160800 | 0
| GENERATOR POTENTIAL XFRMR | GE | SG | Bob Emerson | Vendor quote | 11700 |  |  | 11700 | [20 empty] | 0 |  | 11700 |  | 11700 | 0
| DESCRETE 78 RELAY | GE | SG | Bob Emerson | Vendor quote | 30000 |  |  | 30000 | [20 empty] | 0 |  | 30000 |  | 30000 | 0
| GEN DESCRETE WATT TRANSDUCER | GE | SG | Bob Emerson | Vendor quote | 11400 |  |  | 11400 | [20 empty] | 0 |  | 11400 |  | 11400 | 0
| GEN DESCRETE VAR TRANSDUCER | GE | SG | Bob Emerson | Vendor quote | 11700 |  |  | 11700 | [20 empty] | 0 |  | 11700 |  | 11700 | 0
| GENERATOR MWH METER | GE | SG | Bob Emerson | Vendor quote | 13680 |  |  | 13680 | [20 empty] | 0 |  | 13680 |  | 13680 | 0
| EXHAUST STACK LADDER | GE | SG | Bob Emerson | Vendor quote | 99900 |  |  | 99900 | [20 empty] | 0 |  | 99900 |  | 99900 | 0
| FIXATORS | GE | SG | Bob Emerson | Vendor quote | 0 |  |  | 0 | [20 empty] | 0 |  | -40200 |  | -40200 | 40200 |  | eecc shows credit of 40200 for fixators
| DEDICATED EXPEDITORS |  |  |  |  | 0 |  |  | 0 | [20 empty] | 0 | 31200 | 31200 |  | 31200 | -31200
| CAPITAL SPARES | [28 empty] | 0 | 1500000 | 1500000 |  | 1500000 | -1500000
| HISTORIAN | GE | SG | Bob Emerson | Vendor quote | 110000 |  |  | 110000 | [20 empty] | 0 |  | 110000 |  | 110000 | 0
| TOTAL GE EQUIP |  |  |  |  | 99857180 |  | -408000 | 99449180 | 37377776.48 | 0 | 6859219.62 |  | 6859219.62 |  | 12326713.52 |  | 12919709.86 |  | 15213391.9 |  | 0 | 0 | 3280101 | 0 | 0 | 4852795.92 | 0 |  | 99688927.92 | 1531200 | 1940180 |  | 101629107.92 | -2179927.92
| POWER TRANSFORMERS | ABB | SG | Bob Emerson | Vendor quote | 6150000 |  |  | 6150000 | 1363340 |  | 1845000 |  |  |  | 615000 |  | 1230000 |  | 410000 |  | 419725.46 |  |  | 266934.54 |  |  |  |  | 6150000 |  | 0 |  | 6150000 | 0 |  | 922,500 should be allocated;EECC missing this amount
| AUX TRANSFORMERS | ABB | SG | Bob Emerson | Vendor quote | 162480 |  |  | 162480 | 24814.5 |  | 0 | [5 empty] | 115801 | [6 empty] | 24814.5 |  |  |  |  | 165430 | 0 | 0 |  | 165430 | -2950
| LOAD CENTER TRANSFORMERS | ABB | SG | Bob Emerson | Vendor quote | 59780 |  |  | 59780 | 11303 |  | 0 | [5 empty] | 52749.2 | [6 empty] | 11303.4 |  |  |  |  | 75355.6 | 0 | 0.4 |  | 75356 | -15576
| CIRCUIT BREAKERS | ABB | SG/MJG | Bob Emerson | Vendor quote | 3320690 |  |  | 3320690 | 498103.5 |  | 2162308 | [7 empty] | 164175 |  |  |  |  | 496103.5 |  |  |  |  | 3320690 | 0 | 0 |  | 3320690 | 0
| CHANGE ORDERS | [7 empty] | 0 | [20 empty] | 0 | 0 | 0 |  | 0 | 0
| INSTALLATION OF CIRCUIT BREAKERS | [7 empty] | 0 | [10 empty] | 141000 |  |  |  |  | 301800 |  |  |  |  | 442800 | 0 | 0 |  | 442800 | -442800
| TD OF I-ABB | ABB | SG | Bob Emerson | estimate | 25000 |  |  | 25000 | [20 empty] | 0 | 0 | 0 |  | 0 | 25000
| FREIGHT - TRANSFORMERS | ABB | SG | Bob Emerson | Vendor quote | 146850 |  |  | 146850 | [20 empty] | 0 | 0 | 0 |  | 0 | 146850
| TRANSFORMER INSTALLATION | ABB | SG | Bob Emerson | Vendor quote | 154950 |  |  | 154950 | [20 empty] | 0 | 0 | 0 |  | 0 | 154950
| OFF LOAD CIRCUIT BREAKERS | ABB | SG | Bob Emerson | estimate | 10000 |  |  | 10000 | [20 empty] | 0 | 0 | 0 |  | 0 | 10000
| MISC TVA REQUIREMENTS | ABB | SG | Bob Emerson | estimate | 20000 |  |  | 20000 | [10 empty] | 106600 |  | 25845 | [7 empty] | 132445 | 0 | 0 |  | 132445 | -112445
| TOTAL ABB EQUIP |  |  |  |  | 10049750 |  | 0 | 10049750 | 1897561 | 0 | 4007308 |  | 0 |  | 615000 |  | 1398550.2 |  | 821775 |  | 445570.46 | 0 | 0 | 1100955.94 | 0 | 0 | 0 |  | 10286720.6 | 0 | 0.4 |  | 10286721 | -236971
| TOTAL MAJOR EQUIPMENT |  |  |  |  | 109906930 |  | -408000 | 109498930 | 39275337.48 | 0 | 10866527.62 |  | 6859219.62 |  | 12941713.52 |  | 14318260.06 |  | 16035166.9 |  | 445570.46 | 0 | 3280101 | 1100955.94 | 0 | 4852795.92 | 0 |  | 109975648.52 | 1531200 | 1940180.4 |  | 111915828.92 | -2416898.92 |  | +109906930-408000-40200=109458730 per eecc
EECC PROGRAM MGT |  | 0
| HOME OFFICE | EECC | SG | David Lindquist | estimate | 251225 |  | 146275 | 397500 |  | 136945.15 | 0 | [9 empty] | 229258.93 | 106259.61 | 39750.6 |  | 16656.85 | 4851.78 | 1424.38 |  | 535147.3 | 139613 | 1965.7 |  | 537113 | -139613
| FIELD COORDINATION | EECC | SG | David Lindquist | estimate | 6500 |  | 5700 | 12200 | [20 empty] | 0 | -12200 | 0 |  | 0 | 12200
| TVA INTERFACE COORDINATION | EECC | SG | David Lindquist | estimate | 24500 |  | 0 | 24500 | [12 empty] | 23705.97 | 15200.29 | 157.27 | [5 empty] | 39063.53 | 14564 | 0.47 |  | 39064 | -14564
| EXPENSES | EECC | SG |  | estimate | 113050 |  | 2250 | 115300 |  | 9196.01 | 0 | [9 empty] | 28825.85 | 22405.13 | 1614.84 |  | 10762.23 | 6032.65 |  |  | 78836.71 | -28300 | 8163.29 |  | 87000 | 28300
| DEVELOPMENT AND PERMIT SPPT |  |  |  |  | 0 |  | 70600 | 70600 |  | 87652.89 | [10 empty] | 35124.32 | [7 empty] | 122777.21 | 52177 | 0 |  | 122777.21 | -52177.21
| TOTAL EECC PROGRAM MGT |  |  |  |  | 395275 |  | 224825 | 620100 | 0 | 233794.05 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 316915.07 | 143865.03 | 41522.71 | 0 | 27419.08 | 10884.43 | 1424.38 |  | 775824.75 | 165854 | 10129.46 |  | 785954.21 | -165854.21
ENGINEERED BOP EQUIPMENT
| VALVES/PIPE SPECIALTIES | NEPCO | SG | David Lundquist |  | 21792 |  |  | 21792 |  |  | 0 | [17 empty] | 0 | -21792 | 0 |  | 0 | 21792
| BUS DUCT |  | SG | David Lundquist |  | 785499 |  |  | 785499 |  |  | 40600 | [10 empty] | -40600 | [6 empty] | 0 | -785499 | 0 |  | 0 | 785499
| DRY XMFERS & PANEL |  | SG | David Lundquist |  | 18330 |  |  | 18330 | [20 empty] | 0 | -18330 | 0 |  | 0 | 18330
| 5KV & 480 V SWITCHGEAR & MCCS |  | SG | David Lundquist |  | 357180 |  |  | 357180 |  |  | 53.62 |  | 139280.8 | [8 empty] | -139334 | [6 empty] | 0.42 | -357180 | 0 |  | 0.42 | 357179.58
| 15 KV SWITCHGEAR |  | SG | David Lundquist |  | 125690 |  |  | 125690 | [20 empty] | 0 | -125690 | 0 |  | 0 | 125690
| CONTROL PANEL/TERM BOXES |  | SG | David Lundquist |  | 2762 |  |  | 2762 |  |  | 23002 |  | 26288 | [8 empty] | -49290 | [6 empty] | 0 | -2762 | 0 | 0 | 0 | 2762 | 0
| ELECTRICAL DEVICES |  | SG | David Lundquist |  | 0 |  |  | 0 |  |  | 0 | [17 empty] | 0 | 0 | 0 |  | 0 | 0
| HI VOLT DEVICES |  |  | David Lundquist |  | 0 |  |  | 0 | [21 empty] | 0 | 0 |  | 0 | 0
| DCS |  | SG | David Lundquist |  | 192677 |  |  | 192677 | [20 empty] | 0 | -192677 | 0 |  | 0 | 192677
| SPECIAL SYSTEMS |  | SG | David Lundquist |  | 30000 |  |  | 30000 | [20 empty] | 0 | -30000 | 0 |  | 0 | 30000
| UPS SYSTEM |  | SG | David Lundquist |  | 44197 |  |  | 44197 | [20 empty] | 0 | -44197 | 0 |  | 0 | 44197
| DC SYSTEM |  | SG | David Lundquist |  | 49514 |  |  | 49514 | [20 empty] | 0 | -49514 | 0 |  | 0 | 49514
| FIELD MOUNTED INSTRUMENTS |  | SG | David Lundquist |  | 58003 |  |  | 58003 |  | 35929.35 | 0 | [10 empty] | -35929 | [6 empty] | 0.35 | -58003 | 0 |  | 0.35 | 58002.65
| STACK MONITORING |  | SG | David Lundquist |  | 643354 |  |  | 643354 |  |  |  |  | 0 | [15 empty] | 0 | -643354 | 0 |  | 0 | 643354
| CONTROL VALVES |  | SG | David Lundquist |  | 66337 |  |  | 66337 | 39128 | -39128 | 0 |  | 0 | [15 empty] | 0 | -66337 | 0 |  | 0 | 66337
| PUMPS |  | SG | David Lundquist |  | 16775 |  |  | 16775 | [20 empty] | 0 | -16775 | 0 |  | 0 | 16775
| BRIDGE CRANE |  | SG | David Lundquist |  | 8102 |  |  | 8102 | [20 empty] | 0 | -8102 | 0 |  | 0 | 8102
| MINOR MECH EQUIP |  | SG | David Lundquist |  | 17156 |  |  | 17156 | [20 empty] | 0 | -17156 | 0 |  | 0 | 17156
| PRESSURE REDUCING STATIONS |  | SG | David Lundquist |  | 549000 |  |  | 549000 | [20 empty] | 0 | -549000 | 0 |  | 0 | 549000
| GAS FILTER |  | SG | David Lundquist |  | 95788 |  |  | 95788 | [20 empty] | 0 | -95788 | 0 |  | 0 | 95788
| FIELD/SHOP FAB VESSELS |  | SG | David Lundquist |  | 106000 |  |  | 106000 |  | 39128 | [11 empty] | -39128 | [6 empty] | 0 | -106000 | 0 |  | 0 | 106000
| OIL/WATER SEPARATOR |  | SG | David Lundquist |  | 23828 |  |  | 23828 | [20 empty] | 0 | -23828 | 0 |  | 0 | 23828
| TOTAL ENGINEERED BOP EQUIP |  |  |  |  | 3211984 |  | 0 | 3211984 | 39128 | 35929.35 | 63655.62 |  | 165568.8 |  | 0 |  | 0 |  | 0 |  | 0 | -304281 | 0 | 0 | 0 | 0 | 0 |  | 0.77 | -3211984 | 0 |  | 0.77 | 3211983.23
CONSTRUCTION | [34 empty] | 0
| SITE PREPARATION | NEPCO | SG | David Lundquist | estimate | 28593 |  |  | 28593 |  |  | 3360 |  | 59500 |  | -360 | [6 empty] | 17128 |  | 4927 |  |  |  |  | 84555 | 55962 | 0 |  | 84555 | -55962 |  | eecc has 62500 for estimate
| SITE IMPROVEMENTS |  |  | David Lundquist |  | 392305 |  |  | 392305 |  |  | 0 |  | 28295 |  | 22312 | [5 empty] | 24526 | 91771 | 15358 | 258550 |  | 10055 |  |  | 450867 | 58562 | 0 |  | 450867 | -58562
| UNDERGROUND ELECTRICAL (LAB & MAT) |  |  | David Lundquist |  | 329754 |  |  | 329754 |  |  | 85 |  | 116095 |  | 175561 |  |  |  | 122394 |  | 98652 | 177495 | 30976 | 74578 | 11795 |  |  |  | 807631 | 477877 | 0 |  | 807631 | -477877
| UNDERGROUND PIPING (LAB & MAT) |  |  | David Lundquist |  | 468032 |  |  | 468032 |  |  | 266 |  | 61118 |  | 71517 |  |  |  | 77566 |  | 35507 | 14370 | 127 | 2181 |  |  |  |  | 262652 | -205380 | 0 |  | 262652 | 205380
| CONCRETE |  |  | David Lundquist |  | 1299267 |  |  | 1299267 |  |  | 105428 |  | 33315 |  | 457412 |  |  |  | 298984 |  | 160839 | 339147 | 14297 | 107746 | 3263 | -1778 |  |  | 1518653 | 219386 | 0 |  | 1518653 | -219386
| GROUT & SPECIAL COATINGS |  |  | David Lundquist |  | 72359 |  |  | 72359 | [12 empty] | 8435 | 49961 | 22433 | 5529 | 1650 |  |  |  | 88008 | 15649 | 0 |  | 88008 | -15649
| STRUCTURAL STEEL (LAB & MAT) |  |  | David Lundquist |  | 192039 |  |  | 192039 | [13 empty] | 72813 | 1419 | 20433 | 36708 | 71110 |  |  | 202483 | 10444 | 0 |  | 202483 | -10444
| ARCHECTURAL |  |  | David Lundquist |  | 79153 |  |  | 79153 | [13 empty] | 0 |  |  |  | 46980 |  |  | 46980 | -32173 | 0 |  | 46980 | 32173
| SUBCONTRACT ERECTED BLDG'S |  |  | David Lundquist |  | 326384 |  |  | 326384 | [6 empty] | 22473 | [5 empty] | 105713 | 148445 | 35553 | 26438 |  |  |  |  | 338622 | 12238 | 0 |  | 338622 | -12238
| ABOVE GROUND PIPING |  |  | David Lundquist |  |  |  |  | 0 | [13 empty] | 0 | [6 empty] | 0 |  | 0 |  | 0 | 0
| MATERIAL |  |  | David Lundquist |  | 91291 |  |  | 91291 |  |  | 1231 |  | 129 |  | 11466 |  |  |  | 39952 |  | 63581 | 54015 | 101015 | -7447 | 25242 | 17257 |  |  | 306441 | 215150 | 0 |  | 306441 | -215150
| SUBCONTRACT |  |  | David Lundquist |  | 0 |  |  | 0 | [13 empty] | 0 | [6 empty] | 0 | 0 | 0 |  | 0 | 0
| LABOR |  |  | David Lundquist |  | 151616 |  |  | 151616 | [10 empty] | 2715 |  | 81897 | 324987 | [6 empty] | 409599 | 257983 | 0 |  | 409599 | -257983
| ABOVE GROUND ELECTRICAL |  |  | David Lundquist |  |  |  |  | 0 | [20 empty] | 0 |  | 0 |  | 0 | 0
| MATERIAL |  |  | David Lundquist |  | 566895 |  |  | 566895 | [10 empty] | 580833 |  | 50490 | 319024 | 1075330 | 383598 | 104692 | 94687 |  |  | 2608654 | 1588997 | 0 |  | 2608654 | -2041759 |  | Need to break out labor piece & move
| SUBCONTRACT |  |  | David Lundquist |  | 92834 |  |  | 92834 | [13 empty] | 0 | [6 empty] | 0 | -92834 | 0 |  | 0 | 92834
| LABOR |  |  | David Lundquist |  | 557486 |  |  | 557486 |  |  | 0 |  |  |  | 1777 |  |  |  | 21772 |  | 129389 | 711274 | 129804 | 5251 |  |  |  |  | 999267 | 441781 | 0 |  | 999267 | -441781
| INSTRUMENTATION |  |  | David Lundquist |  | 233106 |  |  | 233106 | [10 empty] | 4104 |  | 542 | 233501 | 101520 | 99402 | 19680 | 5692 |  |  | 464441 | 231335 | 0 |  | 464441 | -231335
| INSULATION |  |  | David Lundquist |  | 315756 |  |  | 315756 | [14 empty] | 161942 | -76357 |  | 13401 |  |  | 98986 | -216770 | 0 |  | 98986 | 216770
| PAINTING |  |  | David Lundquist |  | 121213 |  |  | 121213 | [14 empty] | 272986 | 135739 |  | 1500 |  |  | 410225 | 289012 | 0 |  | 410225 | -289012
| OTSG'S |  |  | David Lundquist |  | 0 |  |  | 0 | [20 empty] | 0 |  | 0 |  | 0 | 0
| MAJOR MECHANICAL EQUIP |  |  | David Lundquist |  | 2025626 |  | 300000 | 2325626 |  |  | 0 |  |  |  | -759 |  |  |  | 176718 |  | 378305 | 1958470 | 547802 | 129669 | 41433 | 127909 |  |  | 3359547 | 1033921 | 0 |  | 3359547 | -1033921
| SWITCHYARD |  |  | David Lundquist |  | 4497959 |  | 609703 | 5107662 |  | 92014 | 11812.7 |  | 9171.5 |  | 391321 |  |  |  | 1446895 |  | 793920 | 1540294 | 609415 | -261044 | 19105 | 45956 |  |  | 4698860.2 | -408802 | 0 |  | 4698860.2 | 408801.8
| ENGINEERING REWORK |  |  | David Lundquist |  | 0 |  | 0 | 0 | [16 empty] | 364 |  |  |  | 364 | 364 | 0 |  | 364 | -364
| Third Party | [23 empty] | 14609.7 | 175065.48 |  |  |  | 189675.18 | 0 | 0 |  | 189675.18 | -189675.18
| TOTAL CONSTRUCTION |  |  |  |  | 11841668 |  | 909703 | 12751371 | 0 | 92014 | 122182.7 |  | 307623.5 |  | 1152720 |  | 0 |  | 2771933 |  | 1931796 | 6052695 | 3119977 | 923802.7 | 438997.48 | 432769 | 0 |  | 17346510.38 | 3952702 | 0 |  | 17346510.38 | -4595139.38
INDIRECTS
| ENGINEERING DIRECT LABOR | NEPCO | SG | David Lundquist | estimate | 502431 |  |  | 502431 |  |  | 74539 |  | 32391 |  | 29554 |  |  |  | 61016 |  | 45639 | 34244 | 4861 | 11293 | 29853 | 48884 |  |  | 372274 | -180138 | 546651 |  | 918925 | -416494
| ENGINEERING CONTRACT LABOR |  |  | David Lundquist |  | 72888 |  |  | 72888 |  |  | 2061 |  | 7110 |  | 20473 |  |  |  | -19199 |  | 24070 | 9799 | 115 | 699 | 1951 |  |  |  | 47079 | -25809 | 0 |  | 47079 | 25809
| EQUIPMENT RENTAL , FUEL SMALL TOOLS |  |  | David Lundquist |  | 944679 |  |  | 944679 |  |  | 9204 |  | 29546 |  | 78636 |  |  |  | 68411 |  | 138302 | 239059 | 64533 | 210126 | 79331 | 33955 |  |  | 951103 | 6424 | 0 |  | 951103 | -6424
| GENERAL PROVISIONS, OVERHEAD, INDIR LABOR |  | SG | David Lundquist | estimate | 6922929 |  |  | 6922929 |  |  | 613553 |  | 239488 |  | 482479 |  |  |  | 385303 |  | 634602 | 1779793 | 609879 | 713507 | 575717 |  |  |  | 6034321 | -888608 | 0 |  | 6034321 | 888608
| STARTUP, TRAINING, MANUALS, CONTINGs, PRORAT ALLOW |  |  |  |  | 917579 |  |  | 917579 |  |  | 0 |  | 17113 |  | 34903 |  |  |  | 45418 |  | 105853 | 1364916 | 799876 | 416874 | 24589 | 428124 |  |  | 3237666 | 2216087 | 0 |  | 3237666 | -2320087
| TOTAL ENGINEERING |  |  |  |  | 9360506 |  | 0 | 9360506 | 0 | 0 | 699357 |  | 325648 |  | 646045 |  | 0 |  | 540949 |  | 948466 | 3427811 | 1479264 | 1352499 | 711441 | 510963 | 0 |  | 10642443 | 1127956 | 546651 |  | 11189094 | -1828588
OTHER COSTS - G&A |  | NEPCO | SG | David Lindquist | estimate | 0 |  |  | 0 |  |  | 14581 |  | 11246 |  | 32377.77 |  |  |  | 59632 |  | 51845 | 184311 | 63648 | 40710 | 17557 | 16987 |  |  | 492894.77 | 492895 | 0.23 |  | 492895 | -492895
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | [18 empty] | 0 |  | 0 |  | 0 | 0
INTEREST CHARGES | [5 empty] | 0 |  | 0 | 0 | 0 | 0 | [18 empty] | 0 | 283000 | 283000 |  | 283000 | -283000
[6 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 283000 | 283000 |  | 283000 | -283000
STARTUP & COMMISSIONING |  | NEPCO | SG | David Lindquist | estimate | 0 |  |  | 0 | 0 | 0 | [20 empty] | 0 |  | 0 | 0
TOTAL NEPCO SCOPE | [5 empty] | 24414158 |  | 909703 | 25323861 | 39128 | 127943.35 | 899776.32 |  | 810086.3 |  | 1831142.77 |  | 0 |  | 3372514 |  | 2932107 | 9360536 | 4662889 | 2317011.7 | 1167995.48 | 960719 | 0 |  | 28481848.92 | 2644569 | 829651.23 |  | 29311500.15 | -3987639.15
| TOTAL EECC & NEPCO SCOPE |  |  |  |  | 134716363 |  | 726528 | 135442891 | 39314465.48 | 361737.4 | 11766303.94 |  | 7669305.92 |  | 14772856.29 |  | 14318260.06 |  | 19407680.9 |  | 3694592.53 | 9504401.03 | 7984512.71 | 3417967.64 | 1195414.56 | 5824399.35 | 1424.38 |  | 139233322.19 | 4341623 | 839780.69 |  | 140073102.88 | -4630211.88
MOBILIZATION OF O&M |  | EI | D. Regain | Noles |  | 600000 |  | 59539 | 659539 | [8 empty] | 72162 |  | 162075 |  | 232976.55 | 64037.38 | 17167.9 | 19695.76 | 463.85 | 0 | 0 |  | 568578.44 | -90960.67 | 0 |  | 568578.44 | 90960.56
| EI Hourly Billing |  | D. Regain | Noles |  | 25000 |  |  | 25000 | 6111 | [19 empty] | 6111 | -31111 | -6110 |  | 1 | 24999
[6 empty] | 625000 |  | 59539 | 684539 | 6111 | 0 | 0 |  | 0 |  | 0 |  | 72162 |  | 162075 |  | 232976.55 | 64037.38 | 17167.9 | 19695.76 | 463.85 | 0 | 0 |  | 574689.44 | -122071.67 | -6110 |  | 568579.44 | 115959.56
SPARE PARTS |  | ECT | VIRGO | Bob Virgo |  | 2000000 |  | -1212200 | 787800 | [14 empty] | 157467.48 | 525705.88 | 11613.5 | 1988 | 0 |  | 696774.86 |  | 91025.14 |  | 787800 | 0
LAND ACQUISITION |  | ECT | BV/MJG | Oscar Dalton/Clay Spears |  | 531298 |  |  | 531298 | 531310 | [9 empty] | 3333.33 | [9 empty] | 534643.33 |  | 0 |  | 534643.33 | -3345.33
| Land Option to Emily Boney |  |  |  |  | 5000 |  |  | 5000 | [20 empty] | 0 | -5000 | 0 |  | 0 | 5000
| Land Purchase Boney |  |  |  |  | 80800 |  |  | 80800 | [20 empty] | 0 | -80800 | 0 |  | 0 | 80800
| Title Insurance |  |  |  |  | 5000 |  |  | 5000 | [20 empty] | 0 | -5000 | 0 |  | 0 | 5000
| Land Option Dalton |  |  |  |  | 0 |  |  | 0 | [20 empty] | 0 |  | 0 |  | 0 | 0
| Land Option Stennis |  |  |  |  | 0 |  |  | 0 | [20 empty] | 0 |  | 0 |  | 0 | 0
| Land Option to Cantrell |  |  |  |  | 1000 |  |  | 1000 | 1000 | [19 empty] | 1000 |  | 0 |  | 1000 | 0
| Land Purchase Cantrell |  |  |  |  | 19000 |  |  | 19000 | [6 empty] | 19000 | [13 empty] | 19000 |  | 0 |  | 19000 | 0
| Title Insurance |  |  |  |  | 5000 |  |  | 5000 | [6 empty] | 3050 | [13 empty] | 3050 | -1950 | 0 |  | 3050 | 1950
[6 empty] | 647098 |  | 0 | 647098 | 532310 | 0 | 0 |  | 0 |  | 22050 |  | 0 |  | 3333.33 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 557693.33 | -92750 | 0 |  | 557693.33 | 89404.67
ENVIRONMENTAL PERMITTING |  | ECT | MM | swag |  | 500000 |  | -300000 | 200000 | 156576 | 50509 | [8 empty] | 29790.65 |  |  |  | 227 |  | 250 |  |  |  | 237352.65 |  | 0 |  | 237352.65 | -37352.65
Neel- Schaffer
GAS INTERCONNECTION |  | ECT | BV/MJG | Chris Meyer |  | 981000 |  |  | 981000 | 738500 |  |  |  | 242359 | [15 empty] | 980859 |  | 141 |  | 981000 | 0 |  | Updated 10/27
ELECTRICAL INTERCONNECTION |  | ECT | BV/MJG | Larry Soderquist | [32 empty] | Pmt 1 on 11/30 25% of Budget per Heather Kroll
| W.O. Cost |  |  |  |  | 2732526 |  |  | 2732526 |  |  | 110523.33 | [5 empty] | 1639658.37 |  |  |  |  | 230833.55 | 864906.18 | [5 empty] | 2845921.43 |  | 0 |  | 2845921.43 | -113395.43
| O.H Cost (21.6%) |  |  |  |  | 590225.616 |  |  | 590225.616 | [15 empty] | 146302.16 |  | 3217.84 | 25992.82 |  | 175512.82 |  | 414712.796 |  | 590225.616 | 0
| System Impact Study |  |  |  |  | 0 |  | 11826 | 11826 | [8 empty] | 11826 | [11 empty] | 11826 |  | 0 |  | 11826 | 0
| Facilities Stdy |  |  |  |  | 0 |  | 48130 | 48130 | [12 empty] | 59846.83 | [7 empty] | 59846.83 |  | 0 |  | 59846.83 | -11716.83
[6 empty] | 3322751.616 |  | 59956 | 3382707.616 | 0 | 0 | 110523.33 |  | 0 |  | 0 |  | 1651484.37 |  | 0 |  | 59846.83 | 230833.55 | 864906.18 | 146302.16 | 0 | 3217.84 | 25992.82 |  | 3093107.08 | 0 | 414712.796 |  | 3507819.876 | -125112.26
SALES TAX ON EQUIPMENT |  | ECT | SG/MG | Pat Maloy |  | 905317 |  |  | 905317 |  | 280627 | 6382.91 | [10 empty] | 85967.61 | [6 empty] | 372977.52 | -518307 | -272977.52 |  | 100000 | 805317
INSURANCE DURING CONSTR |  | ECT | BV/MJG | David Marshall |  | 128340 |  | 38633 | 166973 |  |  | 145042 | [10 empty] | 38633 |  | 38633 |  |  |  |  | 222308 | 57950 | 2615 |  | 224923 | -57950
CAPITALIZED SALARIES |  | ECT | TS | Mike Miller |  | 113333 |  |  | 113333 |  |  |  |  | 8735.19 |  |  |  | 5962.81 |  | 23695.62 |  | 9719.3 | 5090.66 | [6 empty] | 53203.58 | -25000 | 0 |  | 53203.58 | 60129.42
INTEREST DURING CONSTRUCTION |  | ECT | TS | Mike Miller |  | 6794524 | 0 | -3622486 | 3172038 | 2084658 | -1071608 | 342823.65 |  | 321299.92 |  | 443917.85 |  | 528055.69 |  | 124517.17 |  | 725143 | 684126 | -684126 | -326769 |  |  |  |  | 3172038.28 | 0 | 0 |  | 3172038.28 | -0.28
| Interest Credit on Unused Cash | [6 empty] | -309104 | -309104 | [6 empty] | -309104 |  | -117884 | [11 empty] | -426988 |  | 0 |  | -426988 | 117884
COMMITMENT FEE | [7 empty] | 40258 | 40258 |  |  | 11785.19 |  | 10279.42 |  | 6207.4 |  | 6088.63 |  | 5896.87 | [9 empty] | 40257.51 |  | 0.49 |  | 40258 | 0
SWAP GAIN/LOSS | [7 empty] | -10400 | -10400 | [6 empty] | -5265.51 |  | 13199.98 |  | -18333.94 | [9 empty] | -10399.47 |  | 0 |  | -10399.47 | -0.53
| Subtotal - CapX |  |  |  |  | 150733726.616 |  | -4529276 | 146204450.616 | 42832620.48 | -378734.6 | 12382861.02 |  | 8251979.45 |  | 14930662.03 |  | 16477329.54 |  | 19738655.6 | 0 | 4722278.21 | 10613089.23 | 8340155.27 | 3821535.44 | 1207741.91 | 5829605.19 | 27417.2 |  | 148797195.97 | 3641444.33 | 1069187.596 |  | 149866383.566 | -3661932.95
FINANCING FEE |  | ECT | RM | R. Malcom |  | 1500000 |  | -500000 | 1000000 |  | 0 | 937500 | [7 empty] | 83333.33 | [9 empty] | 1020833.33 | -62500 | 0 |  | 1020833.33 | -20833.33
| Escrow | [9 empty] | 55979.1667 | [18 empty] | 55979.1667 | 0 | 0 |  | 55979.1667 | -55979.1667
| Legal Fees | [9 empty] | 2533.3333 | [15 empty] | 83333.33 |  |  | 85866.6633 | 352817 | 0 |  | 85866.6633 | -85866.6633
| Insurance | [9 empty] | 3333.3333 | [18 empty] | 3333.3333 |  | 0 |  | 3333.3333 | -3333.3333
| Mississippi Bond Issuance | [9 empty] | 0 | [18 empty] | 0 |  | 0 |  | 0 | 0
| Other (RW Beck) | [9 empty] | 6540.11 | 4787.55 | [15 empty] | 107679.56 |  | 119007.22 | 33994 | 0 |  | 119007.22 | -119007.22 |  | Beck Professional Services
[6 empty] | 1500000 |  | -500000 | 1000000 | 0 | 68385.9433 | 942287.55 |  | 0 |  | 0 |  | 0 |  | 83333.33 |  | 0 | 0 | 0 | 0 | 0 | 83333.33 | 107679.56 |  | 1285019.7133 | 324311 | 0 |  | 1285019.7133 | -285019.7133
RESALE HANDLING FEES (.25%) |  | ECT |  | Pat Maloy |  |  |  |  | 93542 | 93542 | 479 | [18 empty] | 94021 |  | 0 |  | 94021 | -479
DEVELOPMENT EXPENSES | [33 empty] | 0
| Travel Expenses | [8 empty] | 6644 | 1584 | 564.87 |  | 368.17 |  | 227 |  | 2187.8 |  | 20384.38 |  | 4175.35 | 776.84 | 617.8 | 344.65 |  |  |  |  | 37874.86 |  |  |  | 37874.86
| Deloitt & Touche | [8 empty] | 5024 | [19 empty] | 5024 |  |  |  | 5024
| Utility Consulting Services (Infinergy) | [8 empty] | 8333.35 |  | 3333.33 |  | 3333.33 | [5 empty] | 14074.26 |  | 3359.47 |  | 3385.34 | 6729.58 |  | 3362.57 |  |  | 45911.23 |  |  |  | 45911.23
| GLC Consulting | [10 empty] | 23926.23 | [7 empty] | 113773.61 |  | 61756.65 | 99243.27 |  | 5603 |  |  |  |  | 304302.76 |  |  |  | 304302.76
| HARC Development Service- Tom Young | [8 empty] | 21649 | 833 |  |  |  |  | -22066.15 | [13 empty] | 415.85 |  |  |  | 415.85
| Harry Leather and Ron Anderson | [8 empty] | 0 | 0 | [18 empty] | 0 |  |  |  | 0
| Engineering Assessment | [8 empty] | 16218 | [9 empty] | 1785.83 | [9 empty] | 18003.83 |  |  |  | 18003.83
| Maps | [8 empty] | 307 | [19 empty] | 307 |  |  |  | 307
| Other | [18 empty] | 55632.33 |  | 420.18 | 9949.47 | 44189.56 | 1589.29 |  | 160626.32 |  |  | 272407.15 |  |  |  | 272407.15
| ICF - Studies | [8 empty] | 14935.33 | [11 empty] | 4449.95 |  | 19502.66 | 15230.31 | 3271.03 |  |  |  | 57389.28 |  |  |  | 57389.28
| TOTAL DEVELOPMENT COST | ECT | SG/MM/MJG | Clay Spears |  | 500000 |  | -200000 | 300000 | 73110.68 | 2417 | 27824.43 |  | 3701.5 |  | -21839.15 |  | 2187.8 |  | 205650.41 |  | 74161.6 | 109969.58 | 67695.36 | 29496.83 | 3271.03 | 163988.89 | 0 |  | 741635.96 | 0 | 0 |  | 741635.96 | -441635.96
LEGAL EXPENSE |  | ECT | TS/MM | Doug Pedigo
| Andrews & Kurth | [8 empty] | 72454.41 |  | 2085.5 | [7 empty] | 50523.49 |  |  | 31365.92 |  | 25078.87 |  |  |  |  | 181508.19 |  |  |  | 181508.19
| Goodin, Macbride | [28 empty] | 0 |  |  |  | 0
| Vinson & Elkins | [8 empty] | 5126.21 | [19 empty] | 5126.21 |  |  |  | 5126.21
| Gerald & Brand | [8 empty] | 27693.61 |  | 4398.29 | [7 empty] | 44308.59 |  |  |  |  | 5588.5 |  | 3946.29 |  |  | 85935.28 |  |  |  | 85935.28
| Other | [12 empty] | 150775 | [5 empty] | 126644.02 |  |  | 20622.28 |  | 3064.01 | 3473.93 | 4233.33 |  |  | 308812.57 |  |  |  | 308812.57
| TOTAL LEGAL EXPENSE |  |  |  |  | 850000 |  | -550000 | 300000 | 105274.23 | 0 | 6483.79 | 0 | 150775 | 0 | 0 | 0 | 0 | 0 | 221476.1 | 0 | 0 | 51988.2 | 0 | 33731.38 | 3473.93 | 8179.62 | 0 | 0 | 581382.25 | 0 | 0 |  | 581382.25 | -281382.25
START-UP FUEL |  | ECT |  | K Presto |  | 0 |  | 1000000 | 1000000 | 0 | 0 | 0 | [5 empty] | 10000 |  | 53741.07 |  | 61014 | 11281 | [6 empty] | 136036.07 | -863964 | 0 |  | 136036.07 | 863963.93
| Subtotal - Expense |  |  |  |  | 2850000 |  | -250000 | 2693542 | 271926.91 | 71281.9433 | 976595.77 |  | 154476.5 |  | -21839.15 |  | 12187.8 |  | 564200.91 |  | 135175.6 | 173238.78 | 67695.36 | 63228.21 | 6744.96 | 255501.84 | 107679.56 |  | 2838094.9933 | -539653 | 0 |  | 2838094.9933 | -144552.9933
TOTAL CALEDONIA | [5 empty] | 153583726.616 |  | -4779276 | 148897992.616 | 43104547.39 | -307452.6567 | 13359456.79 |  | 8406455.95 |  | 14908822.88 |  | 16489517.34 |  | 20302856.51 |  | 4857453.81 | 10786328.01 | 8407850.63 | 3884763.65 | 1214486.87 | 6085107.03 | 135096.76 |  | 151635290.9633 | 3101791.33 | 3009367.996 |  | 154644660.9593 | -5746666.3433
TARGET $$/MW | [5 empty] | 341297.1703 |  |  | 330884.428 | [24 empty] | 343654.8021
DEBT RESERVE | [5 empty] | 0 |  |  | 0 | 0 | 0 | 0 | [17 empty] | 0 | 0 | 0 |  | 0 | 0
LESS: DEPRECIATION (BEG 6/99) | [29 empty] | -1714232.391 |  |  |  | -1714232.391
TOTAL CALEDONIA (with Debt Reserve | [5 empty] | 153583726.616 |  | -4779276 | 148897992.616 | [20 empty] | 149921058.5724 |  | 3009367.996 |  | 152930428.5684 | -5746666.3433
TARGET $$/MW (without Debt Reserve) | [5 empty] | 347474.4946 |  |  | 336873.2865 | [24 empty] | 345996.4447
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/TVA_Wkly_Anal___121499.xls'#$Caledonia
Reconciliation to Work Order:
| Balance per Work Order | [7 empty] | 80409665.77 | [24 empty] | 149025995.57
| Balance per Weekly Summary | [7 empty] | 80409665.77 | 151635290.9633 | 3101791.33 | [22 empty] | 150368507.6633
| Difference | [7 empty] | #REF! | [24 empty] | -1342512.0933
Note on K10: Shelly May: combined the original amount of $168,000 with a line labeled "Delete 64G2/21 Y funchtion" with a credit of $(7,200)
Note on K150: Stacey Aune: New estimate per MJ Glasscock 10/26/98
Note on K156: tshepperd: 98 capital 7.5% 99 capital 7.0% Off balance sheet in 99 Not based on current cash flows
Note on K192: tshepperd: This should probably be reduced to $350,000 based on original model and conversation with Ed Hearn
Note on AC191: apearce: includes $119K reclassed by Faith Killen for Project Cheetah costs erroneously booked to her RC
Note on AE23: apearce: Includes a reclass from 7/98 for $953K. Cal's piece is $238K plus Fulton's piece of $314K.
Note on AU121: apearce: includes $250K / 3 plants of addl' manpower req's
Note on AU152: apearce: $57,950 per David Marshall thru 7/15

## NewAlbany
ENRON CAPITAL & TRADE RESOURCES
1999 TVA PEAKING PLANTS
NEW ALBANY | [5 empty] | 387 | MW | [22 empty] | 2025-09-26 22:33 |  | Revision # 56
[14 empty] | Actuals | Actuals | Actuals | Actuals |  | Actuals |  | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals | Actuals |  | Anticipated
[6 empty] | ECT |  |  |  | ECT |  | Actuals to Date | Actuals to Date | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) |  | (Mo-to-date) |  | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | (Mo-to-date) | Actuals to Date | Increase / | ESTIMATE | TOTAL
|  |  | Responsibility | Enron Contact |  | CONTROL BUDGET |  | Increase/(Savings) |  | CURRENT ESTIMATE |  | 1998-12-21 | 12/21-12/31/98 | 1999-01-31 | 1999-02-28 | 1999-03-31 | 1999-04-30 |  | 1999-05-31 |  | 1999-06-30 | 1999-07-31 | 1999-08-31 | 1999-09-30 | 1999-10-31 | 1999-11-30 | 1999-12-31 | Total Project | (Savings) | TO COMPLETE | PROJECT | VARIANCE | Comments |  | Per EECC report
[12 empty] | as of 10/1/99 | as of 10/1/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 |  | as of 12/10/99 |  | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99 | as of 12/10/99
MAJOR EQUIPMENT
| TURBINE UNITS - 7B'S (1 ea) | IBC/DOW-7B | MM | Bob Emerson | Paid | 1347000 |  | 0 |  | 1347000 |  | 1347000 | [15 empty] | 1347000 |  | 0 | 1347000 | 0 | leave at 1347000; do not reflect turbine switch | -1347000 | 0
| DISASSEMBLE | IBC/DOW-7B |  | Bob Emerson |  | 500000 |  | 0 |  | 500000 |  | 611136 | -251403.37 | [14 empty] | 359732.63 | 0 | 39590 | 399322.63 | 100677.37 | leave at Dow actual; do not reflect turbine switch (407000 per IBC Contract) | -611136 | -211813.37
| TURBINE COMMISSION 10% | IBC/DOW-7B | MM | Bob Emerson |  | 134700 |  | 0 |  | 134700 |  | 134700 | [15 empty] | 134700 |  | 0 | 134700 | 0 |  |  | 134700
| KEPCO TURBINE UNITS - 7B'S (4 ea) (Kunsan) | IBC/GE-7B | MM | Miller | estimate | 27503000 |  |  |  | 27503000 |  | 27502774 | [15 empty] | 27502774 |  | 0 | 27502774 | 226 | From Fulton |  | 27502774
| LESS STEAM TURBINE |  |  |  |  | 0 |  | -700000 |  | -700000 |  | 0 |  |  | -700000 | [12 empty] | -700000 |  | 0 | -700000 | 0 |  |  | -700000
| TURBINE COMMISSION IBC/NATOLE - IBC fee 10% | IBC/GE-7B | MM | Miller |  | 3600000 |  | 0 |  | 3600000 |  | 0 |  | 2750277.4 | [13 empty] | 2750277.4 |  | 849722.6 | 3600000 | 0 |  |  | 3600000
| EQUIP DECONSTRUCT MOVE TO PORT | IBC/GE-7B | MM | Miler |  | 1500000 |  | -192340 |  | 1307660 |  | 2682838 | -1059648 | 189260 | [13 empty] | 1812450 | 0 | 0 | 1812450 | -504790 |  | -1375178 | 437272
| FREIGHT |  |  | Miller |  | 0 |  | 1274025 |  | 1274025 |  | 0 | 1312564.44 | 158283.73 |  | 139345 | 481333.14 |  | 1238635.58 |  | 218413.18 | 180471 | [5 empty] | 3729046.07 | 2254002 | 0 | 3729046.07 | -2455021.07 | leave at 1274025; do not reflect turbine switch | -274025 | 3455021.07
| LESS STEAM TURBINE |  |  |  |  | 0 |  | -200500 |  | -200500 |  | 0 |  |  | -200500 | [12 empty] | -200500 |  | 0 | -200500 | 0 |  |  | -200500
| LESS STEAM TURBINE |  |  |  |  | 0 |  | -100000 |  | -100000 |  | 0 |  |  | -100000 | [12 empty] | -100000 |  | 0 | -100000 | 0 |  |  | -100000
| FFREIGHT COMMISSION |  |  |  |  | 0 |  | 89182 |  | 89182 |  | 14347 | [15 empty] | 14347 |  | 74835 | 89182 | 0 |  |  | 89182
| INTEREST/BANK FEES ON LATE PAYMENT TO IBC (KEPCO) |  |  |  |  | 0 |  | 0 |  | 0 |  | 10679.59 | -1512 | [14 empty] | 9167.59 |  | 0 | 9167.59 | -9167.59 |  | -10680 | -1512.41
| KEPCO TURBINE - 7B (1 ea) (Youngwol) | IBC/GE-7B |  | Miler |  |  |  | 0 |  | 0 |  | 0 | [15 empty] | 0 |  | 0 | 0 | 0 |  |  | 0
| PURCHASE, DISASSEMBLY, FREIGHT | IBC/GE-7B |  | Miler |  | 10500000 |  | -3125000 |  | 7375000 |  | 7050000 |  | 1021302.16 |  | 536220.8 | [11 empty] | 8607522.96 |  | -268110 | 8339412.96 | -964412.96 | Remove $268K from column AI after entry hits | 6539349 | 14878761.96
| CAPITAL SPARES | [26 empty] | 0 | 1500000 | 1500000 | 1500000 | -1500000
| TURBINE REFURBISHMENT & DLN (7 UNITS) | IBC/DOW & GE-7B | MM | Miller |  | 14879630 |  | 11905766 |  | 26785396 |  | 15463169 | -2065238 | 9508417.25 |  | 539154.23 | 5461598 |  | 4400794.2 |  | 300070.14 | 581348.5 | 807720.16 | 295000 | 115736.53 | 56819 |  | 35464589.01 |  | -172555.53 | 35292033.48 | -8506637.48 | 4344155.96 | -1164043 | 34127990.48
| Subtotal GE |  |  |  |  | 59964330 |  | 8951133 |  | 68915463 |  | 54816643.59 | -2065236.93 | 13627540.54 | -1000500 | 1214720.03 | 5942931.14 |  | 5639429.78 |  | 518483.32 | 761819.5 | 807720.16 | 295000 | 115736.53 | 56819 | 0 | 80731106.66 | 3754002 | 2023482.07 | 82754588.73 | -13839125.73 |  | 1757287 | 84511875.73
| SPARE PARTS |  |  | Miller |  | 0 |  | 5365100 |  | 5365100 |  | 5364933 | 2065238.15 | 3111381.03 |  | -5415745.57 | 248257.2 |  | 1334949.71 |  | 92003.95 | 13613.06 | 20000 | 1036626 | 20000 |  |  | 7891256.53 |  | 0 | 7891256.53 | -2526156.53 |  | -5488215 | 2403041.53
| IBC PRE-PAY ON COMMISSION | IBC |  | Bob Emerson |  | 0 |  | 0 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| POWER TRANSFORMERS | ABB | SG | Bob Emerson | Vendor quote | 6150000 |  | 0 |  | 6150000 |  | 1380885.67 |  |  |  | 1230000 | 615000 |  | 2460000 |  | 853258.65 |  | 0 | -336693.37 |  |  |  | 6202450.95 |  | 0 | 6202450.95 | -52450.95 |  |  | 6202450.95
| AUX TRANSFORMERS | ABB | SG | Bob Emerson | Vendor quote | 162480 |  | 2950 |  | 165430 |  | 24814.5 |  |  |  |  | 115801 | [6 empty] | 24814.5 |  |  |  | 165430 |  | 0 | 165430 | 0 |  |  | 165430
| LOAD CENTER TRANSFORMERS | ABB | SG | Bob Emerson | Vendor quote | 59780 |  | 15576 |  | 75356 |  | 11303.4 |  |  |  |  | 52749.2 | [6 empty] | 11303.4 |  |  |  | 75356 |  | 0 | 75356 | 0 |  |  | 75356
| CIRCUIT BREAKERS | ABB | SG | Bob Emerson | Vendor quote | 4160160 |  | 0 |  | 4160160 |  | 624024.5 |  | 985050 | 293814.5 | 587629 |  |  | 963531 |  |  |  | 0 | 723289.96 |  |  |  | 4177338.96 | 0 | 0 | 4177338.96 | -17178.96 |  |  | 4177338.96
| CHANGE ORDERS | [8 empty] | 0 | [17 empty] | 0 | 0 | 0 | 0 | 0
| CIRCUIT BREAKER INSTALLATION | [8 empty] | 0 | [11 empty] | 300000 |  | 301800 |  |  |  | 601800 | 0 | 0 | 601800 | -601800
| TD OF I-ABB | ABB | SG | Bob Emerson | estimate | 15000 |  | 10000 |  | 25000 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 25000 |  |  | 0
| FREIGHT - TRANSFORMERS | ABB | SG | Bob Emerson | Vendor quote | 146850 |  | 0 |  | 146850 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 146850 |  |  | 0
| TRANSFORMER INSTALLATION | ABB | SG | Bob Emerson | Vendor quote | 154950 |  | 0 |  | 154950 |  | 0 | 0 | [5 empty] | 0 | [8 empty] | 0 |  | 0 | 0 | 154950 |  |  | 0
| OFF LOAD CIRCUIT BREAKERS | ABB | SG | Bob Emerson | estimate | 10000 |  | 0 |  | 10000 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 10000 |  |  | 0
| MISC TVA REQUIREMENTS | ABB | SG | Bob Emerson | estimate | 10000 |  | -10000 |  | 0 |  | 0 | 0 | [5 empty] | 107900 |  |  |  | 6600 |  |  |  |  | 114500 |  | 0 | 114500 | -114500 |  |  | 114500
| Subtotal ABB |  |  |  |  | 10869220 |  | 5383626 |  | 10887746 |  | 2041028.07 | 0 | 985050 | 293814.5 | 1817629 | 783550.2 |  | 3531431 |  | 853258.65 | 300000 | 6600 | 724514.49 | 0 | 0 | 0 | 11336875.91 | 0 | 0 | 11336875.91 | -449129.91
| TOTAL MAJOR EQUIPMENT |  |  |  |  | 70833550 |  | 19699859 |  | 85168309 |  | 62222604.66 | 1.22 | 17723971.57 | -706685.5 | -2383396.54 | 6974738.54 |  | 10505810.49 |  | 1463745.92 | 1075432.56 | 834320.16 | 2056140.49 | 135736.53 | 56819 | 0 | 99959239.1 | 3754002 | 2023482.07 | 101982721.17 | -16814412.17 |  | -3730928 | 98251793.17
EECC PROGRAM MGT
| HOME OFFICE | EECC | SG | Bob Emerson | estimate | 251225 |  | 146275 |  | 397500 |  |  | 39379.34 | 31484.89 |  |  | 15908 |  |  |  | 324657.91 | 137517.53 | 178192.36 |  | 23268.37 | 7845.45 | 51444.89 | 809698.74 | 468500 | 56301.26 | 866000 | -468500
| FIELD COORDINATION | EECC | SG | Bob Emerson | estimate | 6500 |  | 5700 |  | 12200 |  |  | 0 | [14 empty] | 0 | -12200 | 0 | 0 | 12200
| TVA INTERFACE COORDINATION | EECC | SG | Bob Emerson | estimate | 24500 |  | 0 |  | 24500 |  |  | 0 | [7 empty] | 23705.97 | 15200.28 | 157.27 |  |  |  |  | 39063.52 | 15500 | 936.48 | 40000 | -15500
| EXPENSES | EECC | SG | Bob Emerson | estimate | 113050 |  | 2250 |  | 115300 |  |  | 3268 | 5198.51 | [6 empty] | 53346.41 | 21603.17 | -8068.33 |  | 83826.31 | 731.68 |  | 159905.75 | 49700 | 5094.25 | 165000 | -49700
| DEVELOPMENT & PERMIT SUPPORT | EECC | SG | Bob Emerson |  | 0 |  | 92331 |  | 92331 |  |  | 92330.74 | [7 empty] | 139668.15 |  | -103320 |  |  |  |  | 128678.89 | 36348 | 0.11 | 128679 | -36348
| TOTAL EECC PROGRAM MGT |  |  |  |  | 395275 |  | 246556 |  | 641831 |  | 0 | 134978.08 | 36683.4 | 0 | 0 | 15908 |  | 0 |  | 541378.44 | 174320.98 | 66961.3 | 0 | 107094.68 | 8577.13 | 51444.89 | 1137346.9 | 557848 | 62332.1 | 1199679 | -557848 |  |  | 99451472.17
ENGINEERED BOP EQUIPMENT
| VALVES & SPECIALTIES | NEPCO | SG | David Lundquist | estimate | 53649 |  | 6456 |  | 60105 |  | 0 | 0 | [14 empty] | 0 | -60105 | 0 | 0 | 60105
| BUS DUCT | [6 empty] | 636961 |  | 636961 | [17 empty] | 0 | -636961 | 0 | 0 | 636961
| DRY TRANSFORMS AND PANELS | [6 empty] | 16500 |  | 16500 | [17 empty] | 0 | -16500 | 0 | 0 | 16500
| 5KV & 600 V SWITCHGEAR AND MCC'S | [6 empty] | 375110 |  | 375110 |  |  |  |  | 139280.8 | 0 | [5 empty] | -139281 | [5 empty] | -0.2 | -375110 | 0.2 | 0 | 375110
| 15 KV SWITCHGEAR | [6 empty] | 132000 |  | 132000 | [17 empty] | 0 | -132000 | 0 | 0 | 132000
| CONTROL PANELS/TERMINATION BOXES | [6 empty] | 586658 |  | 586658 |  | 0 | 0 | 0 | 0 | [12 empty] | 0 | -586658 | 0 | 0 | 586658
| ELECTRICAL DEVICES | [6 empty] | 0 |  | 0 |  | 0 | 0 | 0 | 0 | [12 empty] | 0 | 0 | 0 | 0 | 0
| DCS | [6 empty] | 202350 |  | 202350 | [17 empty] | 0 | -202350 | 0 | 0 | 202350
| UPS SYSTEM | [6 empty] | 46416 |  | 46416 | [17 empty] | 0 | -46416 | 0 | 0 | 46416
| DC SYSTEM | [6 empty] | 99000 |  | 99000 | [17 empty] | 0 | -99000 | 0 | 0 | 99000
| FIELD MOUNTED INSTRUMENTS | [6 empty] | 57202 |  | 57202 |  |  |  | 11290.7 | [7 empty] | -11291 | [5 empty] | -0.3 | -57202 | 0.3 | 3.638e-12 | 57202
| STACK MONITORING | [6 empty] | 420261 |  | 420261 | [17 empty] | 0 | -420261 | 0 | 0 | 420261
| CONTROL VALVES | [6 empty] | 69600 |  | 69600 | [17 empty] | 0 | -69600 | 0 | 0 | 69600
| PUMPS\ |  |  | David Lundquist |  | 8800 |  | 22000 |  | 30800 |  | 0 | 0 | [14 empty] | 0 | -30800 | 0 | 0 | 30800
| BRIDGE CRANE | [8 empty] | 0 | [17 empty] | 0 |  | 0 | 0 | 0
| COMBUSTION TURBINE GENERATOR | [6 empty] | 945000 |  | 945000 | [17 empty] | 0 | -945000 | 0 | 0 | 945000
| MINOR MECHANICAL EQUIPMENT | [8 empty] | 0 | [17 empty] | 0 | 0 | 0 | 0 | 0
| PRESSURE REDUCING STATION | [6 empty] | 549000 |  | 549000 |  |  |  |  | 38094 | [6 empty] | -38094 | [5 empty] | 0 | -549000 | 0 | 0 | 549000
| WATER WASH SKID | [6 empty] | 120000 |  | 120000 |  |  |  | 0 | [13 empty] | 0 | -120000 | 0 | 0 | 120000
| FIELD/SHOP FAB VESSELS | [6 empty] | 6000 |  | 6000 |  |  | 16171.1 | [8 empty] | -16171 | [5 empty] | 0.1 | -6000 | 0 | 0.1 | 5999.9
| EQUIP & DEVICES |  |  |  |  | 4206853 |  | -4206853 |  |  |  | 31643 | -31643 | [14 empty] | 0 |  | 0 | 0 | 0
| SWITCHYARD |  |  |  |  | 1500000 |  | -1500000 | [7 empty] | 0 | [11 empty] | 0 | 0 | 0 | 0 | 0
| INSTRUMENTATION |  |  |  |  | 547063 |  | -547063 | [19 empty] | 0 |  | 0 | 0 | 0
| FREIGHT |  |  |  |  | 113880 |  | -113880 | [19 empty] | 0 |  | 0 | 0 | 0
| OTHER |  | SG | David Lundquist | estimate | 142000 |  | -142000 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| TOTAL ENGINEERED BOP EQUIP |  |  |  |  | 6572245 |  | -2219282 |  | 4352963 |  | 31643 | -15471.9 | 11290.7 | 177374.8 | 0 | 0 |  | 0 |  | 0 | -204837 | 0 | 0 | 0 | 0 | 0 | -0.4 | -4352963 | 0.5 | 0.1 | 4352962.9
BULK MATERIAL
| PIPING | NEPCO | SG | David Lundquist | estimate | 248807 |  | -248807 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| ELECTRICAL |  | SG | David Lundquist | estimate | 1024801 |  | -1024801 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| CIVIL |  | SG | David Lundquist | estimate | 811714 |  | -811714 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| INSTRUMENTATION |  | SG | David Lundquist | estimate | 12470 |  | -12470 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| TOTAL BULK MATERIAL |  |  |  |  | 2097792 |  | -2097792 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONSTRUCTION
| SITE PREPARATION | [6 empty] | 462972 |  | 462972 | [5 empty] | 386650 |  |  | 107869 |  | -17093 | 160315 | 63657 | 110496 | 7566 | 91598 |  | 911058 | 448086 | 0 | 911058 | -448086
| SITE IMPROVEMENTS | [6 empty] | 532399 |  | 532399 | [11 empty] | 17959 | 3946 | 45942 | 317486 | -139173 |  | 246160 | -425780 | 0 | 246160 | 286239
| UNDERGROUND ELECTRICAL (LAB & MATL) | [6 empty] | 738930 |  | 738930 | [5 empty] | 76630 |  |  | 60189 |  | 138436 | 139912 | 39882 | 14874 | 1468 |  |  | 471391 | -267539 | 0 | 471391 | 267539
| UNDERGROUND PIPING (LAB & MATL) | [6 empty] | 401168 |  | 401168 | [5 empty] | 16373 |  |  | 46593 |  | 126396 | 60892 | 4047 | 4220 | 69 | 2229 |  | 260819 | -140349 | 0 | 260819 | 140349
| CONCRETE | [6 empty] | 1766324 |  | 1766324 |  |  |  | 845 | 14356 | 225357 |  |  | 276181 |  | 526718 | 286701 | 67689 | 13834 | 12775 | 3700 |  | 1428156 | -338168 | 0 | 1428156 | 338168
| GROUT & SPECIAL COATINGS | [6 empty] | 72583 |  | 72583 | [11 empty] | 17509 | 11804 | 3434 |  |  |  | 32747 | -39836 | 0 | 32747 | 39836
| STRUCTURAL STEEL (LAB & MATL) | [6 empty] | 24454 |  | 24454 | [8 empty] | 1450 |  | 22 | 109663 | 3467 | 1944 |  |  |  | 116546 | 92092 | 0 | 116546 | -92092
| ARCHITECTURAL | [6 empty] | 35400 |  | 35400 | [10 empty] | 16709 | 40813 | 4555 |  |  | 293 |  | 62370 | 26970 | 0 | 62370 | -26970
| SUBCONTRACT ERECTED BUILDINGS | [6 empty] | 297005 |  | 297005 | [10 empty] | 76275 | 47475 | 12631 | 266264 | 38449 |  |  | 441094 | 142541 | 0 | 441094 | -144089
| ABOVE GROUND PIPING | [8 empty] | 0 | [17 empty] | 0 |  | 0 | 0 | 0
| MATERIAL | [6 empty] | 53364 |  | 53364 | [8 empty] | 226 |  | 2455 | 81111 | 21068 | 116620 | 13969 | 7589 |  | 243038 | 189674 | 0 | 243038 | -189674
| SUBCONTRACT | [6 empty] | 0 |  | 0 | [17 empty] | 0 | 0 | 0 | 0 | 0
| LABOR | [6 empty] | 84253 |  | 84253 | [5 empty] | 720 |  |  |  |  | 20186 | 89088 |  | 631 |  |  |  | 110625 | 26372 | 0 | 110625 | -26372
| ABOVE GROUND ELECTRICAL | [8 empty] | 0 | [17 empty] | 0 |  | 0 | 0 | 0
| MATERIAL | [6 empty] | 597175 |  | 597175 | [8 empty] | 63923 |  | 36130 | 525079 |  | 382740 | 18555 | 62368 |  | 1088795 | 491620 | 0 | 1088795 | -491620
| SUBCONTRACT | [6 empty] | 190000 |  | 190000 | [17 empty] | 0 | -190000 | 0 | 0 | 190000
| LABOR | [6 empty] | 538044 |  | 538044 | [10 empty] | 65736 | 403323 | 36550 | 29041 |  | 55136 |  | 589786 | 51742 | 0 | 589786 | -51742
| INSTRUMENTATION | [6 empty] | 230432 |  | 230432 | [8 empty] | 11921 |  | 3430 | 113325 | 228451 | 6215 | 28577 | 1595 |  | 393514 | 163082 | 0 | 393514 | -163082
| INSULATION | [6 empty] | 329958 |  | 329958 | [11 empty] | 0 | [5 empty] | 0 | -329958 | 0 | 0 | 329958
| PAINTING | [6 empty] | 120865 |  | 120865 | [11 empty] | 0 |  | 64650 |  |  |  | 64650 | -56215 | 0 | 64650 | 56215
| COMBUSTION TURBINE/GENERATOR | [6 empty] | 1099682 |  | 1099682 | [11 empty] | 0 | [5 empty] | 0 | -1099682 | 0 | 0 | 1099682
| MAJOR MECHANICAL EQUIPMENT | [6 empty] | 105810 |  | 105810 | [5 empty] | 1164 |  |  | 118814 |  | 537451 | 1342208 | -264468 | 42014 | 625232 | 728688 |  | 3131103 | 3025293 | 0 | 3131103 | -3025293
| ENGINEERING-CONTRACT LABOR | [6 empty] | 0 |  | 0 |  |  |  |  | 2655 | 9356 |  |  | -12011 |  |  | 60091 | [5 empty] | 60091 | 60091 | 0 | 60091 | -60091
| CIVIL WORK & FOUNDATIONS | NEPCO | SG | David Lundquist | estimate | 1277936 |  | -1277936 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| MAJOR EQUIPMENT ERECTION |  | SG | David Lundquist | estimate | 2045710 |  | -2045710 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| BOP EQUIPMENT ERECTION |  | SG | David Lundquist | estimate | 279055 |  | -279055 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| PIPING EXTERNAL TO EQUIPMENT |  | SG | David Lundquist | estimate | 257278 |  | -257278 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| ELECTRICAL/I&C INSTALLATION |  | SG | David Lundquist | estimate | 1405318 |  | -1405318 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| SWITCHYARD |  |  | David Lundquist |  | 0 |  | 8565579 |  | 8565579 |  |  | 254573.36 | 167778.54 | 208706.5 | 345849 |  |  | 2895829 |  | 1849499 | 2207728 | 134528 | 110547 | 42298 | 90809 |  | 8308145.4 | -257434 | 0 | 8308145.4 | 257433.6
| TTS Scope |  | SG | David Lundquist | estimate | 4503021 |  | -4503021 |  | 0 |  | 0 | 0 | [9 empty] | 1442555 | 1085705 |  |  |  | 2528260 | 2528260 | 0 | 2528260 | -2528260
| Third Party | [8 empty] | 0 | [13 empty] | 159789.95 | 61914.57 |  |  | 221704.52 |  | 0 | 221704.52 | -221704.52
| TOTAL CONSTRUCTION |  |  |  |  | 9768318 | 0 | 6478079 | 0 | 16246397 | 0 | 0 | 254573.36 | 168623.54 | 225717.5 | 1062099 | 0 |  | 3570984 |  | 3382350 | 5703192 | 1810362 | 2458960.95 | 1168358.57 | 904832 | 0 | 20710052.92 | 4100862 | 0 | 20710052.92 | -4463655.92
INDIRECTS
| ENGINEERING-DIRECT LABOR | [6 empty] | 356828 |  | 356828 |  |  |  | 209239 | 17821 | 23019 |  |  | 62454 |  | 54096 | 180008 | 76393 | 41252 | -81857 | -159204 |  | 423221 | -310426 | 1842444 | 2265665 | -1908837
| EQUIP RENTAL, FUEL, SMALL TOOLS | [6 empty] | 1194879 |  | 1194879 |  |  |  |  | 11066 | 42161 |  |  | 145566 |  | 77856 | 254976 | 83020 | 147045 | 67769 | 126562 |  | 956021 | -238858 | 0 | 956021 | 238858
| GENERAL PROVISIONS, OVERHEAD, INDIR LABOR | [6 empty] | 5774584 |  | 5774584 |  |  |  |  | 231203 | 564654 |  |  | 502492 |  | 702372 | 654187 | 2803209 | 843487 | 432007 |  |  | 6733611 | 134132 | 0 | 6733611 | -959027
| STARTUP, TRAINING, MANUALS, CONTINGs, PRORAT ALLOW | [6 empty] | 2205795 |  | 2205795 |  |  |  | 0 | 6069 | 33964 |  |  | 31530 |  | 113729 | 746438 | 410118 | 344336 | 119527 | 257014 |  | 2062725 | -143070 | 0 | 2062725 | 143070
| ENGINEERING | NEPCO | SG | David Lundquist | estimate | 710800 |  | -710800 |  | 0 |  | 0 | 0 | 0 | [13 empty] | 0 |  | 0 | 0 | 0
| PROJECT MANAGEMENT |  | SG | David Lundquist | estimate | 3163053 |  | -3163053 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| CONSTRUCTION MANAGEMENT |  | SG | David Lundquist | estimate | 1128260 |  | -1128260 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
| TOTAL ENGINEERING |  |  |  |  | 5002113 |  | 4529973 |  | 9532086 |  | 0 | 0 | 209239 | 266159 | 663798 | 0 |  | 742042 |  | 948053 | 1835609 | 3372740 | 1376120 | 537446 | 224372 | 0 | 10175578 | -558222 | 1842444 | 12018022 | -2485936
OTHER COSTS - G&A |  | NEPCO | SG | David Lundquist | estimate | 954000 |  | 21000 |  | 975000 |  | 0 | 0 | 3788 | 5112 | 31066.15 |  |  | 77634 |  | 77947 | 168687 | 56620 | 66155 | 29590 | 20326 |  | 536925.15 | -438075 | 0 | 536925.15 | 438074.85
| NOT IDENTIFIED |  |  |  |  | 275432 |  | -275432 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
INTEREST CHARGES |  |  |  | David Lundquist |  | 0 |  | 0 |  | 0 | [15 empty] | 0 |  | 0 | 0 | 260000 | 260000 | -260000
SWITCHYARD INCREASE |  | NEPCO | SG | David Lundquist |  | 0 |  | 0 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0
TOTAL NEPCO | [5 empty] | 24669900 |  | 6436546 |  | 31106446 |  | 31643 | 239101.46 | 392941.24 | 674363.3 | 1756963.15 | 0 |  | 4390660 |  | 4408350 | 7502651 | 5239722 | 3901235.95 | 1735394.57 | 1149530 | 0 | 31422555.67 | -1248398 | 1842443.5 | 33525000.17 | -2418554.17 |  |  | 132976472.34
| TOTAL EECC & NEPCO SCOPE |  |  |  |  | 95898725 |  | 26382961 |  | 116916586 |  | 62254247.66 | 374080.76 | 18153596.21 | -32322.2 | -626433.39 | 6990646.54 |  | 14896470.49 |  | 6413474.36 | 8752404.54 | 6141003.46 | 5957376.44 | 1978225.78 | 1214926.13 | 51444.89 | 132519141.67 | 3063452 | 4188257.67 | 136707399.34 | -19790814.34 |  | -3730928 | 132976471.34
MOBILIZATION OF O&M |  | EI | D. Regan | Noles |  | 600000 |  | 68000 |  | 668000 |  | 6110.75 |  | 11486.77 |  |  | 91858 |  | 166373 |  | 242196.48 | 108545.95 | 112784.15 | 37104.92 | 7825.49 | 2323.08 | 0 | 786608.59 | 85707.33 | 0 | 786608.59 | -118608.59 | will be expensed as part of O&M agreement vs. capitalized
| EI Hourly billing | EI | D. Regan | Noles |  | 25000 |  | 0 |  | 25000 | [17 empty] | 0 | -25000 | 0 | 0 | 25000 | will be expensed as part of O&M agreement vs. capitalized
| Subtotal EI |  |  |  |  | 625000 |  | 68000 |  | 693000 |  | 6110.75 | 0 | 11486.77 | 0 | 0 | 91858 |  | 166373 |  | 242196.48 | 108545.95 | 112784.15 | 37104.92 | 7825.49 | 2323.08 | 0 | 786608.59 | 60707.33 | 0 | 786608.59 | -93608.59
SPARE PARTS |  | ECT | BV | Bob Virgo |  | 2000000 |  | -1186950 |  | 813050 |  | 0 | 0 | [9 empty] | 39922.66 | 689523.59 | 18841.83 | 0 | 0 | 748288.08 |  | 64761.92 | 813050 | 0 | Is this related to above payments
LAND ACQUISITION |  | ECT | BV/MJG | Ben Jacoby |  | 169275 |  | 0 |  | 169275 |  | 169276 | [6 empty] | 3333.34 | [8 empty] | 172609.34 |  | 0 | 172609.34 | -3334.34 | Title Charges, reclass $10,000 from Brownsville
| Additional land acquisition option |  |  |  |  | 150000 |  | 0 |  | 150000 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 150000
| Subtotal Land Acquisition |  |  |  |  | 319275 |  | 0 |  | 319275 |  | 169276 | 0 | 0 | 0 | 0 | 0 |  | 3333.34 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 172609.34 | 0 | 0 | 172609.34 | 146665.66
ENVIRONMENTAL PERMITTING |  | ECT | MM | swag |  | 500000 |  | -310000 |  | 190000 |  | 161090.22 | 48441.13 |  | 12317 |  |  |  | 11450.36 |  |  | 10800 | [5 empty] | 244098.71 |  | 0 | 244098.71 | -54098.71
| Other | [12 empty] | 204.75 | [7 empty] | 4030 | 130 |  | 106440 |  |  | 110804.75 |  | 0 | 110804.75 | -110804.75
[6 empty] | 500000 |  | -310000 |  | 190000 |  | 161090.22 | 48441.13 | 204.75 | 12317 | 0 | 0 |  | 11450.36 |  | 0 | 14830 | 130 | 0 | 106440 | 0 | 0 | 354903.46 | 0 | 0 | 354903.46 | -164903.46
GAS INTERCONNECTION |  | ECT | BV/MJG | Chris Meyer |  | 0 |  | 0 |  | 0 |  | 0 | 0 | [14 empty] | 0 |  | 0 | 0 | 0 | $854,000 to be paid by Columbia Gas
ELECTRICAL INTERCONNECTION |  | ECT | BV/MJG | Larry Soderquist | [26 empty] | 0 |  | Pmt 1 on 11/30 25% of Budget per Heather Kroll
| W.O. Cost |  |  |  |  | 1674539 |  | 0 |  | 1674539 |  | 0 | 0 | 71059.96 |  |  | 707190.32 |  |  |  | 644133.13 | 169598.18 | 127893.85 |  |  |  |  | 1719875.44 |  | 0 | 1719875.44 | -45336.44
| O.H Cost (21.6%) |  |  |  |  | 361700.424 |  | 0 |  | 361700.424 |  | 0 | 0 | [10 empty] | 72187.99 | 12905.28 | 156683.79 | 5257.23 | 247034.29 |  | 114666.134 | 361700.424 | 0
| System Impact Study |  |  |  |  | 0 |  | 11826 |  | 11826 |  | 0 | 0 |  |  |  | 11826 | [10 empty] | 11826 |  | 0 | 11826 | 0
| Facilities Study |  |  |  |  | 0 |  | 33768 |  | 33768 |  | 0 | 0 | [9 empty] | 57404.8 |  |  |  |  | 57404.8 |  | 0 | 57404.8 | -23636.8
| Subtotal Electrical Interconnection |  |  |  |  | 2036239.424 |  | 45594 |  | 2081833.424 |  | 0 | 0 | 71059.96 | 0 | 0 | 719016.32 |  | 0 |  | 644133.13 | 169598.18 | 185298.65 | 72187.99 | 12905.28 | 156683.79 | 5257.23 | 2036140.53 | 0 | 114666.134 | 2150806.664 | -68973.24
SALES TAX ON EQUIPMENT |  | ECT | SG/MG | Pat Maloy |  | 363000 |  | 0 |  | 363000 |  |  | 162185.68 | 64952.32 | 4730.46 | [6 empty] | 85967.61 | [5 empty] | 317836.07 | -31132 | -217836.07 | 100000 | 263000
INSURANCE DURING CONSTR |  | ECT | BV/MG | David Marshall |  | 100000 |  | 55279 |  | 155279 |  | 0 | 0 |  |  | 201497.24 |  |  | 22112 |  |  |  |  | 67029.5 |  |  |  | 290638.74 | -9473 | 35888.26 | 326527 | -171248
CAPITALIZED SALARIES |  | ECT | TS | Mike Miller |  | 113333 |  | 0 |  | 113333 |  | 0 | 0 |  | 11126.71 |  | 3774.9 |  | 29107.82 |  | 13553.04 | 6061.43 | [5 empty] | 63623.9 | -29999 | 0 | 63623.9 | 49709.1
INTEREST DURING CONSTRUCTION |  | ECT | TS | Mike Miller |  | 5166466.5672 |  | -1002563 |  | 4163903.5672 |  | 913875 | 448366 | 436078.94 | 434033.21 | 422737.7 | 505583.13 |  | 264882.85 |  | 738348 | 659904 | -659904 |  |  |  |  | 4163904.83 | 0 | 0 | 4163904.83 | -1.2628
| Interest Credit on Usused Cash | [6 empty] | -94899 |  | -94899 | [5 empty] | -94899 | -64384 | [10 empty] | -159283 |  | 0 | -159283 | 64384
COMMITMENT FEE | [7 empty] | 24072 |  | 24072 |  |  |  | 7392.73 | 4682.38 | 4180.83 | 4002.47 |  | 3813.77 | [8 empty] | 24072.18 |  | 0 | 24072.18 | -0.18
SWAP GAIN/LOSS | [7 empty] | -15668 |  | -15668 | [6 empty] | 2665.56 |  | -18333.93 | [8 empty] | -15668.37 |  | 0.37 | -15668 | 0
| Subtotal - CapX |  |  |  |  | 107122038.9912 |  | 23965826 |  | 125722764.9912 |  | 63504599.63 | 1033073.57 | 18744771.68 | 434567.56 | -92916.62 | 8253162.92 | 0 | 15379209.7 | 0 | 8051705.01 | 9797311.71 | 5819234.92 | 6823222.44 | 2124238.38 | 1373933 | 56702.12 | 141302816.02 | 3053555.33 | 4185738.284 | 145488554.304 | -19765790.3128
FINANCING FEE |  | ECT | RM | R. Malcolm |  | 1500000 |  | -500000 |  | 1000000 |  |  | 0 | 806250 |  |  |  |  | 83333.33 | [8 empty] | 889583.33 | -193750 | 0 | 889583.33 | 110416.67
| Escrow |  |  |  |  | 0 |  | 0 |  | 0 |  |  | 55979.1667 | [14 empty] | 55979.1667 | 0 | 0 | 55979.1667 | -55979.1667
| Legal Fees |  |  |  |  | 0 |  | 0 |  | 0 |  |  | 2533.3333 | [12 empty] | 83333.33 |  | 85866.6633 | 352817 | 0 | 85866.6633 | -85866.6633
| Insurance |  |  |  |  | 0 |  | 0 |  | 0 |  |  | 3333.3333 |  |  | 0 | [11 empty] | 3333.3333 | 0 | 0 | 3333.3333 | -3333.3333
| Mississippi Bond Issuance | [6 empty] | 0 |  | 0 | [17 empty] | 0 |  | 0 | 0 | 0
| Other (RW Beck) |  |  |  |  | 0 |  | 0 |  | 0 |  |  | 6540.11 | 4787.54 | [12 empty] | 107679.56 | 119007.21 | 33994 | 0 | 119007.21 | -119007.21 | Beck Professional Services
[6 empty] | 1500000 |  | -500000 |  | 1000000 |  | 0 | 68385.9433 | 811037.54 | 0 | 0 | 0 |  | 83333.33 |  | 0 | 0 | 0 | 0 | 0 | 83333.33 | 107679.56 | 1153769.7033 | 193061 | 0 | 1153769.7033 | -153769.7033
RESALE HANDLING FEES (.25%) |  | ECT |  | P Maloy |  | 0 |  | 63535.15 |  | 63535.15 |  | 63535.15 |  |  |  |  | -826 | [10 empty] | 62709.15 | -826 | 0 | 62709.15 | 826
DEVELOPMENT EXPENSES |  | ECT | MM | swag | [26 empty] | 0
| Travel Expenses | [10 empty] | 6743 | 602 | 564.87 | 1465.1 | 6454.99 | 5322.99 |  | 23937.67 |  | 4980.79 | 641.49 | 832.45 | 53.73 | 708.22 |  |  | 52307.3 |  |  | 52307.3
| Deloitte & Touche | [10 empty] | 5024 | [15 empty] | 5024 |  |  | 5024
| Utility Consulting Services (Infinergy) | [10 empty] | 8333.33 |  | 3333.33 | 3333.33 |  |  |  | 10536.23 |  | 3359.47 |  | 3385.34 | 6729.58 |  | 3362.58 |  | 42373.19 |  |  | 42373.19
| GLC Consulting | [10 empty] | 0 | [6 empty] | 109207.96 |  | 30022.42 | 66006.48 |  | 19997.91 |  |  |  | 225234.77 |  |  | 225234.77
| Harry Leather and Ron Anderson | [10 empty] | 122126.87 |  | 25448.82 | [13 empty] | 147575.69 |  |  | 147575.69 |  | Will net against IBC Commission
| HARC Development Service- Tom Young | [10 empty] | 21649 | 833 |  |  | -22066.15 | [11 empty] | 415.85 |  |  | 415.85
| Engineering Assessment | [10 empty] | 16218 | [6 empty] | 1785.85 | [8 empty] | 18003.85 |  |  | 18003.85
| ICF - Studies | [10 empty] | 4999.33 | [8 empty] | 4449.95 |  | 19502.67 | 15230.29 | 3271.03 |  |  | 47453.27 |  |  | 47453.27
| Other | [10 empty] | 0 |  |  |  | 1652 |  |  | 3123.25 |  |  | 22392.82 | 54989.57 | 13214.29 | 4115 |  |  | 99486.93 |  |  | 99486.93
| Power Systems SPC | [26 empty] | 0 |  |  | 0
| Maps | [10 empty] | 307 | [15 empty] | 307 |  |  | 307
| TOTAL DEVELOPMENT EXPENSE |  |  |  |  | 500000 |  | -200000 |  | 300000 |  | 185400.53 | 1435 | 29347.02 | 4798.43 | -13959.16 | 5322.99 |  | 148590.96 |  | 42812.63 | 89040.79 | 78710.03 | 55225.8 | 8094.25 | 3362.58 | 0 | 638181.85 | 0 | 0 | 638181.85 | -338181.85
LEGAL EXPENSES |  | ECT | TS/MM | Doug Pedigo
| Vinson & Elkins | [10 empty] | 5126.21 | [15 empty] | 5126.21 |  |  | 5126.21
| Andrews & Kurth | [10 empty] | 73646.08 | [6 empty] | 46466.78 |  |  | 33638.24 |  | 25078.87 |  |  |  | 178829.97 |  |  | 178829.97
| Goodin, Macbride | [10 empty] | 0 | [15 empty] | 0 |  |  | 0
| Stokes and Bartholomew | [10 empty] | 5964.94 | [15 empty] | 5964.94 |  |  | 5964.94
| Other | [10 empty] | 0 |  |  | 133167 |  |  |  | 7264.77 |  |  | 21232.26 |  | 3064.01 | 2973.91 | 2233.33 |  | 169935.28 |  |  | 169935.28
| Gerald & Brand | [10 empty] | 27693.61 |  | 5497.86 |  |  |  |  | 136383.74 |  |  |  |  | 5588.49 |  | 3946.28 |  | 179109.98 |  |  | 179109.98
| TOTAL LEGAL EXPENSE |  |  |  |  | 850000 |  | -550000 |  | 300000 |  | 112430.84 | 0 | 5497.86 | 133167 | 0 | 0 |  | 190115.29 |  | 0 | 54870.5 | 0 | 33731.37 | 2973.91 | 6179.61 | 0 | 538966.38 | 0 | 0 | 538966.38 | -238966.38
START-UP FUEL |  | ECT |  | K Presto |  | 0 |  | 1000000 |  | 1000000 |  | 0 | 0 | 0 |  |  | 50000 |  | 54683.74 |  | 131581 | 138751 | [5 empty] | 375015.74 | -650000 | 0 | 375015.74 | 624984.26
| Subtotal - Expense |  |  |  |  | 2850000 |  | -186464.85 |  | 2663535.15 |  | 361366.52 | 69820.9433 | 845882.42 | 137965.43 | -13959.16 | 54496.99 |  | 476723.32 |  | 174393.63 | 282662.29 | 78710.03 | 88957.17 | 11068.16 | 92875.52 | 107679.56 | 2768642.8233 | -457765 | 0 | 2768642.8233 | -105107.6733
TOTAL NEW ALBANY | [5 empty] | 109972038.9912 |  | 23779361.15 |  | 128386300.1412 |  | 63865966.15 | 1102894.5133 | 19590654.1 | 572532.99 | -106875.78 | 8307659.91 |  | 15855933.02 |  | 8226098.64 | 10079974 | 5897944.95 | 6912179.61 | 2135306.54 | 1466808.52 | 164381.68 | 144071458.8433 | 2595790.33 | 4185738.284 | 148257197.1273 | -19870897.9862
[14 empty] | . | . | . | . |  | . |  | . | . | . | . | . | . | . | . | .
TARGET $$/MW | [5 empty] | 281979.5872 |  |  |  | 329195.6414 | [20 empty] | 380146.6593
DEBT RESERVE | [5 empty] | 0 |  |  |  | 0 |  |  |  | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0
LESS DEPRECIATION (BEG 7/99) | [27 empty] | -1462905.5418 |  |  | -1462905.5418
TOTAL NEW ALBANY (with Debt Reserve | [5 empty] | 109972038.9912 |  | 23779361.15 |  | 128386300.1412 | [17 empty] | 142608553.3016 |  | 4185738.284 | 146794291.5856 | -19870897.9862
TARGET $$/MW (without Debt Reserve) | [5 empty] | 284165.4754 |  |  |  | 331747.5456 | [20 empty] | 379313.4149
0
'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/TVA_Wkly_Anal___121499.xls'#$NewAlbany
Reconciliation to Work Order:
| Balance per Work Order | [29 empty] | 141153553.19
| Balance per Weekly Summary | [29 empty] | 142554159.6933
| Difference | [29 empty] | -1400606.5033
Note on K174: tshepperd: 98 capital 7.5% 99 capital 7.0% Not based on current cash flows
Note on K214: tshepperd: This should probably be around $350,000 based on original Model and conversation with Ed Hearn
Note on U22: Stacey Aune: Amount represents freight costs for four turbines of which 25% stays on New Albany
Note on Y16: Shelly May: includes $110,166 to American Navigation for moving #1&2 from Pens to NA
Note on Y22: Shelly May: includes $536,221 to Intermarine for moving #5&6 from Masan to Pens; I unit here and 1 unit to Walton
Note on Y24: Shelly May: incl $(113)k for scrap sale of BOP from Korea and $593 refurb contr scope change + 10% IBC fee ($652k)
Note on AC24: apearce: reclassed to Doyle project - DOW units
Note on AC213: apearce: includes $119K reclassed by Faith Killen for Project Cheetah legal exps erroneously booked to her RC
Note on AI111: apearce: move $1282565 back down to contract labor on 8/24 report
Note on AK30: apearce: Includes $52,451 for repair of transformer which caught on fire.
Note on AU145: apearce: includes 250K / 3 plants of add'l manpower req's
Note on AW170: apearce: per david marshall, $82,918 plus possible trueup of $20K thru 8/31
Note on BC24: apearce: reclassed to Doyle project - DOW units

## Parts_Refurb $s (hidden)
| Spare Parts | Spare Parts
| Actuals | per Invy Detail
Dynegy | 5000000 | 5000000
Natole | 359700 | 359700
Turbine Resources | 1126671.15 | 1126671.15
|  | -1013887.05 | Not yet paid
Natole | 943800 | 943800
Selkirk | 3111381.03 | 3111381.03
Dow | 161700 | 161700 | incl in Dow Turbine line of budget
Elliot |  | 198000 | Not yet paid
IBC Refurb of spares (Wood Group) |  | 1082508.47 | Not yet paid
Spare parts before adjustment | 10703252.18 | 10969873.6
Parts staying at New Albany | 4391315.49
Refurb cost of parts staying at New Albany | 886191.12 |  | Not yet paid need to reconcile with IBC
Spare parts after adjustment for Units 1-4 | 5277506.61
Adjustment amount to New Albany cost summary | -5425745.57
Estimate to complete Units 5-6 at New Albany | 2000000
Total Estimated Project cost for spares at New Albany | 7277506.61
| Refurbishment | Refurbishment
| Actuals | Total Estimate
IBC Contract Payment #1 | 13392698 | 13392698
IBC Contract Payment #2 | 9374889 | 9374889
IBC Contract Payment #3 |  | 2678540 | Not yet paid
IBC Contract Payment #4 - Final |  | 1339270 | Not yet paid
Contract Out of Scope Work | 652369.63 | 652369.63 | LEC Combustion Burners ($593k scope change + 10% IBC fee)
WH Rent | 5400 | 5400
Misc Credit | -167 | -167
TTS out of scope refurb expenses | 10246.5 | 10246.5
Waterway lease and Port of Pensacola chgs | 123281.75 | 123281.75
Scrap sale | -113214.4 | -113214.4
Other costs to complete |  | 0 | Per final refurb analysis
Refurb cost before adjustment | 23445503.48 | 27463313.48