## Sheet1
Transwestern Pipeline Company
2002 Pipeline Integrity Program
CAPITAL
Project Description | 2002 | Plan | Estimate
Reallocation from O&M |  | 900000
Install pig traps on 30" San Juan Lateral | 3rd Qtr | 0 | 2500000
Replace 24" Panhandle River Crossing | 3rd Qtr | 885558 | 885558
Install McLean Pig Receiver | 3rd Qtr | 181272 | 181272
Smartpig Crawford Lateral (See O&M) |  | 175312 | 0
TW MAOP Upgrade Project |  | 150000 | 0
Placeholder for TW Smartpig Project |  | 1270660 | 0
|  | 3562802 | 3566830
O&M
Project Description | 2002 | Plan | Estimate
Pipeline Integrity Program |  | 4000000
Reallocation to Capital |  | -900000
Smartpig/caliper 24" Panhandle Lat. P2-P3 | Mid-Nov | 0 | 225000
Smartpig/caliper 30" ML Sta1-Needles | Late-Jun | 0 | 250000
Smartpig/caliper 30" Loopline 1-Needles | Late Jun | 0 | 250000
Smartpig/caliper 16" Crawford Lateral | Mid-Nov | 0 | 200000
CI Survey | 3rd/4th Qtrs | 0 | 100000
Pipeline recoat - Albuquerque | 3rd Qtr | 0 | 50000
Repairs on 30" Mainline Sta 1-Needles -smartpig | Sept | 0 | 350000
Repairs on 30" Loop Line Sta 1-Needles - smartpig | Sept | 0 | 300000
1725000
Repairs on 30" ML 7-6 (Main) | 2nd - New | 0 | 350000
Repairs on 30" ML 8-7 (Main) | 2nd - New | 0 | 275000
Repairs on 30" ML 5-4 (Loop) | 2nd - New | 0 | 450000
Repairs on 30" ML 5-4 (Main) | 2nd - New | 0 | 300000
|  | 0 | 1375000
|  | 3100000 | 3100000