## Sheet1
Updated: | 2001-11-27 |  |  |  |  | TW
Capital Budget 2001
Through Month of |  | OCTOBER
Project in Budget | Status | Budget $ |  | Work Order $'s | Comm | Actuals | $'s Est Needed to Complete | JAN | FEB | MAR | APR | MAY | JUN | JULY | AUG | SEP | OCT | NOV | DEC | TOTAL | Over/(Under) WO | Over/(Under) Budget
Business Development
New Rates & Revenue |  | 0 | 3 |  |  | 0 | 0 | [12 empty] | 0 | 0
FERC 637 | Available | 127000 | 2/3 |  |  | 0 | 0 | [12 empty] | 0 | 0 | -127000
GISB Ver 1.5 |  | 0 | 1 | 0 |  | 0 | 0 | [12 empty] | 0 | 0
GISB Imbalance Trading |  | 0 | 3 | 0 |  |  | 0 | [12 empty] | 0 | 0
New Contract Cap/Rel System | [6 empty] | 0 | [12 empty] | 0 | 0
C.006360 | A |  |  | 327880 |  | 102904 | 224976 | OCT: 102904; NOV: 224976 | 327880 | 0
C.006361 | A |  |  | 42120 |  | 0 | 42120 | OCT: 0; NOV: 14040; DEC: 28080 | 42120 | 0
Total |  | 370000 |  | 370000 |  | 102904 | 267096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 102904 | 239016 | 28080 | 370000 | 0 | 0
Cross Contract Ranking |  | 0 | 3 | 0 |  |  | 0 | [13 empty] | 0
TW Flow Direction | Available | 50000 |  |  |  | 0 | 0 | [12 empty] | 0 |  | -50000
Cap Anaylsis Carryover C.000691 Liccardo | F | 73000 | 2 | 73000 | 5222 | 64143 | 3635 | 18932 | 21698 | 17250 | 991 | 82 | 742 | 141 | 213 | 4094 | 0 |  | 8857 | 73000 | 0 | 0
EDI Upload Carryover C.006244 Liccardo | A | 90000 | 1 | 90000 |  | 17688 | 72312 | 542 | 320 | 5959 | 734 | 2582 | 415 | 1054 | 435 | 421 | 5226 |  | 72312 | 90000 | 0 | 0
0
Market Intelligence C.005451 Zhou | A | 40000 |  | 38594 |  | 36949 | 1645 |  | 787 | 5106 | 1548 | 10272 | 8509 | 2543 | 3945 | 3909 | 330 | 1645 |  | 38594 | 0 | -1406
Marketing DataMart for Reporting | Available | 20000 |  |  |  | 0 | 0 | [12 empty] | 0 | 0 | -20000
MFE Enhancements | Available | 20000 |  |  |  | 0 | 0 | [12 empty] | 0 | 0 | -20000
0
Environmnetal Auditing & Permitting(cancelled) |  | 0 | 4 |  |  |  | 0 | [12 empty] | 0 | 0
Enterprise Data Logger(CANCELLED) |  | 0 | 4 |  |  |  | 0 | [12 empty] | 0 | 0
PILARS - O&E C.006929 |  | 72600 | 4 | 72600 |  | 11322 | 61278 | OCT: 11322; NOV: 30641; DEC: 30637 | 72600 | 0 | 0
Web Interface Project O&E(cancelled) |  | 0 | 4 |  |  |  | 0 | [12 empty] | 0 | 0
Engine/Compressor Health(cancelled) |  | 0 | 4 |  |  |  | 0 | [12 empty] | 0 | 0
PDMS | COMMITTED | 67400 | 4 |  |  | 0 | 0 | DEC: 67400 | 67400 |  | 0
Blankets
Infra Desktop B.060002.GS.MKSV Steward | A | 20000 |  | 20000 | 1820 | 5540 | 12640 | JULY: 5540; AUG: 0; SEP: 0; OCT: 0; NOV: 14460 | 20000 | 0 | 0
Blanket Gas Control B.060002.GS.GC Kenagy | A | 10000 |  | 10000 |  | 0 | 10000 | AUG: 0; SEP: 0; OCT: 0; DEC: 10000 | 10000 | 0 | 0
O&E Desktop B.06002.GB.HOPS | A | 17000 |  | 17000 |  | 0 | 17000 | OCT: 0; NOV: 8500; DEC: 8500 | 17000 | 0 | 0
Field Desktop B.060001.BC Rich | A | 200000 |  | 200000 |  | 1575 | 198425 | FEB: -2365; MAY: 3940; AUG: 0; NOV: 45000; DEC: 153423 | 199998 | -2 | -2
TOTAL CAPITAL |  | 1177000 |  | 891194 | 7042 | 240121 | 644031 | 19474 | 20440 | 28315 | 3273 | 16876 | 9666 | 9278 | 4593 | 8424 | 119782 | 339262 | 379209 | 958592 | -2 | -218408
Available funds |  | -218408 |  | 285806
|  |  | 1 | EDI Upload Cap Rel C6244 is being funded by GISB Ver 1.5 Dollars
|  |  | 2 | Cap Analysis C.000691 is being funded by Replace Contract System
|  |  | 3 | $100.000 Dollars to fund New Rates and Revenue system moved to NNG
|  |  | 4 | Dollars to fund new O&E project
Status
A - Active |  |  |  | 'file:///mnt/12tb/@roms/datasets/enron/EDRM Enron Email Data Set v2 XML/filtered-attachments/xls/TW__Cap_for_Tracy.xls'#$Sheet1
F - Finished
H - Hold
C - Cancelled