## Timeline
TransPecos Timeline 2002
UP TO FERC FILING
| Agreement | FEBRUARY | MARCH |  |  |  | APRIL |  | MAY |  | JUNE
Language
PEMEX Letter Agreement (LA)
PEMEX LA Sent and Signed | LOI offer valid until 3/4 | 2002-02-01 | 2002-03-04
PEMEX to Submit $.261 Bid for Transportation During Open Season | due by the end of the open season |  |  | 2002-03-11 |  | 2002-03-28
PEMEX LOI Automatically Terminates | date in LOI | [10 empty] | 2002-07-01
KMI/TW Letter Agreement (LA)
Construction Participant Designated -engineering, development, construction, filing & reporting responsibilities | due 60 days after PEMEX LA is signed |  | 2002-03-04 | [5 empty] | 2002-05-03
Sign Joint Development Agreement | due 75 days after PEMEX LA is signed |  | 2002-03-04 | [6 empty] | 2002-05-18
Sign Operations Agreement | due 75 days after PEMEX LA is signed |  | 2002-03-04 | [6 empty] | 2002-05-18
Management Committee Created | due 75 days after PEMEX LA is signed |  | 2002-03-04 | [6 empty] | 2002-05-18
LOI Automatically Terminates with 30 Day Notification | date in LA | [10 empty] | 2002-06-30
OTHER DATES
Open Season | not defined anticipate start 1 week after PEMEX LA signed |  |  |  | 2002-03-11 | 2002-03-28
Negotiate Definitive Transportation Agreement with PEMEX | not defined anticpate 20 days from end of open season | [5 empty] | 2002-04-19 | 2002-04-19