## Sheet1
Transmission Constraint Projects - Status as of 1/25/2001
Project Title | ERCOT Designation | Designated Transmission Service Provider | Start Construction | Original Completion | Revised Completion | Expected CCN Filing Date | Date CCN Filed | Expected CCN Date | Date CCN Received | Status Info
Pawnee-Coleto Creek 345 KV Line | Normal | AEP | 2001-03-01 | Summer 2002 | 2002-03-02 |  | 1999-11-01 | 2000-08-01 | 2000-11-01 | PUCT Docket 21741; Motions for Rehearing Filed by Intervenors, PUC to consider rehearing by 3/7/01
San Miguel-Pawnee 345 KV Line | Normal | STEC | {1} | Summer 2002 | 2002-01-01 |  | 1999-12-01 | 2000-10-01 | 2000-11-01 | PUCT Docket 21747; Approval could be Aug, 2000 depending upon Comm. ruling on siting questions; STEC & landowners have reached a stipulated agreement
Limestone-Watermill 345 KV Line | Critical | TXU/REIT | 1999-11-01 | Summer 2002 | 2001-05-01 |  | 1999-04-01 |  | Nov-99/Jan-00 {3} | PUCT Dockets 20790 & 21497
Military Highway 138 KV Dynamic Reactive Resource | Critical | AEP | 1999-07-01 | 2000-07-01 | 2000-11-01 | N/A | N/A | N/A | N/A | In-Service
345 KV Series Capacitor Line Compensation | Critical | AEP | 2000-07-01 | 2000-12-01 | 2001-09-01 | N/A | N/A | N/A | N/A | Under Construction
Morgan Creek-Red Creek-Commanche Switch 345 KV Line | Critical | AEP | {1} | Summer 2003 | {2} | 2000-06-01 | 2000-07-01 | 2001-06-01 |  | PUC Docket 22798, SOAH Docket 473-00-2199, Hearing tentatively scheduled for February 2001
Morgan Creek-Red Creek-Commanche Switch 345 KV Line | Critical | TXU | {1} | Summer 2003 | 2002-12-01 | 2000-06-01 |  | 2001-06-01 |  | PUCT Docket 22823
Graham-Jacksboro 345 KV Line | Critical | TXU | {1} | Summer 2003 | 2002-12-01 | 2001-02-01 |  | 2001-08-01
Monticello-Farmersville-Anna Switch 345 KV Lines | Critical | TXU | {1} | Summer 2003 | 2002-12-01
Monticello-Farmersville Section |  |  |  |  | 2000-12-01 | N/A |  |  |  | Project complete & In-Service
Monticello-Valley Junction Section |  |  |  |  | 2002-12-01 | N/A
Valley Junction-Anna Switch Section |  |  |  |  | 2002-12-01 | 2000-06-01 | 2000-06-01 | 2000-12-01 | 2001-01-01 | PUCT Docket 22665
{1} Construction is scheduled to begin immediately upon receipt of regulatory approvals, right-of-way acquisition and environmental permits.
{2} CSW is investigating feasibility of completion in 2002.
{3} CCN approved in two sections