## Transmission
2001 / 02 Winter Assessment
SERC REGION
Scheduled Transmission Facility Additions, Retirements, and Re-ratings
Transmission Facilities (230 kV and Above) Scheduled for Initial Service, Retirement, or Re-rating between October 1, 2001 and February 28, 2002.
Reporting Entity | Region / Subregion | Facility | Length (Miles) |  |  | Type of Change | Operating Date
|  |  |  | Capacity | Voltage |  | Expected | Actual
|  |  |  | MVA | kV
Dominion Virginia Power | SERC/VACAR | Gainesville Transformer |  | 100 | 230/115 | New | 2001-11-01
Duke Power Company | SERC/VACAR | Sadler Tie |  | 448 MVA non-contingency 448 MVA contingency | 230/100 kV | Added tx capacity | 2001-10-01
Municipal Electric Authority of Georgia | SERC/SOU | 2nd Pitts Transformer |  | 336 | 230/115 | Add | 2001-07-16
Municipal Electric Authority of Georgia | SERC/SOU | 2nd Sandersville Transformer |  | 140 | 230/115 | Add | 2001-11-15
Municipal Electric Authority of Georgia | SERC/SOU | Barnesville Transformer |  | 300 | 230/115 | Add | 2001-07-01
Southern Company | SERC/SOU | Dawson Crossing - McGrau Ford | 16 | 602 | 230 | New Line | 2001-10-16
Southern Company | SERC/SOU | Lawrenceville - Suwanee | 6.65 | 664 | 230 | New Line | 2001-12-21
Southern Company | SERC/SOU | Lansing Smith - South Bainbridge | 19 | 509 | 230 | Upgrade | 2001-10-26
Southern Company | SERC/SOU | Jonesboro - Stockbridge | 4.7 | 602 | 230 | New Line | 2001-10-05
Transmission Facilities (230 kV and Above) Scheduled for Initial Service, Retirement, or Re-rating between March, 2001 and September 2001 NOT reported in 2001 Summer Assessment
Reporting Entity | Region / Subregion | Facility | Length (Miles) |  |  | Type of Change | Operating Date
|  |  |  | Capacity | Voltage |  | Expected | Actual
|  |  |  | MVA | kV
Dominion Virginia Power | SERC/VACAR | Shawboro - Kitty Hawk 230 kV Line #2064 | 36.9 | 1026 | 230 | Conversion | 2001-05-01 | 2001-03-01
Dominion Virginia Power | SERC/VACAR | Shawboro - Kitty Hawk 230 kV Line #2073 | 36.9 | 1026 | 230 | Conversion | 2001-05-01 | 2001-03-01
Dominion Virginia Power | SERC/VACAR | Possum Point Transformer |  | 840 | 500/230 | New | 2001-03-01 | 2001-04-01
Dominion Virginia Power | SERC/VACAR | Mt. Storm Capacitors |  | 300 | 500 | New | 2001-04-01 | 2001-06-01
Dominion Virginia Power | SERC/VACAR | Ladysmith - Ladysmith CT Line #2089 | 3.94 | 1047 | 230 | New | 2001-06-01 | 2001-02-01
Tennessee Valley Authority | SERC/TVA | Rock Spring Switching Station | N/A |  | 230 | new |  | 2001-05-01
Tennessee Valley Authority | SERC/TVA | Rock Spring-County Line 230 kV Line | 19.7 | 530S/707W | 230 | new |  | 2001-05-01
Transmission Facilities (230 kV and Above) Scheduled for initial service, Retirement, or Re-rating between March 1, 2001 and September 30, 2001.
From 2001 Summer Assessment (Update Actual Operating Date)
Reporting Entity | Subregion | Facility | Length (Miles) |  |  | Type of Change | Operating Date
|  |  |  | Capacity | Voltage |  | Expected | Actual
|  |  |  | MVA | kV
Entergy | SERC / Entergy | China-Jacinto 230kV Line | 49.46 | 750 | 230 | Bundle Conductor | 2001-03-01 | 2001-06-01
Entergy | SERC / Entergy | Amelia-Helbig 230kV Line | 10.27 | 685 | 230 | Bundle Conductor | 2001-09-30 | project postponed to 2003
Entergy | SERC / Entergy | Nelson-Verdine 230kV Line | 3.29 | 641 | 230 | Reconduct | 2001-06-01 | 2001-03-24
Alabama Electric Cooperative, Inc. | SERC / Southern | Gantt - Opp 230 KV TL | 19 | 586 | 230 | Addition | 2001-08-01 | 2001-09-07
| SERC / Southern | Chickasaw - Silverhill #1 line | 28.2 | 807 | 230 | re-rate | 2001-06-01
| SERC / Southern | Barry - Chickasaw line | 18.7 | 1004 | 230 | re-rate | 2001-06-01
| SERC / Southern | Ellicott-North Brewton | 61 | 1244 | 500 | new | 2001-06-01
| SERC / Southern | Fuller Road-Goat Rock SS | 8.6 | 502 | 230 | new | 2001-06-01
| SERC / Southern | Cornish Mountain - Porterdale line | 5 | 602 | 230 | new | 2001-03-01
| SERC / Southern | Vidalia #2 transformer |  | 300 | 230/115 | upgrade | 2001-04-01
| SERC / Southern | Rosier Road - South Augusta line | 6 | 602 | 230 | new | 2001-05-01
| SERC / Southern | Thomson Primary transformer |  | 140 | 230/115 | new | 2001-05-01
| SERC / Southern | Lawrenceville - Suwanee | 7 | 664 | 230 | new | 2001-06-01
| SERC / Southern | Big Shanty - South Acworth line | 10 | 866 | 230 | new | 2001-06-01
| SERC / Southern | Jonesboro - Stockbridge line | 5 | 602 | 230 | new | 2001-07-01
| SERC / Southern | Cartersville - Nelson | 27 | 866 | 230 | new | 2001-08-01
| SERC / Southern | Dawson Crossing transformer |  | 300 | 230/115 | new | 2001-09-01
| SERC / Southern | Cartersville -South Ackworth | 16 | 866 | 230 | new | 2001-06-01
| SERC / Southern | Dawson Crossing- McGraw Ford | 16 | 602 | 230 | new | 2001-06-01
| SERC / Southern | South Acworth - Hawkins Store 230 kV | 7 | 230 | 230 | Addition | 2001-06-01
| SERC / Southern | Deerfield Loop 230 kV | 4 | 230 | 230 | Addition | 2001-03-01
| SERC / Southern | Factory Shoals - Buzzard Roost 230 kV | 2.1 | 115 | 230 | Addition | 2001-07-01
| SERC / Southern | Alligator Swamp - Santa Rosa Energy line | 8 | 602 | 230 | new | 2001-06-01
| SERC / Southern | Kiln-Necaise | 9.9 | 301 | 230 | new | 2001-06-01
| SERC / TVA | Lagoon Creek 500 kV Switching Station | N/A | 800 | 500/13.8 | New | 2001-06-01
Tennessee Valley Authority | SERC / TVA | Shelby 500 kV Substation (2nd Bank) | N/A | 1200 | 500/161 | New | 2001-06-01 | 2001-07-01
| SERC / VACAR | Tiger Tie | N/A | 448 MVA non-contingency 150 MVA contingency | 230/100 kV | Added tx capacity | 2001-06-01
| SERC / VACAR | Sadler Tie | N/A | 448 MVA non-contingency 150 MVA contingency | 230/100 kV | Added tx capacity | 2001-09-30
| SERC / VACAR | J.S. Rainey - Greenwood County #1 | 29.67 | 956 | 230 | New Addition | 2001-04-01
| SERC / VACAR | J. S. Rainey - Greenwood County #2 | 29.67 | 956 | 230 | New Addition | 2001-04-01

## Generation
2001 / 02 Winter Assessment
SERC Region
Scheduled Generating Unit Additions, Retirements, and Re-Ratings
Generating Units Scheduled for Initial Service, Retirement, or Re-Rating between October 1, 2001 and February 28, 2002.
Reporting Entity | Region / Subregion | [5 empty] | Operating Date
|  | Unit | MW Change | Unit Type | Fuel Type | Change to Unit | Effective | Actual
Alabama Electric Cooperative, Inc. | SERC / SOU | VANN 1, 2, & 3 | 577 | CSCCG | Gas | New | 2001-12-10
Carolina Power & Light Company | SERC / VACAR | Harris #1 | 40 | Nuclear | Nuclear |  | 2002-01-02
Dominion Virginia Power | SERC / VACAR | Possum Point 1 | 74 | Fossil-Steam | Heavy Oil | Retirement | 2001-12-31
Dominion Virginia Power | SERC / VACAR | Possum Point 2 | 71 | Fossil-Steam | Heavy Oil | Retirement | 2001-12-31
Old Dominion Electric Cooperative | SERC / VACAR | Pointon 1 | 2 | Internal Combustion | Diesel | New | 2001-10-15
Old Dominion Electric Cooperative | SERC / VACAR | Pointon 2 | 2 | Internal Combustion | Diesel | New | 2001-10-15
Old Dominion Electric Cooperative | SERC / VACAR | Southampton 1 | 2 | Internal Combustion | Diesel | New | 2001-11-01
Old Dominion Electric Cooperative | SERC / VACAR | Southampton 2 | 2 | Internal Combustion | Diesel | New | 2001-11-01
South Carolina Public Service Authority | SERC / VACAR | RAINEY-CT1A | 168 | CT | NG | Initial Service | 2002-01-01
South Carolina Public Service Authority | SERC / VACAR | RAINEY-CT1B | 168 | CT | NG | Initial Service | 2002-01-01
South Carolina Public Service Authority | SERC / VACAR | RAINEY-ST1S | 172 | CW | CW | Initial Service | 2002-01-01
Tennessee Valley Authority | SERC / TVA | Cumberland | 8 | Steam Turbine | Bituminous Coal | Re-rating | 2001-11-01
Generating Units Scheduled for Initial Service, Retirement, or Re-Rating between March 2001 through September 2001 NOT reported in 2001 Summer Assessment
Reporting Entity | Region / Subregion | [5 empty] | Operating Date
|  | Unit | MW Change | Unit Type | Fuel Type | Change to Unit | Effective | Actual
Carolina Power & Light Company | CAPO | Rowan County |  |  |  | now a merchant plant |  | 2001-09-10
Dominion Virginia Power | VACAR | Hopewell Cogen | 336.6 | NUG | Natural Gas |  | 2001-06-21 | 2001-06-21
Dominion Virginia Power | VACAR | Cogentrix - Portsmouth | 105 | NUG | Coal |  | 2001-06-23 | 2001-06-23
Southern | Southern Power | Dahlberg 9 | 80 | CT | Natural Gas | Initial Service | 2001-06-01 | 2001-06-01
Southern | Southern Power | Dahlberg 10 | 80 | CT | Natural Gas | Initial Service | 2001-06-01 | 2001-06-01
Generating Units Scheduled for Initial Service, Retirement, or Re-Rating between March 1, 2001 and September 30, 2001.
From 2001 Summer Assessment (Update Actual Operating Date)
Reporting Entity | Subregion | [5 empty] | Operating Date
|  | Unit | MW Change | Unit Type | Fuel Type | Change to Unit | Effective | Actual
Associated Electric Coop Inc | SERC / Entergy | St. Francis #2 | 220 | CS | NG |  | 2001-03-31 | 2001-04-01
Entergy | SERC / Entergy | Warren Power | 360 | Combustion Turbine | Natural Gas | New | 2001-06-01 | 2001-07-09
Entergy | SERC / Entergy | Duke Attala | 561 | Combined Cycle | Natural Gas | New | 2001-06-01 | 2001-06-18
Entergy | SERC / Entergy | Calcasieu | 175 | Combustion Turbine | Natural Gas | New | 2001-06-01 | 2001-07-09
Entergy | SERC / Entergy | SRW Cogen | 535 | Combined Cycle | Natural Gas | New | 2001-08-01 | 2001-09-25
Entergy | SERC / Entergy | BASF | 75 | Combustion Turbine | Natural Gas | New | 2001-06-01 | 2001-08-26
Entergy | SERC / Entergy | CLECO Midstream | 150 | Combined Cycle | Natural Gas | New | 2001-06-01 | 2001-05-23
LAGN | SERC / Entergy | Sterlington #8 | 25 | CT | NG | New | 2001-04-01
LAGN | SERC / Entergy | Sterlington #6 | 25 | CT | NG | New | 2001-05-01
LAGN | SERC / Entergy | Sterlington #7 | 25 | CT | NG | New | 2001-05-01
LAGN | SERC / Entergy | BCI Pkr #1 | 119 | CT | NG | New | 2001-06-01
LAGN | SERC / Entergy | BCI Pkr #2 | 119 | CT | NG | New | 2001-07-01
Southern | SERC / Southern | Barry 7 | 540 | CC | NG | Initial Service | 2001-06-01 | 2001-06-01
Southern | SERC / Southern | Daniel 3 | 540 | CC | NG | Initial Service | 2001-06-01 | 2001-05-01
Southern | SERC / Southern | Daniel 4 | 540 | CC | NG | Initial Service | 2001-06-01 | 2001-04-01
TVA | SERC / TVA | Lagoon Creek | 616 | Gas Turbine | Natural Gas | Initial Service | 2001-06-01
TVA | SERC / TVA | Raccoon Mountain | 46 | Pumped Storage | Water | Re-rating | 2001-05-01
TVA | SERC / TVA | Red Hills (IPP) | 440 | Fluidized Bed Combustion | Lignite | Initial Service | 2001-05-01 | 2001-11-01
TVA | SERC / TVA | Various Hydros | 43 | Hydraulic Turbine | Water | Re-rating | 2001-07-01
South Carolina Electric & Gas | SERC / VACAR | Urquhart No. 1 | 5 | ST | BIT | Decrease | 2001-06-01
South Carolina Electric & Gas | SERC / VACAR | Urquhart No. 2 | 5 | ST | BIT | Decrease | May
South Carolina Electric & Gas | SERC / VACAR | Fairfield PS No. 3 | 12 | PS | WAT | Increase | 2001-06-01
South Carolina Electric & Gas | SERC / VACAR | Fairfield PS No. 4 | 12 | PS | WAT | Increase | 2001-06-01
Old Dominion Electric Cooperative | SERC / VACAR | Nottoway 1 | 2 | IC | DFO | new | 2001-07-01 | Not In Serice
Old Dominion Electric Cooperative | SERC / VACAR | Nottoway 2 | 2 | IC | DFO | new | 2001-07-01 | Not In Serice
Old Dominion Electric Cooperative | SERC / VACAR | Ponton 1 | 2 | IC | DFO | new | 2001-07-01 | Not In Serice
Old Dominion Electric Cooperative | SERC / VACAR | Ponton 2 | 2 | IC | DFO | new | 2001-07-01 | Not In Serice
South Carolina Public Service Authority | SERC / VACAR | Horry LFG | 1063 | IC | MTE | New Addition | 2001-08-01
Dominion Virginia Power | SERC / VACAR | Ladysmtih Unit 1 | 144 | CT | Gas/Oil | Initial Service | 2001-06-01 | 2001-03-23
Dominion Virginia Power | SERC / VACAR | Ladysmith Unit 2 | 144 | CT | Gas/Oil | Initial Service | 2001-06-01 | 2001-04-01
Dominion Virginia Power | SERC / VACAR | Doswell CT | 155 | CT | Gas/Oil | Initial Service | 2001-06-01 | 2001-06-01
Carolina Power & Light Company | SERC / VACAR | Richmond County #1-4 | 620 | Combustine Turbine | Natural Gas | Initial Service | 2001-06-01
Carolina Power & Light Company | SERC / VACAR | Rowan County #1-3 | 459 | Combustine Turbine | Natural Gas | Initial Service | 2001-06-01 | 2001-05-01
Carolina Power & Light Company | SERC / VACAR | Broad River #4 | 453 | Combustine Turbine | Natural Gas |  | 2001-06-01
Duke Energy | SERC / VACAR | Rowan IPP | +453 | 3 Combustion Turbines | Natural Gas / Fuel Oil | New Facility | 2001-06-01
Duke Energy | SERC / VACAR | Broad River IPP | +302 | 2 Combustion Turbines | Natural Gas / Fuel Oil | Total Capacity increase from 453 MW to 755 MW. | 2001-07-01
Who should report this unit?