## Turbine Payments
Contract Date March 4, 1999 |  |  | Contract Date March 18, 1999 |  |  | Contract Date September 3, 1999 | [11 empty] | Contract Date May 14, 1999
4 Gas Turbines |  |  | 4 Gas Turbines |  |  | 4 Gas Turbines |  |  | 4 Gas Turbines |  |  | 4 Gas Turbines |  |  | 4 Gas Turbines |  |  | 10 Gas Turbines
2 Steam Turbines |  |  | 2 Steam Turbines |  |  | 2 Steam Turbines |  |  | 2 Steam Turbines |  |  | 2 Steam Turbines |  |  | 2 Steam Turbines |  |  | 10 Steam Turbines
GE |  |  | GE |  |  | GE |  |  | GE |  |  | GE |  |  | GE |  |  | ABB |  | Total
1999-03-01 | 4000000 |  | 1999-03-01 | 4000000 |  | 1999-03-01 | 0 |  | 1999-03-01 | 0 |  | 1999-03-01 | 0 |  | 1999-03-01 | 0 |  | 1999-03-01 | 0 | 8000000
1999-05-01 | 4000000 |  | 1999-05-01 | 4000000 |  | 1999-05-01 | 0 |  | 1999-05-01 | 0 |  | 1999-05-01 | 0 |  | 1999-05-01 | 0 |  | 1999-05-01 | 4000000 | 12000000
1999-08-01 | 2400000 |  | 1999-08-01 | 2400000 |  | 1999-08-01 | 0 |  | 1999-08-01 | 0 |  | 1999-08-01 | 0 |  | 1999-08-01 | 0 |  | 1999-08-01 | 0 | 4800000
1999-09-01 | 0 |  | 1999-09-01 | 0 |  | 1999-09-01 | 5034543 |  | 1999-09-01 | 5017271 |  | 1999-09-01 | 4974093 |  | 1999-09-01 | 4974093 |  | 1999-09-01 | 2000000 | 22000000
1999-10-01 | 0 |  | 1999-10-01 | 0 |  | 1999-10-01 | 0 |  | 1999-10-01 | 0 |  | 1999-10-01 | 0 |  | 1999-10-01 | 0 |  | 1999-10-01 | 4000000 | 4000000
1999-11-01 | 0 |  | 1999-11-01 | 0 |  | 1999-11-01 | 0 |  | 1999-11-01 | 0 |  | 1999-11-01 | 0 |  | 1999-11-01 | 0 |  | 1999-11-01 | 0 | 0
1999-12-01 | 8522000 |  | 1999-12-01 | 2400000 |  | 1999-12-01 | 0 |  | 1999-12-01 | 0 |  | 1999-12-01 | 0 |  | 1999-12-01 | 0 |  | 1999-12-01 | 0 | 10922000
2000-01-01 | 9723000 |  | 2000-01-01 | 0 |  | 2000-01-01 | 0 |  | 2000-01-01 | 0 |  | 2000-01-01 | 0 |  | 2000-01-01 | 0 |  | 2000-01-01 | 2000000 | 11723000
2000-02-01 | 8262500 |  | 2000-02-01 |  |  | 2000-02-01 | 0 |  | 2000-02-01 | 0 |  | 2000-02-01 | 0 |  | 2000-02-01 | 0 |  | 2000-02-01 | 0 | 8262500
2000-03-01 | 4624740 |  | 2000-03-01 | 3637760 |  | 2000-03-01 | 0 |  | 2000-03-01 | 0 |  | 2000-03-01 | 0 |  | 2000-03-01 | 0 |  | 2000-03-01 | 0 | 8262500
Paid to date | 41532240 |  | Paid to date | 16437760 |  | Paid to date | 5034543 |  | Paid to date | 5017271 |  | Paid to date | 4974093 |  | Paid to date | 4974093 |  | Paid to date | 12000000 | 89970000
2000-04-01 | 11900260 |  | 2000-04-01 | 4612160 |  | 2000-04-01 | 12455457 |  | 2000-04-01 | 12412729 |  | 2000-04-01 | 12305907 |  | 2000-04-01 | 12305907 |  | 2000-04-01 | 0 | 65992420
2000-05-01 | 8262500 |  | 2000-05-01 | 6008800 |  | 2000-05-01 | 0 |  | 2000-05-01 | 0 |  | 2000-05-01 | 0 |  | 2000-05-01 | 0 |  | 2000-05-01 | 20000000 | 34271300
2000-06-01 | 8262500 |  | 2000-06-01 | 7405440 |  | 2000-06-01 | 0 |  | 2000-06-01 | 0 |  | 2000-06-01 | 0 |  | 2000-06-01 | 0 |  | 2000-06-01 | 12000000 | 27667940
2000-07-01 | 8262500 |  | 2000-07-01 | 7405440 |  | 2000-07-01 | 0 |  | 2000-07-01 | 0 |  | 2000-07-01 | 0 |  | 2000-07-01 | 0 |  | 2000-07-01 | 10000000 | 25667940
2000-08-01 | 8262500 |  | 2000-08-01 | 7405440 |  | 2000-08-01 | 0 |  | 2000-08-01 | 0 |  | 2000-08-01 | 0 |  | 2000-08-01 | 0 |  | 2000-08-01 | 0 | 15667940
2000-09-01 | 8262500 |  | 2000-09-01 | 7405440 |  | 2000-09-01 | 0 |  | 2000-09-01 | 0 |  | 2000-09-01 | 0 |  | 2000-09-01 | 0 |  | 2000-09-01 | 0 | 15667940
2000-10-01 | 8262500 |  | 2000-10-01 | 7405440 |  | 2000-10-01 | 0 |  | 2000-10-01 | 0 |  | 2000-10-01 | 0 |  | 2000-10-01 | 0 |  | 2000-10-01 | 0 | 15667940
2000-11-01 | 8262500 |  | 2000-11-01 | 7405440 |  | 2000-11-01 | 0 |  | 2000-11-01 | 0 |  | 2000-11-01 | 0 |  | 2000-11-01 | 0 |  | 2000-11-01 | 0 | 15667940
2000-12-01 | 8262500 |  | 2000-12-01 | 7405440 |  | 2000-12-01 | 3498000 |  | 2000-12-01 | 3486000 |  | 2000-12-01 | 4509000 |  | 2000-12-01 | 4509000 |  | 2000-12-01 | 0 | 31669940
2001-01-01 | 8262500 |  | 2001-01-01 | 7405440 |  | 2001-01-01 | 3498000 |  | 2001-01-01 | 3486000 |  | 2001-01-01 | 4509000 |  | 2001-01-01 | 4509000 |  | 2001-01-01 | 0 | 31669940
2001-02-01 | 8262500 | Ship Date | 2001-02-01 | 7405440 |  | 2001-02-01 | 3498000 |  | 2001-02-01 | 3486000 |  | 2001-02-01 | 4509000 |  | 2001-02-01 | 4509000 |  | 2001-02-01 | 0 | 31669940
2001-03-01 | 7143500 | Ship Date | 2001-03-01 | 7405440 |  | 2001-03-01 | 3498000 |  | 2001-03-01 | 3486000 |  | 2001-03-01 | 5562000 |  | 2001-03-01 | 4509000 |  | 2001-03-01 | 0 | 31603940
2001-04-01 | 2959000 | Ship Date | 2001-04-01 | 7405440 |  | 2001-04-01 | 3498000 |  | 2001-04-01 | 3486000 |  | 2001-04-01 | 6237000 |  | 2001-04-01 | 4887000 |  | 2001-04-01 | 0 | 28472440
2001-05-01 | 8120000 |  | 2001-05-01 | 7405440 |  | 2001-05-01 | 3498000 |  | 2001-05-01 | 3486000 |  | 2001-05-01 | 6237000 |  | 2001-05-01 | 4887000 |  | 2001-05-01 | 0 | 33633440
2001-06-01 | 0 |  | 2001-06-01 | 7405440 |  | 2001-06-01 | 3498000 |  | 2001-06-01 | 3486000 |  | 2001-06-01 | 6237000 |  | 2001-06-01 | 5562000 |  | 2001-06-01 | 0 | 26188440
2001-07-01 | 0 |  | 2001-07-01 | 7405440 |  | 2001-07-01 | 3498000 |  | 2001-07-01 | 3486000 |  | 2001-07-01 | 6615000 |  | 2001-07-01 | 5562000 |  | 2001-07-01 | 0 | 26566440
2001-08-01 | 0 |  | 2001-08-01 | 5586560 | Ship Date | 2001-08-01 | 3498000 |  | 2001-08-01 | 3486000 |  | 2001-08-01 | 6615000 |  | 2001-08-01 | 6237000 |  | 2001-08-01 | 0 | 25422560
2001-09-01 | 0 |  | 2001-09-01 | 5586560 |  | 2001-09-01 | 3498000 |  | 2001-09-01 | 4539000 |  | 2001-09-01 | 7290000 |  | 2001-09-01 | 6237000 |  | 2001-09-01 | 0 | 27150560
2001-10-01 | 4060000 |  | 2001-10-01 | 2793280 | Ship Date | 2001-10-01 | 3498000 |  | 2001-10-01 | 4539000 |  | 2001-10-01 | 7290000 |  | 2001-10-01 | 6912000 |  | 2001-10-01 | 0 | 29092280
2001-11-01 | 4060000 |  | 2001-11-01 | 1458720 | Ship Date | 2001-11-01 | 3498000 |  | 2001-11-01 | 5592000 |  | 2001-11-01 | 7965000 |  | 2001-11-01 | 7290000 |  | 2001-11-01 | 0 | 29863720
2001-12-01 | 0 |  | 2001-12-01 | 0 | Ship Date | 2001-12-01 | 4848000 |  | 2001-12-01 | 5592000 |  | 2001-12-01 | 7965000 |  | 2001-12-01 | 7965000 |  | 2001-12-01 | 0 | 26370000
2002-01-01 | 0 |  | 2002-01-01 | 8120000 |  | 2002-01-01 | 4848000 |  | 2002-01-01 | 5592000 |  | 2002-01-01 | 8640000 |  | 2002-01-01 | 7965000 |  | 2002-01-01 | 0 | 35165000
2002-02-01 | 0 |  | 2002-02-01 | 0 |  | 2002-02-01 | 5616000 |  | 2002-02-01 | 6972000 |  | 2002-02-01 | 8640000 |  | 2002-02-01 | 8640000 |  | 2002-02-01 | 0 | 29868000
2002-03-01 | 0 |  | 2002-03-01 | 0 |  | 2002-03-01 | 5616000 |  | 2002-03-01 | 8025000 |  | 2002-03-01 | 14310000 | Ship Date | 2002-03-01 | 8640000 |  | 2002-03-01 | 0 | 36591000
2002-04-01 | 0 |  | 2002-04-01 | 0 |  | 2002-04-01 | 7671000 |  | 2002-04-01 | 8025000 |  | 2002-04-01 | 18765000 | Ship Date | 2002-04-01 | 14310000 | Ship Date | 2002-04-01 | 0 | 48771000
2002-05-01 | 0 |  | 2002-05-01 | 0 |  | 2002-05-01 | 8055000 |  | 2002-05-01 | 8715000 |  | 2002-05-01 | 6750000 |  | 2002-05-01 | 18765000 | Ship Date | 2002-05-01 | 0 | 42285000
2002-06-01 | 0 |  | 2002-06-01 | 4060000 |  | 2002-06-01 | 8745000 |  | 2002-06-01 | 8715000 |  | 2002-06-01 | 13500000 | Ship Date | 2002-06-01 | 6750000 |  | 2002-06-01 | 0 | 41770000
2002-07-01 | 0 |  | 2002-07-01 | 4060000 |  | 2002-07-01 | 8745000 |  | 2002-07-01 | 8715000 |  | 2002-07-01 | 3375000 |  | 2002-07-01 | 13500000 | Ship Date | 2002-07-01 | 0 | 38395000
2002-08-01 | 0 |  | 2002-08-01 | 0 |  | 2002-08-01 | 8745000 |  | 2002-08-01 | 24510000 | Ship Date | 2002-08-01 | 0 |  | 2002-08-01 | 3375000 |  | 2002-08-01 | 0 | 36630000
2002-09-01 | 0 |  | 2002-09-01 | 0 |  | 2002-09-01 | 18870000 | Ship Date | 2002-09-01 | 8715000 |  | 2002-09-01 | 0 |  | 2002-09-01 | 0 |  | 2002-09-01 | 0 | 27585000
2002-10-01 | 0 |  | 2002-10-01 | 0 |  | 2002-10-01 | 14505000 | Ship Date | 2002-10-01 | 13800000 | Ship Date | 2002-10-01 | 0 |  | 2002-10-01 | 0 |  | 2002-10-01 | 0 | 28305000
2002-11-01 | 0 |  | 2002-11-01 | 0 |  | 2002-11-01 | 15720000 | Ship Date | 2002-11-01 | 3450000 |  | 2002-11-01 | 0 |  | 2002-11-01 | 0 |  | 2002-11-01 | 0 | 19170000
2002-12-01 | 0 |  | 2002-12-01 | 0 |  | 2002-12-01 | 3450000 |  | 2002-12-01 | 0 |  | 2002-12-01 | 0 |  | 2002-12-01 | 0 |  | 2002-12-01 | 0 | 3450000
Total | 162400000 |  | Total | 162400000 |  | Total | 174900000 |  | Total | 174300000 |  | Total | 172800000 |  | Total | 172800000 |  | Total | 54000000 | 1073600000
Shipment STG#1 - Feb 2001 |  |  | Shipment STG#1&2 - Aug 2001 |  |  | Shipment GTG #11&12 - Sep 2002 |  |  | Shipment GTG #9&10 - Aug 2002 |  |  | Shipment STG #1&2 - Mar 2002 |  |  | Shipment STG #3&4 - Apr 2002
Shipment GTG #1&2, STG #2 - Mar 2001 |  |  | Shipment GTG #1&2 - Oct 2001 |  |  | Shipment STG #7&8 - Oct 2002 |  |  | Shipment STG #5&6 - Aug 2002 |  |  | Shipment GTG #1&2 - Apr 2002 |  |  | Shipment GTG #3&4 - May 2002
Available to Ship GTG #3&4 - April 2001 |  |  | Available to Ship GTG #3 - Nov 2001 |  |  | Shipment GTG #15&16 - Nov 2002 |  |  | Shipment GTG #13&14 - Oct 2002 |  |  | Shipment GTG #5&6 - Jun 2002 |  |  | Shipment GTG #7&8 - Jul 2002
Available to Ship GTG #4 - Dec 2001
$3,637,760 originally due in March has | [5 empty] | $12,445,457 originally due in January has |  |  | $12,412,729 originally due in January has |  |  | $12,305,907 originally due in January has |  |  | $12,305,907 originally due in January has |  |  | $10,000,000 originally due in March
been pushed to April. | [5 empty] | been pushed to April. |  |  | been pushed to April. |  |  | been pushed to April. |  |  | been pushed to April. |  |  | has been pushed to May.
$5,000,000 due as a result of
the proposed change order
is included in the total due
in May.