## Detail by Turbine
Turbine Position Report
Detail by Turbine
2001-06-29 | [8 empty] | Financial Data as of | 2001-06-30
Line | Status |  | Vendor | Contract / PO # | Serial # | Model | Output @ ISO | Heat Rate (HHV) | New/Used | Delivery Date | Owner | DASH Approval Date | Notice to Proceed Given | Status of Financing | Controlled By | Originator / Developer | Project Manager | Project Name | Contract Cost | Contract Paid to Date (Scheduled) | Cancel-lation Payment | Comments | Status Update
1 | Committed | 3 | GE | BD-2-00 |  | 7EA | 83 | 11900 | New | 2000-03-01 | E-Next Generation | $4MM Paid | N | N/A | EA |  |  | Northwestern Corp. | 19.1325 | 11.4795 | 7.2703 | EE&CC purchased these turbines spec; Delainey accepts responsibility for removing from LJM | Exclusivity payment received for sale on 4/30. Next payment due in July.
2 | Committed | 2 | GE | BD-2-00 |  | 7EA | 83 | 11900 | New | 2001-03-01 | E-Next Generation | $4MM Paid | N | N/A | EA |  |  | Northwestern Corp. | 19.1325 | 19.1325 | 19.1325 | EE&CC purchased these turbines spec; Delainey accepts responsibility for removing from LJM - Blue Dog | Exclusivity payment received for sale on 4/30. Next payment due in July.
3 | Tentative | 4 | GE |  |  | 7FA |  |  |  |  | E-Next Generation | $16.5MM on 2/16/01 | N | N/A | EA | Jake Thomas/Laura Wente |  | Columbia / Longview | 39.2 | 8.624 | 6.272
4 | Tentative | 2 | Mitsubishi |  |  | MHI 501F Simple Cycle | 184 | 10256 | New | 2001-06-01 | West LB | $2.5MM on 1/31/01 | N | N/A | EA |  |  | Fort Pierce | 43.618 | 43.618 | 43.618
5 | Tentative | 2 | Mitsubishi |  |  | MHI 501F Simple Cycle | 184 | 10256 | New | 2002-05-01 | West LB | Analyzing | N | N/A | EA |  | Jeff Westfahl | Eletrobolt II | 36.854 | 14.7416 | 36.854
6 | Tentative | 2 | Mitsubishi |  |  | MHI 501F Simple Cycle | 184 | 10256 | New | 2002-05-01 | West LB | Analyzing | N | N/A | EA |  | Jeff Westfahl | Eletrobolt II | 36.854 | 14.7416 | 36.854
7 | Available | 2 | Mitsubishi |  |  | MHI 501F Simple Cycle | 184 | 10256 | New | 2001-09-01 | West LB | Analyzing | N | N/A | EA |  |  | Unassigned | 43.618 | 43.618 | 43.618
8 | Available | 3 | Westing- house | Y2K(6)-2-98 |  | 501D5A Simple Cycle | 122 | 10856 | New | being cleaned | ENE B/S | Analyzing | N | N/A | EA | David Fairley, Mathew Gimble |  | Unassigned | 24.506 | 24.506 | 24.506 | CALME purchased turbine from ENA; turbine has not yet cleared customs; generator incurred salt water damage while unloading
9 | Available | 1 |  |  |  | 9FA STAG Power Islands | 375 | 10456 | New | 2001-10-01 | Whitewing | Analyzing | N | N/A | EWS | John Chappell | Stephen Heck | Arcos | 83.4167 | 59.2258 | 54.3877
10 | Available | 1 |  |  |  | 9FA STAG Power Islands | 375 | 10456 | New | 2001-11-01 | Whitewing | Analyzing | N | N/A | EWS | John Chappell | Stephen Heck | Arcos | 83.4167 | 59.2258 | 54.3877
11 | Available | 1 |  |  |  | 9FA STAG Power Islands | 375 | 10456 | New | 2001-12-01 | Whitewing | Analyzing | N | N/A | EWS | John Chappell | Stephen Heck | Arcos | 83.4167 | 59.2258 | 54.3877
12 | Available | 3 | ABB |  |  | 11N1 | 83 | 11447 | Used | Delivered | West LB | Analyzing | N | N/A | EA |  |  | Unassigned | 17.25 | 17.25 | 17.25 |  | Negotiations ongoing with 3 to 4 interested parties.
13 | Available | 3 | ABB |  |  | 11N1 | 83 | 11447 | Used | Delivered | West LB | Analyzing | N | N/A | EA |  |  | Unassigned | 17.25 | 17.25 | 17.25 |  | Negotiations ongoing with 3 to 4 interested parties.
14 | Available | 2 | GE |  |  | Fr 6B 60 hz power barges (BV = 0) | 31 | 10151 | Used | Delivered | ENE B/S | Analyzing | N | N/A | EGM |  |  | Unassigned | 6.5 | 6.5 | 6.5 | submitted PPA to NY controller; structuring desk issues (formerly LIPA)
15 | Available | 2 | GE |  |  | Fr 6B 60 hz power barges (BV = 0) | 31 | 10151 | Used | Delivered | ENE B/S | Analyzing | N | N/A | EGM |  |  | Unassigned | 6.5 | 6.5 | 6.5 | submitted PPA to NY controller; structuring desk issues
16 | Available | 3 | Korean |  |  | Steam Turbine (book value =0) | 110 | N/A | Used | Delivered | ENE B/S | Analyzing | N | N/A | EA | Robert Virgo |  | Unassigned | 2.3 | 2.3 | 0 | package with Korean used GE7B's / currently under sale negotiations - written off to zero on G/L
Note on M5: Stephanie K McGinnis: use last signature date per DASH
Note on N5: Stephanie K McGinnis: When EPC contract is officially turned on

## Summary by Status
Turbine Position Report | [6 empty] | CONFIDENTIAL
Summary by Status
2001-06-29
($ MMs)
[6 empty] | Financial Data as of | 2001-06-30
UNITS | MODEL | CONTROLLED BY | PROJECT(S) | DASH APPROVAL DATE / STATUS | CONTRACT COST | SCHEDULED CONTRACT PYMTS TO DATE | CANCELLATION COST TO DATE | STATUS
COMMITTED - turbines committed to deals which have been DASHed and financing is in process.
2 | 7EA | EA | Northwestern Corp. | $4MM Paid | 38.265 | 30.612 | 26.4029 | Committed
2 |  |  | Total Committed |  | 38.265 | 30.612 | 26.4029
TENTATIVE - turbines tentatively committed to ONE deal which has not yet been DASHed, but is likely to be.
1 | MHI 501F simple cycle | EA | Fort Pierce | $2.5MM on 1/31/01 | 43.618 | 43.618 | 43.618 | Tentative
1 | 7FA | EA | Columbia / Longview | $16.5MM on 2/16/01 | 39.2 | 8.624 | 6.272 | Tentative
2 | MHI 501F simple cycle | EA | Eletrobolt II | Analyzing | 73.708 | 29.4832 | 73.708 | Tentative
4 |  |  | Total Tentative |  | 156.526 | 81.7252 | 123.598
AVAILABLE - turbines which may be potential matches with SEVERAL deals, none of which have been approved to date.
1 | MHI 501F simple cycle | EA | Unassigned | Analyzing | 43.618 | 43.618 | 43.618 | Available
1 | 501D5A simple cycle | EA | Unassigned | Analyzing | 24.506 | 24.506 | 24.506 | Available
3 | 9FA STAG power islands | EWS | Arcos | Analyzing | 250.25 | 177.6775 | 163.163 | Available
2 | 11N1 | EA | Unassigned | Analyzing | 34.5 | 34.5 | 34.5 | Available
2 | Fr 6B 60hz power barges (BV=0) | EGM | Unassigned | Analyzing | 13 | 13 | 13 | Available
1 | Steam Turbine (BV = 0) | EA | Unassigned | Analyzing | 2.3 | 2.3 | 0 | Available
10 |  |  | Total Available |  | 368.174 | 295.6015 | 278.787
NEGOTIATING - turbines for which the purchase is currently being negotiated, but Enron does not yet have control of these turbines.
0 |  |  | Total Negotiating |  | 0 | 0 | 0
16 | UNITS - TOTAL |  | GRAND TOTALS |  | 562.965 | 407.9387 | 428.7878
SCHEDULED VS CANCELLATION PAYMENTS
($ MMs)
* Total Cancellation Payments = Total Enron Exposure
Cumulative Cancellation Cost to Date $429MM
Incremental Cancellation
Cost $21MM
Cumulative Payments to Date $408MM

## Summary by Type
Turbine Position Report | [7 empty] | CONFIDENTIAL
Summary by Turbine Type
2001-06-29
($ MMs)
[7 empty] | Financial Data as of | 2001-06-30
UNITS | MODEL | CONTROLLED BY | PROJECT(S) | DASH APPROVAL DATE / STATUS | CONTRACT COST | SCHEDULED CONTRACT PYMTS TO DATE | CANCELLATION | STATUS
2 | 11N1 | EA | Unassigned | Analyzing | 34.5 | 34.5 | 34.5 | Available
1 | 501D5A simple cycle | EA | Unassigned | Analyzing | 24.506 | 24.506 | 24.506 | Available
2 | MHI 501F simple cycle | EA | Eletrobolt II | Analyzing | 73.708 | 29.4832 | 73.708 | Tentative
1 | MHI 501F simple cycle | EA | Fort Pierce | $2.5MM on 1/31/01 | 43.618 | 43.618 | 43.618 | Tentative
1 | MHI 501F simple cycle | EA | Unassigned | Analyzing | 43.618 | 43.618 | 43.618 | Available
2 | 7EA | EA | Northwestern Corp. | $4MM Paid | 38.265 | 30.612 | 26.4029 | Committed
1 | 7FA | EA | Columbia / Longview | $16.5MM on 2/16/01 | 39.2 | 8.624 | 6.272 | Tentative
3 | 9FA STAG power islands | EWS | Arcos | Analyzing | 250.25 | 177.6775 | 163.163 | Available
2 | Fr 6B 60hz power barges (BV=0) | EGM | Unassigned | Analyzing | 13 | 13 | 13 | Available
1 | Steam Turbine (BV = 0) | EA | Unassigned | Analyzing | 2.3 | 2.3 | 0 | Available
16 |  |  |  | total per above | 562.965 | 407.9387 | 428.7878
16 |  |  |  | per Summary By Status report | 562.965 | 407.9387 | 428.7878
0 |  |  |  | Difference | 0 | 0 | 0

## Summary by Region
Turbine Position Report | [7 empty] | CONFIDENTIAL
Summary by Controlling Region
2001-06-29
($ MMs)
[7 empty] | Financial Data as of | 2001-06-30
UNITS | MODEL | CONTROLLED BY | STATUS | DASH APPROVAL DATE / STATUS | PROJECT(S) | CONTRACT COST | SCHEDULED CONTRACT PYMTS TO DATE | CANCELLATION
EWS
3 | 9FA STAG power islands | EWS | Available | Analyzing | Arcos | 250.25 | 177.6775 | 163.163
[5 empty] | TOTAL EECC | 250.25 | 177.6775 | 163.163
EA
1 | 501D5A simple cycle | EA | Available | Analyzing | Unassigned | 24.506 | 24.506 | 24.506
1 | MHI 501F simple cycle | EA | Tentative | $2.5MM on 1/31/01 | Fort Pierce | 43.618 | 43.618 | 43.618
1 | 7FA | EA | Tentative | $16.5MM on 2/16/01 | Columbia / Longview | 39.2 | 8.624 | 6.272
2 | 11N1 | EA | Available | Analyzing | Unassigned | 34.5 | 34.5 | 34.5
2 | 7EA | EA | Committed | $4MM Paid | Northwestern Corp. | 38.265 | 30.612 | 26.4029
1 | Steam Turbine (BV = 0) | EA | Available | Analyzing | Unassigned | 2.3 | 2.3 | 0
2 | MHI 501F simple cycle | EA | Tentative | Analyzing | Eletrobolt II | 73.708 | 29.4832 | 73.708
1 | MHI 501F simple cycle | EA | Available | Analyzing | Unassigned | 43.618 | 43.618 | 43.618
[5 empty] | TOTAL EA | 299.715 | 217.2612 | 252.6249
EGM
2 | Fr 6B 60hz power barges (BV=0) | EGM | Available | Analyzing | Unassigned | 13 | 13 | 13
16 | UNITS - TOTAL |  |  |  | GRAND TOTALS | 562.965 | 407.9387 | 428.7878
[5 empty] | per Summary By Status report | 562.965 | 407.9387 | 428.7878
[5 empty] | Difference | 0 | 0 | 0

## Cost Cancel Details
Turbine Position Report
Cost / Cancellation Details
|  |  | 1998-10-01 | 1998-11-01 | 1998-12-02 | 1999-01-02 | 1999-02-02 | 1999-03-05 | 1999-04-05 | 1999-05-06 | 1999-06-06 | 1999-07-07 | 1999-08-07 | 1999-09-07 | 1999-10-08 | 1999-11-08 | 1999-12-09 | 2000-01-09 | 2000-02-09 | 2000-03-11 | 2000-04-11 | 2000-05-12 | 2000-06-12 | 2000-07-13 | 2000-08-13 | 2000-09-13 | 2000-10-14 | 2000-11-14 | 2000-12-15 | 2001-01-15 | 2001-02-15 | 2001-03-18 | 2001-04-18 | 2001-05-19 | 2001-06-19 | 2001-07-20 | 2001-08-20 | 2001-09-20 | 2001-10-21 | 2001-11-21 | 2001-12-22 | 2002-01-22 | 2002-02-22 | 2002-03-25 | 2002-04-25 | 2002-05-26 | 2002-06-26 | 2002-07-27 | 2002-08-27 | 2002-09-27 | 2002-10-28 | 2002-11-28 | 2002-12-29 | CK TTL
1 | 7EA | Northwestern Corp.
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.453% | 9.547% | 0% | 0% | 0% | 0% | 0% | 6% | 9% | 7% | 6% | 9% | 7% | 6% | 4% | 4% | 3% | 2% | 0% | 0% | 0% | 22% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.453% | 10% | 10% | 10% | 10% | 10% | 10% | 16% | 25% | 32% | 38% | 47% | 54% | 60% | 64% | 68% | 71% | 73% | 73% | 73% | 73% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 14% | 16% | 18% | 20% | 22% | 24% | 26% | 28% | 30% | 32% | 34% | 36% | 38% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 19.1325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08667 | 1.9132 | 1.9132 | 1.9132 | 1.9132 | 1.9132 | 1.9132 | 3.0612 | 4.7831 | 6.1224 | 7.2703 | 8.9923 | 10.3316 | 11.4795 | 12.2448 | 13.0101 | 13.5841 | 13.9667 | 13.9667 | 13.9667 | 13.9667 | 18.1759 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.2959 | 2.6785 | 3.0612 | 3.4438 | 3.8265 | 4.2092 | 4.5918 | 4.9745 | 5.3571 | 5.7397 | 6.1224 | 6.505 | 6.8877 | 7.2703 | 7.653 | 7.653 | 7.653 | 7.653 | 7.653 | 7.653 | 7.653 | 7.653 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325
2 | 7EA | Northwestern Corp.
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 7.5% | 7.5% | 8% | 8% | 8% | 8% | 8% | 8% | 22% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 17.5% | 25% | 33% | 41% | 49% | 57% | 65% | 73% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13% | 2% | 2% | 3% | 3% | 3% | 3% | 3% | 3% | 2% | 3% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 13% | 15% | 17% | 20% | 23% | 26% | 29% | 32% | 35% | 37% | 40% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 19.1325 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9132 | 1.9132 | 3.3482 | 4.7831 | 6.3137 | 7.8443 | 9.3749 | 10.9055 | 12.4361 | 13.9667 | 18.1759 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.4872 | 2.8699 | 3.2525 | 3.8265 | 4.4005 | 4.9745 | 5.5484 | 6.1224 | 6.6964 | 7.079 | 7.653 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325 | 19.1325
3 | 7FA | Columbia / Longview
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 8% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 20% | 5% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 13% | 16% | 19% | 22% | 25% | 28% | 31% | 34% | 37% | 40% | 43% | 47% | 51% | 55% | 59% | 63% | 67% | 71% | 75% | 95% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 0% | 0% | 0% | 0% | 0% | 60% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 12% | 14% | 16% | 18% | 20% | 22% | 24% | 26% | 28% | 30% | 32% | 34% | 36% | 38% | 40% | 40% | 40% | 40% | 40% | 40% | 100%
| $ Scheduled Payments | 39.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.96 | 5.096 | 6.272 | 7.448 | 8.624 | 9.8 | 10.976 | 12.152 | 13.328 | 14.504 | 15.68 | 16.856 | 18.424 | 19.992 | 21.56 | 23.128 | 24.696 | 26.264 | 27.832 | 29.4 | 37.24 | 39.2 | 39.2
| $ Cancellation | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.92 | 3.92 | 4.704 | 5.488 | 6.272 | 7.056 | 7.84 | 8.624 | 9.408 | 10.192 | 10.976 | 11.76 | 12.544 | 13.328 | 14.112 | 14.896 | 15.68 | 15.68 | 15.68 | 15.68 | 15.68 | 15.68 | 39.2
4 | MHI 501F Simple Cycle | Fort Pierce
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 10% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 20% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 25% | 25% | 25% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 60% | 60% | 60% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 43.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5427 | 10.9045 | 10.9045 | 10.9045 | 17.4472 | 17.4472 | 17.4472 | 17.4472 | 17.4472 | 17.4472 | 17.4472 | 26.1708 | 26.1708 | 26.1708 | 34.8944 | 34.8944 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618
| $ Cancellation | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618
5 | MHI 501F Simple Cycle | Eletrobolt II
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 20% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 25% | 25% | 25% | 25% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 60% | 60% | 60% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 36.854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6854 | 3.6854 | 3.6854 | 3.6854 | 3.6854 | 3.6854 | 9.2135 | 9.2135 | 9.2135 | 9.2135 | 14.7416 | 14.7416 | 14.7416 | 14.7416 | 14.7416 | 14.7416 | 14.7416 | 22.1124 | 22.1124 | 22.1124 | 29.4832 | 29.4832 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854
| $ Cancellation | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854
6 | MHI 501F Simple Cycle | Eletrobolt II
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 20% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 25% | 25% | 25% | 25% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 60% | 60% | 60% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 36.854 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.6854 | 3.6854 | 3.6854 | 3.6854 | 3.6854 | 3.6854 | 3.6854 | 9.2135 | 9.2135 | 9.2135 | 9.2135 | 14.7416 | 14.7416 | 14.7416 | 14.7416 | 14.7416 | 14.7416 | 14.7416 | 22.1124 | 22.1124 | 22.1124 | 29.4832 | 29.4832 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854
| $ Cancellation | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854 | 36.854
7 | MHI 501F Simple Cycle | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 10% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 20% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 25% | 25% | 25% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 60% | 60% | 60% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 43.618 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5427 | 10.9045 | 10.9045 | 10.9045 | 17.4472 | 17.4472 | 17.4472 | 17.4472 | 17.4472 | 17.4472 | 17.4472 | 26.1708 | 26.1708 | 26.1708 | 34.8944 | 34.8944 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618 | 43.618
8 | 501D5A Simple Cycle | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 15% | 10% | 10% | 10% | 7.5% | 7.5% | 5% | 5% | 5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 0% | 5% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 15% | 25% | 35% | 45% | 52.5% | 60% | 65% | 70% | 75% | 77.5% | 80% | 82.5% | 85% | 87.5% | 90% | 90% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 5% | 0% | 10% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 65% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 5% | 5% | 15% | 15% | 15% | 15% | 15% | 20% | 20% | 20% | 25% | 25% | 25% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 24.506 | 0 | 0 | 0 | 0 | 3.6759 | 6.1265 | 8.5771 | 11.0277 | 12.8657 | 14.7036 | 15.9289 | 17.1542 | 18.3795 | 18.9921 | 19.6048 | 20.2174 | 20.8301 | 21.4428 | 22.0554 | 22.0554 | 23.2807 | 23.2807 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506
| $ Cancellation | Available | 1.2253 | 1.2253 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 4.9012 | 4.9012 | 4.9012 | 6.1265 | 6.1265 | 6.1265 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506
9 | 9FA STAG Power Islands | Arcos
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 23% | 5% | 5% | 5% | 5% | 5% | 4% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 6% | 7% | 6% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 33% | 38% | 43% | 48% | 53% | 58% | 62% | 65% | 68% | 71% | 73% | 75% | 77% | 79% | 85% | 92% | 98% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 1.3% | 1.7% | 1.6% | 2.7% | 4.9% | 5.9% | 5.8% | 5% | 5.3% | 5.4% | 5.3% | 4.1% | 3% | 3.2% | 1.8% | 1.7% | 1.4% | 1.2% | 9.6% | 9.5% | 9.2% | 0.4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 11.3% | 13% | 14.6% | 17.3% | 22.2% | 28.1% | 33.9% | 38.9% | 44.2% | 49.6% | 54.9% | 59% | 62% | 65.2% | 67% | 68.7% | 70.1% | 71.3% | 80.9% | 90.4% | 99.6% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 83.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 8.3417 | 8.3417 | 27.5275 | 31.6983 | 35.8692 | 40.04 | 44.2108 | 48.3817 | 51.7183 | 54.2208 | 56.7233 | 59.2258 | 60.8942 | 62.5625 | 64.2308 | 65.8992 | 70.9042 | 76.7433 | 81.7483 | 82.5825 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 9.4261 | 10.8442 | 12.1788 | 14.4311 | 18.5185 | 23.4401 | 28.2782 | 32.4491 | 36.8702 | 41.3747 | 45.7957 | 49.2158 | 51.7183 | 54.3877 | 55.8892 | 57.3073 | 58.4751 | 59.4761 | 67.4841 | 75.4087 | 83.083 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
10 | 9FA STAG Power Islands | Arcos
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 23% | 5% | 5% | 5% | 5% | 5% | 4% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 6% | 7% | 6% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 33% | 38% | 43% | 48% | 53% | 58% | 62% | 65% | 68% | 71% | 73% | 75% | 77% | 79% | 85% | 92% | 98% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 1.3% | 1.7% | 1.6% | 2.7% | 4.9% | 5.9% | 5.8% | 5% | 5.3% | 5.4% | 5.3% | 4.1% | 3% | 3.2% | 1.8% | 1.7% | 1.4% | 1.2% | 9.6% | 9.5% | 9.2% | 0.4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 11.3% | 13% | 14.6% | 17.3% | 22.2% | 28.1% | 33.9% | 38.9% | 44.2% | 49.6% | 54.9% | 59% | 62% | 65.2% | 67% | 68.7% | 70.1% | 71.3% | 80.9% | 90.4% | 99.6% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 83.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 8.3417 | 8.3417 | 27.5275 | 31.6983 | 35.8692 | 40.04 | 44.2108 | 48.3817 | 51.7183 | 54.2208 | 56.7233 | 59.2258 | 60.8942 | 62.5625 | 64.2308 | 65.8992 | 70.9042 | 76.7433 | 81.7483 | 82.5825 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 9.4261 | 10.8442 | 12.1788 | 14.4311 | 18.5185 | 23.4401 | 28.2782 | 32.4491 | 36.8702 | 41.3747 | 45.7957 | 49.2158 | 51.7183 | 54.3877 | 55.8892 | 57.3073 | 58.4751 | 59.4761 | 67.4841 | 75.4087 | 83.083 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
11 | 9FA STAG Power Islands | Arcos
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 23% | 5% | 5% | 5% | 5% | 5% | 4% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 6% | 7% | 6% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 33% | 38% | 43% | 48% | 53% | 58% | 62% | 65% | 68% | 71% | 73% | 75% | 77% | 79% | 85% | 92% | 98% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 1.3% | 1.7% | 1.6% | 2.7% | 4.9% | 5.9% | 5.8% | 5% | 5.3% | 5.4% | 5.3% | 4.1% | 3% | 3.2% | 1.8% | 1.7% | 1.4% | 1.2% | 9.6% | 9.5% | 9.2% | 0.4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 11.3% | 13% | 14.6% | 17.3% | 22.2% | 28.1% | 33.9% | 38.9% | 44.2% | 49.6% | 54.9% | 59% | 62% | 65.2% | 67% | 68.7% | 70.1% | 71.3% | 80.9% | 90.4% | 99.6% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 83.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 8.3417 | 8.3417 | 27.5275 | 31.6983 | 35.8692 | 40.04 | 44.2108 | 48.3817 | 51.7183 | 54.2208 | 56.7233 | 59.2258 | 60.8942 | 62.5625 | 64.2308 | 65.8992 | 70.9042 | 76.7433 | 81.7483 | 82.5825 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 9.4261 | 10.8442 | 12.1788 | 14.4311 | 18.5185 | 23.4401 | 28.2782 | 32.4491 | 36.8702 | 41.3747 | 45.7957 | 49.2158 | 51.7183 | 54.3877 | 55.8892 | 57.3073 | 58.4751 | 59.4761 | 67.4841 | 75.4087 | 83.083 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
12 | 11N1 | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 17.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25
13 | 11N1 | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 17.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25
14 | Fr 6B 60 hz power barges (BV = 0) | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
15 | Fr 6B 60 hz power barges (BV = 0) | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
16 | Steam Turbine (book value =0) | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | [8 empty] | 0%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
| $ Scheduled Payments | 2.3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTALS:
SUM OF COMMITTED
| $ Scheduled Payments | 38.265 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9999 | 3.8265 | 5.2614 | 6.6964 | 8.227 | 9.7576 | 11.2882 | 13.9667 | 17.2192 | 20.0891 | 25.4462 | 28.1248 | 29.4641 | 30.612 | 31.3773 | 32.1426 | 32.7166 | 33.0992 | 33.0992 | 33.0992 | 33.0992 | 37.3084 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265
| $ Cancellation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.7831 | 5.5484 | 6.3137 | 7.2703 | 8.227 | 9.1836 | 10.1402 | 11.0968 | 12.0535 | 12.8188 | 13.7754 | 25.6376 | 26.0202 | 26.4029 | 26.7855 | 26.7855 | 26.7855 | 26.7855 | 26.7855 | 26.7855 | 26.7855 | 26.7855 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265 | 38.265
SUM OF TENTATIVE
| $ Scheduled Payments | 181.032 | 0 | 0 | 0 | 0 | 3.6759 | 6.1265 | 8.5771 | 11.0277 | 12.8657 | 14.7036 | 15.9289 | 17.1542 | 18.3795 | 18.9921 | 19.6048 | 20.2174 | 27.3728 | 32.3473 | 32.9599 | 32.9599 | 40.7279 | 48.0987 | 49.324 | 49.324 | 49.324 | 49.324 | 49.324 | 63.5757 | 71.0638 | 74.1998 | 84.0994 | 90.8035 | 106.2312 | 107.4072 | 108.5832 | 109.7592 | 110.9352 | 112.1112 | 120.658 | 129.2048 | 130.7728 | 139.7116 | 148.6504 | 157.5892 | 166.528 | 168.096 | 169.664 | 171.232 | 179.072 | 181.032 | 181.032
| $ Cancellation |  | 1.2253 | 1.2253 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 4.9012 | 4.9012 | 4.9012 | 6.1265 | 6.1265 | 6.1265 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 52.1951 | 52.1951 | 52.1951 | 68.124 | 141.832 | 141.832 | 141.832 | 141.832 | 141.832 | 141.832 | 141.832 | 145.752 | 145.752 | 146.536 | 147.32 | 148.104 | 148.888 | 149.672 | 150.456 | 151.24 | 152.024 | 152.808 | 153.592 | 154.376 | 155.16 | 155.944 | 156.728 | 157.512 | 157.512 | 157.512 | 157.512 | 157.512 | 157.512 | 181.032
SUM OF AVAILABLE
| $ Scheduled Payments | 343.668 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 2.3 | 8.8427 | 13.2045 | 13.2045 | 60.7045 | 92.2722 | 92.2722 | 92.2722 | 149.8297 | 162.3422 | 174.8547 | 187.3672 | 208.6033 | 221.1158 | 231.1258 | 247.3569 | 254.8644 | 271.0955 | 276.1005 | 281.1055 | 286.1105 | 291.1155 | 306.1305 | 323.648 | 338.663 | 341.1655 | 343.668 | 343.668 | 343.668 | 343.668 | 343.668 | 343.668 | 343.668 | 343.668 | 343.668 | 343.668
| $ Cancellation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43.618 | 68.643 | 119.3962 | 123.6505 | 127.6545 | 134.4112 | 146.6735 | 161.4383 | 175.9528 | 188.4652 | 201.7285 | 215.242 | 228.5052 | 238.7655 | 246.273 | 254.281 | 258.7855 | 263.0398 | 266.5433 | 269.5462 | 293.5702 | 317.344 | 340.367 | 341.368 | 341.368 | 341.368 | 341.368 | 341.368 | 341.368 | 341.368 | 341.368 | 341.368 | 341.368 | 341.368
GRAND TOTALS:
| $ Scheduled Payments | 562.965 | 0 | 0 | 0 | 0 | 3.6759 | 6.1265 | 8.5771 | 11.0277 | 12.8657 | 14.7036 | 18.2289 | 19.4542 | 20.6795 | 21.2921 | 21.9048 | 22.5175 | 36.2155 | 45.5517 | 46.1644 | 95.6643 | 136.8266 | 145.6323 | 148.2926 | 207.3807 | 221.4238 | 235.4669 | 250.6579 | 289.3983 | 312.2687 | 330.7718 | 359.5811 | 375.132 | 407.9387 | 414.885 | 421.8313 | 428.5863 | 435.1499 | 451.3409 | 477.4052 | 500.967 | 509.2467 | 521.6446 | 530.5834 | 539.5222 | 548.461 | 550.029 | 551.597 | 553.165 | 561.005 | 562.965 | 562.965
| $ Cancellation |  | 1.2253 | 1.2253 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 4.9012 | 4.9012 | 4.9012 | 6.1265 | 6.1265 | 6.1265 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 95.8131 | 120.8381 | 176.3745 | 197.3229 | 275.8002 | 283.5136 | 296.7325 | 312.4538 | 327.925 | 341.3941 | 355.614 | 373.8128 | 388.0326 | 410.9391 | 419.6132 | 428.7878 | 434.459 | 439.4973 | 443.7847 | 447.5718 | 472.3798 | 496.9375 | 520.7445 | 522.5295 | 534.793 | 535.577 | 536.361 | 537.145 | 537.145 | 537.145 | 537.145 | 537.145 | 537.145 | 560.665
| $ Exposure |  | 1.2253 | 1.2253 | 3.6759 | 3.6759 | 0 | -2.4506 | -4.9012 | -6.1265 | -7.9645 | -9.8024 | -12.1024 | -13.3277 | -14.553 | -12.715 | -13.3277 | -13.9404 | -27.6384 | 50.2614 | 74.6737 | 80.7102 | 60.4963 | 130.1679 | 135.221 | 89.3518 | 91.0301 | 92.4581 | 90.7362 | 66.2157 | 61.544 | 57.2608 | 51.358 | 44.4812 | 20.8492 | 19.574 | 17.6659 | 15.1985 | 12.4218 | 21.0388 | 19.5323 | 19.7775 | 13.2828 | 13.1484 | 4.9936 | -3.1612 | -11.316 | -12.884 | -14.452 | -16.02 | -23.86 | -25.82 | -2.3
| check totals per detail above | 562.965 | 0 | 0 | 0 | 0 | 3.6759 | 6.1265 | 8.5771 | 11.0277 | 12.8657 | 14.7036 | 18.2289 | 19.4542 | 20.6795 | 21.2921 | 21.9048 | 22.5175 | 36.2155 | 45.5517 | 46.1644 | 95.6643 | 136.8266 | 145.6323 | 148.2926 | 207.3807 | 221.4238 | 235.4669 | 250.6579 | 289.3983 | 312.2687 | 330.7718 | 359.5811 | 375.132 | 407.9387 | 414.885 | 421.8313 | 428.5863 | 435.1499 | 451.3409 | 477.4052 | 500.967 | 509.2467 | 521.6446 | 530.5834 | 539.5222 | 548.461 | 550.029 | 551.597 | 553.165 | 561.005 | 562.965 | 562.965
|  |  | 1.2253 | 1.2253 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 4.9012 | 4.9012 | 4.9012 | 6.1265 | 6.1265 | 6.1265 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 95.8131 | 120.8381 | 176.3745 | 197.3229 | 275.8002 | 283.5136 | 296.7325 | 312.4538 | 327.925 | 341.3941 | 355.614 | 373.8128 | 388.0326 | 410.9391 | 419.6132 | 428.7878 | 434.459 | 439.4973 | 443.7847 | 447.5718 | 472.3798 | 496.9375 | 520.7445 | 522.5295 | 534.793 | 535.577 | 536.361 | 537.145 | 537.145 | 537.145 | 537.145 | 537.145 | 537.145 | 560.665
|  |  | 1.2253 | 1.2253 | 3.6759 | 3.6759 | 0 | -2.4506 | -4.9012 | -6.1265 | -7.9645 | -9.8024 | -12.1024 | -13.3277 | -14.553 | -12.715 | -13.3277 | -13.9404 | -27.6384 | 50.2614 | 74.6737 | 80.7102 | 60.4963 | 130.1679 | 135.221 | 89.3518 | 91.0301 | 92.4581 | 90.7362 | 66.2157 | 61.544 | 57.2608 | 51.358 | 44.4812 | 20.8491 | 19.574 | 17.6659 | 15.1985 | 12.4218 | 21.0388 | 19.5323 | 19.7775 | 13.2828 | 13.1484 | 4.9936 | -3.1612 | -11.316 | -12.884 | -14.452 | -16.02 | -23.86 | -25.82 | -2.3
| Differences between subtotals and details | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1369e-13 | 0 | 1.7053e-13 | -1.1369e-13 | 1.1369e-13 | 0 | 0 | -2.2737e-13 | -5.6843e-14 | 0 | 1.1369e-13 | 1.1369e-13 | 1.1369e-13 | 1.1369e-13 | 1.1369e-13 | 1.1369e-13 | 1.1369e-13 | 1.1369e-13 | 0

## NTP or Sold
| Line | Status |  | Vendor | Contract / PO # | Serial # | Model | Output @ ISO | Heat Rate (HHV) | New/Used | Delivery Date | Owner | DASH Approval Date | Notice to Proceed Given | Status of Financing | Controlled By | Originator / Developer | Project Manager | Project Name | Contract Cost | Contract Paid to Date (Scheduled) | Cancel-lation Payment | Comments
|  | NTP | 1 | GE | NJ-2-99 |  | 7FA - now simple cycle | 156 | 10456 | New | 2000-08-01 | East Coast Power | 2000-01-10 | N | N/A | ECP |  |  | East Coast Power - Linden 6 (ECP) | 35 | 0 | 1.75 | DASH name ENA Turbine Divestiture to ECP
|  | NTP | 1 | GE | 24-LM6K-2-99 | 309266 | LM6000 | 44 | 9030 | New | 2000-08-01 | West LB | $2.7MM on 4/19/00 | N | N/A | ENA | James Ducote/ Janet Dietrich | Roger Tietz | Sandhill Power / Austin (ENA) | 14 | 2.7965 | 1.3767
|  | NTP | 1 | GE | 24-LM6K-2-99 | 309547 | LM6000 | 44 | 9030 | New | 2000-09-01 | West LB | $2.7MM on 4/19/00 | N | N/A | ENA | James Ducote/ Janet Dietrich | Roger Tietz | Sandhill Power / Austin (ENA) | 14 | 2.7965 | 1.3767
|  | NTP | 1 | GE | 24-LM6K-2-99 | 309575 | LM6000 | 44 | 9030 | New | 2000-09-01 | West LB | $2.7MM on 4/19/00 | N | N/A | ENA | James Ducote/ Janet Dietrich | Roger Tietz | Sandhill Power / Austin (ENA) | 14 | 2.7965 | 1.3767
|  | NTP | 1 | GE | 24-LM6K-2-99 | 309578 | LM6000 | 44 | 9030 | New | 2000-09-01 | West LB | $2.7MM on 4/19/00 | N | N/A | ENA | James Ducote/ Janet Dietrich | Roger Tietz | Sandhill Power / Austin (ENA) | 14 | 2.7965 | 1.3767
|  | NTP | 1 | GE |  |  | Fr 6B 60 hz power barges | 33.4 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 | 8 | Nigerian barge not yet converted to 50hz
|  | NTP | 1 | GE |  |  | Fr 6B 60 hz power barges | 33.4 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 | 8 | Nigerian barge not yet converted to 50hz
|  | NTP | 1 | GE |  |  | Fr 6B 60 hz power barges | 33.4 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 | 8 | Nigerian barge not yet converted to 50hz
|  | NTP | 1 | GE |  |  | Fr 6B 60 hz power barges | 29 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 | 8 | Nigerian barge not yet converted to 50hz
|  | NTP | 1 | GE |  |  | Fr 6B 60 hz power barges | 29 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 | 8 | Nigerian barge not yet converted to 50hz
|  | NTP | 1 | GE |  |  | Fr 6B 60 hz power barges | 29 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 | 8 | Nigerian barge not yet converted to 50hz
|  | NTP | 1 | GE |  |  | Fr 6B 60 hz power barges | 29 | 10151 | Used | Delivered | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 8 | 8 | 8 | Nigerian barge not yet converted to 50hz
|  | NTP | 1 | GE |  |  | Fr 6B 50hz power barges | 31 | 10151 | Used | NTP + 180 to Nigeria | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 7 | 7 | 7
|  | NTP | 1 | GE |  |  | Fr 6B 50hz power barges | 31 | 10151 | Used | NTP + 180 to Nigeria | ENE B/S | 2000-06-20 | N | N/A | APACHI | Sean Long | Gavin Gaul | Nigeria Barge II (APACHI) | 7 | 7 | 7
|  | Sold | 2 | GE | GP-2-00 |  | 7FA w/ STG | 500 | 10456 | New | 2001-09-01 | West LB | 2000-08-01 | N | N/A | EECC | Jude Rolfes |  | Gen Power - Dell, Arkansas location; duct fired (EECC) - 49% | 45.6765 | 18.8145 | 15.746 | EE&CC to accept limited NTP by September 2000 - trying to obtain financing currently; 2 on 1 configuration
|  | Sold | 2 | GE | GP-2-00 |  | 7FA w/ STG | 500 | 10456 | New | 2001-10-01 | West LB | 2000-08-01 | N | N/A | EECC | Jude Rolfes |  | Gen Power - Dell, Arkansas location; duct fired (EECC) - 49% | 45.6765 | 17.9774 | 15.746 | EE&CC to accept limited NTP by September 2000 - trying to obtain financing currently; 2 on 1 configuration
|  | Sold | 2 | GE | GP-2-00 |  | 7FA w/ STG | 500 | 10456 | New | 2001-07-01 | West LB | 2000-08-01 | N | N/A | EECC | Jude Rolfes |  | Gen Power - McAdams, Mississippi location; duct fired (EECC) - 49% | 45.4265 | 19.5888 | 14.9051 | turbines "on hold" until 10/31/00 - trying to obtain financing currently; 2 on 1 configuration
|  | Sold | 2 | GE | GP-2-00 |  | 7FA w/ STG | 500 | 10456 | New | 2001-08-01 | West LB | 2000-08-01 | N | N/A | EECC | Jude Rolfes |  | Gen Power - McAdams, Mississippi location; duct fired (EECC) - 49% | 45.4265 | 18.8963 | 14.9051 | turbines "on hold" until 10/31/00 - trying to obtain financing currently; 2 on 1 configuration
| 16 | Available | 2 | GE | 24-LM6K-2-99 | 309604 | LM6000 | 44 | 9030 | New | 2000-11-01 | West LB | Analyzing | N | N/A | ENA |  |  | Unassigned | 14.2 | 5.6774 | 2.3114 | (formerly Tri-Valley)
| 17 | Available | 2 | GE | 24-LM6K-2-99 | 309719 | LM6000 | 44 | 9030 | New | 2000-11-01 | West LB | Analyzing | N | N/A | ENA |  |  | Unassigned | 14.2 | 5.6774 | 2.3114 | (formerly LODI)
| 4 | Committed | 1 | GE | VITRO-2-99 |  | 7FA | 171 | 10456 | New | 2000-10-01 | ENE B/S | 2000-10-02 | N | Term Sheet | ENA | Max Yazguirre | Manuel Cavazos | Vitro (ENA) | 31.2466 | 31.2466 | 31.2466 | turbine in storage
| 4 | Committed | 1 | GE | 24-LM6K-2-99 | 309420 | LM6000 | 44 | 9030 | New | 2000-09-01 | West LB | $177.5MM on 11/27/00 | N | OPEN | ENA | Thomas | Edward Dannhaus | Fountain Valley PSCO (ENA) - 90% | 14.5 | 5.7974 | 2.3603 | BOD voting on approval 12/12/00
| 5 | Committed | 1 | GE | 24-LM6K-2-99 | 309505 | LM6000 | 44 | 9030 | New | 2000-09-01 | West LB | $177.5MM on 11/27/00 | N | OPEN | ENA | Thomas | Edward Dannhaus | Fountain Valley PSCO (ENA) - 90% | 14.5 | 5.7974 | 2.3603 | BOD voting on approval 12/12/00
| 6 | Committed | 1 | GE | 24-LM6K-2-99 | 309573 | LM6000 | 44 | 9030 | New | 2000-10-01 | West LB | $177.5MM on 11/27/00 | N | OPEN | ENA | Thomas | Edward Dannhaus | Fountain Valley PSCO (ENA) - 90% | 14.5 | 5.7974 | 2.3603 | BOD voting on approval 12/12/00
| 7 | Committed | 1 | GE | 24-LM6K-2-99 | 309601 | LM6000 | 44 | 9030 | New | 2000-11-01 | West LB | $177.5MM on 11/27/00 | N | OPEN | ENA | Thomas | Edward Dannhaus | Fountain Valley PSCO (ENA) - 90% | 14.5 | 5.7974 | 2.3603 | BOD voting on approval 12/12/00
| 8 | Committed | 2 | GE | 24-LM6K-2-99 | 309101 | LM6000 | 44 | 9030 | New | 2000-06-01 | West LB | $177.5MM on 11/27/00 | N | OPEN | ENA | Thomas | Edward Dannhaus | Fountain Valley PSCO (ENA) - 90% | 14.8 | 5.9173 | 2.4091 | BOD voting on approval 12/12/00
| 9 | Committed | 2 | GE | 24-LM6K-2-99 | 309123 | LM6000 | 44 | 9030 | New | 2000-06-01 | West LB | $177.5MM on 11/27/00 | N | OPEN | ENA | Thomas | Edward Dannhaus | Fountain Valley PSCO (ENA) - 90% | 14.8 | 5.9173 | 2.4091 | BOD voting on approval 12/12/00
13 | Tentative | 4 | GE |  |  | 7FA | 171 | 10456 | New |  |  | partial 7/17/00 | N | N/A | ENA |  |  | Pastoria (ENA) | 0 | 0 | 0 | payment due November 2001
4 | Committed | 1 | GE | 24-LM6K-2-99 | 308898 | LM6000 | 44 | 9030 | New | 2000-06-20 | West LB | 2000-12-19 | N | N/A | ESA | Brett Wiggs | Bill Sullivan | Elektrobolt (ESA) - 85% | 14.2 | 7.0979 | 2.769 | being re-DASHed | Contract to be signed within the next 5 business days as of 1/25/01.
5 | Committed | 1 | GE | 24-LM6K-2-99 | 308951 | LM6000 | 44 | 9030 | New | 2000-07-01 | West LB | 2000-12-19 | N | N/A | ESA | Brett Wiggs | Bill Sullivan | Elektrobolt (ESA) - 85% | 14.2 | 7.0979 | 2.769 | being re-DASHed | Contract to be signed within the next 5 business days as of 1/25/01.
6 | Committed | 1 | GE | 24-LM6K-2-99 | 308972 | LM6000 | 44 | 9030 | New | 2000-08-01 | West LB | 2000-12-19 | N | N/A | ESA | Brett Wiggs | Bill Sullivan | Elektrobolt (ESA) - 85% | 14.2 | 7.0979 | 2.769 | being re-DASHed | Contract to be signed within the next 5 business days as of 1/25/01.
7 | Committed | 1 | GE | 24-LM6K-2-99 | 308999 | LM6000 | 44 | 9030 | New | 2000-07-01 | West LB | 2000-12-19 | N | N/A | ESA | Brett Wiggs | Bill Sullivan | Elektrobolt (ESA) - 85% | 14.2 | 7.0979 | 2.769 | being re-DASHed | Contract to be signed within the next 5 business days as of 1/25/01.
8 | Committed | 1 | GE | 24-LM6K-2-99 | 309020 | LM6000 | 44 | 9030 | New | 2000-07-01 | West LB | 2000-12-19 | N | N/A | ESA | Brett Wiggs | Bill Sullivan | Elektrobolt (ESA) - 85% | 14.2 | 7.0979 | 2.769 | being re-DASHed | Contract to be signed within the next 5 business days as of 1/25/01.
9 | Committed | 1 | GE | 24-LM6K-2-99 | 309073 | LM6000 | 44 | 9030 | New | 2000-07-01 | West LB | 2000-12-19 | N | N/A | ESA | Brett Wiggs | Bill Sullivan | Elektrobolt (ESA) - 85% | 14.2 | 7.0979 | 2.769 | being re-DASHed | Contract to be signed within the next 5 business days as of 1/25/01.
10 | Committed | 1 | GE | 24-LM6K-2-99 | NSN | LM6000 | 44 | 9030 | New | 2000-01-01 | West LB | 2000-12-19 | N | N/A | ESA | Brett Wiggs | Bill Sullivan | Elektrobolt (ESA) - 85% | 14.2 | 7.0979 | 2.769 | being re-DASHed | Contract to be signed within the next 5 business days as of 1/25/01.
11 | Committed | 1 | GE | 24-LM6K-2-99 | NSN | LM6000 | 44 | 9030 | New | 2000-01-01 | West LB | 2000-12-19 | N | N/A | ESA | Brett Wiggs | Bill Sullivan | Elektrobolt (ESA) - 85% | 14.2 | 7.0979 | 2.769 | being re-DASHed | Contract to be signed within the next 5 business days as of 1/25/01.
1 | Committed | 1 | GE |  |  | 7FA | 171 | 10456 | New | 2002-07-01 | E-Next Generation | $70MM on 7/17/00 | N | N/A | EA | David Parquet | Mike Obert | Pastoria | 64.706 | 8.4118 | 8.4118 | First payment due in November 2000; 2 on 1 configuration
2 | Committed | 1 | GE |  |  | 7FA | 171 | 10456 | New | 2002-07-01 | E-Next Generation | $70 MM on 7/17/00 | N | N/A | EA | David Parquet | Mike Obert | Pastoria | 64.706 | 8.4118 | 8.4118 | First payment due in November 2000; 2 on 1 configuration
3 | Committed | 1 | GE |  |  | 7FA | 171 | 10456 | New | 2002-07-01 | E-Next Generation | $70MM on 7/17/00 | N | N/A | EA | David Parquet | Mike Obert | Pastoria | 68.587 | 8.9163 | 8.9163 | First payment due in November 2000
4 | Committed |  | GE |  |  | 7FA |  |  |  |  | E-Next Generation | Approved | N | N/A | EA |  |  | Pastoria Expansion | 66 | 0 | 2.5
12 | Tentative | 2 | GE | 297 760 turbine 337x815 gen |  | 7FA - now simple cycle | 171 | 10456 | New | 2001-09-01 | ENE B/S | Approved | N | N/A | EWS | Dick Westfahl |  | NEPCO / NESCO - Goldendale (EECC) | 36.2474 | 35.613 | 35.7036 |  | Contract in the works, possible buyer
1 | Committed | 1 | GE |  |  | LM6000 |  |  | New | 2002-12-01 |  | $200MM DASHed on 4/19/01 | N | N/A | EA | Maurice Gilbert |  | Las Vegas CoGen II | 15.7697 | 5.5194 | 4.7309
2 | Committed | 1 | GE |  |  | LM6000 |  |  | New | 2002-01-01 |  | $200MM DASHed on 4/19/01 | N | N/A | EA | Maurice Gilbert |  | Las Vegas CoGen II | 15.7697 | 5.5194 | 4.7309
3 | Committed | 1 | GE |  |  | LM6000 |  |  | New | 2002-01-01 |  | $200MM DASHed on 4/19/01 | N | N/A | EA | Maurice Gilbert |  | Las Vegas CoGen II | 15.7697 | 5.5194 | 4.7309
4 | Committed | 1 | GE |  |  | LM6000 |  |  | New | 2002-01-01 |  | $200MM DASHed on 4/19/01 | N | N/A | EA | Maurice Gilbert |  | Las Vegas CoGen II | 15.7697 | 5.5194 | 4.7309
|  |  | 1998-10-01 | 1998-11-01 | 1998-12-02 | 1999-01-02 | 1999-02-02 | 1999-03-05 | 1999-04-05 | 1999-05-06 | 1999-06-06 | 1999-07-07 | 1999-08-07 | 1999-09-07 | 1999-10-08 | 1999-11-08 | 1999-12-09 | 2000-01-09 | 2000-02-09 | 2000-03-11 | 2000-04-11 | 2000-05-12 | 2000-06-12 | 2000-07-13 | 2000-08-13 | 2000-09-13 | 2000-10-14 | 2000-11-14 | 2000-12-15 | 2001-01-15 | 2001-02-15 | 2001-03-18 | 2001-04-18 | 2001-05-19 | 2001-06-19 | 2001-07-20 | 2001-08-20 | 2001-09-20 | 2001-10-21 | 2001-11-21 | 2001-12-22 | 2002-01-22 | 2002-02-22 | 2002-03-25 | 2002-04-25 | 2002-05-26 | 2002-06-26 | 2002-07-27 | 2002-08-27 | 2002-09-27 | 2002-10-28 | 2002-11-28 | 2002-12-29 | CK TTL
| 7FA - now simple cycle | East Coast Power - Linden 6 (ECP)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 1% | 1% | 1% | 1% | 1% | 1% | 4% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 10% | 15% | 5% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 10% | 11% | 12% | 13% | 14% | 15% | 16% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 80% | 95% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 1% | 1% | 1% | 1% | 1% | 1% | 1.9% | 2.9% | 3.4% | 6.1% | 6.2% | 4.8% | 6.1% | 5.7% | 2.5% | 2.9% | 3.9% | 2% | 2.4% | 33.2% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 10% | 11% | 12% | 13% | 14% | 15% | 16% | 17.9% | 20.8% | 24.2% | 30.3% | 36.5% | 41.3% | 47.4% | 53.1% | 55.6% | 58.5% | 62.4% | 64.4% | 66.8% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 3.5 | 3.85 | 4.2 | 4.55 | 4.9 | 5.25 | 5.6 | 7 | 8.75 | 10.5 | 12.25 | 14 | 15.75 | 17.5 | 19.25 | 21 | 22.75 | 24.5 | 28 | 33.25 | 35 | 35 | 35 | 35 | 35
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 1.75 | 3.5 | 3.85 | 4.2 | 4.55 | 4.9 | 5.25 | 5.6 | 6.265 | 7.28 | 8.47 | 10.605 | 12.775 | 14.455 | 16.59 | 18.585 | 19.46 | 20.475 | 21.84 | 22.54 | 23.38 | 35 | 35 | 35 | 35 | 35
| LM6000 | Sandhill Power / Austin (ENA)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 1.3961 | 2.0963 | 2.7965 | 3.4968 | 4.197 | 4.8972 | 5.5975 | 6.2977 | 6.9979 | 7.6982 | 8.3984 | 9.0986 | 9.7989 | 10.4991 | 11.1993 | 11.8996 | 12.5998 | 13.3 | 13.3 | 13.3 | 13.3 | 13.3 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.92556 | 1.1511 | 1.3767 | 1.6022 | 1.8278 | 2.0533 | 2.2789 | 2.5044 | 2.73 | 2.9556 | 3.1811 | 3.4067 | 3.6322 | 3.8578 | 4.0833 | 4.3089 | 4.5344 | 4.76 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
| LM6000 | Sandhill Power / Austin (ENA)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 1.3961 | 2.0963 | 2.7965 | 3.4968 | 4.197 | 4.8972 | 5.5975 | 6.2977 | 6.9979 | 7.6982 | 8.3984 | 9.0986 | 9.7989 | 10.4991 | 11.1993 | 11.8996 | 12.5998 | 13.3 | 13.3 | 13.3 | 13.3 | 13.3 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.92556 | 1.1511 | 1.3767 | 1.6022 | 1.8278 | 2.0533 | 2.2789 | 2.5044 | 2.73 | 2.9556 | 3.1811 | 3.4067 | 3.6322 | 3.8578 | 4.0833 | 4.3089 | 4.5344 | 4.76 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
| LM6000 | Sandhill Power / Austin (ENA)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 1.3961 | 2.0963 | 2.7965 | 3.4968 | 4.197 | 4.8972 | 5.5975 | 6.2977 | 6.9979 | 7.6982 | 8.3984 | 9.0986 | 9.7989 | 10.4991 | 11.1993 | 11.8996 | 12.5998 | 13.3 | 13.3 | 13.3 | 13.3 | 13.3 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.92556 | 1.1511 | 1.3767 | 1.6022 | 1.8278 | 2.0533 | 2.2789 | 2.5044 | 2.73 | 2.9556 | 3.1811 | 3.4067 | 3.6322 | 3.8578 | 4.0833 | 4.3089 | 4.5344 | 4.76 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
| LM6000 | Sandhill Power / Austin (ENA)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 0.69583 | 1.3961 | 2.0963 | 2.7965 | 3.4968 | 4.197 | 4.8972 | 5.5975 | 6.2977 | 6.9979 | 7.6982 | 8.3984 | 9.0986 | 9.7989 | 10.4991 | 11.1993 | 11.8996 | 12.5998 | 13.3 | 13.3 | 13.3 | 13.3 | 13.3 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.7 | 0.92556 | 1.1511 | 1.3767 | 1.6022 | 1.8278 | 2.0533 | 2.2789 | 2.5044 | 2.73 | 2.9556 | 3.1811 | 3.4067 | 3.6322 | 3.8578 | 4.0833 | 4.3089 | 4.5344 | 4.76 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14 | 14
| Fr 6B 60 hz power barges | Nigeria Barge II (APACHI)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Fr 6B 60 hz power barges | Nigeria Barge II (APACHI)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Fr 6B 60 hz power barges | Nigeria Barge II (APACHI)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| 7FA | Vitro (ENA)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 77.67% | 0% | 11.16% | 11.16% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 77.67% | 77.67% | 88.84% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.2% | 1.8% | 1.5% | 2% | 2.5% | 3% | 0% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 23.2% | 25% | 26.5% | 28.5% | 31% | 34% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 31.2466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.2705 | 24.2705 | 27.7586 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2492 | 7.8117 | 8.2804 | 8.9053 | 9.6865 | 10.6238 | 10.6238 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466 | 31.2466
| Fr 6B 60 hz power barges | Nigeria Barge II (APACHI)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Fr 6B 60 hz power barges | Nigeria Barge II (APACHI)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Fr 6B 60 hz power barges | Nigeria Barge II (APACHI)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Fr 6B 60 hz power barges | Nigeria Barge II (APACHI)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| Fr 6B 50hz power barges | Nigeria Barge II (APACHI)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| $ Cancellation | NTP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| Fr 6B 50hz power barges | Nigeria Barge II (APACHI)
| % Progress Payments |  | 5.3% | 1% | 1% | 1% | 1% | 1% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 16.2% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 5.3% | 6.3% | 7.3% | 8.3% | 9.3% | 10.3% | 14.2% | 18.1% | 22% | 25.9% | 29.8% | 33.7% | 37.6% | 41.5% | 45.4% | 49.3% | 53.2% | 57.1% | 61% | 64.9% | 68.8% | 85% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 4.3% | 1% | 1% | 1% | 1% | 1% | 1% | 1% | 0.9% | 1.3% | 1.6% | 1.6% | 1.5% | 1.5% | 1.1% | 0.9% | 1.3% | 1.6% | 1.4% | 1.6% | 2.5% | 2.7% | 67.2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 4.3% | 5.3% | 6.3% | 7.3% | 8.3% | 9.3% | 10.3% | 11.3% | 12.2% | 13.5% | 15.1% | 16.7% | 18.2% | 19.7% | 20.8% | 21.7% | 23% | 24.6% | 26% | 27.6% | 30.1% | 32.8% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 7 | 0.371 | 0.441 | 0.511 | 0.581 | 0.651 | 0.721 | 0.994 | 1.267 | 1.54 | 1.813 | 2.086 | 2.359 | 2.632 | 2.905 | 3.178 | 3.451 | 3.724 | 3.997 | 4.27 | 4.543 | 4.816 | 5.95 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| $ Cancellation | NTP | 0.301 | 0.371 | 0.441 | 0.511 | 0.581 | 0.651 | 0.721 | 0.791 | 0.854 | 0.945 | 1.057 | 1.169 | 1.274 | 1.379 | 1.456 | 1.519 | 1.61 | 1.722 | 1.82 | 1.932 | 2.107 | 2.296 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
| 7FA w/ STG | Gen Power - Dell, Arkansas location; duct fired (EECC) - 49%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 7.2% | 3.8% | 19.9% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3.1% | 4% | 4% | 20% | 4% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 12.2% | 16% | 35.9% | 38.9% | 41.9% | 44.9% | 47.9% | 50.9% | 53.9% | 56.9% | 59.9% | 63% | 67% | 71% | 91% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.1% | 3.7% | 5.2% | 10% | 2% | 2% | 2% | 2% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.1% | 14.8% | 20% | 30% | 32% | 34% | 36% | 38% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 34.8777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7439 | 4.2551 | 5.5804 | 12.5211 | 13.5674 | 14.6138 | 15.6601 | 16.7064 | 17.7528 | 18.7991 | 19.8454 | 20.8918 | 21.973 | 23.3681 | 24.7632 | 31.7387 | 33.1339 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777
| $ Cancellation | Sold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8714 | 5.1619 | 6.9755 | 10.4633 | 11.1609 | 11.8584 | 12.556 | 13.2535 | 13.9511 | 13.9511 | 13.9511 | 13.9511 | 13.9511 | 13.9511 | 13.9511 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777
| 7FA w/ STG | Gen Power - Dell, Arkansas location; duct fired (EECC) - 49%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 7% | 3.5% | 19% | 2.5% | 2.5% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3.5% | 4% | 20% | 4% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 12% | 15.5% | 34.5% | 37% | 39.5% | 42.5% | 45.5% | 48.5% | 51.5% | 54.5% | 57.5% | 60.5% | 63.5% | 67% | 71% | 91% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.1% | 3.7% | 5.2% | 10% | 2% | 2% | 2% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.1% | 14.8% | 20% | 30% | 32% | 34% | 36% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 34.8777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7439 | 4.1853 | 5.406 | 12.0328 | 12.9048 | 13.7767 | 14.823 | 15.8694 | 16.9157 | 17.962 | 19.0084 | 20.0547 | 21.101 | 22.1474 | 23.3681 | 24.7632 | 31.7387 | 33.1339 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777
| $ Cancellation | Sold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8714 | 5.1619 | 6.9755 | 10.4633 | 11.1609 | 11.8584 | 12.556 | 13.9511 | 13.9511 | 13.9511 | 13.9511 | 13.9511 | 13.9511 | 13.9511 | 13.9511 | 13.9511 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777 | 34.8777
| Steam Turbine Generator for above 2 | Gen Power - Dell, Arkansas location; duct fired (EECC) - 49%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 6.68% | 3.34% | 18.32% | 2.56% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3.1% | 3.5% | 3.5% | 25% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 11.68% | 15.02% | 33.34% | 35.9% | 38.9% | 41.9% | 44.9% | 47.9% | 50.9% | 53.9% | 56.9% | 59.9% | 63% | 66.5% | 70% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 14.5% | 9.5% | 7% | 4% | 11% | 8% | 11% | 10% | 3% | 4% | 6% | 2% | 3% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 19.5% | 29% | 36% | 40% | 51% | 59% | 70% | 80% | 83% | 87% | 93% | 95% | 98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 21.5975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0799 | 2.5226 | 3.2439 | 7.2006 | 7.7535 | 8.4014 | 9.0494 | 9.6973 | 10.3452 | 10.9931 | 11.6411 | 12.289 | 12.9369 | 13.6064 | 14.3624 | 15.1183 | 20.5176 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975
| $ Cancellation | Sold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0799 | 1.0799 | 1.0799 | 4.2115 | 6.2633 | 7.7751 | 8.639 | 11.0147 | 12.7425 | 15.1183 | 17.278 | 17.9259 | 18.7898 | 20.0857 | 20.5176 | 21.1656 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975
| 7FA w/ STG | Gen Power - McAdams, Mississippi location; duct fired (EECC) - 49%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 7.2% | 3.8% | 19.9% | 3.8% | 3.8% | 3.9% | 3.9% | 3.9% | 3.9% | 3.9% | 4% | 4% | 4% | 20% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 12.2% | 16% | 35.9% | 39.7% | 43.5% | 47.4% | 51.3% | 55.2% | 59.1% | 63% | 67% | 71% | 75% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.1% | 3.7% | 5.2% | 10% | 2% | 2% | 2% | 2% | 2% | 0% | 0% | 0% | 0% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.1% | 14.8% | 20% | 30% | 32% | 34% | 36% | 38% | 40% | 40% | 40% | 40% | 40% | 40% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 34.6277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7314 | 4.2246 | 5.5404 | 12.4314 | 13.7472 | 15.0631 | 16.4135 | 17.764 | 19.1145 | 20.465 | 21.8155 | 23.2006 | 24.5857 | 25.9708 | 32.8964 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277
| $ Cancellation | Sold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8437 | 5.1249 | 6.9255 | 10.3883 | 11.0809 | 11.7734 | 12.466 | 13.1585 | 13.8511 | 13.8511 | 13.8511 | 13.8511 | 13.8511 | 13.8511 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277
| 7FA w/ STG | Gen Power - McAdams, Mississippi location; duct fired (EECC) - 49%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 7% | 3.5% | 19% | 3.5% | 3.5% | 3.5% | 3.6% | 3.6% | 3.7% | 3.7% | 3.7% | 3.7% | 4% | 4% | 20% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 12% | 15.5% | 34.5% | 38% | 41.5% | 45% | 48.6% | 52.2% | 55.9% | 59.6% | 63.3% | 67% | 71% | 75% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.1% | 3.7% | 5.2% | 10% | 2% | 2% | 2% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.1% | 14.8% | 20% | 30% | 32% | 34% | 36% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 34.6277 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7314 | 4.1553 | 5.3673 | 11.9466 | 13.1585 | 14.3705 | 15.5825 | 16.8291 | 18.0757 | 19.3569 | 20.6381 | 21.9194 | 23.2006 | 24.5857 | 25.9708 | 32.8964 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277
| $ Cancellation | Sold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.8437 | 5.1249 | 6.9255 | 10.3883 | 11.0809 | 11.7734 | 12.466 | 13.8511 | 13.8511 | 13.8511 | 13.8511 | 13.8511 | 13.8511 | 13.8511 | 13.8511 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277 | 34.6277
| Steam Turbine Generator for above 2 | Gen Power - McAdams, Mississippi location; duct fired (EECC) - 49%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 7% | 3.58% | 19.2% | 3.55% | 3.58% | 3.62% | 3.66% | 3.66% | 3.7% | 3.7% | 3.74% | 3.74% | 3.85% | 10.07% | 15.29% | 3.06% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 12% | 15.58% | 34.78% | 38.33% | 41.91% | 45.53% | 49.19% | 52.85% | 56.55% | 60.25% | 63.99% | 67.73% | 71.58% | 81.65% | 96.94% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 14.5% | 5.5% | 4% | 11% | 11% | 8% | 5% | 12% | 7% | 3% | 7% | 5% | 2% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 19.5% | 25% | 29% | 40% | 51% | 59% | 64% | 76% | 83% | 86% | 93% | 98% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 21.5975 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0799 | 2.5917 | 3.3649 | 7.5116 | 8.2783 | 9.0515 | 9.8334 | 10.6238 | 11.4143 | 12.2134 | 13.0125 | 13.8203 | 14.628 | 15.4595 | 17.6344 | 20.9366 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975
| $ Cancellation | Sold | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0799 | 1.0799 | 1.0799 | 4.2115 | 5.3994 | 6.2633 | 8.639 | 11.0147 | 12.7425 | 13.8224 | 16.4141 | 17.9259 | 18.5739 | 20.0857 | 21.1656 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975 | 21.5975
1&2 | 7FA | Pastoria
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 1% | 1% | 1% | 1% | 1% | 1% | 4% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 10% | 15% | 5% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 10% | 11% | 12% | 13% | 14% | 15% | 16% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 80% | 95% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 1% | 1% | 1% | 1% | 1% | 1% | 1.9% | 2.9% | 3.4% | 6.1% | 6.2% | 4.8% | 6.1% | 5.7% | 2.5% | 2.9% | 3.9% | 2% | 2.4% | 33.2% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 10% | 11% | 12% | 13% | 14% | 15% | 16% | 17.9% | 20.8% | 24.2% | 30.3% | 36.5% | 41.3% | 47.4% | 53.1% | 55.6% | 58.5% | 62.4% | 64.4% | 66.8% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 129.412 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4706 | 12.9412 | 14.2353 | 15.5294 | 16.8236 | 18.1177 | 19.4118 | 20.7059 | 25.8824 | 32.353 | 38.8236 | 45.2942 | 51.7648 | 58.2354 | 64.706 | 71.1766 | 77.6472 | 84.1178 | 90.5884 | 103.5296 | 122.9414 | 129.412 | 129.412 | 129.412 | 129.412 | 129.412
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.4706 | 6.4706 | 6.4706 | 6.4706 | 6.4706 | 6.4706 | 6.4706 | 6.4706 | 6.4706 | 6.4706 | 6.4706 | 6.4706 | 12.9412 | 14.2353 | 15.5294 | 16.8236 | 18.1177 | 19.4118 | 20.7059 | 23.1647 | 26.9177 | 31.3177 | 39.2118 | 47.2354 | 53.4472 | 61.3413 | 68.7178 | 71.9531 | 75.706 | 80.7531 | 83.3413 | 86.4472 | 129.412 | 129.412 | 129.412 | 129.412 | 129.412
3 | 7FA | Pastoria
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 1% | 1% | 1% | 1% | 1% | 1% | 4% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 10% | 15% | 5% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 10% | 11% | 12% | 13% | 14% | 15% | 16% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 80% | 95% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 1% | 1% | 1% | 1% | 1% | 1% | 1.9% | 2.9% | 3.4% | 6.1% | 6.2% | 4.8% | 6.1% | 5.7% | 2.5% | 2.9% | 3.9% | 2% | 2.4% | 33.2% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 10% | 11% | 12% | 13% | 14% | 15% | 16% | 17.9% | 20.8% | 24.2% | 30.3% | 36.5% | 41.3% | 47.4% | 53.1% | 55.6% | 58.5% | 62.4% | 64.4% | 66.8% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 68.587 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4293 | 6.8587 | 7.5446 | 8.2304 | 8.9163 | 9.6022 | 10.2881 | 10.9739 | 13.7174 | 17.1468 | 20.5761 | 24.0054 | 27.4348 | 30.8641 | 34.2935 | 37.7229 | 41.1522 | 44.5816 | 48.0109 | 54.8696 | 65.1577 | 68.587 | 68.587 | 68.587 | 68.587 | 68.587
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4293 | 3.4293 | 3.4293 | 3.4293 | 3.4293 | 3.4293 | 3.4293 | 3.4293 | 3.4293 | 3.4293 | 3.4293 | 3.4293 | 6.8587 | 7.5446 | 8.2304 | 8.9163 | 9.6022 | 10.2881 | 10.9739 | 12.2771 | 14.2661 | 16.5981 | 20.7819 | 25.0343 | 28.3264 | 32.5102 | 36.4197 | 38.1344 | 40.1234 | 42.7983 | 44.17 | 45.8161 | 68.587 | 68.587 | 68.587 | 68.587 | 68.587
4 | 7FA | Pastoria Expansion
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 1% | 1% | 1% | 1% | 1% | 1% | 4% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 10% | 15% | 5% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 10% | 11% | 12% | 13% | 14% | 15% | 16% | 20% | 25% | 30% | 35% | 40% | 45% | 50% | 55% | 60% | 65% | 70% | 80% | 95% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 1% | 1% | 1% | 1% | 1% | 1% | 1.9% | 2.9% | 3.4% | 6.1% | 6.2% | 4.8% | 6.1% | 5.7% | 2.5% | 2.9% | 3.9% | 2% | 2.4% | 33.2% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 10% | 11% | 12% | 13% | 14% | 15% | 16% | 17.9% | 20.8% | 24.2% | 30.3% | 36.5% | 41.3% | 47.4% | 53.1% | 55.6% | 58.5% | 62.4% | 64.4% | 66.8% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 6.6 | 7.26 | 7.92 | 8.58 | 9.24 | 9.9 | 10.56 | 13.2 | 16.5 | 19.8 | 23.1 | 26.4 | 29.7 | 33 | 36.3 | 39.6 | 42.9 | 46.2 | 52.8 | 62.7 | 66 | 66 | 66 | 66 | 66
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 3.3 | 6.6 | 7.26 | 7.92 | 8.58 | 9.24 | 9.9 | 10.56 | 11.814 | 13.728 | 15.972 | 19.998 | 24.09 | 27.258 | 31.284 | 35.046 | 36.696 | 38.61 | 41.184 | 42.504 | 44.088 | 66 | 66 | 66 | 66 | 66
| LM6000 | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| LM6000 | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
4 | LM6000 | Fountain Valley PSCO (ENA) - 90%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 1.4459 | 2.1712 | 2.8964 | 3.6217 | 4.3469 | 5.0721 | 5.7974 | 6.5226 | 7.2479 | 7.9731 | 8.6983 | 9.4236 | 10.1488 | 10.8741 | 11.5993 | 12.3246 | 13.0498 | 13.775 | 13.775 | 13.775 | 13.775 | 13.775 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.95861 | 1.1922 | 1.4258 | 1.6594 | 1.8931 | 2.1267 | 2.3603 | 2.5939 | 2.8275 | 3.0611 | 3.2947 | 3.5283 | 3.7619 | 3.9956 | 4.2292 | 4.4628 | 4.6964 | 4.93 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
5 | LM6000 | Fountain Valley PSCO (ENA) - 90%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 1.4459 | 2.1712 | 2.8964 | 3.6217 | 4.3469 | 5.0721 | 5.7974 | 6.5226 | 7.2479 | 7.9731 | 8.6983 | 9.4236 | 10.1488 | 10.8741 | 11.5993 | 12.3246 | 13.0498 | 13.775 | 13.775 | 13.775 | 13.775 | 13.775 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.95861 | 1.1922 | 1.4258 | 1.6594 | 1.8931 | 2.1267 | 2.3603 | 2.5939 | 2.8275 | 3.0611 | 3.2947 | 3.5283 | 3.7619 | 3.9956 | 4.2292 | 4.4628 | 4.6964 | 4.93 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
6 | LM6000 | Fountain Valley PSCO (ENA) - 90%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 1.4459 | 2.1712 | 2.8964 | 3.6217 | 4.3469 | 5.0721 | 5.7974 | 6.5226 | 7.2479 | 7.9731 | 8.6983 | 9.4236 | 10.1488 | 10.8741 | 11.5993 | 12.3246 | 13.0498 | 13.775 | 13.775 | 13.775 | 13.775 | 13.775 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.95861 | 1.1922 | 1.4258 | 1.6594 | 1.8931 | 2.1267 | 2.3603 | 2.5939 | 2.8275 | 3.0611 | 3.2947 | 3.5283 | 3.7619 | 3.9956 | 4.2292 | 4.4628 | 4.6964 | 4.93 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
7 | LM6000 | Fountain Valley PSCO (ENA) - 90%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 0.72068 | 1.4459 | 2.1712 | 2.8964 | 3.6217 | 4.3469 | 5.0721 | 5.7974 | 6.5226 | 7.2479 | 7.9731 | 8.6983 | 9.4236 | 10.1488 | 10.8741 | 11.5993 | 12.3246 | 13.0498 | 13.775 | 13.775 | 13.775 | 13.775 | 13.775 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.725 | 0.95861 | 1.1922 | 1.4258 | 1.6594 | 1.8931 | 2.1267 | 2.3603 | 2.5939 | 2.8275 | 3.0611 | 3.2947 | 3.5283 | 3.7619 | 3.9956 | 4.2292 | 4.4628 | 4.6964 | 4.93 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5 | 14.5
8 | LM6000 | Fountain Valley PSCO (ENA) - 90%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 1.4758 | 2.2161 | 2.9563 | 3.6966 | 4.4368 | 5.1771 | 5.9173 | 6.6576 | 7.3978 | 8.1381 | 8.8783 | 9.6186 | 10.3588 | 11.099 | 11.8393 | 12.5795 | 13.3198 | 14.06 | 14.06 | 14.06 | 14.06 | 14.06 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.97844 | 1.2169 | 1.4553 | 1.6938 | 1.9322 | 2.1707 | 2.4091 | 2.6476 | 2.886 | 3.1244 | 3.3629 | 3.6013 | 3.8398 | 4.0782 | 4.3167 | 4.5551 | 4.7936 | 5.032 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8
9 | LM6000 | Fountain Valley PSCO (ENA) - 90%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 0.7356 | 1.4758 | 2.2161 | 2.9563 | 3.6966 | 4.4368 | 5.1771 | 5.9173 | 6.6576 | 7.3978 | 8.1381 | 8.8783 | 9.6186 | 10.3588 | 11.099 | 11.8393 | 12.5795 | 13.3198 | 14.06 | 14.06 | 14.06 | 14.06 | 14.06 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.74 | 0.97844 | 1.2169 | 1.4553 | 1.6938 | 1.9322 | 2.1707 | 2.4091 | 2.6476 | 2.886 | 3.1244 | 3.3629 | 3.6013 | 3.8398 | 4.0782 | 4.3167 | 4.5551 | 4.7936 | 5.032 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8 | 14.8
10 | 7FA | Pastoria (ENA)
| % Progress Payments | [52 empty] | 0%
% Cumulative Progress Payments
| % Cancellation | [52 empty] | 0%
% Cumulative Cancellation
| $ Scheduled Payments |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| $ Cancellation | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | LM6000 | Elektrobolt (ESA) - 85%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
5 | LM6000 | Elektrobolt (ESA) - 85%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
6 | LM6000 | Elektrobolt (ESA) - 85%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
7 | LM6000 | Elektrobolt (ESA) - 85%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
8 | LM6000 | Elektrobolt (ESA) - 85%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
9 | LM6000 | Elektrobolt (ESA) - 85%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
10 | LM6000 | Elektrobolt (ESA) - 85%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
11 | LM6000 | Elektrobolt (ESA) - 85%
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
9 | 7FA - now simple cycle | NEPCO / NESCO - Goldendale (EECC)
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.81% | 1.41% | 0% | 0% | 0% | 6.65% | 5.69% | 5.69% | 5.69% | 5.69% | 5.69% | 5.69% | 5.69% | 5.69% | 5.69% | 5.69% | 21.48% | 1.75% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 11.81% | 13.22% | 13.22% | 13.22% | 13.22% | 19.87% | 25.56% | 31.25% | 36.94% | 42.63% | 48.32% | 54.01% | 59.7% | 65.39% | 71.08% | 76.77% | 98.25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | -5% | 10% | 5% | 4% | 0% | 0% | 0% | 0% | 0% | 0% | 64.5% | 1.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 15% | 25% | 30% | 34% | 34% | 34% | 34% | 34% | 34% | 34% | 98.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 36.2474 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4.2808 | 4.7919 | 4.7919 | 4.7919 | 4.7919 | 7.2024 | 9.2648 | 11.3273 | 13.3898 | 15.4522 | 17.5147 | 19.5772 | 21.6397 | 23.7021 | 25.7646 | 27.8271 | 35.613 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474
| $ Cancellation | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.2495 | 5.4371 | 9.0618 | 10.8742 | 12.3241 | 12.3241 | 12.3241 | 12.3241 | 12.3241 | 12.3241 | 12.3241 | 35.7036 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474 | 36.2474
7 | #REF! | #REF!
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
8 | #REF! | #REF!
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
9 | #REF! | #REF!
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
10 | #REF! | #REF!
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 5.002% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 4.97% | 9.972% | 14.97% | 19.98% | 24.98% | 29.98% | 34.98% | 39.98% | 44.98% | 49.99% | 54.99% | 59.99% | 64.99% | 69.99% | 74.99% | 80% | 85% | 90% | 95% | 95% | 95% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 1.611% | 66% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 6.611% | 8.222% | 9.833% | 11.44% | 13.06% | 14.67% | 16.28% | 17.89% | 19.5% | 21.11% | 22.72% | 24.33% | 25.94% | 27.56% | 29.17% | 30.78% | 32.39% | 34% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 14.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 0.70577 | 1.416 | 2.1262 | 2.8365 | 3.5467 | 4.257 | 4.9672 | 5.6774 | 6.3877 | 7.0979 | 7.8081 | 8.5184 | 9.2286 | 9.9389 | 10.6491 | 11.3593 | 12.0696 | 12.7798 | 13.49 | 13.49 | 13.49 | 13.49 | 13.49 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
| $ Cancellation | #REF! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.71 | 0.93878 | 1.1676 | 1.3963 | 1.6251 | 1.8539 | 2.0827 | 2.3114 | 2.5402 | 2.769 | 2.9978 | 3.2266 | 3.4553 | 3.6841 | 3.9129 | 4.1417 | 4.3704 | 4.5992 | 4.828 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2 | 14.2
3 | LM6000 | Las Vegas CoGen II
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 10% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 25% | 35% | 45% | 55% | 65% | 75% | 85% | 85% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 15.7697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3655 | 3.9424 | 5.5194 | 7.0964 | 8.6733 | 10.2503 | 11.8273 | 13.4043 | 13.4043 | 14.9812 | 14.9812 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.577 | 3.1539 | 4.7309 | 6.3079 | 7.8849 | 9.4618 | 11.0388 | 12.6158 | 12.6158 | 14.1928 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697
4 | LM6000 | Las Vegas CoGen II
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 10% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 25% | 35% | 45% | 55% | 65% | 75% | 85% | 85% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 15.7697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3655 | 3.9424 | 5.5194 | 7.0964 | 8.6733 | 10.2503 | 11.8273 | 13.4043 | 13.4043 | 14.9812 | 14.9812 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.577 | 3.1539 | 4.7309 | 6.3079 | 7.8849 | 9.4618 | 11.0388 | 12.6158 | 12.6158 | 14.1928 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697
5 | LM6000 | Las Vegas CoGen II
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 10% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 25% | 35% | 45% | 55% | 65% | 75% | 85% | 85% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 15.7697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3655 | 3.9424 | 5.5194 | 7.0964 | 8.6733 | 10.2503 | 11.8273 | 13.4043 | 13.4043 | 14.9812 | 14.9812 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.577 | 3.1539 | 4.7309 | 6.3079 | 7.8849 | 9.4618 | 11.0388 | 12.6158 | 12.6158 | 14.1928 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697
6 | LM6000 | Las Vegas CoGen II
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 10% | 0% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 25% | 35% | 45% | 55% | 65% | 75% | 85% | 85% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 0% | 10% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 50% | 60% | 70% | 80% | 80% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 15.7697 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.3655 | 3.9424 | 5.5194 | 7.0964 | 8.6733 | 10.2503 | 11.8273 | 13.4043 | 13.4043 | 14.9812 | 14.9812 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697
| $ Cancellation | Committed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.577 | 3.1539 | 4.7309 | 6.3079 | 7.8849 | 9.4618 | 11.0388 | 12.6158 | 12.6158 | 14.1928 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697 | 15.7697
Formulas:
Contract / PO # = +[Vendor]+31
Serial # = +[Contract / PO #]+31
Model = +[Serial #]+31
Output @ ISO = +[Model]+31
Heat Rate (HHV) = +[Output @ ISO]+31
New/Used = +[Heat Rate (HHV)]+31
Delivery Date = +[New/Used]+31
Owner = +[Delivery Date]+31
DASH Approval Date = +[Owner]+31
Notice to Proceed Given = +[DASH Approval Date]+31
Status of Financing = +[Notice to Proceed Given]+31
Controlled By = +[Status of Financing]+31
Originator / Developer = +[Controlled By]+31
Project Manager = +[Originator / Developer]+31
Project Name = +[Project Manager]+31
Contract Cost = +[Project Name]+31
Contract Paid to Date (Scheduled) = +[Contract Cost]+31
Cancel-lation Payment = +[Contract Paid to Date (Scheduled)]+31
Comments = +[Cancel-lation Payment]+31
Note on H4: Stephanie K McGinnis: Cogen Tech machine
Note on H16: Stephanie K McGinnis: left outside and water got into gauges
Note on H17: Stephanie K McGinnis: left outside and water got into gauges
Note on H24: Stephanie K McGinnis: CoGen Tech machine; ABB STG not ordered yet
Note on N3: Stephanie K McGinnis: use last signature date per DASH
Note on O3: Stephanie K McGinnis: When EPC contract is officially turned on