## Detail by Turbine
Turbine Position Report
Detail by Turbine
2001-11-15 | [8 empty] | Financial Data as of | 2001-11-30
Line | Status |  | Vendor | Contract / PO # | Serial # | Model | Output @ ISO | Heat Rate (HHV) | New/Used | Delivery Date | Owner | DASH Approval Date | Notice to Proceed Given | Status of Financing | Controlled By | Originator / Developer | Project Manager | Project Name | Contract Cost | Contract Paid to Date (Scheduled) | Cancel-lation Payment | Comments | Status Update
1 | Tentative | 4 | GE |  |  | 7FA |  |  |  | 2002-12-02 | E-Next Generation | $16.5MM on 2/16/01 | N | N/A | EA | Jake Thomas/Laura Wente |  | Columbia / Longview | 39.2 | 14.504 | 10.192 |  | Favorable indicative bids from prospective buyers of the Longview Project.
2 | Available | 2 | Mitsubishi |  |  | MHI 501F Simple Cycle | 184 | 10256 | New | 2001-09-01 | West LB | Analyzing | N | N/A | EA |  |  | Unassigned | 37.1702 | 29.7361 | 37.1702 | Mitsubishis are in EGAS but are controlled by EA. #2 | All MHI 501s belong to Stan Horton's group (EGS) but are managed by EA.
3 | Available | 3 | Westing- house | Y2K(6)-2-98 |  | 501D5A Simple Cycle | 122 | 10856 | New | Now | ENE B/S | Analyzing | N | N/A | EA | David Fairley, Mathew Gimble |  | Unassigned | 24.506 | 24.5062 | 24.506 |  | Negotiating non-exclusive broker contract with Navigant Consulting.
4 | Available | 1 | GE |  |  | 9FA STAG Power Islands | 375 | 10456 | New | 2001-10-01 | Whitewing | Analyzing | N | N/A | EEL | John Chappell | Stephen Heck | Arcos | 83.4167 | 70.9042 | 67.4841
5 | Available | 1 | GE |  |  | 9FA STAG Power Islands | 375 | 10456 | New | 2001-11-01 | Whitewing | Analyzing | N | N/A | EEL | John Chappell | Stephen Heck | Arcos | 83.4167 | 70.9042 | 67.4841
6 | Available | 1 | GE |  |  | 9FA STAG Power Islands | 375 | 10456 | New | 2001-12-01 | Whitewing | Analyzing | N | N/A | EEL | John Chappell | Stephen Heck | Arcos | 83.4167 | 70.9042 | 67.4841
7 | Available | 3 | ABB |  |  | 11N1 | 83 | 11447 | Used | Now | West LB | Analyzing | N | N/A | EA |  |  | Unassigned | 17.25 | 17.25 | 17.25 | Canada will take a $4.3MM write-down on turbine. | Examining Cuiaba site as alternative use for turbines based on gas producer participation in project with significant equity risk.
8 | Available | 3 | ABB |  |  | 11N1 | 83 | 11447 | Used | Now | West LB | Analyzing | N | N/A | EA |  |  | Unassigned | 17.25 | 17.25 | 17.25 | Canada will take a $4.3MM write-down on turbine. | Examining Cuiaba site as alternative use for turbines based on gas producer participation in project with significant equity risk.
9 | Available | 2 | GE |  |  | Fr 6B 60 hz power barges (BV = 0) | 31 | 10151 | Used | Delivered | ENE B/S | Analyzing | N | N/A | EGM |  |  | Unassigned | 6.5 | 6.5 | 6.5 | Submitted PPA to NY controller; structuring desk issues (formerly LIPA)
10 | Available | 2 | GE |  |  | Fr 6B 60 hz power barges (BV = 0) | 31 | 10151 | Used | Delivered | ENE B/S | Analyzing | N | N/A | EGM |  |  | Unassigned | 6.5 | 6.5 | 6.5 | Submitted PPA to NY controller; structuring desk issues
11 | Available | 2 | Mitsubishi |  |  | MHI 501F Simple Cycle | 184 | 10256 | New | 2001-06-01 | West LB | $2.5MM on 1/31/01 | N | N/A | EA |  |  | Unassigned | 37.1702 | 37.1702 | 37.1702 | Mitsubishis are in EGAS but are controlled by EA. #1 | Investment Memo being prepared & should be issued by week of 8/20. All MHI 501s belong to Stan Horton's group (EGS) but are managed by EA.
12 | Available | 2 | Mitsubishi |  |  | MHI 501F Simple Cycle | 184 | 10256 | New | 2002-05-01 | West LB | Analyzing | N | N/A | EA |  | Jeff Westfahl | Unassigned | 33.8104 | 13.5242 | 33.8104 | Mitsubishis are in EGAS but are controlled by EA. #3 | Negotiations for sale have fallen thru. All MHI 501s belong to Stan Horton's group (EGS) but are managed by EA.
13 | Available | 2 | Mitsubishi |  |  | MHI 501F Simple Cycle | 184 | 10256 | New | 2002-05-01 | West LB | Analyzing | N | N/A | EA |  | Jeff Westfahl | Unassigned | 33.8104 | 13.5242 | 33.8104 | Mitsubishis are in EGAS but are controlled by EA. #4 | Negotiations for sale have fallen thru. All MHI 501s belong to Stan Horton's group (EGS) but are managed by EA.
14 | Available |  | GE |  |  | LM6000 |  |  |  |  | PGE | Analyzing |  |  | PGE |  |  | Unassigned | 0 | 0 | 0
Note on M5: Stephanie K McGinnis: use last signature date per DASH
Note on N5: Stephanie K McGinnis: When EPC contract is officially turned on

## Summary by Status
Turbine Position Report | [8 empty] | CONFIDENTIAL
Summary by Status
2001-11-15
($ MMs)
[8 empty] | Financial Data as of | 2001-11-30
UNITS | MODEL | CONTROLLED BY | PHYSICAL LOCATION | FINANCING VEHICLE | PROJECT(S) | DASH APPROVAL DATE / STATUS | CONTRACT COST | SCHEDULED CONTRACT PYMTS TO DATE | CANCELLATION COST TO DATE | STATUS
COMMITTED - turbines committed to deals which have been DASHed and financing is in process.
0 |  |  |  |  | Total Committed |  | 0 | 0 | 0
TENTATIVE - turbines tentatively committed to ONE deal which has not yet been DASHed, but is likely to be.
1 | 7FA | EA | In Fabrication | E-Next Generation | Columbia / Longview | DASH 11/16/01 | 39.2 | 14.504 | 10.192 | Tentative
1 |  |  |  |  | Total Tentative |  | 39.2 | 14.504 | 10.192
AVAILABLE - turbines which may be potential matches with SEVERAL deals, none of which have been approved to date.
1 | 501D5A simple cycle | EA | Houston Ship Channel | Balance Sheet | Unassigned | Analyzing | 24.506 | 24.5062 | 24.506 | Available
1 | 9FA STAG power islands | EA | Shipboard to Cadiz, Spain | Whitewing | Arcos | Analyzing | 191.3393 | 166.3145 | 159.4742 | Available
2 | 9FA STAG power islands | EEL | In Fabrication | Whitewing | Arcos | Analyzing | 250.25 | 212.7125 | 202.4522 | Available
2 | 11N1 | EA | Calgary | Whitewing | Unassigned | Analyzing | 34.5 | 34.5 | 34.5 | Available
2 | MHI 501F simple cycle (Units 1 & 2) | EA | Shipboard to Freeport, TX | West LB CAA | Unassigned | $2.5MM on 1/31/01 | 37.1702 | 37.1702 | 37.1702 | Available
2 | MHI 501F simple cycle (Units 3 & 4) | EA | In Fabrication | West LB CAA | Unassigned | Analyzing | 104.791 | 56.7845 | 104.791 | Available
2 | Fr 6B 60hz power barges (BV=0) | EGM | East River / NY | Balance Sheet | Unassigned | Analyzing | 13 | 13 | 13 | Available
1 | LM6000 | PGE | S&S / Houston | Balance Sheet / PGE | Unassigned | Analyzing | 0 | 0 | 0 | Available
13 |  |  |  |  | Total Available |  | 655.5565 | 544.9879 | 575.8936
NEGOTIATING - turbines for which the purchase is currently being negotiated, but Enron does not yet have control of these turbines.
0 |  |  |  |  | Total Negotiating |  | 0 | 0 | 0
14 | UNITS - TOTAL |  |  |  | GRAND TOTALS |  | 694.7565 | 559.4919 | 586.0856
SCHEDULED VS CANCELLATION PAYMENTS
($ MMs)
* Total Cancellation Payments = Total Enron Exposure
Cumulative Cancellation Cost to Date $427MM
Incremental Cancellation
Cost $34MM
Cumulative Payments to Date $393MM

## Summary by Type
Turbine Position Report | [7 empty] | CONFIDENTIAL
Summary by Turbine Type
2001-11-15
($ MMs)
[7 empty] | Financial Data as of | 2001-11-30
UNITS | MODEL | CONTROLLED BY | PROJECT(S) | DASH APPROVAL DATE / STATUS | CONTRACT COST | SCHEDULED CONTRACT PYMTS TO DATE | CANCELLATION | STATUS
2 | 11N1 | EA | Unassigned | Analyzing | 34.5 | 34.5 | 34.5 | Available
1 | 501D5A simple cycle | EA | Unassigned | Analyzing | 24.506 | 24.5062 | 24.506 | Available
2 | MHI 501F simple cycle (Units 3 & 4) | EA | Unassigned | Analyzing | 104.791 | 56.7845 | 104.791 | Available
2 | MHI 501F simple cycle (Units 1 & 2) | EA | Unassigned | $2.5MM on 1/31/01 | 37.1702 | 37.1702 | 37.1702 | Available
1 | 7FA | EA | Columbia / Longview | DASH 11/16/01 | 39.2 | 14.504 | 10.192 | Tentative
2 | 9FA STAG power islands | EEL | Arcos | Analyzing | 250.25 | 212.7125 | 202.4522 | Available
2 | Fr 6B 60hz power barges (BV=0) | EGM | Unassigned | Analyzing | 13 | 13 | 13 | Available
1 | LM6000 | PGE | Unassigned | Analyzing | 0 | 0 | 0 | Available
13 |  |  |  | total per above | 503.4172 | 393.1773 | 426.6114
14 |  |  |  | per Summary By Status report | 694.7565 | 559.4919 | 586.0856
-1 |  |  |  | Difference | -191.3393 | -166.3145 | -159.4742

## Summary by Region
Turbine Position Report | [7 empty] | CONFIDENTIAL
Summary by Controlling Region
2001-11-15
($ MMs)
[7 empty] | Financial Data as of | 2001-11-30
UNITS | MODEL | CONTROLLED BY | STATUS | DASH APPROVAL DATE / STATUS | PROJECT(S) | CONTRACT COST | SCHEDULED CONTRACT PYMTS TO DATE | CANCELLATION
EEL
2 | 9FA STAG power islands | EEL | Available | Analyzing | Arcos | 250.25 | 212.7125 | 202.4522
[5 empty] | TOTAL EEL | 250.25 | 212.7125 | 202.4522
EA
1 | 501D5A simple cycle | EA | Available | Analyzing | Unassigned | 24.506 | 24.5062 | 24.506
1 | 7FA | EA | Tentative | DASH 11/16/01 | Columbia / Longview | 39.2 | 14.504 | 10.192
2 | 11N1 | EA | Available | Analyzing | Unassigned | 34.5 | 34.5 | 34.5
2 | MHI 501F simple cycle (Units 3 & 4) | EA | Available | Analyzing | Unassigned | 104.791 | 56.7845 | 104.791
2 | MHI 501F simple cycle (Units 1 & 2) | EA | Available | $2.5MM on 1/31/01 | Unassigned | 37.1702 | 37.1702 | 37.1702
[5 empty] | TOTAL EA | 240.1672 | 167.4648 | 211.1592
EGM
2 | Fr 6B 60hz power barges (BV=0) | EGM | Available | Analyzing | Unassigned | 13 | 13 | 13
PGE
1 | LM6000 | PGE | Available | Analyzing | Unassigned | 0 | 0 | 0
13 | UNITS - TOTAL |  |  |  | GRAND TOTALS | 503.4172 | 393.1773 | 426.6114
[5 empty] | per Summary By Status report | 694.7565 | 559.4919 | 586.0856
[5 empty] | Difference | -191.3393 | -166.3145 | -159.4742

## Cost Cancel Details
Turbine Position Report
Cost / Cancellation Details
|  |  | 1998-10-01 | 1998-11-01 | 1998-12-02 | 1999-01-02 | 1999-02-02 | 1999-03-05 | 1999-04-05 | 1999-05-06 | 1999-06-06 | 1999-07-07 | 1999-08-07 | 1999-09-07 | 1999-10-08 | 1999-11-08 | 1999-12-09 | 2000-01-09 | 2000-02-09 | 2000-03-11 | 2000-04-11 | 2000-05-12 | 2000-06-12 | 2000-07-13 | 2000-08-13 | 2000-09-13 | 2000-10-14 | 2000-11-14 | 2000-12-15 | 2001-01-15 | 2001-02-15 | 2001-03-18 | 2001-04-18 | 2001-05-19 | 2001-06-19 | 2001-07-20 | 2001-08-20 | 2001-09-20 | 2001-10-21 | 2001-11-21 | 2001-12-22 | 2002-01-22 | 2002-02-22 | 2002-03-25 | 2002-04-25 | 2002-05-26 | 2002-06-26 | 2002-07-27 | 2002-08-27 | 2002-09-27 | 2002-10-28 | 2002-11-28 | 2002-12-29 | CK TTL
1 | 7FA | Columbia / Longview
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 20% | 5% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 13% | 16% | 19% | 22% | 25% | 28% | 31% | 34% | 37% | 40% | 43% | 47% | 51% | 55% | 59% | 63% | 67% | 71% | 75% | 95% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 2% | 0% | 0% | 0% | 0% | 0% | 60% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 12% | 14% | 16% | 18% | 20% | 22% | 24% | 26% | 28% | 30% | 32% | 34% | 36% | 38% | 40% | 40% | 40% | 40% | 40% | 40% | 100%
| $ Scheduled Payments | 39.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.92 | 5.096 | 6.272 | 7.448 | 8.624 | 9.8 | 10.976 | 12.152 | 13.328 | 14.504 | 15.68 | 16.856 | 18.424 | 19.992 | 21.56 | 23.128 | 24.696 | 26.264 | 27.832 | 29.4 | 37.24 | 39.2 | 39.2
| $ Cancellation | Tentative | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.92 | 3.92 | 4.704 | 5.488 | 6.272 | 7.056 | 7.84 | 8.624 | 9.408 | 10.192 | 10.976 | 11.76 | 12.544 | 13.328 | 14.112 | 14.896 | 15.68 | 15.68 | 15.68 | 15.68 | 15.68 | 15.68 | 39.2
2 | MHI 501F Simple Cycle | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 15% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 20% | 0% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 25% | 25% | 25% | 25% | 40% | 40% | 40% | 40% | 40% | 40% | 60% | 60% | 60% | 60% | 80% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 37.1702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.717 | 3.717 | 3.717 | 9.2925 | 9.2925 | 9.2925 | 9.2925 | 14.8681 | 14.8681 | 14.8681 | 14.8681 | 14.8681 | 14.8681 | 22.3021 | 22.3021 | 22.3021 | 22.3021 | 29.7361 | 29.7361 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702
3 | MHI 501F Simple Cycle | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 20% | 0% | 20% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 25% | 25% | 25% | 25% | 25% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 60% | 60% | 60% | 80% | 80% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 33.8104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.381 | 3.381 | 3.381 | 3.381 | 3.381 | 3.381 | 3.381 | 8.4526 | 8.4526 | 8.4526 | 8.4526 | 8.4526 | 13.5242 | 13.5242 | 13.5242 | 13.5242 | 13.5242 | 13.5242 | 13.5242 | 20.2862 | 20.2862 | 20.2862 | 27.0483 | 27.0483 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104
4 | MHI 501F Simple Cycle | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 0% | 0% | 20% | 20% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 25% | 25% | 25% | 25% | 25% | 25% | 40% | 40% | 40% | 40% | 40% | 40% | 60% | 60% | 60% | 60% | 60% | 80% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 33.8104 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.381 | 3.381 | 3.381 | 3.381 | 3.381 | 3.381 | 3.381 | 8.4526 | 8.4526 | 8.4526 | 8.4526 | 8.4526 | 8.4526 | 13.5242 | 13.5242 | 13.5242 | 13.5242 | 13.5242 | 13.5242 | 20.2862 | 20.2862 | 20.2862 | 20.2862 | 20.2862 | 27.0483 | 33.8104 | 33.8104 | 33.8104 | 33.8104
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104 | 33.8104
5 | MHI 501F Simple Cycle | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 15% | 0% | 0% | 0% | 0% | 0% | 20% | 0% | 0% | 20% | 20% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 10% | 25% | 25% | 25% | 25% | 25% | 25% | 40% | 40% | 40% | 40% | 40% | 40% | 60% | 60% | 60% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 37.1702 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.717 | 3.717 | 3.717 | 3.717 | 9.2925 | 9.2925 | 9.2925 | 9.2925 | 9.2925 | 9.2925 | 14.8681 | 14.8681 | 14.8681 | 14.8681 | 14.8681 | 14.8681 | 22.3021 | 22.3021 | 22.3021 | 29.7361 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702 | 37.1702
6 | 501D5A Simple Cycle | Unassigned
| % Progress Payments |  | 0% | 0% | 4.938% | 0% | 0% | 0% | 19.7% | 19.66% | 0% | 7.372% | 12.29% | 0% | 9.829% | 2.457% | 5.118% | 2.457% | 0% | 2.457% | 2.457% | 0% | 4.915% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 6.359% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 4.938% | 4.938% | 4.938% | 4.938% | 24.63% | 44.29% | 44.29% | 51.66% | 63.95% | 63.95% | 73.78% | 76.24% | 81.35% | 83.81% | 83.81% | 86.27% | 88.73% | 88.73% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 93.64% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 5% | 0% | 10% | 0% | 0% | 0% | 0% | 5% | 0% | 0% | 5% | 0% | 0% | 10% | 0% | 0% | 0% | 0% | 0% | 0% | 65% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 5% | 5% | 15% | 15% | 15% | 15% | 15% | 20% | 20% | 20% | 25% | 25% | 25% | 35% | 35% | 35% | 35% | 35% | 35% | 35% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 24.506 | 0 | 0 | 1.2102 | 1.2102 | 1.2102 | 1.2102 | 6.037 | 10.8544 | 10.8544 | 12.6609 | 15.6718 | 15.6718 | 18.0805 | 18.6827 | 19.9368 | 20.539 | 20.539 | 21.1412 | 21.7434 | 21.7434 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 22.9478 | 24.5062 | 24.5062 | 24.5062 | 24.5062 | 24.5062 | 24.5062 | 24.5062 | 24.5062 | 24.5062 | 24.5062 | 24.5062 | 24.5062 | 24.5062 | 24.5062
| $ Cancellation | Available | 1.2253 | 1.2253 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 4.9012 | 4.9012 | 4.9012 | 6.1265 | 6.1265 | 6.1265 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506 | 24.506
7 | 9FA STAG Power Islands | Arcos
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 23% | 5% | 5% | 5% | 5% | 5% | 4% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 6% | 7% | 6% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 33% | 38% | 43% | 48% | 53% | 58% | 62% | 65% | 68% | 71% | 73% | 75% | 77% | 79% | 85% | 92% | 98% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 1.3% | 1.7% | 1.6% | 2.7% | 4.9% | 5.9% | 5.8% | 5% | 5.3% | 5.4% | 5.3% | 4.1% | 3% | 3.2% | 1.8% | 1.7% | 1.4% | 1.2% | 9.6% | 9.5% | 9.2% | 0.4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 11.3% | 13% | 14.6% | 17.3% | 22.2% | 28.1% | 33.9% | 38.9% | 44.2% | 49.6% | 54.9% | 59% | 62% | 65.2% | 67% | 68.7% | 70.1% | 71.3% | 80.9% | 90.4% | 99.6% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 83.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 8.3417 | 8.3417 | 27.5275 | 31.6983 | 35.8692 | 40.04 | 44.2108 | 48.3817 | 51.7183 | 54.2208 | 56.7233 | 59.2258 | 60.8942 | 62.5625 | 64.2308 | 65.8992 | 70.9042 | 76.7433 | 81.7483 | 82.5825 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 9.4261 | 10.8442 | 12.1788 | 14.4311 | 18.5185 | 23.4401 | 28.2782 | 32.4491 | 36.8702 | 41.3747 | 45.7957 | 49.2158 | 51.7183 | 54.3877 | 55.8892 | 57.3073 | 58.4751 | 59.4761 | 67.4841 | 75.4087 | 83.083 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
8 | 9FA STAG Power Islands | Arcos
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 23% | 5% | 5% | 5% | 5% | 5% | 4% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 6% | 7% | 6% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 33% | 38% | 43% | 48% | 53% | 58% | 62% | 65% | 68% | 71% | 73% | 75% | 77% | 79% | 85% | 92% | 98% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 1.3% | 1.7% | 1.6% | 2.7% | 4.9% | 5.9% | 5.8% | 5% | 5.3% | 5.4% | 5.3% | 4.1% | 3% | 3.2% | 1.8% | 1.7% | 1.4% | 1.2% | 9.6% | 9.5% | 9.2% | 0.4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 11.3% | 13% | 14.6% | 17.3% | 22.2% | 28.1% | 33.9% | 38.9% | 44.2% | 49.6% | 54.9% | 59% | 62% | 65.2% | 67% | 68.7% | 70.1% | 71.3% | 80.9% | 90.4% | 99.6% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 83.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 8.3417 | 8.3417 | 27.5275 | 31.6983 | 35.8692 | 40.04 | 44.2108 | 48.3817 | 51.7183 | 54.2208 | 56.7233 | 59.2258 | 60.8942 | 62.5625 | 64.2308 | 65.8992 | 70.9042 | 76.7433 | 81.7483 | 82.5825 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 9.4261 | 10.8442 | 12.1788 | 14.4311 | 18.5185 | 23.4401 | 28.2782 | 32.4491 | 36.8702 | 41.3747 | 45.7957 | 49.2158 | 51.7183 | 54.3877 | 55.8892 | 57.3073 | 58.4751 | 59.4761 | 67.4841 | 75.4087 | 83.083 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
9 | 9FA STAG Power Islands | Arcos
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 0% | 0% | 23% | 5% | 5% | 5% | 5% | 5% | 4% | 3% | 3% | 3% | 2% | 2% | 2% | 2% | 6% | 7% | 6% | 1% | 1% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 10% | 10% | 33% | 38% | 43% | 48% | 53% | 58% | 62% | 65% | 68% | 71% | 73% | 75% | 77% | 79% | 85% | 92% | 98% | 99% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 1.3% | 1.7% | 1.6% | 2.7% | 4.9% | 5.9% | 5.8% | 5% | 5.3% | 5.4% | 5.3% | 4.1% | 3% | 3.2% | 1.8% | 1.7% | 1.4% | 1.2% | 9.6% | 9.5% | 9.2% | 0.4% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 10% | 11.3% | 13% | 14.6% | 17.3% | 22.2% | 28.1% | 33.9% | 38.9% | 44.2% | 49.6% | 54.9% | 59% | 62% | 65.2% | 67% | 68.7% | 70.1% | 71.3% | 80.9% | 90.4% | 99.6% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 83.4167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 8.3417 | 8.3417 | 27.5275 | 31.6983 | 35.8692 | 40.04 | 44.2108 | 48.3817 | 51.7183 | 54.2208 | 56.7233 | 59.2258 | 60.8942 | 62.5625 | 64.2308 | 65.8992 | 70.9042 | 76.7433 | 81.7483 | 82.5825 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.3417 | 9.4261 | 10.8442 | 12.1788 | 14.4311 | 18.5185 | 23.4401 | 28.2782 | 32.4491 | 36.8702 | 41.3747 | 45.7957 | 49.2158 | 51.7183 | 54.3877 | 55.8892 | 57.3073 | 58.4751 | 59.4761 | 67.4841 | 75.4087 | 83.083 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167 | 83.4167
10 | 11N1 | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 17.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25
11 | 11N1 | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 17.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25 | 17.25
12 | Fr 6B 60 hz power barges (BV = 0) | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
13 | Fr 6B 60 hz power barges (BV = 0) | Unassigned
| % Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Progress Payments |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| % Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
| % Cumulative Cancellation |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
| $ Scheduled Payments | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
| $ Cancellation | Available | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5
TOTALS:
SUM OF COMMITTED
$ Scheduled Payments
$ Cancellation
SUM OF TENTATIVE
| $ Scheduled Payments | 39.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.92 | 5.096 | 6.272 | 7.448 | 8.624 | 9.8 | 10.976 | 12.152 | 13.328 | 14.504 | 15.68 | 16.856 | 18.424 | 19.992 | 21.56 | 23.128 | 24.696 | 26.264 | 27.832 | 29.4 | 37.24 | 39.2 | 39.2
| $ Cancellation |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.92 | 3.92 | 4.704 | 5.488 | 6.272 | 7.056 | 7.84 | 8.624 | 9.408 | 10.192 | 10.976 | 11.76 | 12.544 | 13.328 | 14.112 | 14.896 | 15.68 | 15.68 | 15.68 | 15.68 | 15.68 | 15.68 | 39.2
SUM OF AVAILABLE
| $ Scheduled Payments | 464.2172 | 0 | 0 | 1.2102 | 1.2102 | 1.2102 | 1.2102 | 6.037 | 10.8544 | 10.8544 | 12.6609 | 15.6718 | 15.6718 | 18.0805 | 18.6827 | 19.9368 | 20.539 | 20.539 | 21.1412 | 29.1774 | 76.6774 | 102.9068 | 108.4824 | 120.82 | 178.3775 | 190.89 | 208.978 | 221.4905 | 234.003 | 252.091 | 272.2441 | 279.7516 | 294.6932 | 302.2007 | 307.2057 | 324.7163 | 342.2269 | 347.2319 | 378.6733 | 403.6249 | 418.6399 | 421.1424 | 437.169 | 437.169 | 437.169 | 443.9311 | 443.9311 | 457.4553 | 464.2174 | 464.2174 | 464.2174 | 464.2174
| $ Cancellation |  | 1.2253 | 1.2253 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 4.9012 | 4.9012 | 4.9012 | 6.1265 | 6.1265 | 6.1265 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 82.9175 | 107.9425 | 158.6957 | 178.8789 | 250.5037 | 257.2604 | 269.5227 | 284.2874 | 298.8019 | 311.3144 | 324.5777 | 338.0912 | 351.3544 | 361.6147 | 369.1222 | 377.1302 | 381.6347 | 385.8889 | 389.3924 | 392.3954 | 416.4194 | 440.1932 | 463.2162 | 464.2172 | 464.2172 | 464.2172 | 464.2172 | 464.2172 | 464.2172 | 464.2172 | 464.2172 | 464.2172 | 464.2172 | 464.2172
GRAND TOTALS:
| $ Scheduled Payments | 503.4172 | 0 | 0 | 1.2102 | 1.2102 | 1.2102 | 1.2102 | 6.037 | 10.8544 | 10.8544 | 12.6609 | 15.6718 | 15.6718 | 18.0805 | 18.6827 | 19.9368 | 20.539 | 20.539 | 21.1412 | 29.1774 | 76.6774 | 102.9068 | 108.4824 | 120.82 | 178.3775 | 190.89 | 208.978 | 221.4905 | 234.003 | 256.011 | 277.3401 | 286.0236 | 302.1412 | 310.8247 | 317.0057 | 335.6923 | 354.3789 | 360.5599 | 393.1773 | 419.3049 | 435.4959 | 439.5664 | 457.161 | 458.729 | 460.297 | 468.6271 | 470.1951 | 485.2873 | 493.6174 | 501.4574 | 503.4174 | 503.4174
| $ Cancellation |  | 1.2253 | 1.2253 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 4.9012 | 4.9012 | 4.9012 | 6.1265 | 6.1265 | 6.1265 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 82.9175 | 107.9425 | 158.6957 | 178.8789 | 250.5037 | 257.2604 | 269.5227 | 284.2874 | 298.8019 | 311.3144 | 324.5777 | 342.0112 | 355.2744 | 366.3187 | 374.6102 | 383.4022 | 388.6907 | 393.7289 | 398.0164 | 401.8034 | 426.6114 | 451.1692 | 474.9762 | 476.7612 | 477.5452 | 478.3292 | 479.1132 | 479.8972 | 479.8972 | 479.8972 | 479.8972 | 479.8972 | 479.8972 | 503.4172
| $ Exposure |  | 1.2253 | 1.2253 | 2.4657 | 2.4657 | 2.4657 | 2.4657 | -2.3611 | -5.9532 | -5.9532 | -7.7597 | -9.5453 | -9.5453 | -11.954 | -10.1056 | -11.3597 | -11.9619 | -11.9619 | 61.7763 | 78.765 | 82.0183 | 75.972 | 142.0213 | 136.4404 | 91.1452 | 93.3974 | 89.8239 | 89.8239 | 90.5747 | 86.0001 | 77.9343 | 80.295 | 72.469 | 72.5775 | 71.685 | 58.0366 | 43.6375 | 41.2435 | 33.4341 | 31.8643 | 39.4803 | 37.1948 | 20.3841 | 19.6001 | 18.8161 | 11.27 | 9.702 | -5.3901 | -13.7202 | -21.5602 | -23.5202 | -0.0002
| check totals per detail above | 503.4172 | 0 | 0 | 1.2102 | 1.2102 | 1.2102 | 1.2102 | 6.037 | 10.8544 | 10.8544 | 12.6609 | 15.6718 | 15.6718 | 18.0805 | 18.6827 | 19.9368 | 20.539 | 20.539 | 21.1412 | 29.1774 | 76.6774 | 102.9068 | 108.4824 | 120.82 | 178.3775 | 190.89 | 208.978 | 221.4905 | 234.003 | 256.011 | 277.3401 | 286.0236 | 302.1412 | 310.8247 | 317.0057 | 335.6923 | 354.3789 | 360.5599 | 393.1773 | 419.3049 | 435.4959 | 439.5664 | 457.161 | 458.729 | 460.297 | 468.6271 | 470.1951 | 485.2873 | 493.6174 | 501.4574 | 503.4174 | 503.4174
|  |  | 1.2253 | 1.2253 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 3.6759 | 4.9012 | 4.9012 | 4.9012 | 6.1265 | 6.1265 | 6.1265 | 8.5771 | 8.5771 | 8.5771 | 8.5771 | 82.9175 | 107.9425 | 158.6957 | 178.8789 | 250.5037 | 257.2604 | 269.5227 | 284.2874 | 298.8019 | 311.3144 | 324.5777 | 342.0112 | 355.2744 | 366.3187 | 374.6102 | 383.4022 | 388.6907 | 393.7289 | 398.0164 | 401.8034 | 426.6114 | 451.1692 | 474.9762 | 476.7612 | 477.5452 | 478.3292 | 479.1132 | 479.8972 | 479.8972 | 479.8972 | 479.8972 | 479.8972 | 479.8972 | 503.4172
|  |  | 1.2253 | 1.2253 | 2.4657 | 2.4657 | 2.4657 | 2.4657 | -2.3611 | -5.9532 | -5.9532 | -7.7597 | -9.5453 | -9.5453 | -11.954 | -10.1056 | -11.3597 | -11.9619 | -11.9619 | 61.7763 | 78.765 | 82.0183 | 75.972 | 142.0213 | 136.4404 | 91.1452 | 93.3974 | 89.8239 | 89.8239 | 90.5747 | 86.0001 | 77.9343 | 80.295 | 72.469 | 72.5775 | 71.685 | 58.0366 | 43.6375 | 41.2435 | 33.4341 | 31.8643 | 39.4803 | 37.1948 | 20.3841 | 19.6001 | 18.8161 | 11.27 | 9.702 | -5.3901 | -13.7202 | -21.5602 | -23.5202 | -0.0002
| Differences between subtotals and details | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.6843e-14 | 5.6843e-14 | 5.6843e-14 | 5.6843e-14 | 0 | 0 | 5.6843e-14