## Sheet3
DPS Article X Cases: 9/21/01--NY New Generation
Case Number | Project | MW | MW Increase | % Probablity | Projected MW Built | Developer | Town/County | Status | Pre-Application Date | DEC Notice of Air & Water Permits | Application Filing Date | Chairman Compliance Determination | Certification Date or Estimated Decision Date | Estimated Earliest In-Service Date* Quarter Year |  | Line Connection | Detailed Location | Zone
99-F-1314 | East River Repowering (Repowering a 200 MW unit) | 360 | 360 |  | 0 | Con Ed | Lower Manhattan | PLN | 1999-09-28 | 8/16/01 (Final) | 2000-06-01 | 7/31/00 (Complies) | 2001-08-30 | 4Q | 2002 | The site includes 69, 138, and 345 kV substations | The Generating Station site also includes 69, 138, and 345 kV (kilovolt) substations | J
97-F-1563 | Athens Generating Plant | 1080 | 1080 | 100% | 1080 | Athens Generating Co., LP | Athens/ Greene | CON | 1997-09-09 | 6/12/00 (Final) | 1998-08-28 | 10/28/98 (Complies) | 2000-06-15 | 3Q | 2003 |  | 30 miles south of Albany (north of Catskill) | F
99-F1625 | Ravenswood Cogeneration Project | 250 | 250 |  | 0 | Keyspan | LIC/ Quieens | PLN | 1999-11-18 | 9/4/01 (Final) | 2000-07-28 | 1/24/01 (Complies) | 2001-09-07 |  | 2003 |  | W/in the city | J
00-F-1356 | Kings Park | 300 | 300 |  | 0 | PPL Global | Smithtown/ Suffolk | PLN | 8/10/00 (PSS); Revision 12/20/00 | N/A | 3Q 2001 | N/A | N/A | 3Q | 2003 | Adjacent to the LIPA's right of way, which also contains underground electric distribution lines to the Pilgrim Substation | On L.I., Industrial section of Kings Park, in Smithtown | K
99-F-0558 | Heritage | 800 | 800 |  | 0 | Heritage, LLC | Scriba/ Oswego | PLN | 1999-04-21 | 11/1/00 (Final) | 2000-02-23 | 4/24/00 (Complies) | 2001-01-17 | 1Q | 2004 |  | Route 1A in the town of Scriba, Oswego County, near Lake Ontario | C
98-F-1968 | Ramapo Energy Project | 1100 | 1100 |  | 0 | Ramapo Energy, LP | Ramapo/ Rockland | PLN | 1998-12-22 | 12/28/00 (Draft) | 1999-11-29 | 1/2/01 (Complies) | 1Q 2002 (Estimated) | 2Q | 2004 | Transmission lines run along the property border | In a Planned Industry Zone | C
00-F-2057 | Besicorp | 510 | 510 |  | 0 | Empire State Newsprint | Rensselaer/ Rensselaer | PLN | 11/22/00 (PSS) | N/A | 3Q 2001 | N/A | N/A | 3Q | 2004 |  |  | F
97-F-2162 | Bethlehem Energy Center | 750 Total**; 350 net Increase | 350 |  | 0 | PSEG Power; New York, Inc.*** | Bethlehem/ Albany | PLN | 1997-12-19 | 9/5/01 (Draft) | 11/27/98****; 7/2/01 (Amendment) | 8/31/201 | 3Q 2002 (Estimated) | 3Q | 2004 | Use existing transmissin lines | 3 miles south of Albany in Bethlehem (Glenmount) | G
99-F-1164 | Bowline Unit 3 | 750 | 750 |  | 0 | Mirant (formerly Southern Conmpany) | Haverstraw/ Rockland | PLN | 1999-08-23 | 1/17/01 (Draft) | 2000-03-20 | 2000-08-10 | 3Q 2002 (Estimated) | 2Q | 2004 | Will connect to Consolidated Edison and Orange & Rockland electric transmission system through a new underground transmission line (345 kV--1.7 miles) adjacent to existing lines | 30 miles north of NYC | G/J
00-F-1256 | Wawayanda | 540 | 540 |  | 0 | Calpine Construction Finance Corp, LP | Wawayanda/ Orange | PLN | 7/27/00 (PSS) | N/A | 2001-08-27 | N/A | N/A | N/A | 2004 | Near Marcy South Transmission Lines | Just outside Middletown NY | I
99-F-1191 | Astoria Energy, LLC | 1000 | 1000 |  | 0 | SCS Energy | Astoria/ Queens | PLN | 1999-08-31 | 2/28/01 (Draft) | 2000-06-19 | 3/1/01 (Complies) | 1Q 2002 (Estimated) | 3Q | 2004 | 138 kV transmissin sytem in Queens Load Pocket | Inside NYC transmission system | J
99-F-1627 | Poletti Station Expansion | 500 | 500 |  | 0 | NYPA | Astoria/ Queens | PLN | 1999-11-19 | 5/2/01 (Draft) | 2000-08-18 | 4/30/01 (Complies) | 2Q 2002 (Estimated) | 3Q | 2004 |  | Across the East River | J
00-F-0566 | Brookhaven | 580 | 580 |  | 0 | Brookhaven Energy, LP | Brookhaven/ Suffolk | PLN | 3/28/00 (PSS) | N/A | 2001-06-25 | 2001-08-15 | 3Q 2002 |  | 2004 | Existing transmission lines adjacent to the property | Souteast Corner of Long Island Expressway and Sills Rd. | K
01-F-0761 | Spagnoli Road Energy Center | 250 | 250 |  | 0 | Keyspan | Melville/ Suffolk | PLN | 3 Q 2001 | 3Q 2001 | 4Q 2001 | N/A | N/A |  | 2004 | Near LIPA's electric transmission system | located in an industrial and commercial area | K
00-F-1522 | Orion Power Astoria Repowering | 1842 Total; 500 Net Increase | 500 |  | 0 | Astoria Genertaing Co.,LP | Astorie/ Queens | PLN | 9/5/00 (PSS) | N/A | 3Q 2001 | N/A | N/A |  | 2005 | The transmission interconnection is switchable under load and can supply either the Astoria East or the Astoria West 138-kV transmission grids |  | J
99-F0961 | Twin Tier Power | 520 | 520 |  | 0 | Twin Tier Power | Nichols/ Tioga | PLN | 1999-07-19 | N/A | On Hold | N/A | N/A | N/A | N/A |  | Lounsberry Industrial Site in the Town of Nichols, Tioga County | C
00-F-1835 | Glenville Energy Park | 520 | 520 |  | 0 | Glenville Energy Park, LLC | Scotia-Glenville/ Schenectady | PLN | 12/29/99 (PSS) | N/A | 3Q 2001 | N/A | N/A | N/A | N/A | Will be interconnected with the Niagara Mohawk transmission grid. The interconnection will be accomplished at a voltage level of either 115 kV or 230 kV. | Scotia-Glenville Industial Park | F
00-F-1295 | Grassy Point (formerly Haverstraw) | 550 | 550 |  | 0 | Haverstraw Bay, LLC | Haverstraw/ Rockland | PLN | 1999-09-24 | N/A | On Hold | N/A | N/A | N/A | N/A |  |  | G/J
99-F-0478 | Sunset Energy Fleet, LLC | 520 | 520 |  | 0 | SEF | Sunset Industrial Park/ Brooklyn | PLN | 1999-04-05 | N/A | 7/26/00**** | 9/25/00 (Deficient) | N/A | N/A | N/A |  |  | J
98-F-1885 | Torne Valley Station | 827 | 827 |  | 0 | Sithe Torne Valley, LLC | Ramapo/ Rockland | PLN | 1998-12-04 | N/A | 11/15/1999**** | 6/19/00; 12/29/99; Deficient | N/A | N/A | N/A |  |  | J
00-F-1133 | Oak Point Energy Generating Facility | 1075 | 1075 |  | 0 | Oak Point, LLC | Bronx | PLN | 7/3/00 (PSS) | N/A | 4Q 2001 | N/A | N/A | N/A | N/A |  |  | J
00-F-1391 | Caithness | 750 | 750 |  | 0 | Caithness Energy, LLC | Brookhaven Suffolk | PLN | 2000-08-17 | N/A | N/A | N/A | N/A | N/A | N/A |  | Brookhaven, Suffolk County, New York | K
01-F-1276 | TransGas Energy | 1100 | 1100 |  | 0 | TransGas Energy Systems, LLC | Greenpoint, Brooklyn | PLN | 9/17/01 (PSS) | N/A | N/A | N/A | N/A | N/A | N/A | The location is accessible to the New York City electric transmission system and has the potential to deliver wholesale power at the lowest possible cost to vulnerable load pockets in Brooklyn, Queens, and Manhattan | One North 12th Street, adjacent to the East River in Greenpoint, Brooklyn, NY | J
|  |  | 14732 |  | 1080
*In-service dates are based on estimates of when an application will be deemed complete, the time nedessary to complete the Article X process and one to two years for construction, dates can change as filing and compliance determination date change.
**Size of repowered projects shows site total and incremental increase resulting from repowering.
***Application was initially filed by Niagra Mohawk Power Corporation
****Completion of filing is pending
|  | Cal '02 | Cal '03 | Cal '04 | Cal '05 | N/A | TOTAL
| Zone C |  |  | 1900 |  | 520 | 2420
| Zone F |  | 1080 | 510 |  | 520 | 2110
| Zone G |  |  | 350 |  |  | 350
| Zone G/J |  |  | 750 |  | 550 | 1300
| Zone I |  |  | 540 |  |  | 540
| Zone J | 360 | 250 | 1500 | 500 | 3522 | 6132
| Zone K |  | 300 | 830 |  | 750 | 1880
| TOTAL | 360 | 1630 | 6380 | 500 | 5862 | 14732

## Sheet2
DPS Article X Cases: 9/21/01--NY New Generation
Case Number | Project | MW | MW Increase | % Probablity | Projected MW Built | Developer | Town/County | Pre-Application Date | DEC Notice of Air & Water Permits | Application Filing Date | Chairman Compliance Determination | Certification Date or Estimated Decision Date | Estimated Earliest In-Service Date* Quarter Year |  | Line Connection | Detailed Location | Zone
99-F-1191 | Astoria Energy, LLC | 1000 | 1000 |  | 0 | SCS Energy | Astoria/ Queens | 1999-08-31 | 2/28/01 (Draft) | 2000-06-19 | 3/1/01 (Complies) | 1Q 2002 (Estimated) | 3Q | 2004 | 138 kV transmissin sytem in Queens Load Pocket | Inside NYC transmission system | J
97-F-1563 | Athens Generating Plant | 1080 | 1080 |  | 0 | Athens Generating Co., LP | Athens/ Greene | 1997-09-09 | 6/12/00 (Final) | 1998-08-28 | 10/28/98 (Complies | 2000-06-15 | 3Q | 2003 |  | 30 miles south of Albany (north of Catskill) | F/G
97-F-2162 | Bethlehem Energy Center | 750 Total**; 350 net Increase | 350 |  | 0 | PSEG Power; New York, Inc.*** | Bethlehem/ Albany | 1997-12-19 | 9/5/01 (Draft) | 11/27/98****; 7/2/01 (Amendment) | 8/31/201 | 3Q 2002 (Estimated) | 3Q | 2004 | Use existing transmissin lines | 3 miles south of Albany in Bethlehem (Glenmount) | G
99-F-1164 | Bowline Unit 3 | 750 | 750 |  | 0 | Mirant (formerly Southern Conmpany) | Haverstraw/ Rockland | 1999-08-23 | 1/17/01 (Draft) | 2000-03-20 | 2000-08-10 | 3Q 2002 (Estimated) | 2Q | 2004 | Will connect to Consolidated Edison and Orange & Rockland electric transmission system through a new underground transmission line (345 kV--1.7 miles) adjacent to existing lines | 30 miles north of NYC | G
00-F-0566 | Brookhaven | 580 | 580 |  | 0 | Brookhaven Energy, LP | Brookhaven/ Suffolk | 3/28/00 (PSS) | N/A | 2001-06-25 | 2001-08-15 | 3Q 2002 |  | 2004 | Existing transmission lines adjacent to the property | Souteast Corner of Long Island Expressway and Sills Rd. | K
99-F-1314 | East River Repowering (Repowering a 200 MW unit) | 360 | 360 |  | 0 | Con Ed | Lower Manhattan | 1999-09-28 | 8/16/01 (Final) | 2000-06-01 | 7/31/00 (Complies) | 2001-08-30 | 4Q | 2002 | The site includes 69, 138, and 345 kV substations | The Generating Station site also includes 69, 138, and 345 kV (kilovolt) substations | J
99-F-0558 | Heritage | 800 | 800 |  | 0 | Heritage, LLC | Scriba/ Oswego | 1999-04-21 | 11/1/00 (Final) | 2000-02-23 | 4/24/00 (Complies) | 2001-01-17 | 1Q | 2004 |  | Route 1A in the town of Scriba, Oswego County, near Lake Ontario | C
99-F-1627 | Poletti Station Expansion | 500 | 500 |  | 0 | NYPA | Astoria/ Queens | 1999-11-19 | 5/2/01 (Draft) | 2000-08-18 | 4/30/01 (Complies) | 2Q 2002 (Estimated) | 3Q | 2004 |  | Across the East River
98-F-1968 | Ramapo Energy Project | 1100 | 1100 |  | 0 | Ramapo Energy, LP | Ramapo/ Rockland | 1998-12-22 | 12/28/00 (Draft) | 1999-11-29 | 1/2/01 (Complies) | 1Q 2002 (Estimated) | 2Q | 2004 | Transmission lines run along the property border | In a Planned Industry Zone | C
99-F1625 | Ravenswood Cogeneration Project | 250 | 250 |  | 0 | Keyspan | LIC/ Quieens | 1999-11-18 | 9/4/01 (Final) | 2000-07-28 | 1/24/01 (Complies) | 2001-09-07 |  | 2003 |  | W/in the city | J
99-F-0478 | Sunset Energy Fleet, LLC | 520 | 520 |  | 0 | SEF | Sunset Industrial Park/ Brooklyn | 1999-04-05 | N/A | 7/26/00**** | 9/25/00 (Deficient) | N/A | N/A | N/A |  |  | J
98-F-1885 | Torne Valley Station | 827 | 827 |  | 0 | Sithe Torne Valley, LLC | Ramapo/ Rockland | 1998-12-04 | N/A | 11/15/1999**** | 6/19/00; 12/29/99; Deficient | N/A | N/A | N/A |  |  | J
00-F-1256 | Wawayanda | 540 | 540 |  | 0 | Calpine Construction Finance Corp, LP | Wawayanda/ Orange | 7/27/00 (PSS) | N/A | 2001-08-27 | N/A | N/A | N/A | 2004 | Near Marcy South Transmission Lines | Just outside Middletown NY | I
00-F-1295 | Grassy Point (formerly Haverstraw) | 550 | 550 |  | 0 | Haverstraw Bay, LLC | Haverstraw/ Rockland | 1999-09-24 | N/A | On Hold | N/A | N/A | N/A | N/A
99-F0961 | Twin Tier Power | 520 | 520 |  | 0 | Twin Tier Power | Nichols/ Tioga | 1999-07-19 | N/A | On Hold | N/A | N/A | N/A | N/A |  | Lounsberry Industrial Site in the Town of Nichols, Tioga County | C
00-F-2057 | Besicorp | 510 | 510 |  | 0 | Empire State Newsprint | Rensselaer/ Rensselaer | 11/22/00 (PSS) | N/A | 3Q 2001 | N/A | N/A | 3Q | 2004 |  |  | F
00-F-1391 | Caithness | 750 | 750 |  | 0 | Caithness Energy, LLC | Brookhaven Suffolk | 2000-08-17 | N/A | N/A | N/A | N/A | N/A | N/A |  | Brookhaven, Suffolk County, New York | K
00-F-1835 | Glenville Energy Park | 520 | 520 |  | 0 | Glenville Energy Park, LLC | Scotia-Glenville/ Schenectady | 12/29/99 (PSS) | N/A | 3Q 2001 | N/A | N/A | N/A | N/A | Will be interconnected with the Niagara Mohawk transmission grid. The interconnection will be accomplished at a voltage level of either 115 kV or 230 kV. | Scotia-Glenville Industial Park | F
00-F-1356 | Kings Park | 300 | 300 |  | 0 | PPL Global | Smithtown/ Suffolk | 8/10/00 (PSS); Revision 12/20/00 | N/A | 3Q 2001 | N/A | N/A | 3Q | 2003 | Adjacent to the LIPA's right of way, which also contains underground electric distribution lines to the Pilgrim Substation | On L.I., Industrial section of Kings Park, in Smithtown | K
00-F-1133 | Oak Point Energy Generating Facility | 1075 | 1075 |  | 0 | Oak Point, LLC | Bronx | 7/3/00 (PSS) | N/A | 4Q 2001 | N/A | N/A | N/A | N/A |  |  | J
00-F-1522 | Orion Power Astoria Repowering | 1842 Total; 500 Net Increase | 500 |  | 0 | Astoria Genertaing Co.,LP | Astorie/ Queens | 9/5/00 (PSS) | N/A | 3Q 2001 | N/A | N/A |  | 2005 | The transmission interconnection is switchable under load and can supply either the Astoria East or the Astoria West 138-kV transmission grids |  | J
01-F-0761 | Spagnoli Road Energy Center | 250 | 250 |  | 0 | Keyspan | Melville/ Suffolk | 3 Q 2001 | 3Q 2001 | 4Q 2001 | N/A | N/A |  | 2004 | Near LIPA's electric transmission system | located in an industrial and commercial area | K
01-F-1276 | TransGas Energy | 1100 | 1100 |  | 0 | TransGas Energy Systems, LLC | Greenpoint, Brooklyn | 9/17/01 (PSS) | N/A | N/A | N/A | N/A | N/A | N/A | The location is accessible to the New York City electric transmission system and has the potential to deliver wholesale power at the lowest possible cost to vulnerable load pockets in Brooklyn, Queens, and Manhattan | One North 12th Street, adjacent to the East River in Greenpoint, Brooklyn, NY
|  |  | 14732 |  | 0

## Sheet1
NY New Generation
Holding Companies | Plant | MW | Note | Unit | Fuel | Mo | Year | City | State | NERC/Reg | Alt Fuel | Status | Zone | % Probability | Projected MW Built | Line Connection | Location
Exelon / Vivendi | Heritage Station (Independence) | 800 |  | CC | NG | Q1 | 2004 | Scriba | NY | NYPP |  | PLN | C | 35% | 280 |  | Route 1A in the town of Scriba, Oswego County, near Lake Ontario
Keyspan | Melville 1 | 79 |  | CC | NG | 5 | 2003 | Melville/ Sufolk Cty | NY | NYPP |  | PLN | K | 35% | 27.65
ABB Energy Ventures | Oak Point | 1075 |  | CC | NG |  | 2003 | New York | NY | NYPP |  | PLN | J | 35% | 376.25
Consolidated Edison | East River | 360 | Repowering a 200 MW unit. Details: http://www.coned.com/coned_search/search_frameset.asp | CC | NG | Q4 | 2002 | New York | NY | NYPP |  | PLN | J | 35% | 126 | The site includes 69, 138, and 345 kV substations | The Generating Station site also includes 69, 138, and 345 kV (kilovolt) substations
Ecorp | Nichols | 520 |  | CC | NG |  | 2003 | Nichols/Tioga Cty | NY | NYPP |  | PLN | C | 35% | 182 |  | Lounsberry Industrial Site in the Town of Nichols, Tioga County
Sunset Energy Fleet | Sunset Fleet | 520 |  | CC | NG |  |  | Brooklyn | NY | NYPP |  | PLN | J | 35% | 182
Exelon / Vivendi | Torne Valley | 827 |  | CC | NG |  | 2003 | Ramapo | NY | NYPP |  | PLN | J | 35% | 289.45
KeySpan | Ravenswood | 250 |  | CC | NG |  | 2003 | Queens | NY | NYPP | FO2 | PLN | J | 35% | 87.5 | W/in the city
Mirant | Bowline | 750 | Transmission details: http://www.mirant.com/bowline/pdf/article7elec.pdf | CC | NG | Q2 | 2004 | West Haverstraw | NY | NYPP |  | PLN | G | 35% | 262.5 | Will connect to Consolidated Edison and Orange & Rockland electric transmission system through a new underground transmission line (345 kV--1.7 miles) adjacent to existing lines | 30 miles north of NYC
PG&E | Athens | 1080 |  | CC | NG | Q3 | 2003 | Athens | NY | NYPP |  | CON | F/G | 100% | 1080 |  | 30 miles south of Albany (north of Catskill)
PPL | King Park | 300 |  | CT | NG | Q3 | 2003 | Smithtown | NY | NYPP | FO2 | PLN | K | 35% | 105 | Adjacent to the LIPA's right of way, which also contains underground electric distribution lines to the Pilgrim Substation | On L.I., Industrial section of Kings Park, in Smithtown
SCS Energy | Astoria/Queens | 1000 |  | CC | NG | Q3 | 2004 | Astoria/ Queens | NY | NYPP | FO2 | PLN | J | 35% | 350 | 138 kV transmissin sytem in Queens Load Pocket | Inside NYC transmission system
Caithness Corp | Island Power Project | 750 |  | CC | NG |  | 2003 | Brookhaven | NY | NYPP |  | PLN | K | 35% | 262.5 |  | Brookhaven, Suffolk County, New York
International Power | Brookhaven | 580 |  | CC | NG |  | 2004 | Brookhaven | NY | NYPP |  | PLN | K | 35% | 203 | Existing transmission lines adjacent to the property | Souteast Corner of Long Island Expressway and Sills Rd.
Bronx Paper Mill | Paper plant | 50 |  | CC | NG | 12 | 2003 | New York | NY | NYPP |  | PLN | J | 35% | 17.5
| TOTAL | 8941 | [11 empty] | TOTAL | 3831.35
| Total Zone C | 1320 | [11 empty] | Total Zone C | 462
| Total Zone F/G | 1080 | [11 empty] | Total Zone F/G | 1080
| Total Zone G | 750 | [11 empty] | Total Zone G | 262.5
| Total Zone J | 4082 | [11 empty] | Total Zone J | 1428.7
| Total Zone K | 1709 | [11 empty] | Total Zone K | 598.15
Holding Companies | Plant | MW |  | Unit | Fuel | Mo | Year | City | State | NERC/Reg | Alt Fuel | Status | Zone | % Probability | Projected MW Built | Line Connection | Location
Vermont Energy Park Holdings | Glenville Energy Park | 520 |  | CC | NG |  | 2004 | Glenville | NY | NYPP |  | PLN | F | 35% | 182 | Will be interconnected with the Niagara Mohawk transmission grid. The interconnection will be accomplished at a voltage level of either 115 kV or 230 kV. | Scotia-Glenville Industial Park
Calpine | Wawayanda Energy Center | 540 |  | CC | NG |  | 2004 | Orange County | NY | NYPP |  | PLN | I | 35% | 189 | Near Marcy South Transmission Lines | Just outside Middletown NY
Goldman Sachs | Astoria Gen Station | 331 |  | CC | NG | 1 | 2004 | Queens | NY | NYPP | FO2 | PLN | J | 35% | 115.85
York Research Corp | North First Street | 500 |  | CT | NG | 1 | 2004 | NA | NY | NYPP |  | PLN |  | 35% | 175
Keyspan | Shoreham Generating Station | 270 |  | CC | NG | 5 | 2004 | Long Island | NY | NYPP |  | PLN | K | 35% | 94.5
NYPA | Charles Polletti Expansion | 500 |  | CC | NG | Q3 | 2004 | Queens | NY | NYPP |  | PLN | J | 35% | 175 |  | Across the East River
Besicorp/Empire St News | Empire State Newsprint | 510 |  | CC | NG | Q3 | 2004 | Albany | NY | NYPP |  | PLN | F | 35% | 178.5
International Power Inc | Ramapo | 1100 |  | CC | NG | Q2 | 2004 | Ramapo | NY | NYPP |  | PLN | C | 35% | 385 | Transmission lines run along the property border | In a Planned Industry Zone
Keyspan | Melville 2 | 270 |  | CC | NG | 6 | 2004 | Melville | NY | NYPP |  | PLN | K | 35% | 94.5
PSEG | Bethlehem Energy Center | 350 | 750 MW Plant Replacing the 400 MW Albany Steam Station | CG | NG | Q3 | 2004 | Kingston | NY | NYPP |  | PLN | G | 35% | 122.5 | Use existing transmissin lines | 3 miles south of Albany in Bethlehem (Glenmount)
| TOTAL | 4891 | [11 empty] | TOTAL | 1711.85
| Total Zone C | 1100 | [11 empty] | Total Zone C | 385
| Total Zone F | 1030 | [11 empty] | Total Zone F | 360.5
| Total Zone G | 350 | [11 empty] | Total Zone G | 122.5
| Total Zone I | 540 | [11 empty] | Total Zone I | 189
| Total Zone J | 831 | [11 empty] | Total Zone J | 290.85
| Total Zone K | 540 | [11 empty] | Total Zone K | 189
Haverstraw Bay, LLC | Grassy Point | 550 |  | CC | NG |  |  | Haverstraw, Rockland | NY | NYPP
Astoria Generating Co., LP | Orion Power Astoria Repowering | 500 | 1842 MW Total--500 MW net increase | CC | NG |  | 2005 | Astoria Queens | NY | NYPP | [5 empty] | The transmission interconnection is switchable under load and can supply either the Astoria East or the Astoria West 138-kV transmission grids
Keyspan | Spagnoli Road Energy Center | 250 |  | CC | NG |  | 2004 | Melville/ Suffolk | NY | NYPP | [5 empty] | Near LIPA's electric transmission system | located in an industrial and commercial area
TransGas energy Sytems, LLC | TransGas Energy | 1100 |  | CC | NG |  |  | Greenpoint, Brooklyn | NY | NYPP | [5 empty] | The location is accessible to the New York City electric transmission system and has the potential to deliver wholesale power at the lowest possible cost to vulnerable load pockets in Brooklyn, Queens, and Manhattan | One North 12th Street, adjacent to the East River in Greenpoint, Brooklyn, NY