## Sheet1
Prepared by
Energy Operations
Updated: 4/4/01
AEP-HPL TRANSITION ISSUES *
System |  | Activity | Point Person | Point Person | Due Date
|  |  | Enron | AEP
Global Counterparty
| 1 | Web page development | Tommy Yanowski IT |  | 2001-04-30
| 2 | Procedures for counterparty updates | Bill Hare EO |  | 2001-04-15
| 3 | Amendment to Service Agreement | Tommy Yanowski IT |  | 2001-04-15
| 4 | Filtering Information in comments/notes Web View | Bill Hare EO |  | 2001-04-15
| 5 | DUN's number for AEP-HPL | Romeo D'Souza/Mike Eiben EO |  | 2001-04-15
| 6 | Banking info from AEP |  | Steve Jackson/Jan with AEP | 2001-05-15
| 7 | Cross reference table for counterparty | Tommy Yanowski IT | Steve Jackson/Don Simpson | 2001-04-30
| 8 | Suspending of counterparty | Bill Hare/Marilyn Colbert/Bob Hall
| 9 | Bank validations | Bill Hare/Marilyn Colbert/Sundar C. IT
| 10 | New business rules | Sundar Chitradurga IT
Global Facilities
| 1 | Global facilities maintenance group split | Mike Eiben EO/Sundar Chitradurga IT |  | 2001-04-30
| 2 | Resolve new pipeline question (not needed) - pipe codes | Mike Eiben EO/Matt Pena/Romeo D'Souza IT |  | 2001-04-15
Global Contracts
| 1 | Script to copy contract data | Cheryl Dudley EO |  | 2001-03-20
| 2 | IT execution of script | Fred IT |  | 2001-05-01
| 3 | Contracts being transferred | George Weissman PS |  | 2001-04-15
| 4 | Contract to be terminated before close | George Weissman PS |  | 2001-04-15
| 5 | Contracts to be terminated after close | George Weissman PS |  | 2001-04-15
| 6 | Access to contracts for data entry before close | George Weissman PS
| 7 | Transport contracts review | Ed Gottlob, Mary Smith,
| 8 | Evergreen Deals | George Weissman PS
Global Rates
| 1 | Cross reference table for rates - Index ID's | Tommy Yanowski IT | Don Simpson | 2001-04-30
Risk/Deal Entry/Sitara
| 1 | Identification of risk portfolios | Mick Walters | Steve Jackson
| 2 | Creation of new risk portfolios | Russ Severson
| 3 | Bridge from AEP trade blotter to Sitara | Tommy Yanowski IT | Don Simpson | 2001-04-30
| 4 | Bridge Error report |  | Don Simpson
| 5 | Base Gas bridge and updates | Tommy Yanowski IT
| 6 | Separate copy of ERMS and CPR | Tommy Yanowski IT
| 7 | Initially deals will be entered into Zianet and Sitara | Mick Walters | Steve Jackson
| 8 | Enron credit and other information on counterparty | Bill Hare EO/TommyYanowski IT/Jay Krish IT
| 9 | Procedures for new portfolios and books after close | Russ Severson
| 10 | Upload of curves in ERMS | Tommy Yanowski IT
| 11 | Curve mappings to locations | Tommy Yanowski IT
Confirmations
| 1 | Will AEP use our confirmation system (only DECAF 2) | Bob Hall EO | Steve Jackson | 2001-04-15
| 2 | AEP wants to confirm intramonth deals only | Kim Theriot
| 3 | Double confirmation of same deal between AEP and ENA
| 4 | Hard coding of Name for confirmations
Scheduling/Allocations/Settlements
| 1 | Bridge Error-Feedback monitor training | Kathryn Bussell EO |  | 2001-05-01
| 2 | Bridge to Sitara not to trade blotter follow-up | Bob Hall EO | Steve Jackson | 2001-04-15
| 3 | Cash accounts amendment | Sandi Braband LG/Bob Hall EO |  | 2001-04-15
| 4 | Hard coding of Name for settlements | Chris Schomer IT |  | 2001-05-01
| 5 | HUB & EDI contracts after four months | Tommy Yanowski IT | Don Simpson | 2001-04-15
| 6 | Notice to counterparties on banking change | Bob Hall EO/Leslie Reeves EO | Steve Jackson | 2001-06-01
| 7 | Account reports and entries | Bob Hall/Bryce Baxter/Chris Schomer IT | Steve Jackson
| 8 | PeopleSoft interface | Chris Schomer IT
| 9 | Credit Data extract | Chris Schomer IT
Transportation Rates
| 1 | HPL transport rates through Sitara only | Kim Olinger EO/Matt Pena IT |  | 2001-05-01
| 2 | Security for transport rates | Kim Olinger EO/Matt Pena IT |  | 2001-05-01
MISC
| 1 | Operational Data Web Site amendment to service agmt | Mike Eiben EO/Tommy Yanowski IT |  | 2001-05-01
| 2 | Tariff filing system amendment to service agmt | Mike Eiben EO/Tommy Yanowski IT |  | 2001-05-01
| 3 | A/R collections after close | Leslie Reeves EO/Bryce Baxter EO |  | 2001-04-30
| 4 | Deals done on Third party pipelines | Bob Hall/Ed Gottlob | Steve Jackson
| 5 | Lotus notes and Spreadsheet | Tommy Yanowski/Cheryl Dudley
Training
| 1 | Training before close | Tommy Yanowski | Steve Jackson
| 2 | Training after close | Bob Hall | Steve Jackson
Security
| 1 | Request Process for additions/deletions and changes for AEP | Tommy Yanowski
| 2 | Super Users after close (issue resolution/training/help) | Bob Hall/Tommy Yanowski
Mini - Month
| 1 | Testing Environments | Matt Pena IT
Key: | IT Information Services
EO Energy Operations
LG Legal
PS Producers Services