## Sheet1
CLEC Licensing and Interconnection Agreement Negotiation
GA Outside Expenses: Legal Fees
TOTAL
CLEC Licensing* |  |  |  |  | 75000
| Spent to date |  |  |  | 75000
| Additional Cost |  |  |  | 0
Interconnection Agreements**
|  | Investigation of |  | Finalize Agreement/
|  | Available Agreements | Negotiation of Terms | File for Approval | TOTAL
| Verizon | 35500 | 18000 | 25000 | 78500
| BellSouth | 10000 | 10000 | 15000 | 35000
| Sprint |  |  | 12000 | 12000
| SBC | 38000 | 10000 | 20000 | 68000
| Qwest | 20000 | 9000 | 20000 | 49000
| Subtotal | 103500 | 47000 | 92000 | 242500
| Spent to date |  |  |  | 140000
| Additional Cost |  |  |  | 102500
GA Internal Resources to complete Interconnection: |  |  |  | 3 people | 2 months
Trading Desk Resources to complete Interconnection: |  |  |  | 2-3 people | 2-3 days/month
(assumes 1 trip/month to Washington, D.C. for 3 months)
* Applications for CLEC Licenses filed in NY, NJ, MA, DC, PA, VA, GA, FL, LA, TX, IL, CA, OR, WA, NV, UT.
All have been approved except NJ, VA and GA. See CLEC Licensing Status.
**Interconnection agreements have been pursued in the above-referenced states plus CO.