## Sheet1
Project Doorstep
Chicago - Metals
Observation | Current Status | Action Plan/Follow up | Person responsible | Time Line
No master agreements with counter-parties | Currently, NY office is sending out contracts and confirmations for all Chicago activity. | Legal Dept. (Houston) have reviewed confirms sent out on Agency business and are in the process of creating General Terms Condition and Master Counter-party agreements for non Agency activity. | Alan Aronowitz | To be determined
Individual responsible for invoicing and traffic function is also authorized to trade. | All invoicing is now done out of the NY office. One accountant who performs some coordination funtions now reports directly to Lou Colarusso in the NY office. | Sytem upgrades to the AS 400 will provide stronger controls of the invoicing process out of NY. | Marcelo Parra | 2001-04-01
Sales agents are used in several foreign locations without written contracts. | The sales agents are being identified and information will be provided to the Tax group in London. | The London Tax Dept. is in the process of formalizing agreements for all Metals Agents. | Naomi Connell / Tina Ward | To be provided by Tax group
Observation | Current Status | Action Plan/Follow up | Person responsible | Time Line
Open position limits and trader limits are not documented. | Position limits and trader limits have been communicated by Sam Hainsworth and Marcelo Parra to this office. Traders in Chicago are NOT permitted to take any positions without Sam's authorization effective November 1, 2000. | Follow up phone conversations with traders have taken place to assure compliance. This office will be an Agency office in January 2001 and all P/L will be managed out of London. | Sam Hainsworth | 2000-11-06
Overall credit function is weak. | Currently the Chicago office has access to AS 400 for all open commitments by counter-party. They also have access to SAP for receivable /aging by counter-party. Credit limit reports are provided by NY Credit. The aggregation of all three is how credit is controlled. | The SAP implementation in London will ultimately link to the Credit Aggregation System. This system will ultimately provide functional Customer Exposure Reports. | Credit: Tim Davies / Marcelo Parra Sytems: Michael Sweeny | 2001-04-01
Observation | Current Status | Action Plan/Follow up | Person responsible | Time Line
Telephone lines are not taped and traders execute deals from home. | Same | This office will relocate to an exisiting Enron Chicago trading office. All phone lines will be taped in new office. A global policy should be implemented for cell phone usage by traders. | Laura Luce (Chicago) /Toby Night (London) | ASAP - need input from responsible parties
Risk Management in NY does not provide the Chicago office with sufficient detail of position, P/L, etc.. | Currently the Chicago office has access to Positions reports via the AS 400. P/L is provided daily. | The P/L responsibility is in London for Prime Aluminum under Sam Hainsworth. NY is responsible for scrap under Sam Hainsworth with oversight from Joe Robertson. Sam and Joe both have access to full details of all activity and sign off on respective P/L's daily. | Sam Hainsworth | November 1,,2000
There are some trades not done in USD. Harry Zlotnick in Cash Management in NY hedges the exposure (ShW discussing with Trina in NY to determine if really true) | This Group does not typically deal in foreign currancy. There has not been any FX trades since March 2000 and none are expected. | A policy is in place that all FX hedging is done via our Houston cash management group headed by Mary Perkins. | Harry Zlotnick | Done
Observation | Current Status | Action Plan/Follow up | Person responsible | Time Line
Stand alone access database does not interface with AS400 additionally, the AS400 does not give all needed information | The group uses an off system database to monitor and control Inventory. The system is designed to support logistics. | AS 400 system updates have been requested to eliminate the need for an off system database. | Michael Sweeny | Not before April 1, 2001