## Sheet2
Prepared by
|  | Energy Operations | EES Gas Solutions
Updated: 7/10/01
System |  | Activity |  | Point Person | Status | Due Date
Intramonth Goals
| 1 | Review Altra reporting |  | Jim Homco |  | 2001-07-31
| 2 | Develop Intramonth P&L/ Position reporting |  | Jim Homco |  | 2001-07-31
| 3 | Altra training |  | Jim Homco | In progress | 2001-07-31
| 4 | Establish procedures to ensure daily system updates and balancing |  | Jim Homco |  | 2001-07-31
Global Counterparty
| 1 | Validate and populate Industrial, Retail, and supply Counterparties |  | James Scribner
| 2 | Credit |  | Scott Mills
| 3 | Obtain list from Altra of Industrial customers - need file/table format |  | Jim Homco or Nagesh?
Global Facilities
| 1 | Validate and populate pipelines and facilities |  | Linda Bryan
Global Contracts
| 1 | Validate and populate contract data |  | Toby Ellis |  | 2001-09-30
| 2 | Find all contracts |  | Toby Ellis
| 3 | IT issue - CORP domain |  | Ramesh Rao
| 4 | Manpower |  | Toby Ellis
| 5 | Obtain contract list from Altra |  | Jim Homco or Nagesh?
| 6 | Bring process down to EWS (now with Legal) |  | Toby Ellis
| 7 | Can data be grouped into templates? |  | Linda Bryan
| 8 | Identify minimum data needed to set contracts up |  | Linda Bryan
Global Rates
| 1 |  |  | James Scribner
Risk/Deal Entry/Sitara
| 1 | Review deal ticket terms |  | Scott Mills
| 2 | Inactivate deals that net out |  | Scott Mills
| 3 | Identify mechanism to know when/what has been checked per deal |  | Scott Mills
| 4 | Establish environment |  | Scott Mills
| 5 | Set up EES as a desk |  | Scott Mills
| 6 | Enter all deals into Sitara |  | Scott Mills
| 7 | Provide Sitara training |  | Scott Mills
| 8 | Manpower |  | Scott Mills
Confirmations
| 1 | Block initial confirmations |  | Leslie Reeves
| 2 | Automate confirmations |  | Leslie Reeves
| 3 | Deal Validation process
Logistics
| 1 | Provide Unify training |  | Donna Greif
| 2 | Establish LDC's up/download capabilities |  | Donna Greif
| 3 | Procedures for PMAs |  | Donna Greif
| 4 | Set up EDI |  | Donna Greif
| 5 | Work with Utilities to provide greater customer detail |  | Donna Greif
| 6 | Conversion Issues |  | Donna Greif
| 8 | Meet with schedulers |  | Donna Greif
Transportation Rates
| 1 | Establish procedures and assign responsibilities |  | Donna Greif
| 2 | Obtain current rates list |  | Cathy Pittenger
| 3 | Obtain and populate Tariff rates |  | Donna Greif
Volume Management /Settlements
| 1 | Retrieve 1 month of invoices from CSC ( Altra only) |  | Bryce Baxter
| 2 | Identify pricing that will not fit into Sitara |  | Bryce Baxter
| 3 | Identify all "miscellaneous other costs" |  | Bryce Baxter
MISC
| 1 | IT concerns |  | Bob Hall
| 3 | CSC relationship |  | Brenda Herod
| 4 | SAP accounting issues |  | Bryce Baxter
| 5 | AVISTA - improve process |  | Cathy Pittenger
| 6 | Existing holes -- have they been addressed |  | Bob Hall
| 7 | Canada deals |  | Cathy Pittenger
Training
Security