## Equip Status
MASTER TURBINE LIST
Company | GT/ST/HRSG | Quantity | Manufacturer | Purchaser | On/Off Balance Sheet | BOP Purchased (Y/N) | Delivery Date(s) | Total Capex Commitment (MM USD) | Project(s) | Originator/Developer | Hz | Total MW @ ISO | Heat Rate | New/Used GT | Comments | Payment Dates & Amounts
ENA | LM6000 | 24 | GE | WLB | Off | Y - Transformers to be purchased from ABB via WLB | 1-3 7/00; 4-6 8/00; 7-8 9/00; 9-11 10/00; 12-13 11/00; 14-15 12/00; 16-18 1/01; 19-20 2/01; 21-22 3/01; 23-24 4/01 | 336 | 2 - Electrocities 4 - Las Vegas Co-Gen 4 - City of Austin 5 - Santee Cooper 6 - Peoples 4 - ENA Other 6 - East Kent Co-op | Miller | 60 | 1164 | 9805 | New
ENA | 501D5A | 1 | Westinghouse | ENA | On | N | 2000-05-30 | 24 | Electrocities, NC | Miller | 60 | 122 |  | New
ENA | 7FA; ST not yet ordered | 1 | GE | WLB | Off | N | 8 to 9/00 | 35 | Midwest/Peoples | Miller | 60 | 156 |  | New | One of orginal Cogen Tech GTs; WLB and Peoples have ADA between themselves | See attached worksheet
ENA | 7FA2 |  | GE | WLB | Off | N |  |  | Pastoria | Parquet | 60 | 750 |  | New
ENA | 7FA | 1 | GE | ENA | On | N | 2000-10-01 | 31 | Canada | Miller | 60 | 171 |  | New
ENA | 11N1 | 2 | ABB | WLB | Off | N | Available Now | 26 |  | Miller | 60 | 166 |  | Used
EECC | 501D5A | 1 | Westinghouse | CALME | On | N | 2001-11-01 | 24 | CALME Panama | Schultz/Barto | 60 | 122 |  | New |  | 90% pd to date; shipment (est 6/3) - 5%; COD (est 8/1) - 5%
EECC | 7FA; 1 - ST | 2 | GE | WLB3 | Off | N | 1 - 7/01; 1 - 8/01; ST 8/01 | 95 | GenPower | Barto | 60 | 600 |  | New |  | See attached worksheet
EECC | 7FA; 1 - ST | 2 | GE | WLB3 | Off | N | 1 - 9/01; 1 - 10/01; ST 9/01 | 95 | GenPower | Barto | 60 | 600 |  | New |  | See attached worksheet
EECC | 7FA; 1- ST2 | 2 | GE | EECC | On | N | 1 - 8/01; 1- 9/01; ST - 9/01 | 90 | 1 - ENA Coyote Springs 2; 1 - NEPCO NESCO | ENA - Thomas; EECC - Westfahl | 60 | 480 |  | New | aka NACO GTs | See attached worksheet
EECC | V94.2; ST; HRSG | 1 | Siemens; Toshiba ST & HRSG | EECC | On | N | 2001-11-01 | 64 | Croatia | Barto | 50 |  | 10083 | Used |  | 5% - manu release; 15% NTP; 15% 3 mos after NTP; 10% 6 mos after NTP; 20% delivery GT; 10% delieveru of generator; 5% delivery of PCC container; 15% completion of erection; 5% pass performance test
EECC | 9FA2 | 3 | GE | EECC3 | On | N | 1 - 10/01; 1 - 11/01; 1 - 12/01 | 249 | Arcos (Spain) | Barto | 50 | 780 | 10083 | New | Subject to Sutton Bridge Settlement; due to timining issues, Izzo has requested Enron to purchase on balance sheet
CALME | F6B Power Barges | 9 | GE | EI Powerbarge Co. |  | N | Available Now | 72 | 2 - LIPA | Baca | 60 | 270 | 12,500 - 13,000 | Used
CALME | F6B | 2 | GEC | ENA | On | N | Available Now | 13 |  | Miller | 60 | 60 |  | Used
ESA | 501F | 2 | Mitsubishi | WLB | Off4 | N | 1- 7/01; 1 - 8/01 | 70 | Riogen | Wiggs | 60 | 368 |  | New
ESA | 501F1 | 2 | Mitsubishi | WLB | Off3,4 | N | 1 - 5/01; 1 - 10/01 | 75 | Cuiaba II or Riogen Expansion | Wiggs | 60 | 368 |  | New
ESA | 7EA2 | 2 | GE | WLB | Off3,4 | N | 1 - 2/01; 1 - 2/02 | 36 | Puerto Suarez | Wiggs | 60 | 156 | 10730 | New |  | See attached worksheet
Enron Europe
APACHI
1ESA has option on these units which it expects to exercise 4/00 or 5/00
2Definitve agreement being negotiated
3Not officially in WLB but currently being sized for WLB
4ESA is currently negotiating a separate WLB-type facility for its projects

## NACO Pmt Schedule
est.
| FY | [7 empty] | 98 | Actual | Actual | Actual | Actual | Actual | Actual | Actual | [5 empty] | 1999 | [12 empty] | 2000 | [10 empty] | 2001 | GRAND | FY
| 1998 |  | July | Aug | Sept | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Total | TOTAL | 2001
NACO - GE 7FA |  | 0.5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550000 | 0 | 0 | 0 | 1550000 | 3100000 | 0 | 310000 | 310000 | 310000 | 310000 | 310000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 10850000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 3100000 | 3100000 | 1550000 | 5000000 | 22050000 | 36000000
Annual Cumulative Total | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550000 | 1550000 | 1550000 | 1550000 | 3100000 |  | 0 | 310000 | 620000 | 930000 | 1240000 | 1550000 | 3100000 | 4650000 | 6200000 | 7750000 | 9300000 | 10850000 |  | 1550000 | 3100000 | 4650000 | 6200000 | 7750000 | 9300000 | 12400000 | 15500000 | 17050000 | 22050000
NACO - GE 7FA |  | 0.5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550000 | 0 | 0 | 0 | 1550000 | 3100000 | 0 | 310000 | 310000 | 310000 | 310000 | 310000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 10850000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 1550000 | 3100000 | 3100000 | 1550000 | 5000000 | 22050000 | 36000000
Annual Cumulative Total | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1550000 | 1550000 | 1550000 | 1550000 | 3100000 |  | 0 | 310000 | 620000 | 930000 | 1240000 | 1550000 | 3100000 | 4650000 | 6200000 | 7750000 | 9300000 | 10850000 |  | 1550000 | 3100000 | 4650000 | 6200000 | 7750000 | 9300000 | 12400000 | 15500000 | 17050000 | 22050000
Reheat Steam Turbine Generator | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 0 | 0 | 500000 | 0 | 0 | 252000 | 0 | 0 | 252000 | 0 | 0 | 252000 | 2200000 | 900000 | 900000 | 4756000 | 900000 | 504000 | 990000 | 1170000 | 1170000 | 1170000 | 1170000 | 1170000 | 3600000 | 900000 | 12744000 | 18000000
Annual Cumulative Total | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 500000 | 500000 | 500000 | 500000 | 500000 |  | 0 | 0 | 252000 | 252000 | 252000 | 504000 | 504000 | 504000 | 756000 | 2956000 | 3856000 | 4756000 |  | 900000 | 1404000 | 2394000 | 3564000 | 4734000 | 5904000 | 7074000 | 8244000 | 11844000 | 12744000
0
Total Cumulative Capital Expenditures | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3600000 | 3600000 | 3600000 | 3600000 | 6700000 | 6700000 | 0 | 620000 | 1492000 | 2112000 | 2732000 | 3604000 | 6704000 | 9804000 | 13156000 | 18456000 | 22456000 | 26456000 | 26456000 | 4000000 | 7604000 | 11694000 | 15964000 | 20234000 | 24504000 | 31874000 | 39244000 | 45944000 | 45944000 | 56844000 | 90000000 | 0
Capitalized Interest | FY |  | 98 Total: 1998; 1999 Total: 1999; 2000 Total: 2000 | 2001 | GRAND | FY
| 1998 |  | July | Aug | Sept | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Total | TOTAL | 2001
6.5% Interest Rate
NACO - GE 7FA | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4197.9167 | 8418.572 | 8464.1726 | 8510.0202 | 12754.0329 | 42344.7145 | 17021.0339 | 17952.8145 | 19729.2255 | 21515.2589 | 23310.9665 | 25116.4009 | 30289.9481 | 38849.852 | 47456.122 | 56109.0093 | 64808.7665 | 73555.6473 | 435715.0453 | 82349.907 | 91191.8024 | 100081.5913 | 109019.5332 | 118005.889 | 127040.9209 | 140322.8093 | 157874.5578 | 171323.4617 | 189991.0471 | 1287201.5198 | 1765261.2795
Annual Cumulative Total | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4197.9167 | 12616.4887 | 21080.6614 | 29590.6816 | 42344.7145 |  | 17021.0339 | 34973.8483 | 54703.0739 | 76218.3327 | 99529.2992 | 124645.7002 | 154935.6482 | 193785.5002 | 241241.6222 | 297350.6315 | 362159.398 | 435715.0453 |  | 82349.907 | 173541.7094 | 273623.3007 | 382642.8339 | 500648.723 | 627689.6439 | 768012.4532 | 925887.011 | 1097210.4727 | 1287201.5198
NACO - GE 7FA | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4197.9167 | 8418.572 | 8464.1726 | 8510.0202 | 12754.0329 | 42344.7145 | 17021.0339 | 17952.8145 | 19729.2255 | 21515.2589 | 23310.9665 | 25116.4009 | 30289.9481 | 38849.852 | 47456.122 | 56109.0093 | 64808.7665 | 73555.6473 | 435715.0453 | 82349.907 | 91191.8024 | 100081.5913 | 109019.5332 | 118005.889 | 127040.9209 | 140322.8093 | 157874.5578 | 171323.4617 | 189991.0471 | 1287201.5198 | 1765261.2795
Annual Cumulative Total | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4197.9167 | 12616.4887 | 21080.6614 | 29590.6816 | 42344.7145 |  | 17021.0339 | 34973.8483 | 54703.0739 | 76218.3327 | 99529.2992 | 124645.7002 | 154935.6482 | 193785.5002 | 241241.6222 | 297350.6315 | 362159.398 | 435715.0453 |  | 82349.907 | 173541.7094 | 273623.3007 | 382642.8339 | 500648.723 | 627689.6439 | 768012.4532 | 925887.011 | 1097210.4727 | 1287201.5198
Reheat Steam Turbine Generator | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1354.1667 | 2715.6684 | 2730.3783 | 2745.1678 | 2760.0375 | 12305.4186 | 2774.9877 | 2790.0189 | 3487.6315 | 4189.0228 | 4211.7133 | 4917.0268 | 5626.1607 | 5656.6357 | 6369.7758 | 13045.1121 | 21511.6065 | 26503.1277 | 101082.8195 | 31521.6863 | 35494.9288 | 39733.443 | 45798.6658 | 52384.2419 | 59005.4899 | 65662.6029 | 72355.7754 | 85666.4525 | 98317.9791 | 585941.2653 | 699329.5035
Annual Cumulative Total | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1354.1667 | 4069.8351 | 6800.2133 | 9545.3812 | 12305.4186 |  | 2774.9877 | 5565.0066 | 9052.638 | 13241.6608 | 17453.3742 | 22370.401 | 27996.5617 | 33653.1974 | 40022.9732 | 53068.0853 | 74579.6918 | 101082.8195 |  | 31521.6863 | 67016.615 | 106750.058 | 152548.7238 | 204932.9657 | 263938.4555 | 329601.0584 | 401956.8338 | 487623.2863 | 585941.2653
Total Cumulative IDC |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9750 | 29302.8125 | 48961.5361 | 68726.7444 | 96994.8476 | 96994.8476 | 36817.0554 | 75512.7032 | 118458.7858 | 165678.3263 | 216511.9727 | 271661.8013 | 337867.8581 | 421224.1978 | 522506.2176 | 647769.3484 | 798898.4878 | 972512.91 | 972512.91 | 196221.5004 | 414100.0338 | 653996.6594 | 917834.3916 | 1206230.4116 | 1519317.7434 | 1865625.9648 | 2253730.8558 | 2682044.2316 | 3160344.3049 | 3160344.3049 | 4229852.0625
Calculation of Cost Basis |  |  | 1999 Total: As of 1999; 2000 Total: As of 2000 | As of 2001
Contract Amount = $80,000,000 | [9 empty] | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Total | TOTAL
7FA Cost = $36,000,000
Interest to date (FASB 34 para. 8) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4197.9167 | 12616.4887 | 21080.6614 | 29590.6816 | 42344.7145 | 42344.7145 | 59365.7483 | 77318.5628 | 97047.7884 | 118563.0472 | 141874.0137 | 166990.4146 | 197280.3627 | 236130.2147 | 283586.3367 | 339695.346 | 404504.1124 | 478059.7597 | 478059.7597 | 560409.6668 | 651601.4691 | 751683.0604 | 860702.5937 | 978708.4827 | 1105749.4036 | 1246072.2129 | 1403946.7707 | 1575270.2324 | 1765261.2795 | 1765261.2795
Total Cost Basis | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1554197.9167 | 1562616.4887 | 1571080.6614 | 1579590.6816 | 3142344.7145 | 3142344.7145 | 3159365.7483 | 3487318.5628 | 3817047.7884 | 4148563.0472 | 4481874.0137 | 4816990.4146 | 6397280.3627 | 7986130.2147 | 9583586.3367 | 11189695.346 | 12804504.1124 | 14428059.7597 | 14428059.7597 | 16060409.6668 | 17701601.4691 | 19351683.0604 | 21010702.5937 | 22678708.4827 | 24355749.4036 | 27596072.2129 | 30853946.7707 | 32575270.2324 | 37765261.2795 | 37765261.2795 | 37765261.2795
Interest to date (FASB 34 para. 8) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4197.9167 | 12616.4887 | 21080.6614 | 29590.6816 | 42344.7145 | 42344.7145 | 59365.7483 | 77318.5628 | 97047.7884 | 118563.0472 | 141874.0137 | 166990.4146 | 197280.3627 | 236130.2147 | 283586.3367 | 339695.346 | 404504.1124 | 478059.7597 | 478059.7597 | 560409.6668 | 651601.4691 | 751683.0604 | 860702.5937 | 978708.4827 | 1105749.4036 | 1246072.2129 | 1403946.7707 | 1575270.2324 | 1765261.2795 | 1765261.2795
Total Cost Basis | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1554197.9167 | 1562616.4887 | 1571080.6614 | 1579590.6816 | 3142344.7145 | 3142344.7145 | 3159365.7483 | 3487318.5628 | 3817047.7884 | 4148563.0472 | 4481874.0137 | 4816990.4146 | 6397280.3627 | 7986130.2147 | 9583586.3367 | 11189695.346 | 12804504.1124 | 14428059.7597 | 14428059.7597 | 16060409.6668 | 17701601.4691 | 19351683.0604 | 21010702.5937 | 22678708.4827 | 24355749.4036 | 27596072.2129 | 30853946.7707 | 32575270.2324 | 37765261.2795 | 37765261.2795 | 37765261.2795
Steam Turbine Cost = $18,000,000
Interest to date (FASB 34 para. 8) | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1354.1667 | 4069.8351 | 6800.2133 | 9545.3812 | 12305.4186 | 12305.4186 | 15080.4063 | 17870.4252 | 21358.0567 | 25547.0795 | 29758.7928 | 34675.8196 | 40301.9803 | 45958.616 | 52328.3919 | 65373.504 | 86885.1105 | 113388.2382 | 113388.2382 | 144909.9244 | 180404.8532 | 220138.2962 | 265936.9619 | 318321.2038 | 377326.6937 | 442989.2966 | 515345.0719 | 601011.5244 | 699329.5035 | 699329.5035
Total Cost Basis | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 501354.1667 | 504069.8351 | 506800.2133 | 509545.3812 | 512305.4186 | 512305.4186 | 515080.4063 | 517870.4252 | 773358.0567 | 777547.0795 | 781758.7928 | 1038675.8196 | 1044301.9803 | 1049958.616 | 1308328.3919 | 3521373.504 | 4442885.1105 | 5369388.2382 | 5369388.2382 | 6300909.9244 | 6840404.8532 | 7870138.2962 | 9085936.9619 | 10308321.2038 | 11537326.6937 | 12772989.2966 | 14015345.0719 | 17701011.5244 | 18699329.5035 | 18699329.5035 | 18699329.5035
[10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3609750 | 3629302.8125 | 3648961.5361 | 3668726.7444 | 6796994.8476 | 6796994.8476 | 6833811.903 | 7492507.5508 | 8407453.6334 | 9074673.1739 | 9745506.8203 | 10672656.6489 | 13838862.7057 | 17022219.0454 | 20475501.0652 | 25900764.196 | 30051893.3354 | 34225507.7576 | 35295015.5152 | 38421729.258 | 42243607.7914 | 46573504.417 | 51107342.1492 | 55665738.1692 | 60248825.501 | 67965133.7224 | 75723238.6134 | 82851551.9892 | 94229852.0625 | 94229852.0625 | 94229852.0625
Revised Capitalized Interest for Fulton
|  |  | July | August | September | October | November
Project 2000 |  |  | 2687500
Brownsville |  |  | 3333.33 | 24298.91 | 7926.76 | 47888.09 | 16336.78
Caledonia |  |  | 3333.33 | 24298.91 | 7926.76 | 47888.09 | 16336.78
New Albany |  |  | 3333.34 | 146425.28 | 8265878 | 14136754.36 | 1666502.89
Fulton |  |  |  | 184304.25 | 116097.12 | 35412.8 | 221406.29
Interest Calculation
|  |  |  | July | Aug | Sept | Oct
Project 2000 |  |  |  | 22395.8333 | 22395.8333 | 22395.8333 | 22395.8333
Brownsville |  |  |  | 27.7778 | 230.2687 | 296.325 | 695.3924
Caledonia |  |  |  | 27.7778 | 230.2687 | 296.325 | 695.3924
New Albany |  |  |  | 27.7778 | 1247.9885 | 70130.3052 | 187936.5915
Fulton |  |  |  | 0 | 1535.8688 | 2503.3448 | 2798.4514
Total to Reclass from Fulton => |  |  |  | 22479.1667 | 24104.3592 | 93118.7885 | 211723.2097
Note on A4: Jody Pierce: Assumes 50% of each STG payment applies.
Note on A7: Jody Pierce: Assumes 50% of each STG payment applies.
Note on A10: Jody Pierce: Assumes 20% of each payment applies. Calculated as 18 million for Steam Turbine div by 90 million total equals 20%
Note on AT4: tshepperd: balance due EECC/EES for Sutton Bridge Settlement
Note on AT7: tshepperd: Balance due EECC/EES for Sutton Bridge Settlement

## GenPower (Dell) Pmt Schedule
EECC
Payment Schedules
Dell Site
| Invoice | Payment | [7 empty] | Monthly | Cumulative
| Month | Due Date | Event | GT 1 | GT 1 $$$ | GT2 | GT 2 $$$ | Stm 1 | Stm 1 $$$ | $$$ | $$$
| 2000-03-01 | 2000-03-01 | Signed LOC | 8.6% | 3165121.64 | 8.5% | 3128317.9 | 8.34% | 1794978.168 | 8088417.708 | 8088417.708
| 2000-03-01 | April 22 - 00 | Progress Payment | 1.8% | 662467.32 | 1.75% | 644065.45 | 1.67% | 359426.084 | 1665958.854 | 9754376.562
| 2000-04-01 | May 22 - 00 | Progress Payment | 1.85% | 680869.19 | 1.75% | 644065.45 | 1.67% | 359426.084 | 1684360.724 | 11438737.286
| 2000-05-01 | June 22 - 00 | Progress Payment | 1.85% | 680869.19 | 1.75% | 644065.45 | 1.67% | 359426.084 | 1684360.724 | 13123098.01
| 2000-06-01 | July 22 - 00 | Progress Payment | 1.9% | 699271.06 | 1.75% | 644065.45 | 1.67% | 359426.084 | 1702762.594 | 14825860.604
| 2000-07-01 | Aug 22 - 00 | Progress Payment | 19.9% | 7323944.26 | 19% | 6992710.6 | 18.32% | 3942925.664 | 18259580.524 | 33085441.128
| 2000-08-01 | Sept 22 - 00 | Progress Payment | 3% | 1104112.2 | 2.5% | 920093.5 | 2.56% | 550976.512 | 2575182.212 | 35660623.34
| 2000-09-01 | Oct 22 - 00 | Progress Payment | 3% | 1104112.2 | 2.5% | 920093.5 | 3% | 645675.6 | 2669881.3 | 38330504.64
| 2000-10-01 | Nov 22 - 00 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 41184404.64
| 2000-11-01 | Dec 22 - 00 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 44038304.64
| 2000-12-01 | Jan 22 - 01 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 46892204.64
| 2001-01-01 | Feb 22 - 01 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 49746104.64
| 2001-02-01 | Mar 22 - 01 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 52600004.64
| 2001-03-01 | April 22 - 01 | Progress Payment | 3% | 1104112.2 | 3% | 1104112.2 | 3% | 645675.6 | 2853900 | 55453904.64
| 2001-04-01 | May 22 - 01 | Progress Payment | 3.1% | 1140915.94 | 3% | 1104112.2 | 3% | 645675.6 | 2890703.74 | 58344608.38
| 2001-05-01 | June 22 - 01 | Progress Payment | 4% | 1472149.6 | 3% | 1104112.2 | 3.1% | 667198.12 | 3243459.92 | 61588068.3
| 2001-06-01 | July 22 - 01 | Progress Payment | 4% | 1472149.6 | 3.5% | 1288130.9 | 3.5% | 753288.2 | 3513568.7 | 65101637
| 2001-07-01 | Aug 22 - 01 | Progress Payment | 4% | 1472149.6 | 4% | 1472149.6 | 3.5% | 753288.2 | 3697587.4 | 68799224.4
| 2001-08-01 | Sept 22 - 01 | GT 1 - STM Shipment | 20% | 7360748 | 4% | 1472149.6 | 25% | 5380630 | 14213527.6 | 83012752
| 2001-09-01 | Oct 22 - 01 | GT 2 Shipment | 5% | 1840187 | 20% | 7360748 | 5% | 1076126 | 10277061 | 93289813
| 2001-10-01 | Nov 22 - 01 | 30 Days After Shipment | 0% | 0 | 5% | 1840187 | 0% | 0 | 1840187 | 95130000
| Total Sales |  |  | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
|  |  |  | 36803740 |  | 36803740 |  | 21522520
| IPS # 91021 |  | Notes:
| 2000-03-06 |  | Payment
The initial payment is due within 3 days of signed Letter of Credit
Progress Payments are due on the 22nd of the indicated month and will be billed 30 days in advance.( Except for the February Payments)
Payments tied to shipment of equipment are due net 15 days after receipt of invoice and certification that equipment has shipped.
August reflects repayment of deferred amounts from February through July 2000.
EECC
Termination Schedules
Dell Site
Cumulative
| Month |  | Termination | GT 1 | GT 1 $$$ | GT2 | GT 2 $$$ | Stm 1 | Stm 1 $$$ | $$$
| 2000-03-01 |  | Signed LOC | 10.4% | 3827588.96 | 10.4% | 3827588.96 | 5% | 1076126 | 8731303.92
| 2000-04-01 |  |  | 10.8% | 3974803.92 | 10.8% | 3974803.92 | 5% | 1076126 | 9025733.84
| 2000-05-01 |  |  | 11.1% | 4085215.14 | 11.1% | 4085215.14 | 5% | 1076126 | 9246556.28
| Jun 15 -00 |  |  | 14.8% | 5446953.52 | 14.8% | 5446953.52 | 5% | 1076126 | 11970033.04
| Jun 16 -00 |  |  | 14.8% | 5446953.52 | 14.8% | 5446953.52 | 10% | 2152252 | 13046159.04
| 2000-07-01 |  |  | 20% | 7360748 | 20% | 7360748 | 15% | 3228378 | 17949874
| 2000-08-01 |  |  | 30% | 11041122 | 30% | 11041122 | 20% | 4304504 | 26386748
| 2000-09-01 |  |  | 32% | 11777196.8 | 32% | 11777196.8 | 24% | 5165404.8 | 28719798.4
| 2000-10-01 |  |  | 34% | 12513271.6 | 34% | 12513271.6 | 28% | 6026305.6 | 31052848.8
| 2000-11-01 |  |  | 36% | 13249346.4 | 36% | 13249346.4 | 40% | 8609008 | 35107700.8
| 2000-12-01 |  |  | 38% | 13985421.2 | 40% | 14721496 | 51% | 10976485.2 | 39683402.4
| 2001-01-01 |  |  | 40% | 14721496 | 40% | 14721496 | 59% | 12698286.8 | 42141278.8
| 2001-02-01 |  |  | 40% | 14721496 | 40% | 14721496 | 70% | 15065764 | 44508756
| 2001-03-01 |  |  | 40% | 14721496 | 40% | 14721496 | 80% | 17218016 | 46661008
| 2001-04-01 |  |  | 40% | 14721496 | 40% | 14721496 | 83% | 17863691.6 | 47306683.6
| 2001-05-01 |  |  | 40% | 14721496 | 40% | 14721496 | 87% | 18724592.4 | 48167584.4
| 2001-06-01 |  |  | 40% | 14721496 | 40% | 14721496 | 93% | 20015943.6 | 49458935.6
| 2001-07-01 |  |  | 40% | 14721496 | 40% | 14721496 | 95% | 20446394 | 49889386
| 2001-08-01 |  |  | 40% | 14721496 | 40% | 14721496 | 98% | 21092069.6 | 50535061.6
| 2001-09-01 |  | GT 1 - STM Shipment | 100% | 36803740 | 40% | 14721496 | 100% | 21522520 | 73047756
| 2001-10-01 |  | GT 2 Shipment | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
| 2001-11-01 |  | 30 Days After Shipment | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
| IPS # 91021 |  | Notes:
2000-03-06
Termination
The buyer may terminate this agreement at any time upon written notification and payment of
termination charges in accordance with the schedule set forth above.
Title to any terminated combustion turbine-generator equipment or accessories remains
with the Seller.
The termination charge for any equipment for which title has transferred is 100%.
Upon Financial Closure EEPC is responsible for 100% of the termination charges.

## Peoples Pmt Schedule
Payment Date | Payments from WestLB to GE
1999-12-31 | 0
2000-01-05 | 2529455.29
2000-02-22 | 0
2000-03-20 | 2529455.29
2000-04-20 | 2529455.29
2000-05-22 | 2529455.29
2000-06-20 | 2529455.29
2000-07-20 | 2529455.29
2000-08-21 | 6485782.8
2000-09-20 | 10766399.45
Total | 32428913.99

## GenPower (McAdams) Pmt Schedule
EECC
Payment Schedules
McAdams Site
| Invoice |  | Payment | [7 empty] | Monthly | Cumulative
| Month |  | Due Date | Event | GT 1 | GT 1 $$$ | GT2 | GT 2 $$$ | Stm 1 | Stm 1 $$$ | $$$ | $$$
| 2000-03-01 |  | 2000-03-22 | Signed LOC | 8.6% | 3165121.64 | 8.5% | 3128317.9 | 8.5% | 1829414.2 | 8122853.74 | 8122853.74
| 2000-03-01 |  | April 22 - 00 | Progress Payment | 1.8% | 662467.32 | 1.75% | 644065.45 | 1.75% | 376644.1 | 1683176.87 | 9806030.61
| 2000-04-01 |  | May 22 - 00 | Progress Payment | 1.85% | 680869.19 | 1.75% | 644065.45 | 1.77% | 380948.604 | 1705883.244 | 11511913.854
| 2000-05-01 |  | June 22 - 00 | Progress Payment | 1.85% | 680869.19 | 1.75% | 644065.45 | 1.77% | 380948.604 | 1705883.244 | 13217797.098
| 2000-06-01 |  | July 22 - 00 | Progress Payment | 1.9% | 699271.06 | 1.75% | 644065.45 | 1.79% | 385253.108 | 1728589.618 | 14946386.716
| 2000-07-01 |  | Aug 22 - 00 | Progress Payment | 19.9% | 7323944.26 | 19% | 6992710.6 | 19.2% | 4132323.84 | 18448978.7 | 33395365.416
| 2000-08-01 |  | Sept 22 - 00 | Progress Payment | 3.8% | 1398542.12 | 3.5% | 1288130.9 | 3.55% | 764049.46 | 3450722.48 | 36846087.896
| 2000-09-01 |  | Oct 22 - 00 | Progress Payment | 3.8% | 1398542.12 | 3.5% | 1288130.9 | 3.58% | 770506.216 | 3457179.236 | 40303267.132
| 2000-10-01 |  | Nov 22 - 00 | Progress Payment | 3.9% | 1435345.86 | 3.5% | 1288130.9 | 3.62% | 779115.224 | 3502591.984 | 43805859.116
| 2000-11-01 |  | Dec 22 - 00 | Progress Payment | 3.9% | 1435345.86 | 3.6% | 1324934.64 | 3.66% | 787724.232 | 3548004.732 | 47353863.848
| 2000-12-01 |  | Jan 22 - 01 | Progress Payment | 3.9% | 1435345.86 | 3.6% | 1324934.64 | 3.66% | 787724.232 | 3548004.732 | 50901868.58
| 2001-01-01 |  | Feb 22 - 01 | Progress Payment | 3.9% | 1435345.86 | 3.7% | 1361738.38 | 3.7% | 796333.24 | 3593417.48 | 54495286.06
| 2001-02-01 |  | Mar 22 - 01 | Progress Payment | 3.9% | 1435345.86 | 3.7% | 1361738.38 | 3.7% | 796333.24 | 3593417.48 | 58088703.54
| 2001-03-01 |  | April 22 - 01 | Progress Payment | 4% | 1472149.6 | 3.7% | 1361738.38 | 3.74% | 804942.248 | 3638830.228 | 61727533.768
| 2001-04-01 |  | May 22 - 01 | Progress Payment | 4% | 1472149.6 | 3.7% | 1361738.38 | 3.74% | 804942.248 | 3638830.228 | 65366363.996
| 2001-05-01 |  | June 22 - 01 | Progress Payment | 4% | 1472149.6 | 4% | 1472149.6 | 3.85% | 828617.02 | 3772916.22 | 69139280.216
| 2001-06-01 |  | July 22 - 01 | Gas 1 Shipment | 20% | 7360748 | 4% | 1472149.6 | 10.07% | 2167317.764 | 11000215.364 | 80139495.58
| 2001-07-01 |  | Aug 22 - 01 | Gas 2 / Steam Shipment | 5% | 1840187 | 20% | 7360748 | 15.29% | 3290793.308 | 12491728.308 | 92631223.888
| 2001-08-01 |  | Sept 22 - 01 | 30 Days After Shipment | 0% | 0 | 5% | 1840187 | 3.06% | 658589.112 | 2498776.112 | 95130000
| Total Sales |  |  |  | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
[5 empty] | 36803740 |  | 36803740 |  | 21522520 |  | 95130000 | 190260000
| IPS # 90070 |  |  | Notes:
| 2000-03-06 |  |  | Payment
The initial payment is due within 3 days of signed Letter of Credit
Progress Payments are due on the 22th of the indicated month and will be billed 30 days in advance.( Except for the February Payments)
Payments tied to shipment of equipment are due net 15 days after receipt of invoice and certification that equipment has shipped.
August reflects repayment of deferred amounts from February through July 2000.
EECC
Termination Schedules
McAdams Site
Cumulative
|  | Month |  | Termination | GT 1 | GT 1 $$$ | GT2 | GT 2 $$$ | Stm 1 | Stm 1 $$$ | $$$
|  | 2000-03-01 |  | Signed LOC | 10.4% | 3827588.96 | 10.4% | 3827588.96 | 5% | 1076126 | 8731303.92
|  | 2000-04-01 |  |  | 10.8% | 3974803.92 | 10.8% | 3974803.92 | 5% | 1076126 | 9025733.84
|  | 2000-05-01 |  |  | 11.1% | 4085215.14 | 11.1% | 4085215.14 | 5% | 1076126 | 9246556.28
|  | Jun 15 -00 |  |  | 14.8% | 5446953.52 | 14.8% | 5446953.52 | 5% | 1076126 | 11970033.04
|  | Jun 16 -00 |  |  | 14.8% | 5446953.52 | 114.8% | 42250693.52 | 11% | 2367477.2 | 50065124.24
|  | 2000-07-01 |  |  | 20% | 7360748 | 20% | 7360748 | 12% | 2582702.4 | 17304198.4
|  | 2000-08-01 |  |  | 30% | 11041122 | 30% | 11041122 | 15% | 3228378 | 25310622
|  | 2000-09-01 |  |  | 32% | 11777196.8 | 32% | 11777196.8 | 25% | 5380630 | 28935023.6
|  | 2000-10-01 |  |  | 34% | 12513271.6 | 34% | 12513271.6 | 29% | 6241530.8 | 31268074
|  | 2000-11-01 |  |  | 36% | 13249346.4 | 36% | 13249346.4 | 40% | 8609008 | 35107700.8
|  | 2000-12-01 |  |  | 38% | 13985421.2 | 40% | 14721496 | 51% | 10976485.2 | 39683402.4
|  | 2001-01-01 |  |  | 40% | 14721496 | 40% | 14721496 | 59% | 12698286.8 | 42141278.8
|  | 2001-02-01 |  |  | 40% | 14721496 | 40% | 14721496 | 64% | 13774412.8 | 43217404.8
|  | 2001-03-01 |  |  | 40% | 14721496 | 40% | 14721496 | 76% | 16357115.2 | 45800107.2
|  | 2001-04-01 |  |  | 40% | 14721496 | 40% | 14721496 | 83% | 17863691.6 | 47306683.6
|  | 2001-05-01 |  |  | 40% | 14721496 | 40% | 14721496 | 86% | 18509367.2 | 47952359.2
|  | 2001-06-01 |  |  | 40% | 14721496 | 40% | 14721496 | 93% | 20015943.6 | 49458935.6
|  | 2001-07-01 |  | Gas 1 Shipment | 100% | 36803740 | 40% | 14721496 | 98% | 21092069.6 | 72617305.6
|  | 2001-08-01 |  | Gas 2 / Steam Shipment | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
|  | 2001-09-01 |  | 30 Days After Shipment | 100% | 36803740 | 100% | 36803740 | 100% | 21522520 | 95130000
[5 empty] | 36803740 |  | 36803740 |  | 21522520
IPS # 90070
| 2000-03-06 |  |  | Termination
The buyer may terminate this agreement at any time upon written notification and payment of
termination charges in accordance with the schedule set forth above.
Title to any terminated combustion turbine-generator equipment or accessories remains
with the Seller.
The termination charge for any equipment for which title has transferred is 100%.
Upon Financial Closure EECC is responsible for 100% of the termination charges.

## Arcos Pmt Schedule
IPS No. 90535 | Payment Schedule
Enron / Arcos de la Frontera
| Month |  | ($000's) | %
MOU
Non-Refundable Down Payment | 2000-04-01 |  | 25025 | 10%
| 2000-04-25 |  | 9030.4 | 2%
| 2000-05-25 |  | 7193.85 | 3%
| 2000-06-25 |  | 7193.85 | 3%
| 2000-07-25 |  | 9591.8 | 4%
| 2000-08-25 |  | 11989.75 | 5%
| 2000-09-25 |  | 14387.7 | 6%
| 2000-10-25 |  | 11989.75 | 5%
| 2000-11-25 |  | 11989.75 | 5%
| 2000-12-25 |  | 11989.75 | 5%
| 2001-01-25 |  | 11989.75 | 5%
| 2001-02-25 |  | 11989.75 | 5%
| 2001-03-25 |  | 9591.8 | 4%
| 2001-04-25 |  | 7193.85 | 3%
| 2001-05-25 |  | 7193.85 | 3%
| 2001-06-25 |  | 7193.85 | 3%
| 2001-07-25 |  | 4795.9 | 2%
| 2001-08-25 |  | 4795.9 | 2%
| 2001-09-25 |  | 4795.9 | 2%
Ship GT1, ST1 | 2001-10-25 |  | 4795.9 | 2%
Ship GT2, ST2 | 2001-11-25 |  | 14387.7 | 6%
Ship GT3, ST3 | 2001-12-25 |  | 16785.65 | 7%
| 2002-01-25 |  | 14387.7 | 6%
| 2002-02-25 |  | 2397.95 | 1%
| 2002-03-25 |  | 2397.95 | 1%
|  |  | 239795 | 100%
245075
Down payment due net 3 days from contract signing / MOU via wire transfer
Progress payments due on 25th of each month
Payments tied to shipment due Net 30 days from receipt of invoice
TDI & Training payments not included in above schedule, and will be
|  | invoiced separately (terms: 10% down, remainder as performed) |  |  | . The current value of these Services is $10,455,000.00

## Puerto Suarez
Months from Purchase Agreement Execution
Calendar Month
7. Event
8. Milestone
Monthly % of CGT Price
Monthly Payment Total for Two (2) % of CTG Price
Cumulative Payment Total for Two (2) % of CTG Price |  |  |  | Monthly % of CTG Price
Motnhs From Date of Execution of Agreement | Calendar Month | Event | Milestone | CTG#1 | CTG#2 | Monthly Payment Total for Two (2) % of CTG Price | Cumulative Payment Total for Two (2) % of CTG Price
0 | Date of Execution of the Purchase Agreement | Monthly Progress Payment | Purchase Agreement Execution | 7.22% | 5% | 6.11% | 6.11%
1 | 2000-05-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 9.72%
2 | 2000-06-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 13.33%
3 | 2000-07-01 | Monthly Progress Payment |  | 7.22% | 5% | 6.11% | 19.44%
4 | 2000-08-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 23.05%
5 | 2000-09-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 26.66%
6 | 2000-10-01 | Monthly Progress Payment |  | 7.22% | 5% | 6.11% | 32.77%
7 | 2000-11-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 36.38%
8 | 2000-12-01 | Monthly Progress Payment |  | 7.22% |  | 3.61% | 39.99%
9 | 2000-01-01 | Monthly Progress Payment |  | 7.24% | 9% | 8.12% | 48.11%
10 | 2000-02-01 | Available to Ship CTG #1 EXW | Available to Ship CTG #1 EXW | 22.22% | 7% | 14.61% | 62.72%
11 | 2000-03-01 | Final Payment CTG #1 | CTG #1 FCA Port of Export | 5.56% | 6% | 5.78% | 68.5%
12 | 2000-04-01 | Monthly Progress Payment |  |  | 9% | 4.5% | 73%
13 | 2000-05-01 | Monthly Progress Payment |  |  | 7% | 3.5% | 76.5%
14 | 2000-06-01 | Monthly Progress Payment |  |  | 6% | 3% | 79.5%
15 | 2000-07-01 | Monthly Progress Payment |  |  | 4% | 2% | 81.5%
16 | 2000-08-01 | Monthly Progress Payment |  |  | 4% | 2% | 83.5%
17 | 2000-09-01 | Monthly Progress Payment |  |  | 3% | 1.5% | 85%
18 | 2000-10-01 | Monthly Progress Payment |  |  | 2.22% | 1.11% | 86.11%
19 | 2000-11-01 | Monthly Progress Payment |  |  |  | 0% | 86.11%
20 | 2000-12-01 | Monthly Progress Payment |  |  |  | 0% | 86.11%
21 | 2000-01-02 | Monthly Progress Payment |  |  |  | 0% | 86.11%
22 | 2000-02-02 | Available to Ship CTG #2 EXW | Available to Ship CTG #2 EXW |  | 22.22% | 11.11% | 97.22%
23 | 2000-03-02 | Final Payment CTG #2 | CTG #2 FCA Port of Export |  | 5.56% | 2.78% | 100%
24 | 2000-04-02 |  |  |  |  | 0% | 100%
|  | Total |  |  |  | Total |  | 100% | 100% | 100%