## Sheet1
Business Unit | POC | Deploy Tech | Deploy Lead | Floor | Users | PCs | Migration Planned | Outlook Team Notified | Pilot User Rolled | Outlook Rolled to Pilot | Migration Completed | Final Acceptance | Notes
Team Broncos Weekly Total of all Groups
April 2nd - 6th
Gas Group-ENW-EO-RM-Special Projects | John Valdes | Eric Zaal | Brian Davis |  | 1 | 1 | 2001-04-02 | 2001-03-23 | N/A | N/A | 2001-04-02 | 2001-04-02 | Melba Bowen
Gas Group-EO-RM-Texas and Central Gas Teams | Jeff Gossett | Chris Austin | Brian Davis |  | 13 | 18 | 2001-04-03 | 2001-03-26 | 2001-03-23 | N/A | 2001-04-04 | 2001-04-06
Gas Group-EO-RM-East and West Gas Teams | Jeff Gossett | Chris Austin | Brian Davis |  | 18 | 19 | 2001-04-03 | 2001-03-26 | 2001-03-23 | N/A | 2001-04-05 | 2001-04-10
ENA - West Power Trading - Origination | Chris Calger | Jason Sonnier | Steve Harrington | Portland | 0 | 2 | 2001-03-27 | 2001-04-11 | 2001-03-23 | N/A | 2001-03-30 | 2001-04-03
ENA - West Power Trading - Risk Management | Fran Chang | Jason Sonnier | Steve Harrington | Portland | 0 | 1 | 2001-03-26 | 2001-03-23 | 2001-03-23 | N/A | 2001-03-26 | 2001-03-28
ENA - West Power Trading - MidMarket | Chris Foster | Jason Sonnier | Steve Harrington | Portland | 2 | 2 | 2001-04-05 | 2001-04-11 | 2001-04-03 | N/A | 2001-04-09 | 2001-04-12
ENA - West Power Trading - Administration | David Steiner | Jason Sonnier | Steve Harrington | Portland | 0 | 1 | 2001-04-06 | 2001-04-11 | N/A | N/A | 2001-04-06 | 2001-04-06
ENA - West Power Trading - IT Development | David Poston | Jason Sonnier | Steve Harrington | Portland | 0 | 1 | 2001-04-06 | 2001-03-23 | 2001-03-23 | N/A | 2001-04-06 | 2001-04-06
ENA - West Power Trading - Trading | Tim Beldon | Jason Sonnier | Steve Harrington | Portland | 2 | 2 | 2001-04-05 | 2001-04-11 | 2001-04-04 | N/A | 2001-04-11 | 2001-04-12
ENA - West Power Trading - Scheduling | Cara Sempberger | Jason Sonnier | Steve Harrington | Portland | 5 | 5 | 2001-04-06 | 2001-04-11 | 2001-04-04 | N/A | 2001-04-06 | 2001-04-11
ENA - West Power Trading - Pwr Tech Analysis | Stan Gray | Jason Sonnier | Steve Harrington | Portland | 0 | 2 | 2001-03-30 | 2001-04-11 | N/A | N/A | 2001-04-09 | 2001-04-11
ENA - West Power Trading - Volume Management | Murray O'Neil | Jason Sonnier | Steve Harrington | Portland | 2 | 2 | 2001-04-05 | 2001-04-11 | 2001-04-03 | N/A | 2001-04-09 | 2001-04-11
ENA - West Power Trading - Real-Time | Jesse Bryson | Jason Sonnier | Steve Harrington | Portland | 11 | 4 | 2001-04-04 | 2001-04-11 | 2001-03-30 | N/A | 2001-04-04 | 2001-04-09
| Total |  |  |  | 54 | 60
April 9th - 13th
ENA - West Power Trading - Trading | Tim Beldon | Jason Sonnier | Steve Harrington | Portland | 12 | 12 | 2001-04-10 | 2001-04-11 | 2001-04-04 | N/A | 2001-04-11 | 2001-04-12
ENA - West Power Trading - Pwr Tech Analysis | Stan Gray | Jason Sonnier | Steve Harrington | Portland | 0 | 2 | 2001-03-30 | 2001-04-11 | N/A | N/A | 2001-04-09 | 2001-04-11
ENA - West Power Trading - West Power Admin | Emily Butler | Jason Sonnier | Steve Harrington | Portland | 0 | 1 | 2001-04-11 | 2001-04-11 | N/A | N/A | 2001-04-11 | 2001-03-28 | UPS PC for Emily
ENA - West Power Trading - MidMarket | David Steiner | Jason Sonnier | Steve Harrington | Portland | 5 | 5 | 2001-04-05 | 2001-04-11 | 2001-04-03 | N/A | 2001-04-09 | 2001-04-12
ENA - West Power Trading - Volume Management | Murray O'Neil | Jason Sonnier | Steve Harrington | Portland | 6 | 6 | 2001-04-09 | 2001-04-11 | 2001-04-03 | N/A | 2001-04-09 | 2001-04-11
ENW - Corporate Development | Pete Davis | Chris Austin | Brian Davis | 26 | 0 | 1 | 2001-04-09 | N/A | N/A | N/A | 2001-04-09 | N/A | travel laptop for developers
ENA - West Power Trading - Origination | Paul Kaufman | Jason Sonnier | Steve Harrington | Portland | 0 | 1 | 2001-04-10 | 2001-04-11 | 2001-03-23 | N/A | 2001-04-10 | N/A
ENA - West Power Trading - Origination | Steve Thome | Chris Austin | Brian Davis | 31 | 0 | 1 | 2001-04-09 | N/A | N/A | N/A | 2001-04-09 | N/A | West Pwr user in Houston
Gas Group-ENW-EO-Asset Ops & Mgmt | Heather Choate | Marcus Richards | Brian Davis |  | 7 | 9 | 2001-04-13 | 2001-04-09 | 2001-04-06 | N/A | 2001-04-13
Gas Group-EGM-GC&P-Products Trading | Ted Robinson | Bharat Mehta | Brian Davis |  | 8 | 13 | 2001-04-09 | 2001-03-26 | 2001-03-26 | N/A | 2001-04-09
ENA - West Power Trading - Fundamental Analysis | Robert Anderson | Jason Sonnier | Steve Harrington | Portland | 5 | 5 | 2001-04-09 | 2001-04-11 | 2001-04-03 | N/A | 2001-04-11
Gas Group-EO-RM-Finance and Administration | Jeff Gossett | Chris Austin | Brian Davis |  | 13 | 13 | 2001-04-04 | 2001-03-29 | 2001-03-23 | N/A | 2001-04-10
| Total |  |  |  | 56 | 69
April 16th - 21st
EGM-Financial Trading-Ag Trading and Origination | Gary Hickerson | Brandon Oliveira | Brian Davis |  | 13 |  | 2001-04-21
EGM-Financial Trading-Equity/FX and Currency | Gary Hickerson | Brandon Oliveira | Brian Davis |  | 27 |  | 2001-04-21
EGM-GP&C-Petrochemicals Trading | Doug Friedman | Patrick Marchand | Brian Davis |  | 8 |  | 2001-04-16 | 2001-03-22 | 2001-03-21
Gas Group-ECT-RC-Central Gas Trading | Airam Arteaga | Juan Jass | Brian Davis |  | 15 |  | 2001-04-20 |  |  | N/A
Gas Group-ECT-RC-Gas Financial Trading | Ina Rangel | Marcus Richards | Brian Davis |  | 9 |  | 2001-04-19
Gas Group-ECT-RC-Gas Fundamental Analysis | Amanda Huble | Juan Jass | Brian Davis |  | 13 |  | 2001-04-18 |  |  | N/A
Gas Group-ECT-RC-West Gas Origination | Jessica Presas | Marcus Richards | Brian Davis |  | 5 |  | 2001-04-19
Gas Group-EGM-GC&P-Crude Trading | Pavel Z | Bharat Mehta | Brian Davis |  | 10 |  | 2001-04-16 |  | 2001-04-03 | N/A
| Total |  |  |  | 100 | 0
April 23rd - 27th
Gas Group-ECT-RC-Mid Market Nymex | Becky Young | Juan Jass | Brian Davis |  | 14
| Total |  |  |  | 14 | 0
April 30th - May 4th
ENA-Power-Power Support-Power Confirms | Rhonda Denton | Brandon Oliveira | Brian Davis | 31 | 10 |  |  |  | 2001-03-21 | N/A
EGM-O&A-Interest Rate/FX and Equities | Sheila Glover | Brandon Oliveira | Brian Davis |  | 19
Gas Group-ECT-RC-East Gas Trading | Kimberly Brown | Kacee Downey | Brian Davis |  | 15
Gas Group-ECT-RC-East Gas Origination | Kimberly Brown | Kacee Downey | Brian Davis |  | 12
Gas Group-ECT-RC-West Gas Trading | Ina Rangel | Kacee Downey | Brian Davis |  | 12
| Total |  |  |  | 0 | 0
Monthly | Grand Total |  |  |  | 224 | 129