## interconnection status report
ILEC: Verizon
| Agreement Name / Agreement Type | Contract Term | Current Status / Accomplishments | Next Steps | Expected Date for PUC Submission | Expected PUC Approval Date | Collo Application Timeframe | Operational Date
NY | Level 3 (Opt-in with a Supplemental Agreement for pricing and specific UNEs) | Expires 9-30-02 (Negotiated) | Negotiated an extension of the arbitration windows in every state through January 2002. Last negotiation was November 7. Verizon forwarded its draft amendment language to Enron on November 7 for CA and VA. Verizon agreed to many of Enron's requests, which include, the ability to use a corporate guaranty as a form of security, the ability to limit audits to services provided under the agreement, limit insurance to the interests of the contract, and that assignment consent will not be unreasonably withheld. Enron stated its intent to have provisioning intervals established for CA agreement. Verizon stated that it would provide pricing for OC-n circuits that are not currently in the CA agreement. Verizon agreed to update the collocation language. Both parties agreed to have a final exchange of documents around Thanksgiving. | Follow-up with Verizon on issues relative to California and finalize the Level-3 amendments for the balance of the Verizon states. Expect to be able to conclude negotiations by end of November | November, 2001 | 2002-02-01 | Approximately 76 days | Verizon treats signature date as effective date; if collo not ready, January 2002.
NJ | Level 3 (Opt-in with a Supplemental Agreement for pricing and specific UNEs) | Expires 9-30-02 (Negotiated) | Same as above. | Same as above. | Same as above. | 2002-02-01 | Approximately 120 days | Verizon treats signature date as effective date; if collo not ready, March 2002.
PA | Level 3 (Opt-in with a Supplemental Agreement for pricing and specific UNEs) | Expires 9-30-02 (Negotiated) | Same as above. | Same as above. | Same as above. | 2002-01-01 | Approximately 120 days | Verizon treats signature date as effective date; if collo not ready, March 2002.
DC | Level 3 (Opt-in with a Supplemental Agreement for pricing and specific UNEs) | Expires 9-30-02 (Negotiated) | Same as above. | Same as above. | Same as above. | 2002-02-01 | Approximately 120 days | Verizon treats signature date as effective date; if collo not ready, March 2002.
VA | Level 3 (Opt-in with a Supplemental Agreement for pricing and specific UNEs) | Expires 9-30-02 (Negotiated) | Same as above. | Same as above. | Same as above. | 2002-03-01 | Approximately 120 days | Verizon treats signature date as effective date; if collo not ready, March 2002.
MA | Level 3 (Opt-in with a Supplemental Agreement for pricing and specific UNEs) | Expires 9-30-02 (Negotiated) | Same as above. | Same as above. | Same as above. | 2002-02-01 | Approximately 76 days | Verizon treats signature date as effective date; if collo not ready, January 2002.
CA (Los Angeles) | SPRINT-GTE (Opt-in or Negotiated with a Supplemental Agreement for pricing and specific UNEs | Expires 4-14-04 (Arbitrated) | Same as above. | Same as above. | Same as above. | 2002-01-01 | TBD | Verizon treats signature date as effective date; however, collo timeframe is still TBD.
ILEC: Qwest
State | Agreement Name / Agreement Type | Contract Term | Current Status / Accomplishments | Next Steps | Expected Date for PUC Submission | Expected PUC Approval Date | Collo Application Time Frame | Operational Date
OR | Electric Lightwave Inc. / opt-in agreement | 3 years ending 6/03 | All pricing information received; Qwest has provided opt-in language and agreed to amend Dispute Resolution, optical pricing, and colocation sections of ELI agreement. Agreements have been circulated for internal review. Have received feedback from tax, legal, credit and accounting. Met with outside counsel to discuss incorporation of internal comments into amendments to ELI agreements. Suggested amendment language sent to Qwest for approval 10/15/01. | EBS to draft three amendments once opt-in language is received. Meet with Qwest to discuss internal comments. Additional amendment language re: Parent Guarantee, Self-Insurance, Payment Dispute and Assignment have been received as of 11/13/01 and final opt-in w/ amendments is being prepared. | End of November, 2001 | commission approval immediate | approx. 120 days | January, 2002
WA | Electric Lightwave Inc. / opt-in agreement | 3 years ending 6/03 | All pricing information received; Qwest has provided opt-in language and agreed to amend Dispute Resolution, optical pricing, and colocation sections of ELI agreement. Agreements have been circulated for internal review. Have received feedback from tax, legal, credit and accounting. Met with outside counsel to discuss incorporation of internal comments into amendments to ELI agreements. Suggested amendment language sent to Qwest for approval 10/15/01. | EBS to draft three amendments once opt-in language is received. Meet with Qwest to discuss internal comments. Additional amendment language re: Parent Guarantee, Self-Insurance, Payment Dispute and Assignment have been received as of 11/13/01 and final opt-in w/ amendments is being prepared. | End of November, 2001 | November, 2001; commission approval 15 days | approx. 120 days | January, 2002
UT | Electric Lightwave Inc. / opt-in agreement | 3 years ending 6/03 | All pricing information received; Qwest has provided opt-in language and agreed to amend Dispute Resolution, optical pricing, and colocation sections of ELI agreement. Agreements have been circulated for internal review. Have received feedback from tax, legal, credit and accounting. Suggested amendment language sent to Qwest for approval 10/15/01. | EBS to draft three amendments once opt-in language is received. Discuss revisions with local counsel. Meet with Qwest to discuss internal comments. Once Amendments for OR and WA are final, they will be added to UT opt-in. | Early December, 2001 | December, 2001; commission approval 30-60 days | approx. 120 days | January, 2002
CO | Modified SGAT / modeled after ELI agreement | 2 years ending approx. 1/03 | All pricing information received; EBS to suggest amendments to CO SGAT; CO SGAT sent to internal review group for comment. | CO agreement will follow OR, WA, and UT opt-ins, EBS will try to adopt ELI conditions into SGAT. New CO SGAT to be approved by COPUC on Nov. 30 | Early December, 2001 | December, 2001; commission approval 30-60 days | approx. 120 days, although timeframe may be reduced pending new SGAT. | February, 2002
ILEC: SBC
State | Agreement Name / Agreement Type | Contract Term | Current Status / Accomplishments | Next Steps | Expected Date for PUC Submission | Expected PUC Approval Date | Collo Application Time Frame | Operational Date
TX | Multi-State Agreement / Negotiated | 1 year plus 90 days | Call with SBC on Wednesday, 11/9. Received red-lines from SBC on 11/8. We negotiated the GTCs for the Multi-State agreement. We are close to wrapping up that negotiation and moving onto negotiating UNEs and collocation. On GTCs, SBC accepted our proposal to limit audits, confidentiality, choice of law, and consent regarding assignment of agreements will not be unreasonably withheld. SBC rejected our proposals for netting and set-off, inclusion of bankruptcy as cause for termination and use of a corporate guaranty as a form of security. | Negotiating red-lines for OSS and Billing on 11/14 and collocation and UNEs on 11/20. | Early December, 2001 | February, 2002 | Approximately 120 day process. | March, 2002
IL | Multi-State Agreement / Negotiated | 1 year plus 90 days | same as above. | same as above | Early December, 2001 | January, 2002 | Approximately 120 day process. | March, 2002
CA | AT&T/Pacific Bell /Amendment for pricing and provisioning. | 6/27/03, arbitrated | SBC has agreed to fill in some of the gaps in the AT&T pricing with the Multi-State. | same as above | Early December, 2001 | December, 2001 | Approximately 120 day process. | March, 2002
ILEC: BellSouth
State | Agreement Name / Agreement Type | Contract Term | Current Status / Accomplishments | Next Steps | Expected Date for PUC Submission | Expected PUC Approval Date | Collo Application Time Frame | Operational Date
GA | BellSouth Standard Agreement/Negotiated | 2 years | Have submitted redline documents to BellSouth. Have received their redline response. Expect a call this week or next week to finalize positions. Have requested and received an extension to the arbitration window until 12/1/01. | Conference Call week of 11/19/01. Expect to be able to conclude negotiations by end of November. | 2001-11-01 | 2002-01-01 | Approximately 130 days. | SBC would treat signature date as effective date; if collocation is not ready, March 2002
FL | BellSouth Standard Agreement/Negotiated | 2 years | same as above | same as above | 2001-11-01 | 2002-01-01 | Approximately 130 days. | SBC would treat signature date as effective date; if collocation is not ready, March 2002
IL | BellSouth Standard Agreement/Negotiated | 2 years | same as above | same as above | 2001-11-01 | 2002-01-01 | Approximately 130 days. | SBC would treat signature date as effective date; if collocation is not ready, March 2002
ILEC: Sprint-Negotiations are lagging other ILECs
State | Agreement Name / Agreement Type | Contract Term | Current Status / Accomplishments | Next Steps | Expected Date for PUC Submission | Expected PUC Approval Date | Collo Application Time Frame | Operational Date
| Sprint/XO Agreement | August, 2002 | Terminated negotiations with Sprint on November 2001. |  |  | 2002-02-01 | TBD | April, 2002