## PreConst. Approvals
XYC Energy Project
Approvals/Activities Required Prior to Start of Construction
Permit/Approval | Issuing Agency | Potential Issues | Schedule | Participants
PSD Permit/ Permit to Construct | State/EPA | Generally required before permanent commitment to the
project (usually pouring concrete) can occur. Some states
allow a construction waiver (ie.construction at risk) for non-
PSD sources.
NPDES - Construction Stormwater | USEPA Reg. __ | Must file NOI at least 48 hours prior to construction of site
General Permit (40 CFR 122) | State | > 5 acres.
* Develop and implement SWPPP
* Submit NOI
* Contact TNRCC re: "Edwards Aquifer Rule"
* Contact FWS re: endangered species
FAA Notice of Proposed Construc- | FAA | Project may not actually trigger notification requirements of
tion or Alteration (14 CFR 77) |  | 14 CFR 77.15, depending on stack height and distance
from nearset airport. May choose to file notice anyways
to be on safe side.
Required for dredge or fill in desinated wetlands.
COE Section 404 Permit | COE | * Wetlands delineation
* Letter of concurrence from COE?
* Permit application/with mitigation measures identified
T&E Species | U.S. Fish & | Survey to confirm no T&E species or habitat will be affected
| Wildlife | by construction or operation of the project.
XYC Energy Project
Activities/Approvals Required Prior to Start of Construction - Continued
Permit/Approval | Issuing Agency | Potential Issues | Schedule | Participants
Federal law restricts disturbing certain historic structures
Cultural Resources Survey | SHPO | May states also have laws re: disturbance of sites. Gener-
ally a survey should be conducted to confirm that the project
will no affect historic, cultural, or archeological resources
Phase I/Phase II Site Investigation | NA | To determine development suitability and potential envi.
liablities
Noise Study | NA | To support project design, assess site suitability, and
to support local land use process.
Building Permit | Local | Required from local jurisdiction prior to start of construction.
State Environmental Policy Act | State | Generally not required in most states.
Typical land use actions include special use permit, zoning
Zoning, Land Use | Local Jurisdiction | change, annexation, site plan approval, subdivision plant, etc.
Most approvals must be completed prior to getting building
permit.

## PreOpera.Approvals
XYZ Energy Project
Activities/Approvals Required Prior to Commercial Operation
Permit/Approval | Issuing Agency | Potential Issues | Schedule | Participants
Acid Rain Permit (40 CFR 72) | State/EPA | Prior to submission need to do the following:
* File Form EIA-860 and obtain ORIS code from DOE/EIA
* ID Designated Representative/Alt and publish notice
* File Designated Representative forms with EPA Acid Rain
Office.
NPDES - Wastewater | State/EPA | Application must be submitted at least 180 days prior to
Discharge Permit (40 CFR 122) |  | commencement of discharge.
Custom Fuel Schedule (40 CFR Part | USEPA | Request for relief from need to do daily
60)
City/County | City/County Fire
Fire Department | Department
Fire Safety Review
Part 75 Acid Rain Monitoring Plan | USEPA - Acid | Required to be submitted at least 45 days prior to certifica-
| Rain Office | tion testing (technically could occur after start of operations)
40 CFR Part 60 Notifications | State/EPA | *Notification of start of construction within 30 days | <30 days after
|  | *Notification of initial startup within 15 days of actual date | <15 days after
|  | * Notification of date that CEMS performance commences | 60 days prior
|  | * Notice of Performance testing 30 days prior to testing | 30 days prior
XYZ Energy Project
Activities/Approvals Required Prior to Commercial Operation - continued
Permit/Approval | Issuing Agency | Potential Issues | Schedule | Participants
Spill Prevention Control and | USEPA | Required for > 1320 gallons of above-ground oil storage.
Countermeasure (SPCC) Plan
COE Section 404 Permit | Army COE | Possibly required for wastewater outfall structure if bank
stabilization or alteration required.
FEMA - Reclassification of Flood | FEMA
Plain
Water Use Permit/Municipal Approval | Varies | Connection to muni. water supply requires approvals. In some
for Water Supply |  | states groundwater/surface water withdrawals require a permit.
Septic Tank/Pretreatement Permit | Local WWTP | Septic tank permit is generally a county permit. If hooking up
to local WWTP, generally need pretreatment application
Facility Response Plan | USEPA | Required per Oil Pollution Prevention Act of 1990 for oil storage
in excess of 1 million gallons
Oil Tank Registration/Fire Safety | Varies | Can be state or local Fire Marshall

## PostOpera.Approvals
XYZ Energy Project
Activities/Approvals Required After Start of Operation
Permit/Approval | Issuing Agency | Potential Issues | Schedule | Participants
Title V (Part 70) Operating Permit | State | Must be filed within 12 months of the start of operation
Part 60 Emission Performance | State/EPA | Must perform 4 load NOx test within 180 days of intial start
Testing |  | or 60 days of achieving maximum production rate.
Notice of Termination (NOT) for | USEPA/State | File when construction site has been stabilized.
General Stormwater Permit