## West
NEWCO Contracts Needed to Establish for Day 1
West Desk
Pipeline | Rate Schedule |  | Service Description | Timing
Colorado Interstate Gas | NNT-1 |  | No Notice Storage | 2 weeks
Colorado Interstate Gas | TF-1 |  | Firm Transport
Colorado Interstate Gas | APAL-1 |  | Parking
Colorado Interstate Gas | HUB-1 |  | Cheyene Hub
Colorado Interstate Gas | HSP-1 |  | Headpool
Colorado Interstate Gas | TI-1 |  | Interruptible Transport
Colorado Interstate Gas | PTS-1 |  | Pooling
ElPaso Natural Gas | POOLAGR | I | Pooling | 2 weeks
ElPaso Natural Gas | FT-1 |  | Firm Transport
ElPaso Natural Gas | IT-1 |  | Interruptible Transport
Kern River Gas Transmission Co. | PS |  | Pooling | 2 weeks
Kern River Gas Transmission Co. | KRF-1 |  | Firm Transport
Kern River Gas Transmission Co. | KRI-1 |  | Interruptible Transport
Northwest Pipeline Corp. | TI-1 |  | Interruptible Transport | 2 weeks
Northwest Pipeline Corp. | TF-1 |  | Firm Transport
Northwest Pipeline Corp. | POOLAGR |  | Pooling
Pacific Gas & Electric Co. (LDC) | G-AA |  | As available transport--onsystem deliveries | 2 weeks
Pacific Gas & Electric Co. (LDC) | G-AAOFF |  | As available - offsystem deliveries
Pacific Gas & Electric Co. (LDC) | G-BAL |  | Balancing
Pacific Gas & Electric Co. (LDC) | G-LEND |  | Lend
Pacific Gas & Electric Co. (LDC) | G-NAAOFF |  | Negotiated as available offsystem deliveries
Pacific Gas & Electric Co. (LDC) | G-NAAON |  | Negotiated as available onsystem deliveries
Pacific Gas & Electric Co. (LDC) | G-PARK |  | Parking
Pacific Gas & Electric Co. (LDC) | G-FS |  | Firm Storage Service
Pacific Gas & Electric Co. (LDC) | G-AFTOFF |  | Annual rates -offsystem deliveries-sfv rate design
Pacific Gas & Electric Co. (LDC) | G-AFT |  | Annual rates -onsystem deliveries -mfv rate design
Pacific Gas & Electric Co. (LDC) | G-FTS |  | Firm Transport
PG&E Gas Transmission-Northwest Corp. | AIS-1 |  | Authorized Imbalance | 2 weeks
PG&E Gas Transmission-Northwest Corp. | PS-1 |  | Parking
PG&E Gas Transmission-Northwest Corp. | POOLING POINT |  | Pooling
PG&E Gas Transmission-Northwest Corp. | FTS-1 |  | Firm Transport
PG&E Gas Transmission-Northwest Corp. | ITS-1 |  | Interruptible Transport
Public Service of Colorado (LDC) | F |  | Firm Transport | 2 weeks
Public Service of Colorado (LDC) | I |  | Interruptible Transport
Questar Pipeline Company | ISS |  | Interruptible Storage | 2 weeks
Questar Pipeline Company | T-2 |  | Interruptible Transport
Trailblazer Pipeline Company | FTS |  | Firm Transport | 2 weeks
Trailblazer Pipeline Company | ITS |  | Interruptible Transport
Trailblazer Pipeline Company | I |  | title transfer
Transwestern Pipeline Company | I |  | Pooling | 2 weeks
Transwestern Pipeline Company | FTS-1 |  | Firm Transport
Transwestern Pipeline Company | ITS-1 |  | Interruptible Transport
Transwestern Pipeline Company | TT-1 |  | title transfer
Williams Field Services Group (Gathering) | I |  | Gathering | 2 weeks
Williams Field Services Group | I |  | Pooling
Williston Basin Interstate Pipeline Co. | IS-1 |  | Interruptible Storage
Wyoming Interstate Company, Ltd. | FT |  | Firm Transport | 2 weeks
Wyoming Interstate Company, Ltd. | IT |  | Interruptible Transport
Wyoming Interstate Company, Ltd. | PTS-1 |  | Pooling
Timing--we've been advised that it may take a while (14-30 days) to get credit set up but once that's completed & we have all entity info we need,
I expect that we could turn-around each pipe in approx. 2 weeks…the whole process should be completed in 3-6 weeks, with the "critical" pipes done first.
Tariff/Credit Issus
1. Will need a DUNS number for the new entity so that credit can be established--this DUNS number acts as the unique company identifier for each pipeline's system
2. Each pipeline will need to set up a business party for the new entity, establish on-line access for schedulers & traders, set-up pools, etc. in their own systems to allow us to access their EBB--we'll also have to execute an EBB agreement (tariff form) with each pipe to gain access.
3. We will need wire transfer accounts set up for the new entity for payment of invoices and receipt of payments from the pipe
4. Depending on the corporate structure and form of incorporation (ie. LLC), a parental guaranty may be required from the majority owner--Several of the pipelines I've spoken to indicated that they'd be seeking letters of credit and/or parental guarantees, depending on the structure of NEWCO.
I told each of them that we expect that NEWCO will be completely independent of any of Enron's pre-petition obligations and that they should treat our request to set up NEWCO as a completely new entity with it's owns DUNS, rather than a assignee of Enron's contracts
5. At some point once we have a better idea what the structure will be, we'll need Legal to prepare a letter describing the new corporate structure so we'll have it available to send to those pipelines that ask
EDI Issues--in order to be able to submit nominations via EDI, we'll also have the following contract & set-up issues:
Each EDI pipeline requires a trading-partner agreement (a standard GISB document) which will have to be executed between each EDI pipe and NEWCO
Once the TPA is in place, we will have to test the EDI maps with each pipeline, a process that can take anywhere from one week to one month
Our EDI process is dependent in part on third-party contracts with the EDI Hub, which manages the internet and firewall issues...so we'll need some guidance on how that relationship will be structured going forward so we can develop a NEWCO EDI Implementation plan.
Credit 1st, signature 2nd
Credit 1st, signature 2nd
Credit 1st, signature 2nd
Need TPA signed and one day of test data
Per Sarah: Let them know the legal entity name, address, telephone, fax, contact list and within 2 - 3 hours they can have a new pool set up.
1 DAY
credit approval time varies 3-6 days, then just a day or two to set up k#
credit approval time varies 3-6 days, then just a day or two to set up k#
credit approval time varies 3-6 days, then just a day or two to set up k#
credit approval time varies 3-6 days, then just a day or two to set up k#
1day
SAME DAY
letter of credit
letter of credit
assignment is quick, ie ENA to new co.
1-2 DAYS
2DAYS
Note on G143: mschrab: Per Tom: 1 day turn around . IT agreements and Storage Agreements are set up on an as needed basis and could probably be set up within a day as well. I am waiting on clarification from Cheryl at Michcon on the transport agreements.
Note on G144: mschrab: credit approval time varies 3-6 days, then just a day or two to set up k#
Note on G158: mschrab: Per Jan - 2 - 3 hours turn around to be able to nominate on their system. We would need to send them the new entity name and complete a new user registration form. As soon as they receive this they will set us up as a nominator on their system. There is no credit check unless you are supplying end users.
Note on G165: mschrab: longer to set up new co.
Note on G166: mschrab: longer to set up new co.
Note on G168: mschrab: INITIALLY $100k IF GUARANTY AND MORE UPON CREDIT APPROVAL

## East
NEWCO Contracts Needed to Establish for Day 1
East Desk
Pipeline | Rate Schedule | Service Description | Timing
Texas Eastern Transmission Co. | IT-1 | Interruptible Transport
Texas Eastern Transmission Co. | TABS | Pooling Contract
Dominion Transmission Inc. | TTT | Pooling Contract | 2 weeks
Dominion Transmission Inc. | ITAGG-G | Applachian Pooling
Dominion Transmission Inc. | ITAGG-G | Applachian Transmission
Dominion Transmission Inc. | MCS | Park & Loan
Dominion Transmission Inc. | IT | Interruptible Transport | 3 weeks
Algonquin Gas Transmission | AIT-1 | Interruptible Transport
Iroquois Gas Transmission System | PALS | Park & Loan | 2 weeks
Iroquois Gas Transmission System | RTS | Interruptible Transport
Texas Gas Transmission Corp. | TAPS | Pooling Contract | 2 weeks
Texas Gas Transmission Corp. | IT | Interruptible Transport
Texas Gas Transmission Corp. | PAL | Park & Loan
Stingray Pipeline Company | IT | Interruptible Transport | 2 weeks
Gulf South Pipeline | ITS | Interruptible Transport | 2 weeks
Gulf South Pipeline | PAL | Park & Loan
Gulf South Pipeline | PS | Pooling Contract
Williams Gas Pipeline--Transco | IT | Interruptible Transport | 2 weeks
Williams Gas Pipeline--Transco | PBS | Park & Loan
Williams Gas Pipeline--Transco | Pooling Service-IT | Pooling Contract
Columbia Gas Transmission Company | IPP | Pooling Contract | 2 weeks
Columbia Gas Transmission Company | AS | Aggregation Pools
Columbia Gas Transmission Company | ITS | Interruptible Transport
Columbia Gas Transmission Company | PAL | Park & Loan
Columbia Gas Transmission Company | SIT | Storage in Transit
National Fuel Gas Supply Corp. | IT | Interruptible Transport | 2 weeks
National Fuel Gas Supply Corp. | IAS | Interruptible Advanced Service
National Fuel Gas Supply Corp. | P1 | Parking
Sabine Pipeline Company | IT | Interruptible Transport | 2 weeks
Sabine Pipeline Company | Parking and Lending | Park & Loan
Sabine HUB | IHT | Intra Hub Transfer | 2 weeks
Southern Natural Gas Company | PSNG | Pooling Contract | 2 weeks
Southern Natural Gas Company | IT | Interruptible Transport
Southern Natural Gas Company | PAL | Park & Loan
Tennessee Gas Pipeline Company | SA | Pooling Contract | 2 weeks
Tennessee Gas Pipeline Company | IT | Interruptible Transport
Tennessee Gas Pipeline Company | PAL | Park & Loan
Sea Robin Pipeline Company | Pooling Service-IT | Pooling Contract | 2 weeks
Sea Robin Pipeline Company | ITS | Interruptible Transport
Columbia Gulf Transmission Company | ITS1 | Interruptible Transport | 2 weeks
Columbia Gulf Transmission Company | ITS2 | Interruptible Transport
Columbia Gulf Transmission Company | AS | Aggregation Pools
Columbia Gulf Transmission Company | IPP | Pooling Contract
Bridgeline Holdings, LP (Intrastate) | FT | Firm Transport | 2 weeks
Bridgeline Holdings, LP (Intrastate) | IT | Interruptible Transport
Bridgeline Holdings, LP (Intrastate) | Storage | Storage Service
Florida Gas Transmission Co. | IPS | Pooling Contract | 2 weeks
Florida Gas Transmission Co. | FTS-1 | Firm Transport (Market Area)
Florida Gas Transmission Co. | FTS-2 | Firm Treansport (Market Area)
Florida Gas Transmission Co. | SFTS | Small Firm Transportation Service
Florida Gas Transmission Co. | ITS-1 | Interruptible Transport (Market Area)
Florida Gas Transmission Co. | ITS-2 | Interruptible Transport (Market Area)
Florida Gas Transmission Co. | ITS-WD | Interruptible Transport (Western Division)
Florida Gas Transmission Co. | FTS-WD | Firm Transport (Western Division)
Florida Gas Transmission Co. | PNR | Park and Ride
Destin Pipeline Company LLC | IDPC | Interruptible Transport | 2 weeks
Venice Gathering System, LLc | ITS | Interruptible Transport | 2 weeks
Venice Gathering System, LLc | PS | Pooling Contract
Egan Hub Partners, LP | IWS | Interruptible Wheeling Service | 2 weeks
Egan Hub Partners, LP | IPS and ILS | Park and Ride
Equitrans, Inc. | POOAGR | Pooling Contract | 2 weeks
Equitrans, Inc. | ITS | Interruptible Transport
Equitrans, Inc. | LPS | Park and Ride
Covepoint | FPS-1 | Firm Storage | 2 weeks
Eastern American (Intrastate) | I | Interruptible Transport(Gathering and Processing) | 2 weeks
Markwest (Intrastate) | I | Interruptible Transport(Gathering and Processing) | 2 weeks
Eastern States (Intrastate) | I | Interruptible Transport(Gathering and Processing) | 2 weeks
Somerset (Intrastate) | I | Interruptible Gathering(Agent) | 2 weeks
Somerset (Intrastate) | I | Interruptible Gathering
Coronado (Intrastate) | I | Interruptible Transport | 2 weeks
Norse (Intrastate) | I | Interruptible Gathering(Agent) | 2 weeks
Norse (Intrastate) | I | Interruptible Gathering
CNR (Intrastate) | I | Interruptible Gathering | 2 weeks
Gatherco (Intrastate) | I | Interruptible Gathering | 2 weeks
Timing--we've been advised that it may take a while (14-30 days) to get credit set up but once that's completed & we have all entity info we need,
I expect that we could turn-around each pipe in approx. 2 weeks…the whole process should be completed in 3-6 weeks, with the "critical" pipes done first.
Tariff/Credit Issus
1. Will need a DUNS number for the new entity so that credit can be established--this DUNS number acts as the unique company identifier for each pipeline's system
2. Each pipeline will need to set up a business party for the new entity, establish on-line access for schedulers & traders, set-up pools, etc. in their own systems to allow us to access their EBB--
we'll also have to execute an EBB agreement (tariff form) with each pipe to gain access.
3. We will need wire transfer accounts set up for the new entity for payment of invoices and receipt of payments from the pipe
4. Depending on the corporate structure and form of incorporation (ie. LLC), a parental guaranty may be required from the majority owner--
Several of the pipelines I've spoken to indicated that they'd be seeking letters of credit and/or parental guarantees, depending on the structure of NEWCO.
I told each of them that we expect that NEWCO will be completely independent of any of Enron's pre-petition obligations and that they should treat our request to set up NEWCO as a completely new entity with it's owns DUNS, rather than a assignee of Enron's contracts
5. At some point once we have a better idea what the structure will be, we'll need Legal to prepare a letter describing the new corporate structure so we'll have it available to send to those pipelines that ask
EDI Issues--in order to be able to submit nominations via EDI, we'll also have the following contract & set-up issues:
Each EDI pipeline requires a trading-partner agreement (a standard GISB document) which will have to be executed between each EDI pipe and NEWCO
Once the TPA is in place, we will have to test the EDI maps with each pipeline, a process that can take anywhere from one week to one month
Our EDI process is dependent in part on third-party contracts with the EDI Hub, which manages the internet and firewall issues...so we'll need some guidance on how that relationship will be structured going forward so we can develop a NEWCO EDI Implementation plan.

## Central
NEWCO Contracts Needed to Establish for Day 1
Central Desk
Pipeline | Rate Schedule | Service Description | Timing
ANR Pipeline Company | IPLS | IPLS (PARK/LEND) | 2 weeks
ANR Pipeline Company | PTS-1 | POOLING
ANR Pipeline Company | ITS | IT TRANSPORT
ANR Pipeline Company |  | EDI process
CONSUMERS (LDC) | I | TITLE TRANSFER | 2 weeks
Great Lakes Transmission LP | IT | IT TRANSPORT | 2 weeks
Great Lakes Transmission LP | MC | PARK & LOAN (STORAGE)
MICHCON (LDC) | I | IT TRANSPORT | 2 weeks
Natural Gas Pipeline Co. | TT | TITLE TRANSFER | 2 weeks
Natural Gas Pipeline Co. | ITS | IT TRANSPORT
Natural Gas Pipeline Co. | FTS | FT TRANSPORT
Natural Gas Pipeline Co. | NSS | NSS STORAGE
Northern Border Pipeline Co. | IT-1 | Interruptible Transportation | 2 weeks
Northern Border Pipeline Co. | IT-1R | Firm Transportation
Northern Border Pipeline Co. | T-1 | Firm Transportation
Northern Border Pipeline Co. | I | Title Transfer
Northern Natural Gas Co. | TI | Interruptible Transportation | 2 weeks
Northern Natural Gas Co. | MPS | Pooling
Northern Natural Gas Co. | IDD | Storage
Northern Natural Gas Co. | TF | Firm Transportation
Northern Natural Gas Co. | TT | Title Transfer
NIGAS (LDC) |  | POOLING | 2 weeks
NIPSCO (LDC) | no title transfer |  | 2 weeks
OneokNG | I | Pooling & Transport | 2 weeks
PEPL | EIT, I, GPS | it, pooling, park/lend | 2 weeks
RELIANT (LDC) | PS, IT, FT | pooling, transport | 2 weeks
PEOPLES (LDC)
Trunkline Gas Company | TABS | TABS POOLING | 2 Weeks
Trunkline Gas Company | IT | IT TRANSPORT
Trunkline Gas Company | I | IT
Transcanada Gas Pipeline | I | IT | 2 weeks
Union Gas | IT | IT Transport | 2 weeks
Union Gas | I | Park/Loan
Timing--we've been advised that it may take a while (14-30 days) to get credit set up but once that's completed & we have all entity info we need,
I expect that we could turn-around each pipe in approx. 2 weeks…the whole process should be completed in 3-6 weeks, with the "critical" pipes done first.
Tariff/Credit Issus
1. Will need a DUNS number for the new entity so that credit can be established--this DUNS number acts as the unique company identifier for each pipeline's system
2. Each pipeline will need to set up a business party for the new entity, establish on-line access for schedulers & traders, set-up pools, etc. in their own systems to allow us to access their EBB--we'll also have to execute an EBB agreement (tariff form) with each pipe to gain access.
3. We will need wire transfer accounts set up for the new entity for payment of invoices and receipt of payments from the pipe
4. Depending on the corporate structure and form of incorporation (ie. LLC), a parental guaranty may be required from the majority owner--Several of the pipelines I've spoken to indicated that they'd be seeking letters of credit and/or parental guarantees, depending on the structure of NEWCO.
I told each of them that we expect that NEWCO will be completely independent of any of Enron's pre-petition obligations and that they should treat our request to set up NEWCO as a completely new entity with it's owns DUNS, rather than a assignee of Enron's contracts
5. At some point once we have a better idea what the structure will be, we'll need Legal to prepare a letter describing the new corporate structure so we'll have it available to send to those pipelines that ask
EDI Issues--in order to be able to submit nominations via EDI, we'll also have the following contract & set-up issues:
Each EDI pipeline requires a trading-partner agreement (a standard GISB document) which will have to be executed between each EDI pipe and NEWCO
Once the TPA is in place, we will have to test the EDI maps with each pipeline, a process that can take anywhere from one week to one month
Our EDI process is dependent in part on third-party contracts with the EDI Hub, which manages the internet and firewall issues...so we'll need some guidance on how that relationship will be structured going forward so we can develop a NEWCO EDI Implementation plan.

## Texas
NEWCO Contracts Needed to Establish for Day 1
Texas Desk
Pipeline | Rate Schedule | Service Description | Priority | Timing
TXU Lone Star | IT | Interruptible Transport | Secondary | 2-3 weeks
Oasis | IT | Interruptible Transport | Secondary | 2-3 weeks
EPGT (PGE Valero) | IT | Interruptible Transport | First | 2-3 weeks
| Hub | Hub Transport | First | 2-3 weeks
| Park &v Loan | Park & Loan | First
Houston Pipeline | IT | Interruptible Transport | Secondary | 2-3 weeks
Midcon--Kinder Morgan Texas Pipeline | IT | Interruptible Transport | Secondary | 2-3 weeks
Westar (Oneok Westex) | IT | Interruptible Transport | Secondary | 2-3 weeks
Channel | IT | Interruptible Transport | Secondary | 2-3 weeks
East Texas Gas Systems (ETXG)--DUKE | IT | Interruptible Transport | First | 2-3 weeks
|  | Cartwheel agreement | First
Duke Guadalupe | IT | Interruptible Transport | Secondary | 2-3 weeks