## Sheet1
Office |  | Number of observations |  | Rating | Closed observations | Open observations with target date after 9/1/00 | Global issues not yet cleared - missed target date | Open observations having missed target date | Item that missed target date or any global issues not yet cleared (whether or not they are past target date or not) | Common findings of office as listed in presentation to JS
Buenos Aires | Feb. 16-18 | 10 | 0 | 1 red, 8 yellow, 1 green | 9 |  |  | 1 | Finalization of translation of open contracts (backlog) | 1, 2, 3, 5, 6
Calgary | May 9-12 | 9 | 0 | 5 red, 4 yellow | 6 | 3 |  |  | Enpower (installation in process), management of fx risks | 1, 2 5, 6
Frankfurt | Feb. 24-25 | 10 | 0 | 1 red, 9 yellow | 10 |  |  |  |  | 1, 2, 5
London Phase I (a) | April 10-14 | 22 | 0 | 3 red, 19 yellow | 11 | 10 | 1 |  | Use of mobile phones to make trades OPEN (database not reflective of this status) | 1, 2, 3, 4, 5, 6
London Phase II (b) | May 23 - June 2 | 26 | 0 | 9 red, 17 yellow | 13 | 5 |  | 8 | OPEN | 1, 2, 3, 5, 6
Oslo | Feb 21-23 | 9 | 0 | 2 red, 7 yellow | 7 | 1 |  | 1 | Tracking and monitoring fx exposures | 1, 5, 6
Panama City | 2000-05-18 | 9 |  | 1 red, 8 yellow | 0* | 3 |  | 6 | OPEN | 1, 4, 5, 6
Sao Paulo | Feb 14-15 | 7 | 0 | 2 red, 5 yellow | 4 | 3 |  |  | Commercial lines not taped | 2, 4, 5, 6
Seoul | April 3-7 | 6 | 0 | 6 yellow | No target dates have been specified. |  |  |  |  | 4
Singapore | March 1-3 | 6 | 0 | 4 red, 2 yellow | 5 |  | 1 |  | Use of mobile phones to make trades. | 1, 2, 4, 5
Sydney | Feb. 28-29 | 6 | 0 | 2 red, 4 yellow | 6 |  |  |  |  | 1, 2, 3, 5, 6
* This report was received at the end of August, which attributes to this low number.
Definitions:
Red | Item extremely high priority. Should be cleared immediately.
Yellow | Key issue which does not violate a global standard.
Green | Finding that represents a weakness, and should be cleared, but not a key issue.
Common findings
1 | Ineffective segregation of duties
2 | Capture of positions not timely or complete
3 | Systems implementation issue: Control requirements vs. critical mass
4 | Phone lines not taped and use of cell phones for trading
5 | Inconsistent operational practices across commodities and locations
6 | Lack of process for creating operational controls for new commodities/businesses