## Sheet1
Relaunch Timescale for EnronOnline/NetcoOnline
2002-03-01 | Initial Documentation to be sent to prospective Buyers for their approval
Documentation to include Password Applications (PA) and Electronic Trading Agreements (ETA)
2002-07-01 | Approvals received from Buyers on PA and ETA format
2002-08-01 | Send/Fax PA and ETA format to Top 50 customers
Top customers will be shown the PA format so that when the final document is received, they do not need to conduct a detailed review.
The only change between the version of the PA and ETA sent on this date and the final version should be the insertion of the new [NetCo] name and website name.
Overview of Relaunch distributed internally
2002-11-01 | Commodity Short Form contracts to Buyers for their approval
Documentation to include General Terms and Conditions (GTCs) for physical natural gas, physical power, financial gas & power.
These documents are the online, commodity specific agreements which customers must accept before transacting on a new commodity type (e.g. US Physical Gas)
2002-11-01 | Assuming a Buyer is selected
Send final PA to Top 50 customers
The [NetCo] company name and website name will be filled in on the previously issued PA formats and the PA's will be faxed or mailed to the top 50 customers
The ETA will be accepted online on launch.
Agree new company name and website name.
2002-11-01 | Key messages distributed internally.
2002-11-01 | Marketing group ensures customers complete PA
Product Control Group commences issuance of User Ids and Passwords
2002-11-01 | Press Release sent to new Buyer for Approval
2002-11-01 | New NetCoOnline splash page available with User Admin functions and downloadable versions of the PA and ETA.
14/1/2002 | Approval received from New Buyer on Press Release
Products to be available on Day 1 defined and listed on website - 'to be coming soon' area listed too.
15/1/2002 | Approval received from New Buyer on GTC's
15/1/2002 | Send out NetCoOnline Press Release
21/1/2002 | Launch of NetCoOnline