## Sheet1
Business Owner | Business | Title | Description | Implementation | Status | Priority | Targeted Completion Date
Allen | Volume Mngt. | ERCOT Automation | ERCOT solution for data collection, charge estimation, customer allocation and reconciliation (between ERCOT, Enron and customer) | ESCA Providing Solution. Currently assessing Loadstar and VMS as possible long term solutions | Working Group developing requirements | 1
Allen | Volume Mngt. | PJM Automation | Port Volume Mngt. for PJM from Access/Excel based solutions to an automated system. | Currently assessing Loadstar, ESCA and VMS as possible long term solutions | Working Group developing requirements | 1
Allen | Volume Mngt | Daily Estimates | New interface to scrape meter websites for all counterparties and markets or receive meter files |  |  | 3
Allen | Volume Mngt. | Dispute Activity | Automate current processes |  |  | 2
Allen | Volume Mngt. | Market Charges Capture | Capture all charges within each market proactively and make available for new service transactions | Currently assessing using Accenture to assist in this area | Working Group developing requirements | 1
Allen | Settlements Reconcile | Flash Automation | Develop system solution to automate current Flash process. |  |  | 3
Allen | Settlements Reconcile | EnPower to Unify | Develop system solution to automate current EnPower to Unify reconciliation process. |  |  | 3
Allen | Settlements Reconcile | Checkout | Develop system solution to automate current spreadsheet based Checkout |  |  | 3
Bentley | PJM MOS | Automate Scheduling - PJM | Strategic solution required for PJM | Currently assessing FSP and ESCA as potential solutions | Working Group developing requirements | 1
Bentley | Trading Hourly | Hourly Traders Workbench | Automate manual/time intensive processes. |  |  | 2
Bentley | Trading General | Consolidated Position Manager Phase II | Combine Consolidated Position Manager and Curve Manager into one application |  | Requires Scoping | 2
White | Risk | Curve Mngr. Phase II | Provide curve shift for GAS and other commodities (gas, c. oil, heating oil, coal, and weather). Currently, positions for other commodities are captured, not prices. Graphical and Tabular changes in curves over time. Swap model. |  | Requires Scoping | 2
White | Risk Deal Capture | Data entry for variable load deals | Currently performed by Risk Management and very time consuming. Will not scale. | Will utilize new system developed by EES. |  | 3
White | Systems Architecture | Portcalc | Portcalc will not scale with increased volume (98) | Will utilize new system developed by EES. |  | 3

## Sheet2
Business Owner | Business | Title | Description | Implementation | Status | Priority | Targeted Completion Date
Allen | Volume Mngt. Upload | Upload | Enhance Deal Upload program to include power transmission transactions |  | New Requirement | 1
Allen | Settlements Reporting | CARP Report | Time to run month-end CARP report is excessive |  | New Requirement | 1
Bentley | ERCOT MOS | ESCA Development | Market Operating System | ESCA | In Development. Working Group currently assessing GAPs | 1
Bentley | Trading | Consolidated Position Manager Phase I | Provide consolidated position for all open trades with sorting options by market type, product type, and custom selection | Luu | In Development: Currently waiting for product release for testing | 1
Bentley | Scheduling | Modify Trade | Record EnPower deals that have received modifications within a past user defined period. |  | Requires Scoping | 2
Bentley | Scheduling Interface with Deal Capture | Pre-Schedule Workspace | Replace Excel Macros and Lotus Notes Confirmations | Luu | In Development | 1
Bentley | Scheduling Interface with Deal Capture | Pre-Schedule Confirmation | Replace Excel Macros and Lotus Notes Confirmations | Luu | In Development | 1
White, Allen | Risk | Pub Posting | Pub Posting requires new solution that will scale and will allow for configurable data intervals (ERCOT is 15 minutes). |  | Requires Scoping: Debra to set up meeting by 9/20/01 | 1
White | Risk | Curve Mngr. | Curve Manager and Curve Shift Position Mgr. Phase I | Nommensen | Testing | 1
White | Risk | New Oracle Curve Files | Change the curve files to read from the new oracle curve tables | Nommensen - Required once curve manager utilized | Not Started | 1
White | Risk | New Oracle Curve Files | Modify all risk spreadsheets to utilize the new oracle curve tables | Nommensen - Required once curve manager utilized | Not Started | 1
White | Risk | Create Link | Create Link between Excel valued deals (Asian - 1 YR, Compund and Contingent) and oracle adhoc tables | This is a quick fix solution until capability to enter 1 yr asian deals, compund, and contingent deals is available (see next requirement) | Not Started | 1
White | Risk -Valuation | Portcalc – Deal Type | Valuation of Asian (1 YR), Compound and Contingent Options | Nommensen | Not Started | 3
White | Risk | Portcalc – Deal Type | Asian Options (3 month strip), Averaging Index Forwards | Nommensen | In Production
White | Risk | Portcalc – Deal Type | Renewable Energy Credits, SRA Deal for Australia | Nommensen | In User Test | 3
White | Risk | Portcalc – Deal Type | Canadian Heat Rate Swaps | Nommensen | In User Test | 3
White | Risk | Portcalc – Deal Type | Ancillary Services, Index Options, Averaging Basis Options | Nommensen | Not Started | 3
White | Risk | Options | Management Improvements: Phase II:Portcalc Option Predictives Reporting, Option Blending and Volatility Smile | Nommensen | In Production
White | Risk | Adhoc Table Queries | Provide Mechanism to perform adhoc table queries | Nommensen | Not Started | 3
White | Risk | Cross- Portfolio Flag | Add Cross-Portfolio Flag to deals for Portcalc | Nommensen | On Hold - Resources | 1
White | Risk | TAGG and EnPower Interface | TAGG (ERMS) and EnPower interface requires further development. |  | Requires Scoping | 2
White | Risk | Swaption Volatility | Calculate Swaption Volatility from a curve | Nommensen | Not Started | 3
White | Risk Reporting | Data Inconsistent | Post ID versus Book ID – Inconsistency between EnPower and Corp risk systems |  | Requires Scoping | 3
White | Risk Reporting | VaR | VaR reporting process will not scale |  | Requires Scoping | 3

## Sheet3
Business Owner | Business | Title | Description | Implementation | Status | Priority | Targeted Completion Date
Imai | Fundamentals | MetaStock – Phase II | Off-Peak Power Prices, Additional Power Curves, Strip Averaging, User Profile Improvements, Additional Heat Rate Calcs | Kumar | In Develop |  | 2001-10-01
Imai | Fundamentals | East Desk Portal | Content additions for the ERCOT ISO | Kurmar | In Develop |  | 2001-09-07
Imai | Fundamentals | East Desk Portal | Content additions for the Nuclear Plant Status | Kurmar | In Production |  | Complete
Imai | Fundamentals | East Desk Portal | Content additions for the Hydro Plant Status | Kurmar | In Develop |  | 2001-11-15
Imai | Fundamentals | East Desk Portal | Content additions for the Reuters Feed | Kurmar | In Production |  | Complete
Will | Services | EMS | Upgrade EMS to EMP 2.1.1 | Kumar | In Develop |  | 2001-11-30
Will | Services | EMS | Plant Monitoring and Control Systems (EMS/PI): Netowrk/Firewall/ESA Frame Relay Setup; Parallel EMS Systems Configuration and Installation; Control Room Migration to new bldg.; TVA (Allegheny) RTU Data Points via ICCP | Kumar | In Develop |  | 2001-10-15
Imai | Fundamentals | Databeaon Cubes - Phase II | MW Daily Index Prices for All Regions; DA / Real Time LMP's for PJM/NYISO; 16 Hour Avg / Peak Load for All Reagions; 24 Hour Avg Load for all Regions | Kumar | In Develop |  | 2001-09-15
Will | Services | Extranet | Expose PMI/Fundamental Data to Serrvices Customers | Kumar | Inception