## Business Solutions
2001-08-27
| Primary |  | 3 yr. MTM |  |  |  | Region
Client | Group | Product | Value | Update | Closure | Lead | Contact
EES | Operations | NY EDI |  | Phase II/III rules: completed. Being posted for comments. | 2001-12-01 | Vinio | Frank
|  |  |  | NY EDI Working Group being formed. First meeting August 22. |  | Vinio
|  |  |  | Phase I testing has started. |  | Vinio
|  |  |  | Coordination with EES and CSC to plan for Phase II/III testing. |  | Vinio
EES/ | Operations | ERCOT Retail Rules |  | PIWG: Pilot opened 8/01 (Ramp-up/Back-log) | 2001-12-01 | Nancy
EWS | Physical |  |  | RMS: Multiple Market Issues |  | Nancy
| Desk |  |  | TX SET: Continued development of standardized electronic transactions |  | Nancy
EES | Operations | Operational Support
Ohio
|  | Ohio Bill ready UDC billing |  | Submitted a joint marketer proposal last week | 2001-09-01 | Gloria | Donald
|  | Ohio CRES consolidated billing |  | Working on fundamental questions | 2001-09-01 | Gloria | Donald
|  | Ohio Purchase of receivables stipulation |  | Stipulation now filed with the commission | 2001-09-01 | Gloria | Donald
|  | Slamming Rules |  | Participated in the OSPO discussion on this issue | 2001-09-01 | Gloria | Donald
|  | PUCO Education on wholesale issues |  | Planning the meeting and agenda | 2001-09-01 | Gloria | Donald
Texas
|  | Enron Direct |  | Working on draft Enron Direct contract with legal | 2001-09-01 | Gloria | Donald
|  | Non-PTB Customers |  | Reviewing Reliant's filings for grounds to file complaint | 2001-09-01 | Gloria | Donald
|  | TX Pilot |  | Working with EES to determine possible pilot participation in TXU and Reliant |  | Nancy
|  | Taxes |  | Working with EES Tax Department to understand Tax implications |  | Nancy
Illinois
|  | ComEd |  | Meeting with ComEd to go over the agreements | 2001-09-01 | Gloria | Donald
|  | ComEd |  | Setting up meeting with ComEd and IP to review Operations |  | Nancy
| Operations - EES/EWS | EISB |  | Meeting 7/23. Report at 8/14 GISB/DOE Industry meeting - support but slow moving |  | Nancy

## Regulatory Hedges
2001-08-27
| Primary |  | 3 yr. MTM |  |  |  | Other
Client | Group | Product | Value | Update | Closure | Lead | Contacts
EWS/URM | SERC | GP Rate Case |  | Enron filed intervention in the case. Will advocate weather hedges and rate changes that protect EWS book. |  | Harry | Donald
| Nepool/Nypp | Central Hudson Settlement |  | Joint Proposed Settlement. Will provide tremendous benefit to book position, relative to IBM contract. |  | - | Kathleen
| URM/ |  |  |  |  | Pat
| Ercot/Spp |  |  | Identify means to reduce potential stranded costs (ERCOT)
| URM/Mapp | GPU (NJ) deferral |  | Merger settlement will offer opportunity to lower deferral balance. |  | Pat | Frank Rische
| Main/Pjm | Com Ed Dist Rate Case |  | Assisting with Texas delivery service rate issues.
Mid America Rate Case
| URM/ECAR | Consumers Energy Unbundling Filing |  | Unbundling current rates, intervened in the case through Energy Michigan, a coalition of marketers and IPPS. |  | - | Janine/Kerry
| URM/West |  |  |  |  | Robert
| C-O-W | Oregon Restructuring |  | Meeting with EWS Origination to address issues/ GA support.
|  | PG&E |  | Evaluating potential rate increase exposure
|  | SCE |  | Evaluating potential rate increase exposure
|  | SDG&E |  | Evaluating potential rate increase exposure
| URM/West | Southwest Gas |  |  |  | Pat | Leslie
| Other | Nevada Power |  | Avoid delay in Direct Access Date
|  | Sierra Pacific |  | Avoid delay in Direct Access Date
|  | Arizona Public Service |  | Avoid delay in Direct Access Date
ENA | Storage | Base Gas Monetization Regulatory Support |  | Met with outside counsel and consultants. Reviewing economic model for assumptions. |  | Robert | Donna Fulton
Global | LNG | Elba Island Cerfiticate Application Regulatory Support |  | Review cerficate orders, letter agreement. Provided comments on pricing provisions in Purchase/ Sales agreement. Intervention in certificate amendment expected. |  | Robert | Lisa Yoho