## taskingletter
ENRON ENGINEERING & CONSTRUCTION TASKING LETTER
Customer Company Name |  |  | Enron North America | Date: | 1999-12-17
1. Project Name |  |  | Delmarva Project Due Diligence | Start Date: | 1999-12-17
312 MW SCGT facility
2. Scope of work requested (Provide attachment if necessary):
see attached
Project is a 312 MW nominal rated SCGT located in Virginia
3. Cost Estimate: |  |  | 85000
(provide additional detail with attachment if necessary)
4. Completion Date: |  |  | 2000-03-31
(provide milestone(s) by attachment if necessary)
Estimate by:
| EE&CC Development Engineer |  | Bruce Golden | Date:
print name
| EE&CC Project Manager |  |  | Date:
print name
| EE&CC Vice President Approval |  |  | Date:
signature
| EE&CC VP Proj Dev Approval |  |  | Date:
| (if estimate over $50,000) |  | signature
EE&CC Development Engineer Approval |  |  |  | Date:
Signature
EE&CC Project Manager Approval |  |  |  | Date:
Signature
Customer's Representative
Print Name
Customer's Approval |  |  |  | Date:
Signature
5. EE&CC Work Order Number:
Accounting Signature: |  |  |  | Date:
6. Tasking Letter Closure
Completed:
Cancelled:
| Final Cost: |  |  | Date:
EE&CC Development Engineer |  |  |  | Date:
EE&CC Manager |  |  |  | Date:
Lead Developer |  |  |  | Date:

## simplesummary
EECC PROJECT STAFFING |  | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-03 | 2000-04-03 | Total | rate | Total Costs
|  | mnhrs | mnhrs | mnhrs | mnhrs | mnhrs | mnhrs | $/mnhr
| PROJECT MANAGER | 0 | 0 | 0 | 0 | 0 | 0 | 125 | 0
| PROJECT ENGINEERING MANAGER | 20 | 80 | 60 | 0 | 0 | 160 | 95 | 15200
| ASSISTANT PROJECT MANAGER | 0 | 0 | 0 | 0 | 0 | 0 | 76.6667 | 0
| ENVIRONMENTAL SUPPORT/ENGR | 0 | 12 | 12 | 0 | 0 | 24 | 100 | 2400
| ESTIMATING | 0 | 25 | 15 | 0 | 0 | 40 | 90 | 3600
| SCHEDULING | 0 | 6 | 4 | 0 | 0 | 10 | 80 | 800
| COST ENGINEERING | 0 | 20 | 10 | 0 | 0 | 30 | 80 | 2400
| SPEC/EVAL ENGR | 0 | 80 | 60 | 0 | 0 | 140 | 90 | 12600
| PERFORMANCE/PROCESS ENGINEERING | 0 | 40 | 40 | 0 | 0 | 80 | 90 | 7200
| CONTRACTS | 0 | 40 | 12 | 0 | 0 | 52 | 90 | 4680
| CAD/design | 0 | 10 | 10 | 0 | 0 | 20 | 90 | 1800
| SECRETRIAL/ADMIN | 4 | 62.6 | 44.6 | 0 | 0 | 111.2 | 38.3333 | 4262.6667
| TOTAL | 24 | 375.6 | 267.6 | 0 | 0 | 667.2 |  | 54942.6667
| TOTAL EQUIVALENT STAFFING | 0.14118 | 2.2094 | 1.5741 | 0 | 0
NON-PAYROLL EXPENSES |  | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-03 | 2000-04-03 | Total |  | Total Costs
| TRAVEL | 1 | 2 | 0 | 0 | 0 | 3 | 1400 | 4200
| MISCELLANEOUS EXPENSES | 0 | 0 | 0 | 0 | 0 |  |  | 0
| TOTAL NON-PAYROLL EXPENSE | [7 empty] | 4200
THIRD PARTY COSTS |  | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-03 | 2000-04-03 | Total |  | Total Costs
|  | 0 | 0 | 0 | 0 | 0 |  |  | 0
|  | 0 | 0 | 0 | 0 | 0 |  |  | 0
| Environmental consultant | 0 | 15000 | 10000 | 0 | 0 |  |  | 25000
| TOTAL THIRD PARTY EXPENSE | [7 empty] | 25000
| CONTINGENCY | 0 | 0 | 0 | 0 | 0 |  |  | 0
| TOTAL COSTS | [7 empty] | 84142.6667
| rounded COSTS | [7 empty] | 85000
DEVELOPMENT ENGINEERING SUPPORT |  | 1999-12-01 | 2000-01-01 | 2000-02-01 | 2000-03-03 | 2000-04-03 | Total | rate | Total Costs
|  | mnhrs | mnhrs | mnhrs | mnhrs | mnhrs | mnhrs | $/mnhr
| LEAD DE GENERAL MANAGER | 0 | 4 | 4 | 0 | 0 | 8 | 180 | 1440
| DE GENERAL MANAGER | 8 | 16 | 12 | 0 | 0 | 36 | 153 | 5508
| SECRETRIAL/ADMIN | 2 | 5 | 4 | 0 | 0 | 11 | 38.3333 | 421.6667
| TOTAL | 10 | 25 | 20 | 0 | 0 | 55 |  | 7369.6667
| TOTAL EQUIVALENT STAFFING | 0.058824 | 0.14706 | 0.11765 | 0 | 0

## deliverables
Delmarva Power Project Due Diligence
Section number |  | Section Description | Example/Basis | Responsible to execute
TABLE OF CONTENTS
Section | Section Title
1 | Executive Summary
| 1.1 | Facility Design
| 1.2 | Station Performance
| 1.3 | Project Cost and Schedule
| 1.4 | Environmental, Permits and Licenses
| 1.5 | Contracts and Agreements
| 1.6 | Risk and Insurance Assessment
| 1.7 | Economic Analysis
| 1.8 | Conclusions
2 | Introduction
| 2.1 | Scope of Work
| 2.2 | Project Description
| 2.3 | Principal Project Participants
3 | Facility Design
| 3.1 | Approach
| 3.2 | General Facility Design
| 3.3 | Mechanical Systems
| 3.4 | Civil, Structural and Geotechnical
| 3.5 | Electrical Systems
| 3.6 | Instrumentation and Controls
| 3.7 | Water Treatment
| 3.8 | Off-Sites
4 | Station Performance
| 4.1 | Availability
| 4.2 | Performance Guarantees
| 4.3 | Power Production
| 4.4 | Fuel Consumption
| 4.5 | Performance Testing
5 | Project Costs
| 5.1 | EPC Cost
| 5.2 | Owner Soft Costs
| 5.3 | Annual Operating and Maintenance Cost
6 | Project Schedule
| 6.1 | Schedule Overview
| 6.2 | Engineering and Procurement
| 6.3 | Construction Schedule
7 | Environmental and Permitting
| 7.1 | Review of Available Permits and Licenses
| 7.2 | Un-issued Permits and Licenses
8 | Contracts and Agreements
| 8.1 | Engineering, Procurement and Construction Contract
| 8.2 | Power Purchase Agreement
| 8.3 | Operations and Maintenance Agreement
| 8.4 | Major Equipment Purchase Orders
| 8.5 | Fuel Agreement
9 | Risk and Insurance Assessment
| 9.1 | Engineering, Procurement and Construction Agreement
| 9.2 | Power Purchase Agreement
| 9.3 | Operations and Maintenance Agreement
| 9.4 | Major Equipment Purchase Orders
10 | Economic Analysis
| 10.1 | Engineering, Procurement and Construction Agreement
| 10.2 | Power Purchase Agreement
| 10.3 | Operations and Maintenance Agreement
| 10.4 | Major Equipment Purchase Orders
11 | Default Considerations
| 11.1 | Likely overhaul scope, schedule and cost
| 11.2 | O&M planning

## studyrequirements
|  | DELMARVA |  |  | 1
|  |  | DE | discipline | DE | discipline | DE | discipline | DE | discipline | DE | discipline | DE | discipline | DE | discipline | DE | discipline | DE | discipline | DE | discipline | DE | discipline
|  | 1999-12-17 | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr | mnhr
|  | total | 39.5 | 561 | 5 | 22 | 5 | 59 | 5.5 | 144 | 4 | 82 | 4 | 57 | 2 | 11 | 4 | 59 | 2 | 20 | 3 | 33 | 5 | 74
|  |  | COMPOSITE |  | Executive Summary |  | Introduction |  | Facility Design |  | Station Performance |  | Project Costs |  | Project Schedule |  | Contracts and Agreements |  | Risk and Insurance Assessment |  | Economic Analysis |  | Default Considerations
1 | DE prepares project summary fill-in data sheets |  | 2.5 | 0 | 2 | 0 | 0 | 0 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | meeting with discipline lead to informally review project/issue description, possible scope of work, available information and/or sources of data and solicit |  | 6 | 18 | 0 | 0 | 1 | 0 | 1 | 4 | 1 | 2 | 1 | 3 | 0 | 0 | 1 | 4 | 0 | 1 | 0 | 0 | 1 | 4
discipline questions, interface issues, possible staff, schedule, deliverables
3 | discipline prepares summary scope of work, estimate of resources/estimate of third party costs, summary of deliverables (attach examples of deliverables) |  | 0 | 14 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 4 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 0 | 0 | 2
if examples not available - at least table of contents
4 | DE prepares with PM tasking letter to cover all disciplines necessary for work , obtains customer approval, AFE signoff, has EE&CC paperwork established |  | 3 | 6 | 2 | 4 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
5 | DE conducts "kickoff" meeting with discipline |  | 9.5 | 28 | 0 | 0 | 2 | 4 | 1 | 4 | 1 | 2 | 1 | 3 | 0 | 0 | 1 | 6 | 0.5 | 1 | 1 | 2 | 2 | 6
discipline takes minutes and publishes
6 | Discipline conducts "discovery" - gets vendor data, plant data, weather data, ….. |  | 0 | 48 | 0 | 0 | 0 | 8 | 0 | 12 | 0 | 4 | 0 | 8 | 0 | 2 | 0 | 4 | 0 | 2 | 0 | 4 | 0 | 4
7 | work, work, work |  | 1 | 150 | 0 | 8 | 0 | 8 | 0 | 40 | 0 | 32 | 0 | 12 | 1 | 2 | 0 | 12 | 0 | 4 | 0 | 8 | 0 | 24
8 | Discipline lead reviews "first look" results with engineer |  | 0 | 24 | 0 | 0 | 0 | 2 | 0 | 9 | 0 | 2 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 4
9 | first look review meeting with engineer, lead discipline engineer, EE&CC DE/Business Dev |  | 9 | 30 | 1 | 2 | 1 | 4 | 1 | 6 | 1 | 3 | 1 | 3 | 0 | 2 | 1 | 2 | 1 | 2 | 1 | 2 | 1 | 4
should have summary report in "raw" form
should have calculations in "raw" form - Excel spreadsheets, hand calcs, …
discipline takes minutes and publishes
10 | work, work, work |  | 1 | 96 | 0 | 8 | 0 | 12 | 0 | 24 | 0 | 12 | 0 | 8 | 1 | 2 | 0 | 8 | 0 | 2 | 0 | 4 | 0 | 16
11 | Discipline lead reviews draft final report |  | 0 | 17 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 1 | 0 | 3
12 | Issue draft final report |  | 0 | 31 | 0 | 0 | 0 | 8 | 0 | 8 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 4 | 0 | 1 | 0 | 2 | 0 | 2
should have report summary including original question or request, recommendations and action items for further work (if appropriate)
should have calculations in final form (graphs, charts, tables, heat balances, …)
13 | review meeting with engineer, discipline lead engineer, EE&CC DE/Business Dev and Customer/Client |  | 7.5 | 19 | 0 | 0 | 1 | 2 | 1 | 4 | 1 | 3 | 1 | 2 | 0 | 0 | 1 | 3 | 0.5 | 1 | 1 | 2 | 1 | 2
discipline takes minutes and publishes
14 | incorporate review comments |  | 0 | 34 | 0 | 0 | 0 | 4 | 0 | 12 | 0 | 8 | 0 | 2 | 0 | 1 | 0 | 4 | 0 | 1 | 0 | 1 | 0 | 1
15 | Discipline lead reviews final report |  | 0 | 16 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 1 | 0 | 2 | 0 | 1
16 | Issue final report |  | 0 | 30 | 0 | 0 | 0 | 4 | 0 | 8 | 0 | 4 | 0 | 2 | 0 | 2 | 0 | 4 | 0 | 1 | 0 | 4 | 0 | 1
should have report summary including original question or request, recommendations and action items for further work (if appropriate)
should have calculations in final form (graphs, charts, tables, heat balances, …)
should have copies of any plant data, vendor data and/or ???? Included in report annex