## Exec Summary -ENE Long Turb Pos
Confidential Exhibit I - Enron Long Turbine Position 1 March 2000 5:15 pm F.Kelly6-6207
Item | Turbine (Scope/ Cycle) | Delivery Date(s) | Total MW ISO | Total Capex Commitment $MM | Possible Project Site
ENA
1 | 1 X West 501D5A Simple Cycle | 2000-05-30 | 122 | 24 | ENA - Electrocities, N. Carolina (Remove from "long" list soon when Electrocities confirmed)
2 | 24 X GE LM6000 | July2000 thru April 2001 | 1164 | 335 | Qty 2 - ENA/Electrocities Qty 1 - ENA/Las Vegas Co-Gen Qty 3 - City of Springfield Qty 5 - Sante Cooper Qty 6 - Peoples Qty 3 - ESA Possibly Qty 4 - ENA Other
3 | 1 X GE 7FA Simple Cycle (Cogen Tech Machine) | Aug-Sept 2000 | 156 | 35 | - ENA - Mid West (Peoples) - One of the three orig Cogen Tech Machines
4 | 1 X GE 7FA Combined Cycle (CogenTech Machine; STG not ordered yet) | Oct 2000 | 171 | 31 | ENA - Vitro
5 | 2 X Used ABB11N1 Simple Cycle | Avail Now | 166 | 26 | - Enron Canada Sarnia Peaker Proj - Sarnia DASH was in process
6 | 2 X Used GEC Fr 6B | Avail Now | 60 | 13 | Available
|  |  | 1839 | 464
CALME
7 | 9 X Pwr Barges (Philip GE Fr 6B) | Avail Now | 270 | 72 | APACHI - Lagos
EECC
8 | 2 X GE 7FA Comb Cycle (plus one steam turbine; old Naco machines) | Qty 1 - Aug 2001 Qty 1 - Sept 2001 STG - Sept 2001 | 480 | 90 | - ENA - Several Florida Projects - NESCO
9 | 1 X Siemens V94.2 + 1 Toshiba STG + HRSG 50 hz application | Nov 2001 | 240 | 63.5 | Croatia - Siemens (et all) released - Initial DASH (w/ cancellation risk signed) - EEL has taken cancellation risk
10 | 3 X 9FA STAG Power Islands Combined Cycle 50 hz application | Qty 1 - Oct 2001 Qty 1 - Nov 2001 Qty 1 - Dec 2001 | 780 | 248.5 | EEL - Spain Arcos (Remv from "long" list when firm)
|  |  | 1500 | 402
| Total (Long) |  | 3609 | 938
Confidential - Negot's Potentially Resulting in Additional Long Position 2 March 2000 7:58 am F.Kelly6-6207
Item | Turbine (Scope/ Cycle) | Delivery Date(s) | Total MW ISO | Total Capex Commitment $MM | Possible Project Site
ENA
1 | 5 X Fiat TG50 Used - ENEL (Westinghouse 501D Liscense) 50 hz to be conv to 60 hz | Immed after conversion | 445 | 102 | - ENA various sites - RAC DASH Cmpltd w/ Bd Aprvl - ENEL board to apprv Enron proposal
2 |  |  | 0 | 0
|  |  | 445 | 102
ESA
3 | 2 X GE 7EA's | Qty 1 - Feb 2001 Qty 1 - Feb 2002 | 156 | 36 | Puerto Suarez
4 | 2 X 501F MHI Simple Cycle | Qty 1 - May 2001 Qty 1 - Oct 2001 | 368 | 74.5 | - ESA Light; Cuiaba II; or other Contract being finalized (initialed) - RAC DASH Cmpltd w/ Bd Aprvl
5 | 2 X 501F Westinghouse Simple Cycle | Qty 1 - July 2001 Qty 1 - Aug 2001 | 368 | 70 | - ESA Light; Cuiaba II; or other - Negot's progressing w/ West - RAC DASH Cmpltd w/ Bd Aprvl
|  |  | 892 | 180.5
EECC
6 | 1 X 501D5A Simple Cycle | Nov 2001 | 122 | 24 | - CAMLE - Panama or other - RAC DASH Cmpltd w/ Bd Aprvl - Hold till ESA 501F negot'ed
7 | 2 X GE 7FA's + 1 STG | Qty 1 - July 2001 Qty 1 - Aug 2001 STG - Aug 2001 | 600 | 95 | - Gen Power - Dell, AR - Duct Fired
8 | 2 X GE 7FA's + 1 STG | Qty 1 - Sept 2001 Qty 1 - Oct 2001 STG - Sept 2001 | 600 | 95 | - Gen Power - McAdam, MS - Duct Fired
|  |  | 1322 | 214
| Total - (Negotiating To Be Long) |  | 2659 | 496.5