## Full Turbine Position Spreadsht
Confidential Turbines For Confirmed Deals - Not Long 8 June 2000 5:32 am F.Kelly6-6208
Per EECC
| Item | Turbine (Scope/ Cycle) | Off Bal Sht? | Delivery Date(s) | Total MW ISO | Total Capex Commitment $MM | Initial $/KW | Possible Project Site | Paid to Date $MM | % Enron Ownership | Contract Status | Enron Ownership | Payment and Termination Schedule | Current Cancelation Obligation (Worst Case Long Position) $MM | Salvage Value $MM | Salvage Value $/KW | Current Liquidation "Position" (Salvage less Tot Cmmtmnt) $MM | Current Minimal Position Cancll or Liquidate $MM | Potential Deal PV $MM | Carrying Cost MM$/Mo @ 10%
ENA
Green | 1 | 4 X GE LM6000 | West LB | ??Nov/Dec 2000?? | 194 | 55.8333 | 287.8007 | ENA/City of Austin | 8.5 |  | Executed | ENA | To Be Provided
Green | 2 | 1 X GE 7FA - Now Simple Cycle (old Naco machine) | OBS | Qty 1 - Aug 2001 | 156 | 36 | 230.7692 | Coyote Springs NEPCO Project | 7 |  | Executed | ENA | To Be Provided | 8 | -70 | 448.7179 | -34 | 8 | 20 | #REF!
Green | 3 | 8 X GE 7EA Simple Cycle |  | Shipped | 680 | 142 | 208.8235 | ENA 2000 Pkrs - Lincoln Center, Ill | 135 |  | Executed | ENA | N/A
Green | 4 | 2 X GE 7EA Simple Cycle |  | Shipped | 158 | 36 | 227.8481 | ENA - Doyle | 22 |  | Executed | ENA | N/A
Green | 5 | 1 X GE 7EA Simple Cycle |  | Shipped | 78 | 18 | 230.7692 | ENA - TECO |  |  | Executed | ENA | N/A
Green | 6 | 1 X GE 7FA Simple Cycle (Cogen Tech Machine) |  | Aug 2000 | 156 | 35 | 224.359 | ENA - East Coast Pwr - Linden 6 Confirm GE Re-Structuring Enron Partial Owner | 20 | 30% | Executed | ENA | To Be Provided | 2.1
Green | 7 | 3 X Used GE 7B Simple Cycle Korean used/refurb equip |  | Refurb/Shipped | 165 | 41 | 248.4848 | ENA - Doyle | 22.3 |  | Executed | ENA | N/A
Green | 8 | 4 X W501D5A Simple Cycle |  | Shipped | 488 | 86 | 176.2295 | ENA 2000 Pkrs - Wheatland, Ind | 82 |  | Executed | ENA | N/A
Green | 9 | 3 X W501F Simple Cycle |  | Shipped | 552 | 95 | 172.1014 | ENA 2000 Pkrs - Gleason, Tn | 86 |  | Executed | ENA | N/A
[7 empty] | #DIV/0! |  | 382.8
|  | Total ENA |  |  | 2627 | 544.8333 | 207.3975 |  | 382.8
Confidential Enron Turbine Long Position 8 June 2000 5:32 am F.Kelly6-6208
|  | Per EECC |  |  |  |  | F |  | H | I |  |  |  | J | K | L = K / D | M = K - E | N = Smaller of J or M
| Item | Turbine (Scope/ Cycle) | Off Bal Sht? | Delivery Date(s) | Total MW ISO | Total Capex Commitment $MM | Initial $/KW | Possible Project Site | Paid to Date $MM | % Enron Ownership | Contract Status | Enron Ownership |  | Current Cancelation Obligation (Worst Case Long Position) $MM | Salvage Value $MM | Salvage Value $/KW | Current Liquidation "Position" (Salvage less Tot Cmmtmnt) $MM | Current Minimal Position Cancll or Liquidate $MM | Potential Deal PV $MM | Carrying Cost MM$/Mo @ 10%
ENA
Yellow | 1 | 4 X GE LM6000 | West LB | ?????July2000 thru April 2001 | 194 | 55.8333 | 287.8007 | Qty 4 - ENA/Las Vegas Co-Gen II | 8.5 |  | Executed | ENA | To Be Provided | 13 | -279 | 1438.1443 | -223.1667 | 13 | 20 | #REF!
Red | 2 | 16 X GE LM6000 | West LB | July2000 thru April 2001 | 776 | 223.3333 | 287.8007 | Qty 2 - City of San Antonio Qty 6 - Peoples ***** Qty 6 - East Kentucky Co-op Qty 2 - Con Ed Qty 6 - Florida Merchant Qty 3 - ESA Puerto Suarez Qty 4 - ESA Electrobolt Qty 2 - CALME Venez LNG - Total - Over 26 Opportunities | 34 |  | Executed | ENA | To Be Provided | 13 | -279 | 359.5361 | -55.6667 | 13 | 20 | #REF!
Green | 3 | 1 X GE 7FA Simple Cycle (Cogen Tech Machine) | West LB | Aug-Sept 2000 | 156 | 35 | 224.359 | - ENA - Mid West (Peoples/Dominion) - EECC role to be OE at most - One of the three orig Cog Tech - Sold to Peoples; put expired - Peoples attempting to put at Ellwd - keep on long list per Miller | 7 |  | Executed | ENA | To Be Provided | 8 | -32 | 205.1282 | 3 | 3 | 8 | #REF!
Green | 4 | 1 X GE 7FA Combined Cycle (CogenTech Machine; ABB STG not ordered yet) | OBS | Oct 2000 | 171 | 31 | 181.2865 | - ENA - Vitro - Move off long list soon | 26 |  | Executed | ENA | To Be Provided | 31 | -35 | 204.6784 | -4 | -4 | 23 | #REF!
Yellow | 5 | 3 X GE 7FA + Qty 2 STG's Comb Cycle | OBS | July 2002 | 750 | 220 | 293.3333 | ENA - Pastoria, Calif; Catalytica Comb Syst $5MM due in Aug/Sept 2000 | 0 |  | In Negotiation | ENA | To Be Provided
Green | 6 | 1 X Used Korean Steam Turbine | OBS | Avail Now | 110 | 2.3 | 20.9091 | - Pkg w/Doyle Korean Used GE7B's - negligible amount paid |  |  | Executed | ENA | N/A
Green | 7 | 2 X GE 7FA - Now Simple Cycle (no STG; old Naco machines) | OBS | Qty 1 - Sept 2001 | 240 | 36 | 150 | - NEPCO/NESCO - Goldendale | 7 |  | In Negotiation | ENA | To Be Provided | 8 | -70 | 291.6667 | -34 | 8 | 20 | #REF!
Red | 8 | 2 X Used GEC Fr 6B 50hz | OBS | Avail Now | 60 | 13 | 216.6667 | - Available - Possibly convert to 60 hz & mount on barges for LIPA | 13 |  | Executed | ENA | N/A | 13 | -8 | 133.3333 | 5 | 5 | 0 | #REF!
|  | Subtotal |  |  | 2457 | 616.4667 | 250.9022 |  | 95.5 |  |  |  |  | 86 | -703 | 286.1213 | -308.8333 | 38 | 91 | #REF!
Enron Canada
Red | 9 | 2 X Used ABB11N1 Simple Cycle | West LB | Avail Now | 166 | 26 | 156.6265 | - Enron Canada Sarnia/Moore Peaker Proj | 26 |  | Executed | Enron Canada | N/A | 26 | -24 | 144.5783 | 2 | 2 | 5 | #REF!
|  | Total ENA |  |  | 2623 | 642.4667
Confidential Enron Turbine Long Position 8 June 2000 5:32 am F.Kelly6-6208
|  | Per EECC |  |  |  |  | F |  | H | I |  |  |  | J | K | L = K / D | M = K - E | N = Smaller of J or M
| Item | Turbine (Scope/ Cycle) | Off Bal Sht? | Delivery Date(s) | Total MW ISO | Total Capex Commitment $MM | Initial $/KW | Possible Project Site | Paid to Date $MM | % Enron Ownership | Contract Status | Enron Ownership |  | Current Cancelation Obligation (Worst Case Long Position) $MM | Salvage Value $MM | Salvage Value $/KW | Current Liquidation "Position" (Salvage less Tot Cmmtmnt) $MM | Current Minimal Position Cancll or Liquidate $MM | Potential Deal PV $MM | Carrying Cost MM$/Mo @ 10%
CALME
Red | 10 | 3 X Pwr Barges (Philip GE Fr 6B) | OBS | Avail Now | 90 | 24 | 266.6667 | APACHI - Lagos | 24 |  | Executed | CALME (BargeCo) | N/A | 54 | -45 | 500 | -21 | -21 | 11 | #REF!
Yellow | 11 | 6 X Pwr Barges (Philip GE Fr 6B) | OBS | Avail Now | 180 | 48 | 266.6667 | APACHI - Lagos | 48 |  | Executed | CALME (BargeCo) | N/A | 54 | -45 | 250 | 3 | 3 | 11 | #REF!
|  | Total CALME |  |  | 270 | 72 | 266.6667 |  | 72 |  |  |  |  | 108 | -90 | 333.3333 | -18 | -18
ESA
Red | 12 | 2 X 501F MHI Simple Cycle | West LB | Qty 1 - May 2001 Qty 1 - Oct 2001 | 368 | 74.5 | 202.4457 | - ESA Light; Cuiaba II; or other Contract being finalized (initialed) - RAC DASH Cmpltd w/ Bd Aprvl - Option for two more - see negot'ing turbines | 0 |  | Executed | ESA | To Be Provided | 0 | -45 | 122.2826 | 29.5 | 29.5 | 11 | #REF!
|  | Total ESA |  |  | 368 | 74.5 | 202.4457 |  | 0 |  |  |  |  | 0 | -45 | 122.2826 | 29.5 | 29.5
EECC
Red | 13 | 1 X West 501D5A Simple Cycle | OBS | 2000-09-30 | 122 | 24 | 196.7213 | -Was to be used at ENA/Electrocities, but not approved by Customer board -Janet Deitrich and David Haug exploring | 21 |  | Executed | EECC (Enron Equipment Procurement Company) | N/A | 24 | -24 | 196.7213 | 0 | 0 | 20 | #REF!
Red | 14 | 2 X GE 7EA's | OBS | Qty 1 - 10 Mar 2001 Qty 1 - Feb 2002 | 156 | 36 | 230.7692 | - ENA or EECC 3rd Pty (Blue Dog) - ENA BP Amaco (Choc Bayou) - ENA Central Iowa | 7 |  | In Negotiation | EECC (Enron Engr & Constr Company) | To Be Provided | 8 | -70 | 448.7179 | -34 | 8 | 20 | #REF!
Yellow | 15 | 2 X GE 7FA's w/ STG (confirm STG) | West LB | Qty 1 - July 2001 Qty 1 - Aug 2001 STG - Aug 2001 | 600 | 95 | 158.3333 | - Gen Power - Dell, AR - Duct Fired |  |  | In Negotiation | EECC (Enron Engr & Constr Company) | To Be Provided
Yellow | 16 | 2 X GE 7FA's w/ STG | West LB | Qty 1 - Sept 2001 Qty 1 - Oct 2001 STG - Sept 2001 | 600 | 95 | 158.3333 | - Gen Power - McAdam, MS - Duct Fired |  |  | In Negotiation | EECC (Enron Engr & Constr Company) | To Be Provided
Yellow | 17 | 1 X Siemens V94.2 + 1 Toshiba STG + HRSG 50 hz application | OBS | Nov 2001 | 240 | 63.5 | 264.5833 | Croatia - Siemens (et all) released - Initial DASH (w/ cancellation risk signed) - EEL has taken cancellation risk | 0 |  | Cancelled | EECC (Enron Engr & Constr Company) | N/A | 3 | -60 | 250 | 3.5 | 3 | 16 | #REF!
Yellow | 18 | 3 X 9FA STAG Power Islands Combined Cycle 50 hz application | OBS | Qty 1 - Oct 2001 Qty 1 - Nov 2001 Qty 1 - Dec 2001 | 780 | 248.5 | 318.5897 | EEL - Spain Arcos (Remv from "long" list when firm) | 0 |  | In Negotiation | EECC (Enron Equipment Procurement Company) | To Be Provided | 17 | -225 | 288.4615 | 23.5 | 17 | 25 | #REF!
|  | Total EECC |  |  | 2498 | 562 | 224.98 |  | 7 |  |  |  |  | 28 | -355 | 142.1137 | -7 | 28 | 61 | #REF!
|  | Total (Long) |  |  | 5759 | 1350.9667 | 234.5836 |  | 174.5 |  |  |  |  | 222 | -1193 | 207.154 | -304.3333 | 77.5 | 152 | #REF!
Confidential - Negot's Potentially Resulting in Additional Long Position 8 June 2000 5:32 am F.Kelly6-6207
Per EECC
F
| Item | Turbine (Scope/ Cycle) | Off Bal Sht? | Delivery Date(s) | Total MW ISO | Total Capex Commitment $MM | Initial $/KW | Possible Project Site | Paid to Date $MM | % Enron Ownership | Contract Status | Enron Ownership |  | Current Cancelation Obligation (Worst Case Long Position) $MM | Salvage Value $MM | Salvage Value $/KW | Current Liquidation "Position" (Salvage less Tot Cmmtmnt) $MM | Current Minimal Position Cancll or Liquidate $MM | Potential Deal PV $MM | Carrying Cost MM$/Mo @ 10%
ENA
Red | 1 | 2 X ABB 11N2's | [5 empty] | For Enron Canada - Moore Project - Option paid (or to be paid for $500K) |  |  | In Negotiation | Enron Canada | N/A
[5 empty] | 0 | 0
|  | Total ENA |  |  | 0 | 0
ESA
Red | 2 | 2 X 501F MHI Simple Cycle | West LB | Qty 1 - July 2001 Qty 1 - Aug 2001 | 368 | 70 | 190.2174 | - ESA Light; Cuiaba II; or other Contract being finalized (initialed) - RAC DASH Cmpltd w/ Bd Aprvl |  |  | In Negotiation | ESA | N/A
|  | Total ESA |  |  | 368 | 70 | 190.2174
CALME
[5 empty] | 0 |  |  | Oman
[5 empty] | 0 | 0
EECC
Red | 3 | 1 X 501D5A Simple Cycle |  | Nov 2001 | 122 | 24 | 196.7213 | - CAMLE - Saudi Bid or EECC 3rd Pty or ENA - RAC DASH Cmpltd w/ Bd Aprvl - Blue Girl |  |  | In Negotiation | EECC (Enron Engr & Constr Company) | To Be Provided
|  | Total EECC |  |  | 122 | 24 | 196.7213
|  | Total - (Negotiating To Be Long) |  |  | 490 | 94 | 191.8367