## Sheet1
Office | Number of observations | Closed observations | Open observations with target date after 8/4/00 | Open observations having missed target date | Item that missed target date
Buenos Aires | 10 | 8 | 1 | 1 | 6 contracts still awaiting translation to English - someone has been hired to do all translations.
Calgary | 9 | 6 | 3
Frankfurt | 10 | 8 |  | 2 | Taping telephone lines, ability to produce geographical P&L
Helsinki | 7 | NA | NA | NA
London Phase I | 23 | 12 | 10 | 1 | Taping of mobile phones
London Phase II | 25 | 10 | 13 | 2 | Deal info on credit deal tickets not always complete, master agreements not always in place
Oslo | 9 | 8 |  | 1 | Translation of contracts into English
Sao Paulo | 7 | 4 | 1 | 2 | Translation of older, settled contracts into English, Cuiba positions not centrally managed with golbal crude oil positions.
Seoul | 2 |  | 2
Singapore | 6 | 5 |  | 1 | Use of mobile phones to make trades.
Sydney | 6 | 6
Global issues
Taping of phone lines (cost issue)
Use of mobile phones (should there be a ban on use of mobile phones as most are impossible to tape?)
Translations of settled contracts (all active and new contracts translated but do no one has performed translations of settled contracts)
Use of Enpower - is it required for all power trading offices or only ones with critical mass?