## Nov 2001
| # of Turbine which have operated > 90 days as of |  |  | 2001-11-30 | 67
| Weighted Average Enron Availability MTD |  |  | 2001-11-30 | 87.37%
MONTFORT - 20
EXHIBIT K
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
2001-11-01
2001-11-30 | 1 | 2001-05-07 | 2001-08-05 | 30 | 99.31% | 30 | 99.31% | 1 | May | 2
| 2 | 2001-06-27 | 2001-09-25 | 30 | 99.93% | 30 | 99.93% | 1 | June | 16
| 3 | 2001-05-17 | 2001-08-15 | 30 | 99.56% | 30 | 99.56% | 1 | July | 2 | Project Total to date | Commissioning completed
| 4 | 2001-06-27 | 2001-09-25 | 30 | 86.17% | 30 | 86.17% | 1 |  | 20 | Remaining
| 5 | 2001-06-27 | 2001-09-25 | 30 | 98.73% | 30 | 98.73% | 1 |  | 0
| 6 | 2001-06-01 | 2001-08-30 | 30 | 98.74% | 30 | 98.74% | 1
| 7 | 2001-06-27 | 2001-09-25 | 30 | 99.46% | 30 | 99.46% | 1
| 8 | 2001-06-11 | 2001-09-09 | 30 | 99.01% | 30 | 99.01% | 1
| 9 | 2001-06-11 | 2001-09-09 | 30 | 98.85% | 30 | 98.85% | 1
| 10 | 2001-06-28 | 2001-09-26 | 30 | 96.78% | 30 | 96.78% | 1
| 11 | 2001-06-28 | 2001-09-26 | 30 | 94.94% | 30 | 94.94% | 1
| 12 | 2001-06-21 | 2001-09-19 | 30 | 98.89% | 30 | 98.89% | 1
| 13 | 2001-06-28 | 2001-09-26 | 30 | 98.65% | 30 | 98.65% | 1
| 14 | 2001-06-28 | 2001-09-26 | 30 | 96.94% | 30 | 96.94% | 1
| 15 | 2001-06-28 | 2001-09-26 | 30 | 93.44% | 30 | 93.44% | 1
| 16 | 2001-06-28 | 2001-09-26 | 30 | 96.96% | 30 | 96.96% | 1
| 17 | 2001-06-30 | 2001-09-28 | 30 | 98.48% | 30 | 98.48% | 1
| 18 | 2001-07-02 | 2001-09-30 | 30 | 70.8% | 30 | 70.8% | 1
| 19 | 2001-07-02 | 2001-09-30 | 30 | 95.43% | 30 | 95.43% | 1
| 20 | 2001-06-30 | 2001-09-28 | 30 | 98.9% | 30 | 98.9% | 1
|  |  |  | Average | 96% |  |  | 20
|  |  |  | Weighted Average | 96%
Trent Mesa - 100
EXHIBIT I-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-08-13 | 2001-11-11 | 20 | 85.39% | 20 | 85.39% | 1 | July | 22
| 2 | 2001-08-13 | 2001-11-11 | 20 | 65.95% | 20 | 65.95% | 1 | August | 23
| 3 | 2001-08-13 | 2001-11-11 | 20 | 86.59% | 20 | 86.59% | 1 | September | 42
| 4 | 2001-08-22 | 2001-11-20 | 11 | 99.06% | 11 | 99.06% | 1 | October | 7
| 5 | 2001-08-22 | 2001-11-20 | 11 | 97% | 11 | 97% | 1 | November | 6 | Project Total to date | Commissioning completed
| 6 | 2001-08-22 | 2001-11-20 | 11 | 99.33% | 11 | 99.33% | 1 |  | 100 | Remaining
| 7 | 2001-08-21 | 2001-11-19 | 12 | 89.02% | 12 | 89.02% | 1 |  | 0
| 8 | 2001-08-28 | 2001-11-26 | 5 | 92.31% | 5 | 92.31% | 1
| 9 | 2001-08-22 | 2001-11-20 | 11 | 78.24% | 11 | 78.24% | 1
| 10 | 2001-08-22 | 2001-11-20 | 11 | 85.14% | 11 | 85.14% | 1
| 11 | 2001-08-17 | 2001-11-15 | 16 | 84.44% | 16 | 84.44% | 1
| 12 | 2001-08-13 | 2001-11-11 | 20 | 99.69% | 20 | 99.69% | 1
| 13 | 2001-08-22 | 2001-11-20 | 11 | 69.64% | 11 | 69.64% | 1
| 14 | 2001-08-13 | 2001-11-11 | 20 | 88.2% | 20 | 88.2% | 1
| 15 | 2001-08-22 | 2001-11-20 | 11 | 98.78% | 11 | 98.78% | 1
| 16 | 2001-08-28 | 2001-11-26 | 5 | 81.85% | 5 | 81.85% | 1
| 17 | 2001-08-28 | 2001-11-26 | 5 | 86.83% | 5 | 86.83% | 1
| 18 | 2001-08-28 | 2001-11-26 | 5 | 97.26% | 5 | 97.26% | 1
| 19 | 2001-08-22 | 2001-11-20 | 11 | 97.2% | 11 | 97.2% | 1
| 20 | 2001-08-13 | 2001-11-11 | 20 | 96.97% | 20 | 96.97% | 1
| 21 | 2001-08-06 | 2001-11-04 | 27 | 73.27% | 27 | 73.27% | 1
| 22 | 2001-07-26 | 2001-10-24 | 30 | 89% | 30 | 89% | 1
| 23 | 2001-07-26 | 2001-10-24 | 30 | 37.72% | 30 | 37.72% | 1
| 24 | 2001-07-26 | 2001-10-24 | 30 | 98.89% | 30 | 98.89% | 1
| 25 | 2001-07-26 | 2001-10-24 | 30 | 98.79% | 30 | 98.79% | 1
| 26 | 2001-07-26 | 2001-10-24 | 30 | 97.19% | 30 | 97.19% | 1
| 27 | 2001-07-26 | 2001-10-24 | 30 | 99.57% | 30 | 99.57% | 1
| 28 | 2001-07-26 | 2001-10-24 | 30 | 84.06% | 30 | 84.06% | 1
| 29 | 2001-07-26 | 2001-10-24 | 30 | 87.85% | 30 | 87.85% | 1
| 30 | 2001-07-26 | 2001-10-24 | 30 | 91.15% | 30 | 91.15% | 1
| 31 | 2001-07-26 | 2001-10-24 | 30 | 91.58% | 30 | 91.58% | 1
| 32 | 2001-09-18 | 2001-12-17 | 0 | 72.78% | 0 | 72.78% | 0
| 33 | 2001-07-26 | 2001-10-24 | 30 | 99.07% | 30 | 99.07% | 1
| 34 | 2001-07-26 | 2001-10-24 | 30 | 27.94% | 30 | 27.94% | 1
| 35 | 2001-07-26 | 2001-10-24 | 30 | 51.26% | 30 | 51.26% | 1
| 36 | 2001-07-26 | 2001-10-24 | 30 | 68.38% | 30 | 68.38% | 1
| 37 | 2001-07-26 | 2001-10-24 | 30 | 81.54% | 30 | 81.54% | 1
| 38 | 2001-07-26 | 2001-10-24 | 30 | 95.51% | 30 | 95.51% | 1
| 39 | 2001-07-26 | 2001-10-24 | 30 | 98.55% | 30 | 98.55% | 1
| 40 | 2001-07-26 | 2001-10-24 | 30 | 92.31% | 30 | 92.31% | 1
| 41 | 2001-07-26 | 2001-10-24 | 30 | 96.02% | 30 | 96.02% | 1
| 42 | 2001-07-26 | 2001-10-24 | 30 | 97.4% | 30 | 97.4% | 1
| 43 | 2001-07-26 | 2001-10-24 | 30 | 81.37% | 30 | 81.37% | 1
| 44 | 2001-07-26 | 2001-10-24 | 30 | 95.49% | 30 | 95.49% | 1
| 45 | 2001-08-13 | 2001-11-11 | 20 | 95.48% | 20 | 95.48% | 1
| 46 | 2001-09-18 | 2001-12-17 | 0 | 72.84% | 0 | 72.84% | 0
| 47 | 2001-08-28 | 2001-11-26 | 5 | 96.5% | 5 | 96.5% | 1
| 48 | 2001-08-28 | 2001-11-26 | 5 | 91.31% | 5 | 91.31% | 1
| 49 | 2001-09-18 | 2001-12-17 | 0 | 92.39% | 0 | 92.39% | 0
| 50 | 2001-11-02 | 2002-01-31 | 0 | 84.2% | 0 | 84.2% | 0
| 51 | 2001-09-18 | 2001-12-17 | 0 | 34.08% | 0 | 34.08% | 0
| 52 | 2001-09-04 | 2001-12-03 | 0 | 93.03% | 0 | 93.03% | 0
| 53 | 2001-09-18 | 2001-12-17 | 0 | 77.47% | 0 | 77.47% | 0
| 54 | 2001-09-04 | 2001-12-03 | 0 | 94.96% | 0 | 94.96% | 0
| 55 | 2001-08-29 | 2001-11-27 | 4 | 51.1% | 4 | 51.1% | 1
| 56 | 2001-09-04 | 2001-12-03 | 0 | 83.16% | 0 | 83.16% | 0
| 57 | 2001-09-04 | 2001-12-03 | 0 | 98.46% | 0 | 98.46% | 0
| 58 | 2001-09-18 | 2001-12-17 | 0 | 39.02% | 0 | 39.02% | 0
| 59 | 2001-09-18 | 2001-12-17 | 0 | 95.49% | 0 | 95.49% | 0
| 60 | 2001-09-18 | 2001-12-17 | 0 | 73.1% | 0 | 73.1% | 0
| 61 | 2001-09-18 | 2001-12-17 | 0 | 75.69% | 0 | 75.69% | 0
| 62 | 2001-09-18 | 2001-12-17 | 0 | 79.12% | 0 | 79.12% | 0
| 63 | 2001-09-18 | 2001-12-17 | 0 | 75.53% | 0 | 75.53% | 0
| 64 | 2001-09-04 | 2001-12-03 | 0 | 80.96% | 0 | 80.96% | 0
| 65 | 2001-09-18 | 2001-12-17 | 0 | 45.38% | 0 | 45.38% | 0
| 66 | 2001-09-18 | 2001-12-17 | 0 | 89.59% | 0 | 89.59% | 0
| 67 | 2001-11-02 | 2002-01-31 | 0 | 33.76% | 0 | 33.76% | 0
| 68 | 2001-09-18 | 2001-12-17 | 0 | 85.34% | 0 | 85.34% | 0
| 69 | 2001-09-18 | 2001-12-17 | 0 | 91.69% | 0 | 91.69% | 0
| 70 | 2001-09-06 | 2001-12-05 | 0 | 72.15% | 0 | 72.15% | 0
| 71 | 2001-09-18 | 2001-12-17 | 0 | 93.43% | 0 | 93.43% | 0
| 72 | 2001-09-07 | 2001-12-06 | 0 | 88.45% | 0 | 88.45% | 0
| 73 | 2001-09-18 | 2001-12-17 | 0 | 32.49% | 0 | 32.49% | 0
| 74 | 2001-09-18 | 2001-12-17 | 0 | 95.32% | 0 | 95.32% | 0
| B-5 | 2001-10-20 | 2002-01-18 | 0 | 69.61% | 0 | 69.61% | 0
| 76 | 2001-09-18 | 2001-12-17 | 0 | 41.11% | 0 | 41.11% | 0
| 77 | 2001-09-18 | 2001-12-17 | 0 |  | 0 | 0% | 0
| 78 | 2001-09-18 | 2001-12-17 | 0 | 74.82% | 0 | 74.82% | 0
| 79 | 2001-09-18 | 2001-12-17 | 0 | 88.43% | 0 | 88.43% | 0
| 80 | 2001-09-18 | 2001-12-17 | 0 | 93.56% | 0 | 93.56% | 0
| 81 | 2001-09-18 | 2001-12-17 | 0 | 94.6% | 0 | 94.6% | 0
| 82 | 2001-09-18 | 2001-12-17 | 0 | 74.52% | 0 | 74.52% | 0
| 83 | 2001-09-18 | 2001-12-17 | 0 | 77.59% | 0 | 77.59% | 0
| 84 | 2001-09-18 | 2001-12-17 | 0 | 80.25% | 0 | 80.25% | 0
| 85 | 2001-09-18 | 2001-12-17 | 0 | 90.72% | 0 | 90.72% | 0
| 86 | 2001-09-18 | 2001-12-17 | 0 | 98.41% | 0 | 98.41% | 0
| 87 | 2001-09-07 | 2001-12-06 | 0 | 83.42% | 0 | 83.42% | 0
| 88 | 2001-09-18 | 2001-12-17 | 0 | 47.08% | 0 | 47.08% | 0
| 89 | 2001-09-07 | 2001-12-06 | 0 | 94.9% | 0 | 94.9% | 0
| 90 | 2001-09-18 | 2001-12-17 | 0 | 39.04% | 0 | 39.04% | 0
| 91 | 2001-11-02 | 2002-01-31 | 0 | 97.48% | 0 | 97.48% | 0
| 92 | 2001-11-02 | 2002-01-31 | 0 | 60.87% | 0 | 60.87% | 0
| 93 | 2001-10-31 | 2002-01-29 | 0 | 99.97% | 0 | 99.97% | 0
| 94 | 2001-10-25 | 2002-01-23 | 0 | 72.81% | 0 | 72.81% | 0
| 95 | 2001-11-06 | 2002-02-04 | 0 | 84.02% | 0 | 84.02% | 0
| 96 | 2001-11-06 | 2002-02-04 | 0 | 59.9% | 0 | 59.9% | 0
| B-6 | 2001-10-22 | 2002-01-20 | 0 | 8.4% | 0 | 8.4% | 0
| B-7 | 2001-10-22 | 2002-01-20 | 0 | 57.27% | 0 | 57.27% | 0
| B-8 | 2001-10-19 | 2002-01-17 | 0 | 34.67% | 0 | 34.67% | 0
| B-9 | 2001-10-19 | 2002-01-17 | 0 | 12.9% | 0 | 12.9% | 0
|  |  |  | Average | 79.13% |  |  | 47
|  |  |  | Weighted Average | 83.7%
Mill Run - 10 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-11-02 | 2002-01-31 | 0 |  | 0 | 0% | 0
| 2 | 2001-11-02 | 2002-01-31 | 0 |  | 0 | 0% | 0
| 3 | 2001-11-02 | 2002-01-31 | 0 |  | 0 | 0% | 0 | November | 10 | Project Total to date | Commissioning completed
| 4 | 2001-11-02 | 2002-01-31 | 0 |  | 0 | 0% | 0 |  | 10 | Remaining
| 5 | 2001-11-02 | 2002-01-31 | 0 |  | 0 | 0% | 0 |  | 0
| 6 | 2001-11-02 | 2002-01-31 | 0 |  | 0 | 0% | 0
| 7 | 2001-11-02 | 2002-01-31 | 0 |  | 0 | 0% | 0
| 8 | 2001-11-02 | 2002-01-31 | 0 |  | 0 | 0% | 0
| 9 | 2001-11-02 | 2002-01-31 | 0 |  | 0 | 0% | 0
| 10 | 2001-11-02 | 2002-01-31 | 0 |  | 0 | 0% | 0 | Special note: | Turbines 1, 3 & 4 Previously commissioned on 9/26
|  |  |  | Average | #DIV/0! |  |  | 0 |  | Turbines 6, 7 & 8 Previously commissioned on 9/27
|  |  |  | Weighted Average | #DIV/0!
Fenner - 20 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 2 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 | November | 0
| 3 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 | December | 20 | Project Total to date | Commissioning completed
| 4 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 |  | 20 | Remaining
| 5 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 |  | 0
| 6 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 7 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 8 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 9 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 10 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 11 | 2001-12-18 | 2002-03-18 | 0 |  | 0 | 0% | 0
| 12 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 13 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 14 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 15 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 16 | 2001-12-18 | 2002-03-18 | 0 |  | 0 | 0% | 0
| 17 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 18 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 19 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 20 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!
Somerset - 6 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0
| 2 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0
| 3 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0 | November | 6 | Project Total to date | Commissioning completed
| 4 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0 |  | 6 | Remaining
| 5 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0 |  | 0
| 6 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!
Klondike - 16 WTG
EXHIBIT K-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0
| 2 | 2001-12-30 | 2002-03-30 | 0 |  | 0 | 0% | 0 | November | 0
| 3 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0 | December | 16 | Project Total to date | Commissioning completed
| 4 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0 |  | 16 | Remaining
| 5 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0 |  | 0
| 6 | 2001-12-30 | 2002-03-30 | 0 |  | 0 | 0% | 0
| 7 | 2001-12-30 | 2002-03-30 | 0 |  | 0 | 0% | 0
| 8 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 9 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 10 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 11 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0
| 12 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 13 | 2001-12-28 | 2002-03-28 | 0 |  | 0 | 0% | 0
| 14 | 2001-12-28 | 2002-03-28 | 0 |  | 0 | 0% | 0
| 15 | 2001-12-28 | 2002-03-28 | 0 |  | 0 | 0% | 0
| 16 | 2001-12-27 | 2002-03-27 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!
IM - I - 17 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 31 | 2001-12-12 | 2002-03-12 | 0 |  | 0 | 0% | 0
| 32 | 2001-12-12 | 2002-03-12 | 0 |  | 0 | 0% | 0 | November | 0
| 33 | 2001-12-14 | 2002-03-14 | 0 |  | 0 | 0% | 0 | December | 17 | Project Total to date | Commissioning completed
| 34 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 |  | 17 | Remaining
| 35 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0 |  | 0
| 36 | 2001-12-09 | 2002-03-09 | 0 |  | 0 | 0% | 0
| 37 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 38 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 39 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 40 | 2001-12-07 | 2002-03-07 | 0 |  | 0 | 0% | 0
| 41 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 42 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 43 | 2001-12-10 | 2002-03-10 | 0 |  | 0 | 0% | 0
| 44 | 2001-12-09 | 2002-03-09 | 0 |  | 0 | 0% | 0
| 45 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 46 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 47 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!
IM - II - 90 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0
| 2 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0 | November | 62
| 3 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0 | December | 28 | Project Total to date | Commissioning completed
| 4 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0 |  | 90 | Remaining
| 5 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0 |  | 0
| 7 | 2001-11-23 | 2002-02-21 | 0 |  | 0 | 0% | 0
| 8 | 2001-11-23 | 2002-02-21 | 0 |  | 0 | 0% | 0
| 9 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 13 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0
| 14 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 15 | 2001-11-24 | 2002-02-22 | 0 |  | 0 | 0% | 0
| 17 | 2001-11-17 | 2002-02-15 | 0 |  | 0 | 0% | 0
| 18 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 19 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 20 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 21 | 2001-11-17 | 2002-02-15 | 0 |  | 0 | 0% | 0
| 22 | 2001-11-18 | 2002-02-16 | 0 |  | 0 | 0% | 0
| 23 | 2001-11-19 | 2002-02-17 | 0 |  | 0 | 0% | 0
| 24 | 2001-11-18 | 2002-02-16 | 0 |  | 0 | 0% | 0
| 25 | 2001-11-18 | 2002-02-16 | 0 |  | 0 | 0% | 0
| 26 | 2001-12-01 | 2002-03-01 | 0 |  | 0 | 0% | 0
| 27 | 2001-11-30 | 2002-02-28 | 0 |  | 0 | 0% | 0
| 28 | 2001-11-19 | 2002-02-17 | 0 |  | 0 | 0% | 0
| 29 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0
| 30 | 2001-11-19 | 2002-02-17 | 0 |  | 0 | 0% | 0
| 49 | 2001-11-27 | 2002-02-25 | 0 |  | 0 | 0% | 0
| 50 | 2001-11-22 | 2002-02-20 | 0 |  | 0 | 0% | 0
| 51 | 2001-11-22 | 2002-02-20 | 0 |  | 0 | 0% | 0
| 52 | 2001-11-22 | 2002-02-20 | 0 |  | 0 | 0% | 0
| 53 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 54 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 55 | 2001-11-27 | 2002-02-25 | 0 |  | 0 | 0% | 0
| 56 | 2001-11-26 | 2002-02-24 | 0 |  | 0 | 0% | 0
| 57 | 2001-11-27 | 2002-02-25 | 0 |  | 0 | 0% | 0
| 58 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 59 | 2001-11-26 | 2002-02-24 | 0 |  | 0 | 0% | 0
| 60 | 2001-11-23 | 2002-02-21 | 0 |  | 0 | 0% | 0
| 61 | 2001-11-23 | 2002-02-21 | 0 |  | 0 | 0% | 0
| 62 | 2001-11-24 | 2002-02-22 | 0 |  | 0 | 0% | 0
| 63 | 2001-11-24 | 2002-02-22 | 0 |  | 0 | 0% | 0
| 64 | 2001-11-28 | 2002-02-26 | 0 |  | 0 | 0% | 0
| 65 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 66 | 2001-11-30 | 2002-02-28 | 0 |  | 0 | 0% | 0
| 67 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 68 | 2001-11-28 | 2002-02-26 | 0 |  | 0 | 0% | 0
| 69 | 2001-11-30 | 2002-02-28 | 0 |  | 0 | 0% | 0
| 70 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 71 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 72 | 2001-11-23 | 2002-02-21 | 0 |  | 0 | 0% | 0
| 73 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 74 | 2001-11-24 | 2002-02-22 | 0 |  | 0 | 0% | 0
| 75 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 76 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 77 | 2001-11-24 | 2002-02-22 | 0 |  | 0 | 0% | 0
| 78 | 2001-12-05 | 2002-03-05 | 0 |  | 0 | 0% | 0
| 79 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 80 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 81 | 2001-12-05 | 2002-03-05 | 0 |  | 0 | 0% | 0
| 82 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 83 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 84 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 85 | 2001-12-06 | 2002-03-06 | 0 |  | 0 | 0% | 0
| 86 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 87 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 88 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 89 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 90 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 91 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 92 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 93 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 96 | 2001-12-01 | 2002-03-01 | 0 |  | 0 | 0% | 0
| 100 | 2001-12-01 | 2002-03-01 | 0 |  | 0 | 0% | 0
| 102 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 103 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 104 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 105 | 2001-11-28 | 2002-02-26 | 0 |  | 0 | 0% | 0
| 106 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 107 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 108 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 109 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 113 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 114 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 115 | 2001-11-27 | 2002-02-25 | 0 |  | 0 | 0% | 0
| 116 | 2001-11-26 | 2002-02-24 | 0 |  | 0 | 0% | 0
| 117 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 118 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 119 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 120 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 121 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 122 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!

## Dec 2001
EWCC Totals
| EWCC Commissioned Totals: 2001 |  |  | 279 | OK
EWCC Commissioned Totals per month:
| 2001 Projects |  | # of WTGs | Type
| Montfrot - WI |  | 20 | 1.5 mW | complete |  | January |  | 0
| Trent Mesa - TX |  | 100 | 1.5 mW | complete |  | February |  | 0
| Indian Mesa I - TX |  | 17 | 1.5 mW | complete |  | March |  | 0
| Clear Sky (Indian Mesa II) - TX |  | 90 | 1.5 mW | complete |  | April |  | 0
| Mill Run - PA |  | 10 | 1.5 mW | complete |  | May |  | 2
| Fenner - NY |  | 20 | 1.5 mW | complete |  | June |  | 16
| Somerset - PA |  | 6 | 1.5 mW | complete |  | July |  | 24
| Klondike - WA |  | 16 | 1.5 mW | complete |  | August |  | 23
[7 empty] | September |  | 42
|  | Total for year | 279 | 418.5 | mW |  | October |  | 7
[7 empty] | November |  | 84
[7 empty] | December |  | 81
| # of Turbine which have operated > 90 days as of |  |  | 2001-12-31 | 107 |  | Total for 2001 |  | 279
| Weighted Average Enron Availability MTD |  |  | 2001-12-31 | 93.1%
MONTFORT - 20
EXHIBIT K
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning | Turbines Included |  | Monthly Totals
2001-12-01
2001-12-31 | 1 | 2001-05-07 | 2001-08-05 | 31 |  | 1 |  | May | 2
| 2 | 2001-06-27 | 2001-09-25 | 31 |  | 1 |  | June | 16
| 3 | 2001-05-17 | 2001-08-15 | 31 |  | 1 |  | July | 2 | Project Total to date | Commissioning completed
| 4 | 2001-06-27 | 2001-09-25 | 31 |  | 1 |  |  | 20 | Remaining
| 5 | 2001-06-27 | 2001-09-25 | 31 |  | 1 |  |  | 0
| 6 | 2001-06-01 | 2001-08-30 | 31 |  | 1
| 7 | 2001-06-27 | 2001-09-25 | 31 |  | 1
| 8 | 2001-06-11 | 2001-09-09 | 31 |  | 1
| 9 | 2001-06-11 | 2001-09-09 | 31 |  | 1
| 10 | 2001-06-28 | 2001-09-26 | 31 |  | 1
| 11 | 2001-06-28 | 2001-09-26 | 31 |  | 1
| 12 | 2001-06-21 | 2001-09-19 | 31 |  | 1
| 13 | 2001-06-28 | 2001-09-26 | 31 |  | 1
| 14 | 2001-06-28 | 2001-09-26 | 31 |  | 1
| 15 | 2001-06-28 | 2001-09-26 | 31 |  | 1
| 16 | 2001-06-28 | 2001-09-26 | 31 |  | 1
| 17 | 2001-06-30 | 2001-09-28 | 31 |  | 1
| 18 | 2001-07-02 | 2001-09-30 | 31 |  | 1
| 19 | 2001-07-02 | 2001-09-30 | 31 |  | 1
| 20 | 2001-06-30 | 2001-09-28 | 31 |  | 1
|  |  |  | Average | 87.9% | 20
|  |  |  | Weighted Average | 87.9%
Trent Mesa - 100
EXHIBIT I-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning | Turbines Included |  | Monthly Totals
| 1 | 2001-08-13 | 2001-11-11 | 31 |  | 1 |  | July | 22
| 2 | 2001-08-13 | 2001-11-11 | 31 |  | 1 |  | August | 23
| 3 | 2001-08-13 | 2001-11-11 | 31 |  | 1 |  | September | 42
| 4 | 2001-08-22 | 2001-11-20 | 31 |  | 1 |  | October | 7
| 5 | 2001-08-22 | 2001-11-20 | 31 |  | 1 |  | November | 6 | Project Total to date | Commissioning completed
| 6 | 2001-08-22 | 2001-11-20 | 31 |  | 1 |  |  | 100 | Remaining
| 7 | 2001-08-21 | 2001-11-19 | 31 |  | 1 |  |  | 0
| 8 | 2001-08-28 | 2001-11-26 | 31 |  | 1
| 9 | 2001-08-22 | 2001-11-20 | 31 |  | 1
| 10 | 2001-08-22 | 2001-11-20 | 31 |  | 1
| 11 | 2001-08-17 | 2001-11-15 | 31 |  | 1
| 12 | 2001-08-13 | 2001-11-11 | 31 |  | 1
| 13 | 2001-08-22 | 2001-11-20 | 31 |  | 1
| 14 | 2001-08-13 | 2001-11-11 | 31 |  | 1
| 15 | 2001-08-22 | 2001-11-20 | 31 |  | 1
| 16 | 2001-08-28 | 2001-11-26 | 31 |  | 1
| 17 | 2001-08-28 | 2001-11-26 | 31 |  | 1
| 18 | 2001-08-28 | 2001-11-26 | 31 |  | 1
| 19 | 2001-08-22 | 2001-11-20 | 31 |  | 1
| 20 | 2001-08-13 | 2001-11-11 | 31 |  | 1
| 21 | 2001-08-06 | 2001-11-04 | 31 |  | 1
| 22 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 23 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 24 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 25 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 26 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 27 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 28 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 29 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 30 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 31 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 32 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 33 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 34 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 35 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 36 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 37 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 38 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 39 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 40 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 41 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 42 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 43 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 44 | 2001-07-26 | 2001-10-24 | 31 |  | 1
| 45 | 2001-08-13 | 2001-11-11 | 31 |  | 1
| 46 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 47 | 2001-08-28 | 2001-11-26 | 31 |  | 1
| 48 | 2001-08-28 | 2001-11-26 | 31 |  | 1
| 49 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 50 | 2001-11-02 | 2002-01-31 | 0 |  | 0
| 51 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 52 | 2001-09-04 | 2001-12-03 | 29 |  | 1
| 53 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 54 | 2001-09-04 | 2001-12-03 | 29 |  | 1
| 55 | 2001-08-29 | 2001-11-27 | 31 |  | 1
| 56 | 2001-09-04 | 2001-12-03 | 29 |  | 1
| 57 | 2001-09-04 | 2001-12-03 | 29 |  | 1
| 58 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 59 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 60 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 61 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 62 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 63 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 64 | 2001-09-04 | 2001-12-03 | 29 |  | 1
| 65 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 66 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 67 | 2001-11-02 | 2002-01-31 | 0 |  | 0
| 68 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 69 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 70 | 2001-09-06 | 2001-12-05 | 27 |  | 1
| 71 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 72 | 2001-09-07 | 2001-12-06 | 26 |  | 1
| 73 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 74 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| B-5 | 2001-10-20 | 2002-01-18 | 0 |  | 0
| 76 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 77 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 78 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 79 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 80 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 81 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 82 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 83 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 84 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 85 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 86 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 87 | 2001-09-07 | 2001-12-06 | 26 |  | 1
| 88 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 89 | 2001-09-07 | 2001-12-06 | 26 |  | 1
| 90 | 2001-09-18 | 2001-12-17 | 15 |  | 1
| 91 | 2001-11-02 | 2002-01-31 | 0 |  | 0
| 92 | 2001-11-02 | 2002-01-31 | 0 |  | 0
| 93 | 2001-10-31 | 2002-01-29 | 0 |  | 0
| 94 | 2001-10-25 | 2002-01-23 | 0 |  | 0
| 95 | 2001-11-06 | 2002-02-04 | 0 |  | 0
| 96 | 2001-11-06 | 2002-02-04 | 0 |  | 0
| B-6 | 2001-10-22 | 2002-01-20 | 0 |  | 0
| B-7 | 2001-10-22 | 2002-01-20 | 0 |  | 0
| B-8 | 2001-10-19 | 2002-01-17 | 0 |  | 0
| B-9 | 2001-10-19 | 2002-01-17 | 0 |  | 0
|  |  |  | Average | 94.3% | 87
|  |  |  | Weighted Average | 94.3%
Mill Run - 10 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning | Turbines Included |  | Monthly Totals
| 1 | 2001-11-02 | 2002-01-31 | 0 |  | 0
| 2 | 2001-11-02 | 2002-01-31 | 0 |  | 0
| 3 | 2001-11-02 | 2002-01-31 | 0 |  | 0 |  | November | 10 | Project Total to date | Commissioning completed
| 4 | 2001-11-02 | 2002-01-31 | 0 |  | 0 |  |  | 10 | Remaining
| 5 | 2001-11-02 | 2002-01-31 | 0 |  | 0 |  |  | 0
| 6 | 2001-11-02 | 2002-01-31 | 0 |  | 0
| 7 | 2001-11-02 | 2002-01-31 | 0 |  | 0
| 8 | 2001-11-02 | 2002-01-31 | 0 |  | 0
| 9 | 2001-11-02 | 2002-01-31 | 0 |  | 0
| 10 | 2001-11-02 | 2002-01-31 | 0 |  | 0 |  | Special note: | Turbines 1, 3 & 4 Previously commissioned on 9/26
|  |  |  | Average | #DIV/0! | 0 |  |  | Turbines 6, 7 & 8 Previously commissioned on 9/27
Weighted Average
Fenner - 20 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning | Turbines Included |  | Monthly Totals
| 1 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 2 | 2001-12-11 | 2002-03-11 | 0 |  | 0 |  | November | 0
| 3 | 2001-12-11 | 2002-03-11 | 0 |  | 0 |  | December | 20 | Project Total to date | Commissioning completed
| 4 | 2001-12-11 | 2002-03-11 | 0 |  | 0 |  |  | 20 | Remaining
| 5 | 2001-12-11 | 2002-03-11 | 0 |  | 0 |  |  | 0
| 6 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 7 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 8 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 9 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 10 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 11 | 2001-12-18 | 2002-03-18 | 0 |  | 0
| 12 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 13 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 14 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 15 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 16 | 2001-12-18 | 2002-03-18 | 0 |  | 0
| 17 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 18 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 19 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 20 | 2001-12-11 | 2002-03-11 | 0 |  | 0
|  |  |  | Average | #DIV/0! | 0
Weighted Average
Somerset - 6 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning | Turbines Included |  | Monthly Totals
| 1 | 2001-11-06 | 2002-02-04 | 0 |  | 0
| 2 | 2001-11-06 | 2002-02-04 | 0 |  | 0
| 3 | 2001-11-06 | 2002-02-04 | 0 |  | 0 |  | November | 6 | Project Total to date | Commissioning completed
| 4 | 2001-11-06 | 2002-02-04 | 0 |  | 0 |  |  | 6 | Remaining
| 5 | 2001-11-06 | 2002-02-04 | 0 |  | 0 |  |  | 0
| 6 | 2001-11-06 | 2002-02-04 | 0 |  | 0
|  |  |  | Average | #DIV/0! | 0
Weighted Average
Klondike - 16 WTG
EXHIBIT K-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning | Turbines Included |  | Monthly Totals
| 1 | 2001-12-31 | 2002-03-31 | 0 |  | 0
| 2 | 2001-12-30 | 2002-03-30 | 0 |  | 0 |  | November | 0
| 3 | 2001-12-31 | 2002-03-31 | 0 |  | 0 |  | December | 16 | Project Total to date | Commissioning completed
| 4 | 2001-12-29 | 2002-03-29 | 0 |  | 0 |  |  | 16 | Remaining
| 5 | 2001-12-31 | 2002-03-31 | 0 |  | 0 |  |  | 0
| 6 | 2001-12-30 | 2002-03-30 | 0 |  | 0
| 7 | 2001-12-30 | 2002-03-30 | 0 |  | 0
| 8 | 2001-12-29 | 2002-03-29 | 0 |  | 0
| 9 | 2001-12-29 | 2002-03-29 | 0 |  | 0
| 10 | 2001-12-29 | 2002-03-29 | 0 |  | 0
| 11 | 2001-12-31 | 2002-03-31 | 0 |  | 0
| 12 | 2001-12-29 | 2002-03-29 | 0 |  | 0
| 13 | 2001-12-28 | 2002-03-28 | 0 |  | 0
| 14 | 2001-12-28 | 2002-03-28 | 0 |  | 0
| 15 | 2001-12-28 | 2002-03-28 | 0 |  | 0
| 16 | 2001-12-27 | 2002-03-27 | 0 |  | 0
|  |  |  | Average | #DIV/0! | 0
Weighted Average
IM - I - 17 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning | Turbines Included |  | Monthly Totals
| 31 | 2001-12-12 | 2002-03-12 | 0 |  | 0
| 32 | 2001-12-12 | 2002-03-12 | 0 |  | 0 |  | November | 0
| 33 | 2001-12-14 | 2002-03-14 | 0 |  | 0 |  | December | 17 | Project Total to date | Commissioning completed
| 34 | 2001-12-11 | 2002-03-11 | 0 |  | 0 |  |  | 17 | Remaining
| 35 | 2001-12-08 | 2002-03-08 | 0 |  | 0 |  |  | 0
| 36 | 2001-12-09 | 2002-03-09 | 0 |  | 0
| 37 | 2001-12-08 | 2002-03-08 | 0 |  | 0
| 38 | 2001-12-08 | 2002-03-08 | 0 |  | 0
| 39 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 40 | 2001-12-07 | 2002-03-07 | 0 |  | 0
| 41 | 2001-12-08 | 2002-03-08 | 0 |  | 0
| 42 | 2001-12-08 | 2002-03-08 | 0 |  | 0
| 43 | 2001-12-10 | 2002-03-10 | 0 |  | 0
| 44 | 2001-12-09 | 2002-03-09 | 0 |  | 0
| 45 | 2001-12-08 | 2002-03-08 | 0 |  | 0
| 46 | 2001-12-11 | 2002-03-11 | 0 |  | 0
| 47 | 2001-12-08 | 2002-03-08 | 0 |  | 0
|  |  |  | Average | #DIV/0! | 0
Weighted Average
IM - II - 90 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning | Turbines Included |  | Monthly Totals
| 1 | 2001-11-20 | 2002-02-18 | 0 |  | 0
| 2 | 2001-11-21 | 2002-02-19 | 0 |  | 0 |  | November | 62
| 3 | 2001-11-20 | 2002-02-18 | 0 |  | 0 |  | December | 28 | Project Total to date | Commissioning completed
| 4 | 2001-11-20 | 2002-02-18 | 0 |  | 0 |  |  | 90 | Remaining
| 5 | 2001-11-20 | 2002-02-18 | 0 |  | 0 |  |  | 0
| 7 | 2001-11-23 | 2002-02-21 | 0 |  | 0
| 8 | 2001-11-23 | 2002-02-21 | 0 |  | 0
| 9 | 2001-11-21 | 2002-02-19 | 0 |  | 0
| 13 | 2001-11-20 | 2002-02-18 | 0 |  | 0
| 14 | 2001-11-21 | 2002-02-19 | 0 |  | 0
| 15 | 2001-11-24 | 2002-02-22 | 0 |  | 0
| 17 | 2001-11-17 | 2002-02-15 | 0 |  | 0
| 18 | 2001-11-21 | 2002-02-19 | 0 |  | 0
| 19 | 2001-11-21 | 2002-02-19 | 0 |  | 0
| 20 | 2001-11-21 | 2002-02-19 | 0 |  | 0
| 21 | 2001-11-17 | 2002-02-15 | 0 |  | 0
| 22 | 2001-11-18 | 2002-02-16 | 0 |  | 0
| 23 | 2001-11-19 | 2002-02-17 | 0 |  | 0
| 24 | 2001-11-18 | 2002-02-16 | 0 |  | 0
| 25 | 2001-11-18 | 2002-02-16 | 0 |  | 0
| 26 | 2001-12-01 | 2002-03-01 | 0 |  | 0
| 27 | 2001-11-30 | 2002-02-28 | 0 |  | 0
| 28 | 2001-11-19 | 2002-02-17 | 0 |  | 0
| 29 | 2001-11-20 | 2002-02-18 | 0 |  | 0
| 30 | 2001-11-19 | 2002-02-17 | 0 |  | 0
| 49 | 2001-11-27 | 2002-02-25 | 0 |  | 0
| 50 | 2001-11-22 | 2002-02-20 | 0 |  | 0
| 51 | 2001-11-22 | 2002-02-20 | 0 |  | 0
| 52 | 2001-11-22 | 2002-02-20 | 0 |  | 0
| 53 | 2001-11-25 | 2002-02-23 | 0 |  | 0
| 54 | 2001-11-25 | 2002-02-23 | 0 |  | 0
| 55 | 2001-11-27 | 2002-02-25 | 0 |  | 0
| 56 | 2001-11-26 | 2002-02-24 | 0 |  | 0
| 57 | 2001-11-27 | 2002-02-25 | 0 |  | 0
| 58 | 2001-11-25 | 2002-02-23 | 0 |  | 0
| 59 | 2001-11-26 | 2002-02-24 | 0 |  | 0
| 60 | 2001-11-23 | 2002-02-21 | 0 |  | 0
| 61 | 2001-11-23 | 2002-02-21 | 0 |  | 0
| 62 | 2001-11-24 | 2002-02-22 | 0 |  | 0
| 63 | 2001-11-24 | 2002-02-22 | 0 |  | 0
| 64 | 2001-11-28 | 2002-02-26 | 0 |  | 0
| 65 | 2001-11-29 | 2002-02-27 | 0 |  | 0
| 66 | 2001-11-30 | 2002-02-28 | 0 |  | 0
| 67 | 2001-11-29 | 2002-02-27 | 0 |  | 0
| 68 | 2001-11-28 | 2002-02-26 | 0 |  | 0
| 69 | 2001-11-30 | 2002-02-28 | 0 |  | 0
| 70 | 2001-12-02 | 2002-03-02 | 0 |  | 0
| 71 | 2001-12-02 | 2002-03-02 | 0 |  | 0
| 72 | 2001-11-23 | 2002-02-21 | 0 |  | 0
| 73 | 2001-11-25 | 2002-02-23 | 0 |  | 0
| 74 | 2001-11-24 | 2002-02-22 | 0 |  | 0
| 75 | 2001-11-25 | 2002-02-23 | 0 |  | 0
| 76 | 2001-11-25 | 2002-02-23 | 0 |  | 0
| 77 | 2001-11-24 | 2002-02-22 | 0 |  | 0
| 78 | 2001-12-05 | 2002-03-05 | 0 |  | 0
| 79 | 2001-11-29 | 2002-02-27 | 0 |  | 0
| 80 | 2001-11-29 | 2002-02-27 | 0 |  | 0
| 81 | 2001-12-05 | 2002-03-05 | 0 |  | 0
| 82 | 2001-11-29 | 2002-02-27 | 0 |  | 0
| 83 | 2001-12-02 | 2002-03-02 | 0 |  | 0
| 84 | 2001-12-03 | 2002-03-03 | 0 |  | 0
| 85 | 2001-12-06 | 2002-03-06 | 0 |  | 0
| 86 | 2001-12-04 | 2002-03-04 | 0 |  | 0
| 87 | 2001-12-03 | 2002-03-03 | 0 |  | 0
| 88 | 2001-12-04 | 2002-03-04 | 0 |  | 0
| 89 | 2001-12-04 | 2002-03-04 | 0 |  | 0
| 90 | 2001-12-02 | 2002-03-02 | 0 |  | 0
| 91 | 2001-11-29 | 2002-02-27 | 0 |  | 0
| 92 | 2001-12-08 | 2002-03-08 | 0 |  | 0
| 93 | 2001-12-04 | 2002-03-04 | 0 |  | 0
| 96 | 2001-12-01 | 2002-03-01 | 0 |  | 0
| 100 | 2001-12-01 | 2002-03-01 | 0 |  | 0
| 102 | 2001-12-02 | 2002-03-02 | 0 |  | 0
| 103 | 2001-11-29 | 2002-02-27 | 0 |  | 0
| 104 | 2001-12-03 | 2002-03-03 | 0 |  | 0
| 105 | 2001-11-28 | 2002-02-26 | 0 |  | 0
| 106 | 2001-11-29 | 2002-02-27 | 0 |  | 0
| 107 | 2001-11-29 | 2002-02-27 | 0 |  | 0
| 108 | 2001-12-02 | 2002-03-02 | 0 |  | 0
| 109 | 2001-12-03 | 2002-03-03 | 0 |  | 0
| 113 | 2001-12-02 | 2002-03-02 | 0 |  | 0
| 114 | 2001-11-21 | 2002-02-19 | 0 |  | 0
| 115 | 2001-11-27 | 2002-02-25 | 0 |  | 0
| 116 | 2001-11-26 | 2002-02-24 | 0 |  | 0
| 117 | 2001-12-04 | 2002-03-04 | 0 |  | 0
| 118 | 2001-12-03 | 2002-03-03 | 0 |  | 0
| 119 | 2001-12-03 | 2002-03-03 | 0 |  | 0
| 120 | 2001-12-04 | 2002-03-04 | 0 |  | 0
| 121 | 2001-12-03 | 2002-03-03 | 0 |  | 0
| 122 | 2001-12-03 | 2002-03-03 | 0 |  | 0
|  |  |  | Average | #DIV/0! | 0
Weighted Average
Note on F2: Richard Ellis: cross check of totals

## Jan 2002
| # of Turbine which have operated > 90 days as of |  |  | 2002-01-31 | 128
| Weighted Average Enron Availability MTD |  |  | 2002-01-31 | 89.3%
MONTFORT - 20
EXHIBIT K
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
2002-01-01
2002-01-31 | 1 | 2001-05-07 | 2001-08-05 | 31 | 96.93% | 31 | 96.93% | 1 | May | 2
| 2 | 2001-06-27 | 2001-09-25 | 31 | 97.1% | 31 | 97.1% | 1 | June | 16
| 3 | 2001-05-17 | 2001-08-15 | 31 | 95.23% | 31 | 95.23% | 1 | July | 2 | Project Total to date | Commissioning completed
| 4 | 2001-06-27 | 2001-09-25 | 31 | 95.83% | 31 | 95.83% | 1 |  | 20 | Remaining
| 5 | 2001-06-27 | 2001-09-25 | 31 | 93.29% | 31 | 93.29% | 1 |  | 0
| 6 | 2001-06-01 | 2001-08-30 | 31 | 96.65% | 31 | 96.65% | 1
| 7 | 2001-06-27 | 2001-09-25 | 31 | 97.06% | 31 | 97.06% | 1
| 8 | 2001-06-11 | 2001-09-09 | 31 | 95.37% | 31 | 95.37% | 1
| 9 | 2001-06-11 | 2001-09-09 | 31 | 64.14% | 31 | 64.14% | 1
| 10 | 2001-06-28 | 2001-09-26 | 31 | 96.38% | 31 | 96.38% | 1
| 11 | 2001-06-28 | 2001-09-26 | 31 | 93.87% | 31 | 93.87% | 1
| 12 | 2001-06-21 | 2001-09-19 | 31 | 85.54% | 31 | 85.54% | 1
| 13 | 2001-06-28 | 2001-09-26 | 31 | 95.54% | 31 | 95.54% | 1
| 14 | 2001-06-28 | 2001-09-26 | 31 | 92.35% | 31 | 92.35% | 1
| 15 | 2001-06-28 | 2001-09-26 | 31 | 89.48% | 31 | 89.48% | 1
| 16 | 2001-06-28 | 2001-09-26 | 31 | 89.2% | 31 | 89.2% | 1
| 17 | 2001-06-30 | 2001-09-28 | 31 | 72.9% | 31 | 72.9% | 1
| 18 | 2001-07-02 | 2001-09-30 | 31 | 91.46% | 31 | 91.46% | 1
| 19 | 2001-07-02 | 2001-09-30 | 31 | 95.39% | 31 | 95.39% | 1
| 20 | 2001-06-30 | 2001-09-28 | 31 | 88.38% | 31 | 88.38% | 1
|  |  |  | Average | 91.1% |  |  | 20
|  |  |  | Weighted Average | 91.1%
Trent Mesa - 100
EXHIBIT I-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-08-13 | 2001-11-11 | 31 |  | 0 | 0% | 1 | July | 22
| 2 | 2001-08-13 | 2001-11-11 | 31 | 95.6% | 31 | 95.6% | 1 | August | 23
| 3 | 2001-08-13 | 2001-11-11 | 31 | 71.09% | 31 | 71.09% | 1 | September | 42
| 4 | 2001-08-22 | 2001-11-20 | 31 | 61.27% | 31 | 61.27% | 1 | October | 7
| 5 | 2001-08-22 | 2001-11-20 | 31 | 90.75% | 31 | 90.75% | 1 | November | 6 | Project Total to date | Commissioning completed
| 6 | 2001-08-22 | 2001-11-20 | 31 |  | 0 | 0% | 1 |  | 100 | Remaining
| 7 | 2001-08-21 | 2001-11-19 | 31 | 39.45% | 31 | 39.45% | 1 |  | 0
| 8 | 2001-08-28 | 2001-11-26 | 31 | 78.37% | 31 | 78.37% | 1
| 9 | 2001-08-22 | 2001-11-20 | 31 | 97.93% | 31 | 97.93% | 1
| 10 | 2001-08-22 | 2001-11-20 | 31 | 80.69% | 31 | 80.69% | 1
| 11 | 2001-08-17 | 2001-11-15 | 31 |  | 0 | 0% | 1
| 12 | 2001-08-13 | 2001-11-11 | 31 | 94.84% | 31 | 94.84% | 1
| 13 | 2001-08-22 | 2001-11-20 | 31 | 94.66% | 31 | 94.66% | 1
| 14 | 2001-08-13 | 2001-11-11 | 31 | 97.54% | 31 | 97.54% | 1
| 15 | 2001-08-22 | 2001-11-20 | 31 | 97.62% | 31 | 97.62% | 1
| 16 | 2001-08-28 | 2001-11-26 | 31 | 99.1% | 31 | 99.1% | 1
| 17 | 2001-08-28 | 2001-11-26 | 31 | 99.76% | 31 | 99.76% | 1
| 18 | 2001-08-28 | 2001-11-26 | 31 | 98.73% | 31 | 98.73% | 1
| 19 | 2001-08-22 | 2001-11-20 | 31 | 97.99% | 31 | 97.99% | 1
| 20 | 2001-08-13 | 2001-11-11 | 31 | 99.58% | 31 | 99.58% | 1
| 21 | 2001-08-06 | 2001-11-04 | 31 | 98.39% | 31 | 98.39% | 1
| 22 | 2001-07-26 | 2001-10-24 | 31 | 96% | 31 | 96% | 1
| 23 | 2001-07-26 | 2001-10-24 | 31 | 97.65% | 31 | 97.65% | 1
| 24 | 2001-07-26 | 2001-10-24 | 31 | 96.92% | 31 | 96.92% | 1
| 25 | 2001-07-26 | 2001-10-24 | 31 | 98.47% | 31 | 98.47% | 1
| 26 | 2001-07-26 | 2001-10-24 | 31 | 99.58% | 31 | 99.58% | 1
| 27 | 2001-07-26 | 2001-10-24 | 31 |  | 0 | 0% | 1
| 28 | 2001-07-26 | 2001-10-24 | 31 | 98.24% | 31 | 98.24% | 1
| 29 | 2001-07-26 | 2001-10-24 | 31 |  | 0 | 0% | 1
| 30 | 2001-07-26 | 2001-10-24 | 31 | 91.52% | 31 | 91.52% | 1
| 31 | 2001-07-26 | 2001-10-24 | 31 | 98.37% | 31 | 98.37% | 1
| 32 | 2001-09-18 | 2001-12-17 | 31 | 91.8% | 31 | 91.8% | 1
| 33 | 2001-07-26 | 2001-10-24 | 31 | 92.02% | 31 | 92.02% | 1
| 34 | 2001-07-26 | 2001-10-24 | 31 | 96.97% | 31 | 96.97% | 1
| 35 | 2001-07-26 | 2001-10-24 | 31 | 75.47% | 31 | 75.47% | 1
| 36 | 2001-07-26 | 2001-10-24 | 31 | 96.72% | 31 | 96.72% | 1
| 37 | 2001-07-26 | 2001-10-24 | 31 | 90.3% | 31 | 90.3% | 1
| 38 | 2001-07-26 | 2001-10-24 | 31 | 99.64% | 31 | 99.64% | 1
| 39 | 2001-07-26 | 2001-10-24 | 31 | 96.08% | 31 | 96.08% | 1
| 40 | 2001-07-26 | 2001-10-24 | 31 | 99.79% | 31 | 99.79% | 1
| 41 | 2001-07-26 | 2001-10-24 | 31 | 87.73% | 31 | 87.73% | 1
| 42 | 2001-07-26 | 2001-10-24 | 31 | 99.29% | 31 | 99.29% | 1
| 43 | 2001-07-26 | 2001-10-24 | 31 | 93.43% | 31 | 93.43% | 1
| 44 | 2001-07-26 | 2001-10-24 | 31 | 1.57% | 31 | 1.57% | 1
| 45 | 2001-08-13 | 2001-11-11 | 31 | 99.93% | 31 | 99.93% | 1
| 46 | 2001-09-18 | 2001-12-17 | 31 | 83.56% | 31 | 83.56% | 1
| 47 | 2001-08-28 | 2001-11-26 | 31 | 92.69% | 31 | 92.69% | 1
| 48 | 2001-08-28 | 2001-11-26 | 31 | 94.82% | 31 | 94.82% | 1
| 49 | 2001-09-18 | 2001-12-17 | 31 | 93.36% | 31 | 93.36% | 1
| 50 | 2001-11-02 | 2002-01-31 | 1 | 50.55% | 1 | 50.55% | 1
| 51 | 2001-09-18 | 2001-12-17 | 31 | 91.36% | 31 | 91.36% | 1
| 52 | 2001-09-04 | 2001-12-03 | 31 | 74.37% | 31 | 74.37% | 1
| 53 | 2001-09-18 | 2001-12-17 | 31 | 99.38% | 31 | 99.38% | 1
| 54 | 2001-09-04 | 2001-12-03 | 31 |  | 0 | 0% | 1
| 55 | 2001-08-29 | 2001-11-27 | 31 | 77.7% | 31 | 77.7% | 1
| 56 | 2001-09-04 | 2001-12-03 | 31 |  | 0 | 0% | 1
| 57 | 2001-09-04 | 2001-12-03 | 31 |  | 0 | 0% | 1
| 58 | 2001-09-18 | 2001-12-17 | 31 | 93.41% | 31 | 93.41% | 1
| 59 | 2001-09-18 | 2001-12-17 | 31 | 82.73% | 31 | 82.73% | 1
| 60 | 2001-09-18 | 2001-12-17 | 31 | 92.11% | 31 | 92.11% | 1
| 61 | 2001-09-18 | 2001-12-17 | 31 | 65.49% | 31 | 65.49% | 1
| 62 | 2001-09-18 | 2001-12-17 | 31 | 92.29% | 31 | 92.29% | 1
| 63 | 2001-09-18 | 2001-12-17 | 31 | 99.72% | 31 | 99.72% | 1
| 64 | 2001-09-04 | 2001-12-03 | 31 | 92.03% | 31 | 92.03% | 1
| 65 | 2001-09-18 | 2001-12-17 | 31 |  | 0 | 0% | 1
| 66 | 2001-09-18 | 2001-12-17 | 31 | 99.97% | 31 | 99.97% | 1
| 67 | 2001-11-02 | 2002-01-31 | 1 |  | 0 | 0% | 1
| 68 | 2001-09-18 | 2001-12-17 | 31 | 78.54% | 31 | 78.54% | 1
| 69 | 2001-09-18 | 2001-12-17 | 31 |  | 0 | 0% | 1
| 70 | 2001-09-06 | 2001-12-05 | 31 |  | 0 | 0% | 1
| 71 | 2001-09-18 | 2001-12-17 | 31 | 88.99% | 31 | 88.99% | 1
| 72 | 2001-09-07 | 2001-12-06 | 31 |  | 0 | 0% | 1
| 73 | 2001-09-18 | 2001-12-17 | 31 | 90.81% | 31 | 90.81% | 1
| 74 | 2001-09-18 | 2001-12-17 | 31 | 100% | 31 | 100% | 1
| B-5 | 2001-10-20 | 2002-01-18 | 14 |  | 0 | 0% | 1
| 76 | 2001-09-18 | 2001-12-17 | 31 | 91.72% | 31 | 91.72% | 1
| 77 | 2001-09-18 | 2001-12-17 | 31 | 77.37% | 31 | 77.37% | 1
| 78 | 2001-09-18 | 2001-12-17 | 31 |  | 0 | 0% | 1
| 79 | 2001-09-18 | 2001-12-17 | 31 | 81.25% | 31 | 81.25% | 1
| 80 | 2001-09-18 | 2001-12-17 | 31 | 90.96% | 31 | 90.96% | 1
| 81 | 2001-09-18 | 2001-12-17 | 31 | 97.39% | 31 | 97.39% | 1
| 82 | 2001-09-18 | 2001-12-17 | 31 | 86.81% | 31 | 86.81% | 1
| 83 | 2001-09-18 | 2001-12-17 | 31 |  | 0 | 0% | 1
| 84 | 2001-09-18 | 2001-12-17 | 31 | 73.07% | 31 | 73.07% | 1
| 85 | 2001-09-18 | 2001-12-17 | 31 | 59.03% | 31 | 59.03% | 1
| 86 | 2001-09-18 | 2001-12-17 | 31 |  | 0 | 0% | 1
| 87 | 2001-09-07 | 2001-12-06 | 31 | 87.9% | 31 | 87.9% | 1
| 88 | 2001-09-18 | 2001-12-17 | 31 | 91.35% | 31 | 91.35% | 1
| 89 | 2001-09-07 | 2001-12-06 | 31 |  | 0 | 0% | 1
| 90 | 2001-09-18 | 2001-12-17 | 31 | 91.68% | 31 | 91.68% | 1
| 91 | 2001-11-02 | 2002-01-31 | 1 | 0% | 1 | 0% | 1
| 92 | 2001-11-02 | 2002-01-31 | 1 |  | 0 | 0% | 1
| 93 | 2001-10-31 | 2002-01-29 | 3 | 20.28% | 3 | 20.28% | 1
| 94 | 2001-10-25 | 2002-01-23 | 9 | 69.33% | 9 | 69.33% | 1
| 95 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0
| 96 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0
| B-6 | 2001-10-22 | 2002-01-20 | 12 |  | 0 | 0% | 1
| B-7 | 2001-10-22 | 2002-01-20 | 12 | 82.38% | 12 | 82.38% | 1
| B-8 | 2001-10-19 | 2002-01-17 | 15 | 76.56% | 15 | 76.56% | 1
| B-9 | 2001-10-19 | 2002-01-17 | 15 | 67.32% | 15 | 67.32% | 1
|  |  |  | Average | 85.5% |  |  | 98
|  |  |  | Weighted Average | 88.29%
Mill Run - 10 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-11-02 | 2002-01-31 | 1 | 99.4% | 1 | 99.4% | 1
| 2 | 2001-11-02 | 2002-01-31 | 1 | 93.84% | 1 | 93.84% | 1
| 3 | 2001-11-02 | 2002-01-31 | 1 | 98.78% | 1 | 98.78% | 1 | November | 10 | Project Total to date | Commissioning completed
| 4 | 2001-11-02 | 2002-01-31 | 1 | 97.59% | 1 | 97.59% | 1 |  | 10 | Remaining
| 5 | 2001-11-02 | 2002-01-31 | 1 | 98.98% | 1 | 98.98% | 1 |  | 0
| 6 | 2001-11-02 | 2002-01-31 | 1 | 97.45% | 1 | 97.45% | 1
| 7 | 2001-11-02 | 2002-01-31 | 1 | 87.6% | 1 | 87.6% | 1
| 8 | 2001-11-02 | 2002-01-31 | 1 | 95.87% | 1 | 95.87% | 1
| 9 | 2001-11-02 | 2002-01-31 | 1 | 97.46% | 1 | 97.46% | 1
| 10 | 2001-11-02 | 2002-01-31 | 1 | 89.07% | 1 | 89.07% | 1 | Special note: | Turbines 1, 3 & 4 Previously commissioned on 9/26
|  |  |  | Average | 95.6% |  |  | 10 |  | Turbines 6, 7 & 8 Previously commissioned on 9/27
|  |  |  | Weighted Average | 95.6%
Fenner - 20 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 2 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 | November | 0
| 3 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 | December | 20 | Project Total to date | Commissioning completed
| 4 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 |  | 20 | Remaining
| 5 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 |  | 0
| 6 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 7 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 8 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 9 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 10 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 11 | 2001-12-18 | 2002-03-18 | 0 |  | 0 | 0% | 0
| 12 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 13 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 14 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 15 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 16 | 2001-12-18 | 2002-03-18 | 0 |  | 0 | 0% | 0
| 17 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 18 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 19 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 20 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!
Somerset - 6 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0
| 2 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0
| 3 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0 | November | 6 | Project Total to date | Commissioning completed
| 4 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0 |  | 6 | Remaining
| 5 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0 |  | 0
| 6 | 2001-11-06 | 2002-02-04 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!
Klondike - 16 WTG
EXHIBIT K-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0
| 2 | 2001-12-30 | 2002-03-30 | 0 |  | 0 | 0% | 0 | November | 0
| 3 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0 | December | 16 | Project Total to date | Commissioning completed
| 4 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0 |  | 16 | Remaining
| 5 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0 |  | 0
| 6 | 2001-12-30 | 2002-03-30 | 0 |  | 0 | 0% | 0
| 7 | 2001-12-30 | 2002-03-30 | 0 |  | 0 | 0% | 0
| 8 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 9 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 10 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 11 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0
| 12 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 13 | 2001-12-28 | 2002-03-28 | 0 |  | 0 | 0% | 0
| 14 | 2001-12-28 | 2002-03-28 | 0 |  | 0 | 0% | 0
| 15 | 2001-12-28 | 2002-03-28 | 0 |  | 0 | 0% | 0
| 16 | 2001-12-27 | 2002-03-27 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!
IM - I - 17 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 31 | 2001-12-12 | 2002-03-12 | 0 |  | 0 | 0% | 0
| 32 | 2001-12-12 | 2002-03-12 | 0 |  | 0 | 0% | 0 | November | 0
| 33 | 2001-12-14 | 2002-03-14 | 0 |  | 0 | 0% | 0 | December | 17 | Project Total to date | Commissioning completed
| 34 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 |  | 17 | Remaining
| 35 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0 |  | 0
| 36 | 2001-12-09 | 2002-03-09 | 0 |  | 0 | 0% | 0
| 37 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 38 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 39 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 40 | 2001-12-07 | 2002-03-07 | 0 |  | 0 | 0% | 0
| 41 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 42 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 43 | 2001-12-10 | 2002-03-10 | 0 |  | 0 | 0% | 0
| 44 | 2001-12-09 | 2002-03-09 | 0 |  | 0 | 0% | 0
| 45 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 46 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 47 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!
IM - II - 90 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0
| 2 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0 | November | 62
| 3 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0 | December | 28 | Project Total to date | Commissioning completed
| 4 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0 |  | 90 | Remaining
| 5 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0 |  | 0
| 7 | 2001-11-23 | 2002-02-21 | 0 |  | 0 | 0% | 0
| 8 | 2001-11-23 | 2002-02-21 | 0 |  | 0 | 0% | 0
| 9 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 13 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0
| 14 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 15 | 2001-11-24 | 2002-02-22 | 0 |  | 0 | 0% | 0
| 17 | 2001-11-17 | 2002-02-15 | 0 |  | 0 | 0% | 0
| 18 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 19 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 20 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 21 | 2001-11-17 | 2002-02-15 | 0 |  | 0 | 0% | 0
| 22 | 2001-11-18 | 2002-02-16 | 0 |  | 0 | 0% | 0
| 23 | 2001-11-19 | 2002-02-17 | 0 |  | 0 | 0% | 0
| 24 | 2001-11-18 | 2002-02-16 | 0 |  | 0 | 0% | 0
| 25 | 2001-11-18 | 2002-02-16 | 0 |  | 0 | 0% | 0
| 26 | 2001-12-01 | 2002-03-01 | 0 |  | 0 | 0% | 0
| 27 | 2001-11-30 | 2002-02-28 | 0 |  | 0 | 0% | 0
| 28 | 2001-11-19 | 2002-02-17 | 0 |  | 0 | 0% | 0
| 29 | 2001-11-20 | 2002-02-18 | 0 |  | 0 | 0% | 0
| 30 | 2001-11-19 | 2002-02-17 | 0 |  | 0 | 0% | 0
| 49 | 2001-11-27 | 2002-02-25 | 0 |  | 0 | 0% | 0
| 50 | 2001-11-22 | 2002-02-20 | 0 |  | 0 | 0% | 0
| 51 | 2001-11-22 | 2002-02-20 | 0 |  | 0 | 0% | 0
| 52 | 2001-11-22 | 2002-02-20 | 0 |  | 0 | 0% | 0
| 53 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 54 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 55 | 2001-11-27 | 2002-02-25 | 0 |  | 0 | 0% | 0
| 56 | 2001-11-26 | 2002-02-24 | 0 |  | 0 | 0% | 0
| 57 | 2001-11-27 | 2002-02-25 | 0 |  | 0 | 0% | 0
| 58 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 59 | 2001-11-26 | 2002-02-24 | 0 |  | 0 | 0% | 0
| 60 | 2001-11-23 | 2002-02-21 | 0 |  | 0 | 0% | 0
| 61 | 2001-11-23 | 2002-02-21 | 0 |  | 0 | 0% | 0
| 62 | 2001-11-24 | 2002-02-22 | 0 |  | 0 | 0% | 0
| 63 | 2001-11-24 | 2002-02-22 | 0 |  | 0 | 0% | 0
| 64 | 2001-11-28 | 2002-02-26 | 0 |  | 0 | 0% | 0
| 65 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 66 | 2001-11-30 | 2002-02-28 | 0 |  | 0 | 0% | 0
| 67 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 68 | 2001-11-28 | 2002-02-26 | 0 |  | 0 | 0% | 0
| 69 | 2001-11-30 | 2002-02-28 | 0 |  | 0 | 0% | 0
| 70 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 71 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 72 | 2001-11-23 | 2002-02-21 | 0 |  | 0 | 0% | 0
| 73 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 74 | 2001-11-24 | 2002-02-22 | 0 |  | 0 | 0% | 0
| 75 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 76 | 2001-11-25 | 2002-02-23 | 0 |  | 0 | 0% | 0
| 77 | 2001-11-24 | 2002-02-22 | 0 |  | 0 | 0% | 0
| 78 | 2001-12-05 | 2002-03-05 | 0 |  | 0 | 0% | 0
| 79 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 80 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 81 | 2001-12-05 | 2002-03-05 | 0 |  | 0 | 0% | 0
| 82 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 83 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 84 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 85 | 2001-12-06 | 2002-03-06 | 0 |  | 0 | 0% | 0
| 86 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 87 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 88 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 89 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 90 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 91 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 92 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 93 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 96 | 2001-12-01 | 2002-03-01 | 0 |  | 0 | 0% | 0
| 100 | 2001-12-01 | 2002-03-01 | 0 |  | 0 | 0% | 0
| 102 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 103 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 104 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 105 | 2001-11-28 | 2002-02-26 | 0 |  | 0 | 0% | 0
| 106 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 107 | 2001-11-29 | 2002-02-27 | 0 |  | 0 | 0% | 0
| 108 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 109 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 113 | 2001-12-02 | 2002-03-02 | 0 |  | 0 | 0% | 0
| 114 | 2001-11-21 | 2002-02-19 | 0 |  | 0 | 0% | 0
| 115 | 2001-11-27 | 2002-02-25 | 0 |  | 0 | 0% | 0
| 116 | 2001-11-26 | 2002-02-24 | 0 |  | 0 | 0% | 0
| 117 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 118 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 119 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 120 | 2001-12-04 | 2002-03-04 | 0 |  | 0 | 0% | 0
| 121 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
| 122 | 2001-12-03 | 2002-03-03 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!

## Feb 2002
| # of Turbine which have operated > 90 days as of |  |  | 2002-02-28 | 198
| Weighted Average Enron Availability MTD |  |  | 2002-02-28 | 89%
MONTFORT - 20
EXHIBIT K
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
2002-02-01
2002-02-28 | 1 | 2001-05-07 | 2001-08-05 | 28 | 97.77% | 28 | 97.77% | 1 | May | 2
28 | 2 | 2001-06-27 | 2001-09-25 | 28 | 99.98% | 28 | 99.98% | 1 | June | 16
| 3 | 2001-05-17 | 2001-08-15 | 28 | 99.27% | 28 | 99.27% | 1 | July | 2 | Project Total to date | Commissioning completed
| 4 | 2001-06-27 | 2001-09-25 | 28 | 99% | 28 | 99% | 1 |  | 20 | Remaining
| 5 | 2001-06-27 | 2001-09-25 | 28 | 99.98% | 28 | 99.98% | 1 |  | 0
| 6 | 2001-06-01 | 2001-08-30 | 28 | 99.82% | 28 | 99.82% | 1
| 7 | 2001-06-27 | 2001-09-25 | 28 | 99.1% | 28 | 99.1% | 1
| 8 | 2001-06-11 | 2001-09-09 | 28 | 99.45% | 28 | 99.45% | 1
| 9 | 2001-06-11 | 2001-09-09 | 28 | 97.34% | 28 | 97.34% | 1
| 10 | 2001-06-28 | 2001-09-26 | 28 | 98.73% | 28 | 98.73% | 1
| 11 | 2001-06-28 | 2001-09-26 | 28 | 99.99% | 28 | 99.99% | 1
| 12 | 2001-06-21 | 2001-09-19 | 28 | 98.59% | 28 | 98.59% | 1
| 13 | 2001-06-28 | 2001-09-26 | 28 | 99.68% | 28 | 99.68% | 1
| 14 | 2001-06-28 | 2001-09-26 | 28 | 96.74% | 28 | 96.74% | 1
| 15 | 2001-06-28 | 2001-09-26 | 28 | 96.45% | 28 | 96.45% | 1
| 16 | 2001-06-28 | 2001-09-26 | 28 | 99.4% | 28 | 99.4% | 1
| 17 | 2001-06-30 | 2001-09-28 | 28 | 99.96% | 28 | 99.96% | 1
| 18 | 2001-07-02 | 2001-09-30 | 28 | 95.84% | 28 | 95.84% | 1
| 19 | 2001-07-02 | 2001-09-30 | 28 | 95.27% | 28 | 95.27% | 1
| 20 | 2001-06-30 | 2001-09-28 | 28 | 98.35% | 28 | 98.35% | 1
|  |  |  | Average | 98.54% |  |  | 20
|  |  |  | Weighted Average | 0.98536
Trent Mesa - 100
EXHIBIT I-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-08-13 | 2001-11-11 | 28 | 98.46% | 28 | 98.46% | 1 | July | 22
| 2 | 2001-08-13 | 2001-11-11 | 28 | 99.6% | 28 | 99.6% | 1 | August | 23
| 3 | 2001-08-13 | 2001-11-11 | 28 | 100% | 28 | 100% | 1 | September | 42
| 4 | 2001-08-22 | 2001-11-20 | 28 | 34.81% | 28 | 34.81% | 1 | October | 7
| 5 | 2001-08-22 | 2001-11-20 | 28 | 98.86% | 28 | 98.86% | 1 | November | 6 | Project Total to date | Commissioning completed
| 6 | 2001-08-22 | 2001-11-20 | 28 | 99.64% | 28 | 99.64% | 1 |  | 100 | Remaining
| 7 | 2001-08-21 | 2001-11-19 | 28 | 98.58% | 28 | 98.58% | 1 |  | 0
| 8 | 2001-08-28 | 2001-11-26 | 28 | 92.41% | 28 | 92.41% | 1
| 9 | 2001-08-22 | 2001-11-20 | 28 | 97.98% | 28 | 97.98% | 1
| 10 | 2001-08-22 | 2001-11-20 | 28 | 97.45% | 28 | 97.45% | 1
| 11 | 2001-08-17 | 2001-11-15 | 28 | 97.51% | 28 | 97.51% | 1
| 12 | 2001-08-13 | 2001-11-11 | 28 | 99.73% | 28 | 99.73% | 1
| 13 | 2001-08-22 | 2001-11-20 | 28 | 98.18% | 28 | 98.18% | 1
| 14 | 2001-08-13 | 2001-11-11 | 28 | 97.22% | 28 | 97.22% | 1
| 15 | 2001-08-22 | 2001-11-20 | 28 | 98.14% | 28 | 98.14% | 1
| 16 | 2001-08-28 | 2001-11-26 | 28 | 99.94% | 28 | 99.94% | 1
| 17 | 2001-08-28 | 2001-11-26 | 28 | 99.47% | 28 | 99.47% | 1
| 18 | 2001-08-28 | 2001-11-26 | 28 | 97.48% | 28 | 97.48% | 1
| 19 | 2001-08-22 | 2001-11-20 | 28 | 97.24% | 28 | 97.24% | 1
| 20 | 2001-08-13 | 2001-11-11 | 28 | 99.83% | 28 | 99.83% | 1
| 21 | 2001-08-06 | 2001-11-04 | 28 | 99.84% | 28 | 99.84% | 1
| 22 | 2001-07-26 | 2001-10-24 | 28 | 99.47% | 28 | 99.47% | 1
| 23 | 2001-07-26 | 2001-10-24 | 28 | 99.55% | 28 | 99.55% | 1
| 24 | 2001-07-26 | 2001-10-24 | 28 | 99.46% | 28 | 99.46% | 1
| 25 | 2001-07-26 | 2001-10-24 | 28 | 96.25% | 28 | 96.25% | 1
| 26 | 2001-07-26 | 2001-10-24 | 28 | 92.68% | 28 | 92.68% | 1
| 27 | 2001-07-26 | 2001-10-24 | 28 | 85.85% | 28 | 85.85% | 1
| 28 | 2001-07-26 | 2001-10-24 | 28 | 97.19% | 28 | 97.19% | 1
| 29 | 2001-07-26 | 2001-10-24 | 28 | 98.31% | 28 | 98.31% | 1
| 30 | 2001-07-26 | 2001-10-24 | 28 | 94.81% | 28 | 94.81% | 1
| 31 | 2001-07-26 | 2001-10-24 | 28 | -1.88e-15% | 28 | -1.88e-15% | 1
| 32 | 2001-09-18 | 2001-12-17 | 28 | 90.46% | 28 | 90.46% | 1
| 33 | 2001-07-26 | 2001-10-24 | 28 | 92.03% | 28 | 92.03% | 1
| 34 | 2001-07-26 | 2001-10-24 | 28 | 88.11% | 28 | 88.11% | 1
| 35 | 2001-07-26 | 2001-10-24 | 28 | 66.65% | 28 | 66.65% | 1
| 36 | 2001-07-26 | 2001-10-24 | 28 | 99.44% | 28 | 99.44% | 1
| 37 | 2001-07-26 | 2001-10-24 | 28 | 85.19% | 28 | 85.19% | 1
| 38 | 2001-07-26 | 2001-10-24 | 28 | 74.04% | 28 | 74.04% | 1
| 39 | 2001-07-26 | 2001-10-24 | 28 | 93.98% | 28 | 93.98% | 1
| 40 | 2001-07-26 | 2001-10-24 | 28 | 93.6% | 28 | 93.6% | 1
| 41 | 2001-07-26 | 2001-10-24 | 28 | 96.66% | 28 | 96.66% | 1
| 42 | 2001-07-26 | 2001-10-24 | 28 | 98.45% | 28 | 98.45% | 1
| 43 | 2001-07-26 | 2001-10-24 | 28 | 95.53% | 28 | 95.53% | 1
| 44 | 2001-07-26 | 2001-10-24 | 28 | 2.1% | 28 | 2.1% | 1
| 45 | 2001-08-13 | 2001-11-11 | 28 | 79.29% | 28 | 79.29% | 1
| 46 | 2001-09-18 | 2001-12-17 | 28 | 85.54% | 28 | 85.54% | 1
| 47 | 2001-08-28 | 2001-11-26 | 28 | 95.41% | 28 | 95.41% | 1
| 48 | 2001-08-28 | 2001-11-26 | 28 | 0% | 28 | 0% | 1
| 49 | 2001-09-18 | 2001-12-17 | 28 | 96.38% | 28 | 96.38% | 1
| 50 | 2001-11-02 | 2002-01-31 | 28 | 96.36% | 28 | 96.36% | 1
| 51 | 2001-09-18 | 2001-12-17 | 28 | 99.8% | 28 | 99.8% | 1
| 52 | 2001-09-04 | 2001-12-03 | 28 | 96.26% | 28 | 96.26% | 1
| 53 | 2001-09-18 | 2001-12-17 | 28 | 4.202e-14% | 28 | 4.202e-14% | 1
| 54 | 2001-09-04 | 2001-12-03 | 28 | -4.966e-15% | 28 | -4.966e-15% | 1
| 55 | 2001-08-29 | 2001-11-27 | 28 | 76.97% | 28 | 76.97% | 1
| 56 | 2001-09-04 | 2001-12-03 | 28 | 94.41% | 28 | 94.41% | 1
| 57 | 2001-09-04 | 2001-12-03 | 28 | 95.71% | 28 | 95.71% | 1
| 58 | 2001-09-18 | 2001-12-17 | 28 | 96.83% | 28 | 96.83% | 1
| 59 | 2001-09-18 | 2001-12-17 | 28 | 82.72% | 28 | 82.72% | 1
| 60 | 2001-09-18 | 2001-12-17 | 28 | 99.91% | 28 | 99.91% | 1
| 61 | 2001-09-18 | 2001-12-17 | 28 | 96.96% | 28 | 96.96% | 1
| 62 | 2001-09-18 | 2001-12-17 | 28 | 92.66% | 28 | 92.66% | 1
| 63 | 2001-09-18 | 2001-12-17 | 28 | 98.65% | 28 | 98.65% | 1
| 64 | 2001-09-04 | 2001-12-03 | 28 | 90.8% | 28 | 90.8% | 1
| 65 | 2001-09-18 | 2001-12-17 | 28 | 92.99% | 28 | 92.99% | 1
| 66 | 2001-09-18 | 2001-12-17 | 28 | 94.37% | 28 | 94.37% | 1
| 67 | 2001-11-02 | 2002-01-31 | 28 | 96.52% | 28 | 96.52% | 1
| 68 | 2001-09-18 | 2001-12-17 | 28 | 97.9% | 28 | 97.9% | 1
| 69 | 2001-09-18 | 2001-12-17 | 28 | 0.9188% | 28 | 0.9188% | 1
| 70 | 2001-09-06 | 2001-12-05 | 28 | 64.06% | 28 | 64.06% | 1
| 71 | 2001-09-18 | 2001-12-17 | 28 | 95.34% | 28 | 95.34% | 1
| 72 | 2001-09-07 | 2001-12-06 | 28 | 96.92% | 28 | 96.92% | 1
| 73 | 2001-09-18 | 2001-12-17 | 28 | 93.89% | 28 | 93.89% | 1
| 74 | 2001-09-18 | 2001-12-17 | 28 | 90.27% | 28 | 90.27% | 1
| B-5 | 2001-10-20 | 2002-01-18 | 28 | 82.43% | 28 | 82.43% | 1
| 76 | 2001-09-18 | 2001-12-17 | 28 | 90.59% | 28 | 90.59% | 1
| 77 | 2001-09-18 | 2001-12-17 | 28 | 92.84% | 28 | 92.84% | 1
| 78 | 2001-09-18 | 2001-12-17 | 28 | 96.3% | 28 | 96.3% | 1
| 79 | 2001-09-18 | 2001-12-17 | 28 | 88.63% | 28 | 88.63% | 1
| 80 | 2001-09-18 | 2001-12-17 | 28 | 87% | 28 | 87% | 1
| 81 | 2001-09-18 | 2001-12-17 | 28 | 89.2% | 28 | 89.2% | 1
| 82 | 2001-09-18 | 2001-12-17 | 28 | 88.99% | 28 | 88.99% | 1
| 83 | 2001-09-18 | 2001-12-17 | 28 | 65.56% | 28 | 65.56% | 1
| 84 | 2001-09-18 | 2001-12-17 | 28 | 77.54% | 28 | 77.54% | 1
| 85 | 2001-09-18 | 2001-12-17 | 28 | 79.79% | 28 | 79.79% | 1
| 86 | 2001-09-18 | 2001-12-17 | 28 | 94.03% | 28 | 94.03% | 1
| 87 | 2001-09-07 | 2001-12-06 | 28 | 97.86% | 28 | 97.86% | 1
| 88 | 2001-09-18 | 2001-12-17 | 28 | 86.07% | 28 | 86.07% | 1
| 89 | 2001-09-07 | 2001-12-06 | 28 | 99.2% | 28 | 99.2% | 1
| 90 | 2001-09-18 | 2001-12-17 | 28 | 91.24% | 28 | 91.24% | 1
| 91 | 2001-11-02 | 2002-01-31 | 28 | 75.06% | 28 | 75.06% | 1
| 92 | 2001-11-02 | 2002-01-31 | 28 | 73.27% | 28 | 73.27% | 1
| 93 | 2001-10-31 | 2002-01-29 | 28 | 88.67% | 28 | 88.67% | 1
| 94 | 2001-10-25 | 2002-01-23 | 28 | 85.02% | 28 | 85.02% | 1
| 95 | 2001-11-06 | 2002-02-04 | 25 | 82.5% | 25 | 82.5% | 1
| 96 | 2001-11-06 | 2002-02-04 | 25 | 83.3% | 25 | 83.3% | 1
| B-6 | 2001-10-22 | 2002-01-20 | 28 | 85.85% | 28 | 85.85% | 1
| B-7 | 2001-10-22 | 2002-01-20 | 28 | 98.31% | 28 | 98.31% | 1
| B-8 | 2001-10-19 | 2002-01-17 | 28 | 79.61% | 28 | 79.61% | 1
| B-9 | 2001-10-19 | 2002-01-17 | 28 | 92.76% | 28 | 92.76% | 1
|  |  |  | Average | 85.92% |  |  | 100
|  |  |  | Weighted Average | 85.92%
Mill Run - 10 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-11-02 | 2002-01-31 | 28 | 96.81% | 28 | 96.81% | 1
| 2 | 2001-11-02 | 2002-01-31 | 28 | 94.45% | 28 | 94.45% | 1
| 3 | 2001-11-02 | 2002-01-31 | 28 | 99.56% | 28 | 99.56% | 1 | November | 10 | Project Total to date | Commissioning completed
| 4 | 2001-11-02 | 2002-01-31 | 28 | 98.05% | 28 | 98.05% | 1 |  | 10 | Remaining
| 5 | 2001-11-02 | 2002-01-31 | 28 | 97.91% | 28 | 97.91% | 1 |  | 0
| 6 | 2001-11-02 | 2002-01-31 | 28 | 89.88% | 28 | 89.88% | 1
| 7 | 2001-11-02 | 2002-01-31 | 28 | 92.1% | 28 | 92.1% | 1
| 8 | 2001-11-02 | 2002-01-31 | 28 | 95.75% | 28 | 95.75% | 1
| 9 | 2001-11-02 | 2002-01-31 | 28 | 98.17% | 28 | 98.17% | 1
| 10 | 2001-11-02 | 2002-01-31 | 28 | 97.31% | 28 | 97.31% | 1 | Special note: | Turbines 1, 3 & 4 Previously commissioned on 9/26
|  |  |  | Average | 96% |  |  | 10 |  | Turbines 6, 7 & 8 Previously commissioned on 9/27
|  |  |  | Weighted Average | 96%
Fenner - 20 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 2 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 | November | 0
| 3 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 | December | 20 | Project Total to date | Commissioning completed
| 4 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 |  | 20 | Remaining
| 5 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 |  | 0
| 6 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 7 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 8 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 9 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 10 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 11 | 2001-12-18 | 2002-03-18 | 0 |  | 0 | 0% | 0
| 12 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 13 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 14 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 15 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 16 | 2001-12-18 | 2002-03-18 | 0 |  | 0 | 0% | 0
| 17 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 18 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 19 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 20 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!
Somerset - 6 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-11-06 | 2002-02-04 | 25 | 96.75% | 25 | 96.75% | 1
| 2 | 2001-11-06 | 2002-02-04 | 25 | 98.89% | 25 | 98.89% | 1
| 3 | 2001-11-06 | 2002-02-04 | 25 | 94.27% | 25 | 94.27% | 1 | November | 6 | Project Total to date | Commissioning completed
| 4 | 2001-11-06 | 2002-02-04 | 25 | 97.08% | 25 | 97.08% | 1 |  | 6 | Remaining
| 5 | 2001-11-06 | 2002-02-04 | 25 | 98.68% | 25 | 98.68% | 1 |  | 0
| 6 | 2001-11-06 | 2002-02-04 | 25 | 98.77% | 25 | 98.77% | 1
|  |  |  | Average | 97.41% |  |  | 6
|  |  |  | Weighted Average | 0.97406
Klondike - 16 WTG
EXHIBIT K-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0
| 2 | 2001-12-30 | 2002-03-30 | 0 |  | 0 | 0% | 0 | November | 0
| 3 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0 | December | 16 | Project Total to date | Commissioning completed
| 4 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0 |  | 16 | Remaining
| 5 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0 |  | 0
| 6 | 2001-12-30 | 2002-03-30 | 0 |  | 0 | 0% | 0
| 7 | 2001-12-30 | 2002-03-30 | 0 |  | 0 | 0% | 0
| 8 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 9 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 10 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 11 | 2001-12-31 | 2002-03-31 | 0 |  | 0 | 0% | 0
| 12 | 2001-12-29 | 2002-03-29 | 0 |  | 0 | 0% | 0
| 13 | 2001-12-28 | 2002-03-28 | 0 |  | 0 | 0% | 0
| 14 | 2001-12-28 | 2002-03-28 | 0 |  | 0 | 0% | 0
| 15 | 2001-12-28 | 2002-03-28 | 0 |  | 0 | 0% | 0
| 16 | 2001-12-27 | 2002-03-27 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!
IM - I - 17 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 31 | 2001-12-12 | 2002-03-12 | 0 |  | 0 | 0% | 0
| 32 | 2001-12-12 | 2002-03-12 | 0 |  | 0 | 0% | 0 | November | 0
| 33 | 2001-12-14 | 2002-03-14 | 0 |  | 0 | 0% | 0 | December | 17 | Project Total to date | Commissioning completed
| 34 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0 |  | 17 | Remaining
| 35 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0 |  | 0
| 36 | 2001-12-09 | 2002-03-09 | 0 |  | 0 | 0% | 0
| 37 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 38 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 39 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 40 | 2001-12-07 | 2002-03-07 | 0 |  | 0 | 0% | 0
| 41 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 42 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 43 | 2001-12-10 | 2002-03-10 | 0 |  | 0 | 0% | 0
| 44 | 2001-12-09 | 2002-03-09 | 0 |  | 0 | 0% | 0
| 45 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
| 46 | 2001-12-11 | 2002-03-11 | 0 |  | 0 | 0% | 0
| 47 | 2001-12-08 | 2002-03-08 | 0 |  | 0 | 0% | 0
|  |  |  | Average | #DIV/0! |  |  | 0
|  |  |  | Weighted Average | #DIV/0!
IM - II - 90 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Monthly Totals
| 1 | 2001-11-20 | 2002-02-18 | 11 | 94.59% | 11 | 94.59% | 1
| 2 | 2001-11-21 | 2002-02-19 | 10 | 99.59% | 10 | 99.59% | 1 | November | 62
| 3 | 2001-11-20 | 2002-02-18 | 11 | 99.76% | 11 | 99.76% | 1 | December | 28 | Project Total to date | Commissioning completed
| 4 | 2001-11-20 | 2002-02-18 | 11 | 94.8% | 11 | 94.8% | 1 |  | 90 | Remaining
| 5 | 2001-11-20 | 2002-02-18 | 11 | 86.71% | 11 | 86.71% | 1 |  | 0
| 7 | 2001-11-23 | 2002-02-21 | 8 | 96.16% | 8 | 96.16% | 1
| 8 | 2001-11-23 | 2002-02-21 | 8 | 88.29% | 8 | 88.29% | 1
| 9 | 2001-11-21 | 2002-02-19 | 10 | 94.59% | 10 | 94.59% | 1
| 13 | 2001-11-20 | 2002-02-18 | 11 | 92.36% | 11 | 92.36% | 1
| 14 | 2001-11-21 | 2002-02-19 | 10 | 99.47% | 10 | 99.47% | 1
| 15 | 2001-11-24 | 2002-02-22 | 7 | 85.11% | 7 | 85.11% | 1
| 17 | 2001-11-17 | 2002-02-15 | 14 | 98.67% | 14 | 98.67% | 1
| 18 | 2001-11-21 | 2002-02-19 | 10 | 92.27% | 10 | 92.27% | 1
| 19 | 2001-11-21 | 2002-02-19 | 10 | 95% | 10 | 95% | 1
| 20 | 2001-11-21 | 2002-02-19 | 10 | 95.8% | 10 | 95.8% | 1
| 21 | 2001-11-17 | 2002-02-15 | 14 | 92.47% | 14 | 92.47% | 1
| 22 | 2001-11-18 | 2002-02-16 | 13 | 98.16% | 13 | 98.16% | 1
| 23 | 2001-11-19 | 2002-02-17 | 12 | 99.15% | 12 | 99.15% | 1
| 24 | 2001-11-18 | 2002-02-16 | 13 | 70.41% | 13 | 70.41% | 1
| 25 | 2001-11-18 | 2002-02-16 | 13 | 93.64% | 13 | 93.64% | 1
| 26 | 2001-12-01 | 2002-03-01 | 0 | 97.45% | 0 | 97.45% | 0
| 27 | 2001-11-30 | 2002-02-28 | 1 | 99.08% | 1 | 99.08% | 1
| 28 | 2001-11-19 | 2002-02-17 | 12 | 99.31% | 12 | 99.31% | 1
| 29 | 2001-11-20 | 2002-02-18 | 11 | 98.51% | 11 | 98.51% | 1
| 30 | 2001-11-19 | 2002-02-17 | 12 | 97.15% | 12 | 97.15% | 1
| 49 | 2001-11-27 | 2002-02-25 | 4 | 97.45% | 4 | 97.45% | 1
| 50 | 2001-11-22 | 2002-02-20 | 9 | 88.83% | 9 | 88.83% | 1
| 51 | 2001-11-22 | 2002-02-20 | 9 | 95.38% | 9 | 95.38% | 1
| 52 | 2001-11-22 | 2002-02-20 | 9 | 77.11% | 9 | 77.11% | 1
| 53 | 2001-11-25 | 2002-02-23 | 6 | 94.29% | 6 | 94.29% | 1
| 54 | 2001-11-25 | 2002-02-23 | 6 | 71.35% | 6 | 71.35% | 1
| 55 | 2001-11-27 | 2002-02-25 | 4 | 68.01% | 4 | 68.01% | 1
| 56 | 2001-11-26 | 2002-02-24 | 5 | 93.28% | 5 | 93.28% | 1
| 57 | 2001-11-27 | 2002-02-25 | 4 | 90.15% | 4 | 90.15% | 1
| 58 | 2001-11-25 | 2002-02-23 | 6 | 95.05% | 6 | 95.05% | 1
| 59 | 2001-11-26 | 2002-02-24 | 5 | 48.91% | 5 | 48.91% | 1
| 60 | 2001-11-23 | 2002-02-21 | 8 | 69.41% | 8 | 69.41% | 1
| 61 | 2001-11-23 | 2002-02-21 | 8 | 76.71% | 8 | 76.71% | 1
| 62 | 2001-11-24 | 2002-02-22 | 7 | 98.56% | 7 | 98.56% | 1
| 63 | 2001-11-24 | 2002-02-22 | 7 | 91.78% | 7 | 91.78% | 1
| 64 | 2001-11-28 | 2002-02-26 | 3 | 89.73% | 3 | 89.73% | 1
| 65 | 2001-11-29 | 2002-02-27 | 2 | 89.18% | 2 | 89.18% | 1
| 66 | 2001-11-30 | 2002-02-28 | 1 | 90.25% | 1 | 90.25% | 1
| 67 | 2001-11-29 | 2002-02-27 | 2 | 90.24% | 2 | 90.24% | 1
| 68 | 2001-11-28 | 2002-02-26 | 3 | 79.81% | 3 | 79.81% | 1
| 69 | 2001-11-30 | 2002-02-28 | 1 | 91.75% | 1 | 91.75% | 1
| 70 | 2001-12-02 | 2002-03-02 | 0 | 89.64% | 0 | 89.64% | 0
| 71 | 2001-12-02 | 2002-03-02 | 0 | 92.25% | 0 | 92.25% | 0
| 72 | 2001-11-23 | 2002-02-21 | 8 | 90.56% | 8 | 90.56% | 1
| 73 | 2001-11-25 | 2002-02-23 | 6 | 82.64% | 6 | 82.64% | 1
| 74 | 2001-11-24 | 2002-02-22 | 7 | 75.57% | 7 | 75.57% | 1
| 75 | 2001-11-25 | 2002-02-23 | 6 | 80.07% | 6 | 80.07% | 1
| 76 | 2001-11-25 | 2002-02-23 | 6 | 83.51% | 6 | 83.51% | 1
| 77 | 2001-11-24 | 2002-02-22 | 7 | 76.75% | 7 | 76.75% | 1
| 78 | 2001-12-05 | 2002-03-05 | 0 | 84.87% | 0 | 84.87% | 0
| 79 | 2001-11-29 | 2002-02-27 | 2 | 87.28% | 2 | 87.28% | 1
| 80 | 2001-11-29 | 2002-02-27 | 2 | 72% | 2 | 72% | 1
| 81 | 2001-12-05 | 2002-03-05 | 0 | 81.34% | 0 | 81.34% | 0
| 82 | 2001-11-29 | 2002-02-27 | 2 | 83.46% | 2 | 83.46% | 1
| 83 | 2001-12-02 | 2002-03-02 | 0 | 85.64% | 0 | 85.64% | 0
| 84 | 2001-12-03 | 2002-03-03 | 0 | 73.5% | 0 | 73.5% | 0
| 85 | 2001-12-06 | 2002-03-06 | 0 | 85.13% | 0 | 85.13% | 0
| 86 | 2001-12-04 | 2002-03-04 | 0 | 55.05% | 0 | 55.05% | 0
| 87 | 2001-12-03 | 2002-03-03 | 0 | 82.02% | 0 | 82.02% | 0
| 88 | 2001-12-04 | 2002-03-04 | 0 | 86.75% | 0 | 86.75% | 0
| 89 | 2001-12-04 | 2002-03-04 | 0 | 93.76% | 0 | 93.76% | 0
| 90 | 2001-12-02 | 2002-03-02 | 0 | 56.57% | 0 | 56.57% | 0
| 91 | 2001-11-29 | 2002-02-27 | 2 | 60.62% | 2 | 60.62% | 1
| 92 | 2001-12-08 | 2002-03-08 | 0 | 84.85% | 0 | 84.85% | 0
| 93 | 2001-12-04 | 2002-03-04 | 0 | 82.26% | 0 | 82.26% | 0
| 96 | 2001-12-01 | 2002-03-01 | 0 | 96.79% | 0 | 96.79% | 0
| 100 | 2001-12-01 | 2002-03-01 | 0 | 75.8% | 0 | 75.8% | 0
| 102 | 2001-12-02 | 2002-03-02 | 0 | 80.19% | 0 | 80.19% | 0
| 103 | 2001-11-29 | 2002-02-27 | 2 | 83.71% | 2 | 83.71% | 1
| 104 | 2001-12-03 | 2002-03-03 | 0 | 76.62% | 0 | 76.62% | 0
| 105 | 2001-11-28 | 2002-02-26 | 3 | 76.16% | 3 | 76.16% | 1
| 106 | 2001-11-29 | 2002-02-27 | 2 | 64.98% | 2 | 64.98% | 1
| 107 | 2001-11-29 | 2002-02-27 | 2 | 67.59% | 2 | 67.59% | 1
| 108 | 2001-12-02 | 2002-03-02 | 0 | 53.68% | 0 | 53.68% | 0
| 109 | 2001-12-03 | 2002-03-03 | 0 | 96.58% | 0 | 96.58% | 0
| 113 | 2001-12-02 | 2002-03-02 | 0 | 70.97% | 0 | 70.97% | 0
| 114 | 2001-11-21 | 2002-02-19 | 10 | 75.5% | 10 | 75.5% | 1
| 115 | 2001-11-27 | 2002-02-25 | 4 | 79.15% | 4 | 79.15% | 1
| 116 | 2001-11-26 | 2002-02-24 | 5 | 70.7% | 5 | 70.7% | 1
| 117 | 2001-12-04 | 2002-03-04 | 0 | 60.32% | 0 | 60.32% | 0
| 118 | 2001-12-03 | 2002-03-03 | 0 | 82.46% | 0 | 82.46% | 0
| 119 | 2001-12-03 | 2002-03-03 | 0 | 97.32% | 0 | 97.32% | 0
| 120 | 2001-12-04 | 2002-03-04 | 0 | 83.23% | 0 | 83.23% | 0
| 121 | 2001-12-03 | 2002-03-03 | 0 | 38.92% | 0 | 38.92% | 0
| 122 | 2001-12-03 | 2002-03-03 | 0 | 90.1% | 0 | 90.1% | 0
|  |  |  | Average | 84.36% |  |  | 62
|  |  |  | Weighted Average | 0.88961

## Mar 2002
| # of Turbine which have operated > 90 days as of |  |  | 2002-03-31 | 279
| Weighted Average Enron Availability MTD |  |  | 2002-03-31 | 96.19% | Modified to deduct the 15 tower problems at Trent Mesa
MONTFORT - 20
EXHIBIT K
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
2002-03-01
2002-03-31 | 1 | 2001-05-07 | 2001-08-05 | 31 | 98.4% | 31 | 98.4% | 1
31 | 2 | 2001-06-27 | 2001-09-25 | 31 | 97.65% | 31 | 97.65% | 1
| 3 | 2001-05-17 | 2001-08-15 | 31 | 99.06% | 31 | 99.06% | 1
| 4 | 2001-06-27 | 2001-09-25 | 31 | 97.89% | 31 | 97.89% | 1
| 5 | 2001-06-27 | 2001-09-25 | 31 | 99.3% | 31 | 99.3% | 1
| 6 | 2001-06-01 | 2001-08-30 | 31 | 99.1% | 31 | 99.1% | 1
| 7 | 2001-06-27 | 2001-09-25 | 31 | 95.85% | 31 | 95.85% | 1
| 8 | 2001-06-11 | 2001-09-09 | 31 | 99.15% | 31 | 99.15% | 1
| 9 | 2001-06-11 | 2001-09-09 | 31 | 97.37% | 31 | 97.37% | 1
| 10 | 2001-06-28 | 2001-09-26 | 31 | 97.31% | 31 | 97.31% | 1
| 11 | 2001-06-28 | 2001-09-26 | 31 | 98.78% | 31 | 98.78% | 1
| 12 | 2001-06-21 | 2001-09-19 | 31 | 97.43% | 31 | 97.43% | 1
| 13 | 2001-06-28 | 2001-09-26 | 31 | 99.23% | 31 | 99.23% | 1
| 14 | 2001-06-28 | 2001-09-26 | 31 | 95.17% | 31 | 95.17% | 1
| 15 | 2001-06-28 | 2001-09-26 | 31 | 95.84% | 31 | 95.84% | 1
| 16 | 2001-06-28 | 2001-09-26 | 31 | 98.81% | 31 | 98.81% | 1
| 17 | 2001-06-30 | 2001-09-28 | 31 | 94.44% | 31 | 94.44% | 1
| 18 | 2001-07-02 | 2001-09-30 | 31 | 95.77% | 31 | 95.77% | 1
| 19 | 2001-07-02 | 2001-09-30 | 31 | 97.9% | 31 | 97.9% | 1
| 20 | 2001-06-30 | 2001-09-28 | 31 | 97.72% | 31 | 97.72% | 1
|  |  |  | Average | 97.61% |  |  | 20
|  |  |  | Weighted Average | 97.61%
Trent Mesa - 100
EXHIBIT I-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Comments
| 1 | 2001-08-13 | 2001-11-11 | 31 | 95.18% | 31 | 95.18% | 1
| 2 | 2001-08-13 | 2001-11-11 | 31 | 79.37% | 31 | 79.37% | 1
| 3 | 2001-08-13 | 2001-11-11 | 31 | 91.92% | 31 | 91.92% | 1
| 4 | 2001-08-22 | 2001-11-20 | 31 |  | 0 | 0% | 1 | Tower Fdn (25.5% EA)
| 5 | 2001-08-22 | 2001-11-20 | 31 | 96.03% | 31 | 96.03% | 1
| 6 | 2001-08-22 | 2001-11-20 | 31 |  | 0 | 0% | 1 | Tower Fdn (9.6% EA)
| 7 | 2001-08-21 | 2001-11-19 | 31 | 97.18% | 31 | 97.18% | 1
| 8 | 2001-08-28 | 2001-11-26 | 31 |  | 0 | 0% | 1 | Tower Fdn (25.5% EA)
| 9 | 2001-08-22 | 2001-11-20 | 31 | 98.22% | 31 | 98.22% | 1
| 10 | 2001-08-22 | 2001-11-20 | 31 | 93.51% | 31 | 93.51% | 1
| 11 | 2001-08-17 | 2001-11-15 | 31 | 91.31% | 31 | 91.31% | 1
| 12 | 2001-08-13 | 2001-11-11 | 31 | 98.36% | 31 | 98.36% | 1
| 13 | 2001-08-22 | 2001-11-20 | 31 | 95.99% | 31 | 95.99% | 1
| 14 | 2001-08-13 | 2001-11-11 | 31 |  | 0 | 0% | 1 | Tower Fdn (23.4% EA)
| 15 | 2001-08-22 | 2001-11-20 | 31 | 87.79% | 31 | 87.79% | 1
| 16 | 2001-08-28 | 2001-11-26 | 31 | 95.73% | 31 | 95.73% | 1
| 17 | 2001-08-28 | 2001-11-26 | 31 | 98.34% | 31 | 98.34% | 1
| 18 | 2001-08-28 | 2001-11-26 | 31 | 73.98% | 31 | 73.98% | 1
| 19 | 2001-08-22 | 2001-11-20 | 31 | 95.15% | 31 | 95.15% | 1
| 20 | 2001-08-13 | 2001-11-11 | 31 | 95.77% | 31 | 95.77% | 1
| 21 | 2001-08-06 | 2001-11-04 | 31 | 71% | 31 | 71% | 1
| 22 | 2001-07-26 | 2001-10-24 | 31 | 79.75% | 31 | 79.75% | 1
| 23 | 2001-07-26 | 2001-10-24 | 31 | 91.25% | 31 | 91.25% | 1
| 24 | 2001-07-26 | 2001-10-24 | 31 | 89.5% | 31 | 89.5% | 1
| 25 | 2001-07-26 | 2001-10-24 | 31 | 87.05% | 31 | 87.05% | 1
| 26 | 2001-07-26 | 2001-10-24 | 31 | 89.51% | 31 | 89.51% | 1
| 27 | 2001-07-26 | 2001-10-24 | 31 | 95.3% | 31 | 95.3% | 1
| 28 | 2001-07-26 | 2001-10-24 | 31 | 90.71% | 31 | 90.71% | 1
| 29 | 2001-07-26 | 2001-10-24 | 31 | 84.39% | 31 | 84.39% | 1
| 30 | 2001-07-26 | 2001-10-24 | 31 |  | 0 | 0% | 1 | Tower Fdn (14.8% EA)
| 31 | 2001-07-26 | 2001-10-24 | 31 | 39.37% | 31 | 39.37% | 1
| 32 | 2001-09-18 | 2001-12-17 | 31 | 61.96% | 31 | 61.96% | 1
| 33 | 2001-07-26 | 2001-10-24 | 31 | 79.9% | 31 | 79.9% | 1
| 34 | 2001-07-26 | 2001-10-24 | 31 | 97.89% | 31 | 97.89% | 1
| 35 | 2001-07-26 | 2001-10-24 | 31 | 90.57% | 31 | 90.57% | 1
| 36 | 2001-07-26 | 2001-10-24 | 31 | 96.92% | 31 | 96.92% | 1
| 37 | 2001-07-26 | 2001-10-24 | 31 |  | 0 | 0% | 1 | Tower Fdn (27.3% EA)
| 38 | 2001-07-26 | 2001-10-24 | 31 | 92.83% | 31 | 92.83% | 1
| 39 | 2001-07-26 | 2001-10-24 | 31 | 81.82% | 31 | 81.82% | 1
| 40 | 2001-07-26 | 2001-10-24 | 31 | 94.39% | 31 | 94.39% | 1
| 41 | 2001-07-26 | 2001-10-24 | 31 |  | 0 | 0% | 1 | Tower Fdn (2.5% EA)
| 42 | 2001-07-26 | 2001-10-24 | 31 |  | 0 | 0% | 1 | Tower Fdn (3.1% EA)
| 43 | 2001-07-26 | 2001-10-24 | 31 | 51.92% | 31 | 51.92% | 1
| 44 | 2001-07-26 | 2001-10-24 | 31 | 81.75% | 31 | 81.75% | 1
| 45 | 2001-08-13 | 2001-11-11 | 31 | 57.83% | 31 | 57.83% | 1
| 46 | 2001-09-18 | 2001-12-17 | 31 | 64.4% | 31 | 64.4% | 1
| 47 | 2001-08-28 | 2001-11-26 | 31 |  | 0 | 0% | 1
| 48 | 2001-08-28 | 2001-11-26 | 31 |  | 0 | 0% | 1 | Tower Fdn (EA unavailable)
| 49 | 2001-09-18 | 2001-12-17 | 31 | 92.27% | 31 | 92.27% | 1
| 50 | 2001-11-02 | 2002-01-31 | 31 | 93.53% | 31 | 93.53% | 1
| 51 | 2001-09-18 | 2001-12-17 | 31 | 91.74% | 31 | 91.74% | 1
| 52 | 2001-09-04 | 2001-12-03 | 31 | 91.51% | 31 | 91.51% | 1
| 53 | 2001-09-18 | 2001-12-17 | 31 | 85.96% | 31 | 85.96% | 1
| 54 | 2001-09-04 | 2001-12-03 | 31 | 66.1% | 31 | 66.1% | 1
| 55 | 2001-08-29 | 2001-11-27 | 31 | 81.06% | 31 | 81.06% | 1
| 56 | 2001-09-04 | 2001-12-03 | 31 | 93.03% | 31 | 93.03% | 1
| 57 | 2001-09-04 | 2001-12-03 | 31 | 95.87% | 31 | 95.87% | 1
| 58 | 2001-09-18 | 2001-12-17 | 31 | 80.02% | 31 | 80.02% | 1
| 59 | 2001-09-18 | 2001-12-17 | 31 |  | 0 | 0% | 1 | Tower Fdn (11.7% EA)
| 60 | 2001-09-18 | 2001-12-17 | 31 |  | 0 | 0% | 1 | Tower Fdn (78% EA)
| 61 | 2001-09-18 | 2001-12-17 | 31 | 88.61% | 31 | 88.61% | 1
| 62 | 2001-09-18 | 2001-12-17 | 31 | 79.55% | 31 | 79.55% | 1
| 63 | 2001-09-18 | 2001-12-17 | 31 | 83.89% | 31 | 83.89% | 1
| 64 | 2001-09-04 | 2001-12-03 | 31 | 89.57% | 31 | 89.57% | 1
| 65 | 2001-09-18 | 2001-12-17 | 31 | 91.37% | 31 | 91.37% | 1
| 66 | 2001-09-18 | 2001-12-17 | 31 | 92.39% | 31 | 92.39% | 1
| 67 | 2001-11-02 | 2002-01-31 | 31 | 87.5% | 31 | 87.5% | 1
| 68 | 2001-09-18 | 2001-12-17 | 31 | 97.16% | 31 | 97.16% | 1
| 69 | 2001-09-18 | 2001-12-17 | 31 |  | 0 | 0% | 1 | Tower Fdn (.9% EA)
| 70 | 2001-09-06 | 2001-12-05 | 31 | 57.96% | 31 | 57.96% | 1
| 71 | 2001-09-18 | 2001-12-17 | 31 | 97.71% | 31 | 97.71% | 1
| 72 | 2001-09-07 | 2001-12-06 | 31 | 95.18% | 31 | 95.18% | 1
| 73 | 2001-09-18 | 2001-12-17 | 31 | 83.44% | 31 | 83.44% | 1
| 74 | 2001-09-18 | 2001-12-17 | 31 | 89.26% | 31 | 89.26% | 1
| B-5 | 2001-10-20 | 2002-01-18 | 31 | 88.29% | 31 | 88.29% | 1
| 76 | 2001-09-18 | 2001-12-17 | 31 | 93.73% | 31 | 93.73% | 1
| 77 | 2001-09-18 | 2001-12-17 | 31 | 93.62% | 31 | 93.62% | 1
| 78 | 2001-09-18 | 2001-12-17 | 31 | 93.8% | 31 | 93.8% | 1
| 79 | 2001-09-18 | 2001-12-17 | 31 | 73.12% | 31 | 73.12% | 1
| 80 | 2001-09-18 | 2001-12-17 | 31 | 96.37% | 31 | 96.37% | 1
| 81 | 2001-09-18 | 2001-12-17 | 31 | 97.37% | 31 | 97.37% | 1
| 82 | 2001-09-18 | 2001-12-17 | 31 |  | 0 | 0% | 1 | Tower Fdn (3.1% EA)
| 83 | 2001-09-18 | 2001-12-17 | 31 | 81.27% | 31 | 81.27% | 1
| 84 | 2001-09-18 | 2001-12-17 | 31 | 77.45% | 31 | 77.45% | 1
| 85 | 2001-09-18 | 2001-12-17 | 31 | 82.11% | 31 | 82.11% | 1
| 86 | 2001-09-18 | 2001-12-17 | 31 | 97.19% | 31 | 97.19% | 1
| 87 | 2001-09-07 | 2001-12-06 | 31 | 89.84% | 31 | 89.84% | 1
| 88 | 2001-09-18 | 2001-12-17 | 31 | 87.1% | 31 | 87.1% | 1
| 89 | 2001-09-07 | 2001-12-06 | 31 | 92.02% | 31 | 92.02% | 1
| 90 | 2001-09-18 | 2001-12-17 | 31 | 83.21% | 31 | 83.21% | 1
| 91 | 2001-11-02 | 2002-01-31 | 31 | 77.41% | 31 | 77.41% | 1
| 92 | 2001-11-02 | 2002-01-31 | 31 | 75.72% | 31 | 75.72% | 1
| 93 | 2001-10-31 | 2002-01-29 | 31 | 64.8% | 31 | 64.8% | 1
| 94 | 2001-10-25 | 2002-01-23 | 31 | 65.27% | 31 | 65.27% | 1
| 95 | 2001-11-06 | 2002-02-04 | 31 | 87.63% | 31 | 87.63% | 1
| 96 | 2001-11-06 | 2002-02-04 | 31 | 67.96% | 31 | 67.96% | 1
| B-6 | 2001-10-22 | 2002-01-20 | 31 | 74.83% | 31 | 74.83% | 1
| B-7 | 2001-10-22 | 2002-01-20 | 31 | 93.21% | 31 | 93.21% | 1
| B-8 | 2001-10-19 | 2002-01-17 | 31 |  | 0 | 0% | 1 | Tower Fdn (18.3% EA)
| B-9 | 2001-10-19 | 2002-01-17 | 31 |  | 0 | 0% | 1 | Tower Fdn (2.6% EA)
|  |  |  | Average | 85.62% |  |  | 100
|  |  |  | Weighted Average | 85.62%
Mill Run - 10 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 1 | 2001-11-02 | 2002-01-31 | 31 | 95.73% | 31 | 95.73% | 1
| 2 | 2001-11-02 | 2002-01-31 | 31 | 92.7% | 31 | 92.7% | 1
| 3 | 2001-11-02 | 2002-01-31 | 31 | 80.73% | 31 | 80.73% | 1
| 4 | 2001-11-02 | 2002-01-31 | 31 | 91.63% | 31 | 91.63% | 1
| 5 | 2001-11-02 | 2002-01-31 | 31 | 97.72% | 31 | 97.72% | 1
| 6 | 2001-11-02 | 2002-01-31 | 31 | 96.57% | 31 | 96.57% | 1
| 7 | 2001-11-02 | 2002-01-31 | 31 | 88.68% | 31 | 88.68% | 1
| 8 | 2001-11-02 | 2002-01-31 | 31 | 89% | 31 | 89% | 1
| 9 | 2001-11-02 | 2002-01-31 | 31 | 96.09% | 31 | 96.09% | 1
| 10 | 2001-11-02 | 2002-01-31 | 31 | 95.65% | 31 | 95.65% | 1
|  |  |  | Average | 92.45% |  |  | 10
|  |  |  | Weighted Average | 92.45%
Fenner - 20 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 1 | 2001-12-11 | 2002-03-11 | 21 | 79.6% | 21 | 79.6% | 1
| 2 | 2001-12-11 | 2002-03-11 | 21 | 99.84% | 21 | 99.84% | 1
| 3 | 2001-12-11 | 2002-03-11 | 21 | 92.41% | 21 | 92.41% | 1
| 4 | 2001-12-11 | 2002-03-11 | 21 | 97.61% | 21 | 97.61% | 1
| 5 | 2001-12-11 | 2002-03-11 | 21 | 95.25% | 21 | 95.25% | 1
| 6 | 2001-12-11 | 2002-03-11 | 21 | 98.55% | 21 | 98.55% | 1
| 7 | 2001-12-11 | 2002-03-11 | 21 | 97.71% | 21 | 97.71% | 1
| 8 | 2001-12-11 | 2002-03-11 | 21 | 97% | 21 | 97% | 1
| 9 | 2001-12-11 | 2002-03-11 | 21 | 62.79% | 21 | 62.79% | 1
| 10 | 2001-12-11 | 2002-03-11 | 21 | 84.14% | 21 | 84.14% | 1
| 11 | 2001-12-18 | 2002-03-18 | 14 | 96.21% | 14 | 96.21% | 1
| 12 | 2001-12-11 | 2002-03-11 | 21 | 94.68% | 21 | 94.68% | 1
| 13 | 2001-12-11 | 2002-03-11 | 21 | 96.87% | 21 | 96.87% | 1
| 14 | 2001-12-11 | 2002-03-11 | 21 | 97.72% | 21 | 97.72% | 1
| 15 | 2001-12-11 | 2002-03-11 | 21 | 94.08% | 21 | 94.08% | 1
| 16 | 2001-12-18 | 2002-03-18 | 14 | 95.51% | 14 | 95.51% | 1
| 17 | 2001-12-11 | 2002-03-11 | 21 | 84.43% | 21 | 84.43% | 1
| 18 | 2001-12-11 | 2002-03-11 | 21 | 91.25% | 21 | 91.25% | 1
| 19 | 2001-12-11 | 2002-03-11 | 21 | 94.35% | 21 | 94.35% | 1
| 20 | 2001-12-11 | 2002-03-11 | 21 | 95.07% | 21 | 95.07% | 1
|  |  |  | Average | 92.25% |  |  | 20
|  |  |  | Weighted Average | 92.13%
Somerset - 6 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 1 | 2001-11-06 | 2002-02-04 | 31 | 95.39% | 31 | 95.39% | 1
| 2 | 2001-11-06 | 2002-02-04 | 31 | 98.78% | 31 | 98.78% | 1
| 3 | 2001-11-06 | 2002-02-04 | 31 | 91.07% | 31 | 91.07% | 1
| 4 | 2001-11-06 | 2002-02-04 | 31 | 97.83% | 31 | 97.83% | 1
| 5 | 2001-11-06 | 2002-02-04 | 31 | 99.22% | 31 | 99.22% | 1
| 6 | 2001-11-06 | 2002-02-04 | 31 | 92.05% | 31 | 92.05% | 1
|  |  |  | Average | 95.72% |  |  | 6
|  |  |  | Weighted Average | 95.72%
Klondike - 16 WTG
EXHIBIT K-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 1 | 2001-12-31 | 2002-03-31 | 1 | 100% | 1 | 100% | 1
| 2 | 2001-12-30 | 2002-03-30 | 2 | 100% | 2 | 100% | 1
| 3 | 2001-12-31 | 2002-03-31 | 1 | 100% | 1 | 100% | 1
| 4 | 2001-12-29 | 2002-03-29 | 3 | 100% | 3 | 100% | 1
| 5 | 2001-12-31 | 2002-03-31 | 1 | 100% | 1 | 100% | 1
| 6 | 2001-12-30 | 2002-03-30 | 2 | 100% | 2 | 100% | 1
| 7 | 2001-12-30 | 2002-03-30 | 2 | 100% | 2 | 100% | 1
| 8 | 2001-12-29 | 2002-03-29 | 3 | 100% | 3 | 100% | 1
| 9 | 2001-12-29 | 2002-03-29 | 3 | 100% | 3 | 100% | 1
| 10 | 2001-12-29 | 2002-03-29 | 3 | 100% | 3 | 100% | 1
| 11 | 2001-12-31 | 2002-03-31 | 1 | 90.43% | 1 | 90.43% | 1
| 12 | 2001-12-29 | 2002-03-29 | 3 | 88.75% | 3 | 88.75% | 1
| 13 | 2001-12-28 | 2002-03-28 | 4 | 99.69% | 4 | 99.69% | 1
| 14 | 2001-12-28 | 2002-03-28 | 4 | 97.67% | 4 | 97.67% | 1
| 15 | 2001-12-28 | 2002-03-28 | 4 | 99.64% | 4 | 99.64% | 1
| 16 | 2001-12-27 | 2002-03-27 | 5 | 99.38% | 5 | 99.38% | 1
|  |  |  | Average | 98.47% |  |  | 16
|  |  |  | Weighted Average | 98.61%
IM - I - 17 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 31 | 2001-12-12 | 2002-03-12 | 20 | 98.26% | 20 | 98.26% | 1
| 32 | 2001-12-12 | 2002-03-12 | 20 | 98.46% | 20 | 98.46% | 1
| 33 | 2001-12-14 | 2002-03-14 | 18 | 99.84% | 18 | 99.84% | 1
| 34 | 2001-12-11 | 2002-03-11 | 21 | 98.43% | 21 | 98.43% | 1
| 35 | 2001-12-08 | 2002-03-08 | 24 | 61.31% | 24 | 61.31% | 1
| 36 | 2001-12-09 | 2002-03-09 | 23 | 95.66% | 23 | 95.66% | 1
| 37 | 2001-12-08 | 2002-03-08 | 24 | 98.17% | 24 | 98.17% | 1
| 38 | 2001-12-08 | 2002-03-08 | 24 | 89.62% | 24 | 89.62% | 1
| 39 | 2001-12-11 | 2002-03-11 | 21 | 99.9% | 21 | 99.9% | 1
| 40 | 2001-12-07 | 2002-03-07 | 25 | 97.93% | 25 | 97.93% | 1
| 41 | 2001-12-08 | 2002-03-08 | 24 | 65.97% | 24 | 65.97% | 1
| 42 | 2001-12-08 | 2002-03-08 | 24 | 94.31% | 24 | 94.31% | 1
| 43 | 2001-12-10 | 2002-03-10 | 22 | 99.23% | 22 | 99.23% | 1
| 44 | 2001-12-09 | 2002-03-09 | 23 | 97.53% | 23 | 97.53% | 1
| 45 | 2001-12-08 | 2002-03-08 | 24 | 98.58% | 24 | 98.58% | 1
| 46 | 2001-12-11 | 2002-03-11 | 21 | 91.93% | 21 | 91.93% | 1
| 47 | 2001-12-08 | 2002-03-08 | 24 | 92.91% | 24 | 92.91% | 1
|  |  |  | Average | 92.83% |  |  | 17
|  |  |  | Weighted Average | 92.47%
IM - II - 90 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 1 | 2001-11-20 | 2002-02-18 | 31 | 95.6% | 31 | 95.6% | 1
| 2 | 2001-11-21 | 2002-02-19 | 31 | 96.04% | 31 | 96.04% | 1
| 3 | 2001-11-20 | 2002-02-18 | 31 | 95.39% | 31 | 95.39% | 1
| 4 | 2001-11-20 | 2002-02-18 | 31 | 84.58% | 31 | 84.58% | 1
| 5 | 2001-11-20 | 2002-02-18 | 31 | 96.51% | 31 | 96.51% | 1
| 7 | 2001-11-23 | 2002-02-21 | 31 | 99.53% | 31 | 99.53% | 1
| 8 | 2001-11-23 | 2002-02-21 | 31 | 95.43% | 31 | 95.43% | 1
| 9 | 2001-11-21 | 2002-02-19 | 31 | 96.37% | 31 | 96.37% | 1
| 13 | 2001-11-20 | 2002-02-18 | 31 | 90.92% | 31 | 90.92% | 1
| 14 | 2001-11-21 | 2002-02-19 | 31 | 93.82% | 31 | 93.82% | 1
| 15 | 2001-11-24 | 2002-02-22 | 31 | 55.95% | 31 | 55.95% | 1
| 17 | 2001-11-17 | 2002-02-15 | 31 | 97.82% | 31 | 97.82% | 1
| 18 | 2001-11-21 | 2002-02-19 | 31 | 99.66% | 31 | 99.66% | 1
| 19 | 2001-11-21 | 2002-02-19 | 31 | 97.76% | 31 | 97.76% | 1
| 20 | 2001-11-21 | 2002-02-19 | 31 | 96.99% | 31 | 96.99% | 1
| 21 | 2001-11-17 | 2002-02-15 | 31 | 99.04% | 31 | 99.04% | 1
| 22 | 2001-11-18 | 2002-02-16 | 31 | 94.2% | 31 | 94.2% | 1
| 23 | 2001-11-19 | 2002-02-17 | 31 | 81.89% | 31 | 81.89% | 1
| 24 | 2001-11-18 | 2002-02-16 | 31 | 98.78% | 31 | 98.78% | 1
| 25 | 2001-11-18 | 2002-02-16 | 31 | 99.42% | 31 | 99.42% | 1
| 26 | 2001-12-01 | 2002-03-01 | 31 | 98.51% | 31 | 98.51% | 1
| 27 | 2001-11-30 | 2002-02-28 | 31 | 99.01% | 31 | 99.01% | 1
| 28 | 2001-11-19 | 2002-02-17 | 31 | 89.29% | 31 | 89.29% | 1
| 29 | 2001-11-20 | 2002-02-18 | 31 | 99.56% | 31 | 99.56% | 1
| 30 | 2001-11-19 | 2002-02-17 | 31 | 98.94% | 31 | 98.94% | 1
| 49 | 2001-11-27 | 2002-02-25 | 31 | 99.72% | 31 | 99.72% | 1
| 50 | 2001-11-22 | 2002-02-20 | 31 | 98.1% | 31 | 98.1% | 1
| 51 | 2001-11-22 | 2002-02-20 | 31 | 86% | 31 | 86% | 1
| 52 | 2001-11-22 | 2002-02-20 | 31 | 93.99% | 31 | 93.99% | 1
| 53 | 2001-11-25 | 2002-02-23 | 31 | 81.58% | 31 | 81.58% | 1
| 54 | 2001-11-25 | 2002-02-23 | 31 | 93.5% | 31 | 93.5% | 1
| 55 | 2001-11-27 | 2002-02-25 | 31 | 98.2% | 31 | 98.2% | 1
| 56 | 2001-11-26 | 2002-02-24 | 31 | 98.84% | 31 | 98.84% | 1
| 57 | 2001-11-27 | 2002-02-25 | 31 | 97.39% | 31 | 97.39% | 1
| 58 | 2001-11-25 | 2002-02-23 | 31 | 91.13% | 31 | 91.13% | 1
| 59 | 2001-11-26 | 2002-02-24 | 31 | 96.79% | 31 | 96.79% | 1
| 60 | 2001-11-23 | 2002-02-21 | 31 | 99.04% | 31 | 99.04% | 1
| 61 | 2001-11-23 | 2002-02-21 | 31 | 74.93% | 31 | 74.93% | 1
| 62 | 2001-11-24 | 2002-02-22 | 31 | 99.1% | 31 | 99.1% | 1
| 63 | 2001-11-24 | 2002-02-22 | 31 | 87.77% | 31 | 87.77% | 1
| 64 | 2001-11-28 | 2002-02-26 | 31 | 98.54% | 31 | 98.54% | 1
| 65 | 2001-11-29 | 2002-02-27 | 31 | 95.57% | 31 | 95.57% | 1
| 66 | 2001-11-30 | 2002-02-28 | 31 | 98.54% | 31 | 98.54% | 1
| 67 | 2001-11-29 | 2002-02-27 | 31 |  | 0 | 0% | 1
| 68 | 2001-11-28 | 2002-02-26 | 31 | 97.14% | 31 | 97.14% | 1
| 69 | 2001-11-30 | 2002-02-28 | 31 | 99.18% | 31 | 99.18% | 1
| 70 | 2001-12-02 | 2002-03-02 | 30 | 79.08% | 30 | 79.08% | 1
| 71 | 2001-12-02 | 2002-03-02 | 30 | 98.27% | 30 | 98.27% | 1
| 72 | 2001-11-23 | 2002-02-21 | 31 | 98.71% | 31 | 98.71% | 1
| 73 | 2001-11-25 | 2002-02-23 | 31 | 97.56% | 31 | 97.56% | 1
| 74 | 2001-11-24 | 2002-02-22 | 31 | 95.35% | 31 | 95.35% | 1
| 75 | 2001-11-25 | 2002-02-23 | 31 | 98.29% | 31 | 98.29% | 1
| 76 | 2001-11-25 | 2002-02-23 | 31 | 88.05% | 31 | 88.05% | 1
| 77 | 2001-11-24 | 2002-02-22 | 31 | 98.56% | 31 | 98.56% | 1
| 78 | 2001-12-05 | 2002-03-05 | 27 | 95.37% | 27 | 95.37% | 1
| 79 | 2001-11-29 | 2002-02-27 | 31 | 97.13% | 31 | 97.13% | 1
| 80 | 2001-11-29 | 2002-02-27 | 31 | 96.72% | 31 | 96.72% | 1
| 81 | 2001-12-05 | 2002-03-05 | 27 | 70.3% | 27 | 70.3% | 1
| 82 | 2001-11-29 | 2002-02-27 | 31 | 98.94% | 31 | 98.94% | 1
| 83 | 2001-12-02 | 2002-03-02 | 30 | 98.55% | 30 | 98.55% | 1
| 84 | 2001-12-03 | 2002-03-03 | 29 | 84.67% | 29 | 84.67% | 1
| 85 | 2001-12-06 | 2002-03-06 | 26 | 94.94% | 26 | 94.94% | 1
| 86 | 2001-12-04 | 2002-03-04 | 28 | 47.12% | 28 | 47.12% | 1
| 87 | 2001-12-03 | 2002-03-03 | 29 | 98.48% | 29 | 98.48% | 1
| 88 | 2001-12-04 | 2002-03-04 | 28 | 98.45% | 28 | 98.45% | 1
| 89 | 2001-12-04 | 2002-03-04 | 28 | 99.21% | 28 | 99.21% | 1
| 90 | 2001-12-02 | 2002-03-02 | 30 | 99.07% | 30 | 99.07% | 1
| 91 | 2001-11-29 | 2002-02-27 | 31 | 91.61% | 31 | 91.61% | 1
| 92 | 2001-12-08 | 2002-03-08 | 24 | 98.06% | 24 | 98.06% | 1
| 93 | 2001-12-04 | 2002-03-04 | 28 | 94.81% | 28 | 94.81% | 1
| 96 | 2001-12-01 | 2002-03-01 | 31 | 99.05% | 31 | 99.05% | 1
| 100 | 2001-12-01 | 2002-03-01 | 31 | 93.36% | 31 | 93.36% | 1
| 102 | 2001-12-02 | 2002-03-02 | 30 | 99.15% | 30 | 99.15% | 1
| 103 | 2001-11-29 | 2002-02-27 | 31 | 98.99% | 31 | 98.99% | 1
| 104 | 2001-12-03 | 2002-03-03 | 29 | 92.24% | 29 | 92.24% | 1
| 105 | 2001-11-28 | 2002-02-26 | 31 | 75.8% | 31 | 75.8% | 1
| 106 | 2001-11-29 | 2002-02-27 | 31 | 93.11% | 31 | 93.11% | 1
| 107 | 2001-11-29 | 2002-02-27 | 31 | 90.01% | 31 | 90.01% | 1
| 108 | 2001-12-02 | 2002-03-02 | 30 | 79.47% | 30 | 79.47% | 1
| 109 | 2001-12-03 | 2002-03-03 | 29 | 98.77% | 29 | 98.77% | 1
| 113 | 2001-12-02 | 2002-03-02 | 30 | 92.89% | 30 | 92.89% | 1
| 114 | 2001-11-21 | 2002-02-19 | 31 | 97.36% | 31 | 97.36% | 1
| 115 | 2001-11-27 | 2002-02-25 | 31 | 98.54% | 31 | 98.54% | 1
| 116 | 2001-11-26 | 2002-02-24 | 31 | 79.5% | 31 | 79.5% | 1
| 117 | 2001-12-04 | 2002-03-04 | 28 | 93.01% | 28 | 93.01% | 1
| 118 | 2001-12-03 | 2002-03-03 | 29 | 98.37% | 29 | 98.37% | 1
| 119 | 2001-12-03 | 2002-03-03 | 29 | 90.15% | 29 | 90.15% | 1
| 120 | 2001-12-04 | 2002-03-04 | 28 | 99.08% | 28 | 99.08% | 1
| 121 | 2001-12-03 | 2002-03-03 | 29 | 77.68% | 29 | 77.68% | 1
| 122 | 2001-12-03 | 2002-03-03 | 29 | 92.26% | 29 | 92.26% | 1
|  |  |  | Average | 93.17% |  |  | 90
|  |  |  | Weighted Average | 93.23%

## Apr 2002
| # of Turbine which have operated > 90 days as of |  |  | 2002-04-30 | 279
| Weighted Average Enron Availability MTD |  |  | 2002-04-30 | 0% | Modified to deduct the 15 tower problems at Trent Mesa
MONTFORT - 20
EXHIBIT K
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
2002-04-01
2002-04-30 | 1 | 2001-05-07 | 2001-08-05 | 30 |  | 0 | 0% | 1
30 | 2 | 2001-06-27 | 2001-09-25 | 30 |  | 0 | 0% | 1
| 3 | 2001-05-17 | 2001-08-15 | 30 |  | 0 | 0% | 1
| 4 | 2001-06-27 | 2001-09-25 | 30 |  | 0 | 0% | 1
| 5 | 2001-06-27 | 2001-09-25 | 30 |  | 0 | 0% | 1
| 6 | 2001-06-01 | 2001-08-30 | 30 |  | 0 | 0% | 1
| 7 | 2001-06-27 | 2001-09-25 | 30 |  | 0 | 0% | 1
| 8 | 2001-06-11 | 2001-09-09 | 30 |  | 0 | 0% | 1
| 9 | 2001-06-11 | 2001-09-09 | 30 |  | 0 | 0% | 1
| 10 | 2001-06-28 | 2001-09-26 | 30 |  | 0 | 0% | 1
| 11 | 2001-06-28 | 2001-09-26 | 30 |  | 0 | 0% | 1
| 12 | 2001-06-21 | 2001-09-19 | 30 |  | 0 | 0% | 1
| 13 | 2001-06-28 | 2001-09-26 | 30 |  | 0 | 0% | 1
| 14 | 2001-06-28 | 2001-09-26 | 30 |  | 0 | 0% | 1
| 15 | 2001-06-28 | 2001-09-26 | 30 |  | 0 | 0% | 1
| 16 | 2001-06-28 | 2001-09-26 | 30 |  | 0 | 0% | 1
| 17 | 2001-06-30 | 2001-09-28 | 30 |  | 0 | 0% | 1
| 18 | 2001-07-02 | 2001-09-30 | 30 |  | 0 | 0% | 1
| 19 | 2001-07-02 | 2001-09-30 | 30 |  | 0 | 0% | 1
| 20 | 2001-06-30 | 2001-09-28 | 30 |  | 0 | 0% | 1
|  |  |  | Average | #DIV/0! |  |  | 20
|  |  |  | Weighted Average | #DIV/0!
Trent Mesa - 100
EXHIBIT I-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included | Comments
| 1 | 2001-08-13 | 2001-11-11 | 30 |  | 0 | 0% | 1
| 2 | 2001-08-13 | 2001-11-11 | 30 |  | 0 | 0% | 1
| 3 | 2001-08-13 | 2001-11-11 | 30 |  | 0 | 0% | 1
| 4 | 2001-08-22 | 2001-11-20 | 30 |  | 0 | 0% | 1 | Tower Fdn (25.5% EA)
| 5 | 2001-08-22 | 2001-11-20 | 30 |  | 0 | 0% | 1
| 6 | 2001-08-22 | 2001-11-20 | 30 |  | 0 | 0% | 1 | Tower Fdn (9.6% EA)
| 7 | 2001-08-21 | 2001-11-19 | 30 |  | 0 | 0% | 1
| 8 | 2001-08-28 | 2001-11-26 | 30 |  | 0 | 0% | 1 | Tower Fdn (25.5% EA)
| 9 | 2001-08-22 | 2001-11-20 | 30 |  | 0 | 0% | 1
| 10 | 2001-08-22 | 2001-11-20 | 30 |  | 0 | 0% | 1
| 11 | 2001-08-17 | 2001-11-15 | 30 |  | 0 | 0% | 1
| 12 | 2001-08-13 | 2001-11-11 | 30 |  | 0 | 0% | 1
| 13 | 2001-08-22 | 2001-11-20 | 30 |  | 0 | 0% | 1
| 14 | 2001-08-13 | 2001-11-11 | 30 |  | 0 | 0% | 1 | Tower Fdn (23.4% EA)
| 15 | 2001-08-22 | 2001-11-20 | 30 |  | 0 | 0% | 1
| 16 | 2001-08-28 | 2001-11-26 | 30 |  | 0 | 0% | 1
| 17 | 2001-08-28 | 2001-11-26 | 30 |  | 0 | 0% | 1
| 18 | 2001-08-28 | 2001-11-26 | 30 |  | 0 | 0% | 1
| 19 | 2001-08-22 | 2001-11-20 | 30 |  | 0 | 0% | 1
| 20 | 2001-08-13 | 2001-11-11 | 30 |  | 0 | 0% | 1
| 21 | 2001-08-06 | 2001-11-04 | 30 |  | 0 | 0% | 1
| 22 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 23 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 24 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 25 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 26 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 27 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 28 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 29 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 30 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1 | Tower Fdn (14.8% EA)
| 31 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 32 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 33 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 34 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 35 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 36 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 37 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1 | Tower Fdn (27.3% EA)
| 38 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 39 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 40 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 41 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1 | Tower Fdn (2.5% EA)
| 42 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1 | Tower Fdn (3.1% EA)
| 43 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 44 | 2001-07-26 | 2001-10-24 | 30 |  | 0 | 0% | 1
| 45 | 2001-08-13 | 2001-11-11 | 30 |  | 0 | 0% | 1
| 46 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 47 | 2001-08-28 | 2001-11-26 | 30 |  | 0 | 0% | 1
| 48 | 2001-08-28 | 2001-11-26 | 30 |  | 0 | 0% | 1 | Tower Fdn (EA unavailable)
| 49 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 50 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 51 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 52 | 2001-09-04 | 2001-12-03 | 30 |  | 0 | 0% | 1
| 53 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 54 | 2001-09-04 | 2001-12-03 | 30 |  | 0 | 0% | 1
| 55 | 2001-08-29 | 2001-11-27 | 30 |  | 0 | 0% | 1
| 56 | 2001-09-04 | 2001-12-03 | 30 |  | 0 | 0% | 1
| 57 | 2001-09-04 | 2001-12-03 | 30 |  | 0 | 0% | 1
| 58 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 59 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1 | Tower Fdn (11.7% EA)
| 60 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1 | Tower Fdn (78% EA)
| 61 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 62 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 63 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 64 | 2001-09-04 | 2001-12-03 | 30 |  | 0 | 0% | 1
| 65 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 66 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 67 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 68 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 69 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1 | Tower Fdn (.9% EA)
| 70 | 2001-09-06 | 2001-12-05 | 30 |  | 0 | 0% | 1
| 71 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 72 | 2001-09-07 | 2001-12-06 | 30 |  | 0 | 0% | 1
| 73 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 74 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| B-5 | 2001-10-20 | 2002-01-18 | 30 |  | 0 | 0% | 1
| 76 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 77 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 78 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 79 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 80 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 81 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 82 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1 | Tower Fdn (3.1% EA)
| 83 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 84 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 85 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 86 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 87 | 2001-09-07 | 2001-12-06 | 30 |  | 0 | 0% | 1
| 88 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 89 | 2001-09-07 | 2001-12-06 | 30 |  | 0 | 0% | 1
| 90 | 2001-09-18 | 2001-12-17 | 30 |  | 0 | 0% | 1
| 91 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 92 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 93 | 2001-10-31 | 2002-01-29 | 30 |  | 0 | 0% | 1
| 94 | 2001-10-25 | 2002-01-23 | 30 |  | 0 | 0% | 1
| 95 | 2001-11-06 | 2002-02-04 | 30 |  | 0 | 0% | 1
| 96 | 2001-11-06 | 2002-02-04 | 30 |  | 0 | 0% | 1
| B-6 | 2001-10-22 | 2002-01-20 | 30 |  | 0 | 0% | 1
| B-7 | 2001-10-22 | 2002-01-20 | 30 |  | 0 | 0% | 1
| B-8 | 2001-10-19 | 2002-01-17 | 30 |  | 0 | 0% | 1 | Tower Fdn (18.3% EA)
| B-9 | 2001-10-19 | 2002-01-17 | 30 |  | 0 | 0% | 1 | Tower Fdn (2.6% EA)
|  |  |  | Average | #DIV/0! |  |  | 100
|  |  |  | Weighted Average | #DIV/0!
Mill Run - 10 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 1 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 2 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 3 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 4 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 5 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 6 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 7 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 8 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 9 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
| 10 | 2001-11-02 | 2002-01-31 | 30 |  | 0 | 0% | 1
|  |  |  | Average | #DIV/0! |  |  | 10
|  |  |  | Weighted Average | #DIV/0!
Fenner - 20 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 1 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 2 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 3 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 4 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 5 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 6 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 7 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 8 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 9 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 10 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 11 | 2001-12-18 | 2002-03-18 | 30 |  | 0 | 0% | 1
| 12 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 13 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 14 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 15 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 16 | 2001-12-18 | 2002-03-18 | 30 |  | 0 | 0% | 1
| 17 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 18 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 19 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 20 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
|  |  |  | Average | #DIV/0! |  |  | 20
|  |  |  | Weighted Average | #DIV/0!
Somerset - 6 WTG
EXHIBIT P
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 1 | 2001-11-06 | 2002-02-04 | 30 |  | 0 | 0% | 1
| 2 | 2001-11-06 | 2002-02-04 | 30 |  | 0 | 0% | 1
| 3 | 2001-11-06 | 2002-02-04 | 30 |  | 0 | 0% | 1
| 4 | 2001-11-06 | 2002-02-04 | 30 |  | 0 | 0% | 1
| 5 | 2001-11-06 | 2002-02-04 | 30 |  | 0 | 0% | 1
| 6 | 2001-11-06 | 2002-02-04 | 30 |  | 0 | 0% | 1
|  |  |  | Average | #DIV/0! |  |  | 6
|  |  |  | Weighted Average | #DIV/0!
Klondike - 16 WTG
EXHIBIT K-2
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 1 | 2001-12-31 | 2002-03-31 | 30 |  | 0 | 0% | 1
| 2 | 2001-12-30 | 2002-03-30 | 30 |  | 0 | 0% | 1
| 3 | 2001-12-31 | 2002-03-31 | 30 |  | 0 | 0% | 1
| 4 | 2001-12-29 | 2002-03-29 | 30 |  | 0 | 0% | 1
| 5 | 2001-12-31 | 2002-03-31 | 30 |  | 0 | 0% | 1
| 6 | 2001-12-30 | 2002-03-30 | 30 |  | 0 | 0% | 1
| 7 | 2001-12-30 | 2002-03-30 | 30 |  | 0 | 0% | 1
| 8 | 2001-12-29 | 2002-03-29 | 30 |  | 0 | 0% | 1
| 9 | 2001-12-29 | 2002-03-29 | 30 |  | 0 | 0% | 1
| 10 | 2001-12-29 | 2002-03-29 | 30 |  | 0 | 0% | 1
| 11 | 2001-12-31 | 2002-03-31 | 30 |  | 0 | 0% | 1
| 12 | 2001-12-29 | 2002-03-29 | 30 |  | 0 | 0% | 1
| 13 | 2001-12-28 | 2002-03-28 | 30 |  | 0 | 0% | 1
| 14 | 2001-12-28 | 2002-03-28 | 30 |  | 0 | 0% | 1
| 15 | 2001-12-28 | 2002-03-28 | 30 |  | 0 | 0% | 1
| 16 | 2001-12-27 | 2002-03-27 | 30 |  | 0 | 0% | 1
|  |  |  | Average | #DIV/0! |  |  | 16
|  |  |  | Weighted Average | #DIV/0!
IM - I - 17 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 31 | 2001-12-12 | 2002-03-12 | 30 |  | 0 | 0% | 1
| 32 | 2001-12-12 | 2002-03-12 | 30 |  | 0 | 0% | 1
| 33 | 2001-12-14 | 2002-03-14 | 30 |  | 0 | 0% | 1
| 34 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 35 | 2001-12-08 | 2002-03-08 | 30 |  | 0 | 0% | 1
| 36 | 2001-12-09 | 2002-03-09 | 30 |  | 0 | 0% | 1
| 37 | 2001-12-08 | 2002-03-08 | 30 |  | 0 | 0% | 1
| 38 | 2001-12-08 | 2002-03-08 | 30 |  | 0 | 0% | 1
| 39 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 40 | 2001-12-07 | 2002-03-07 | 30 |  | 0 | 0% | 1
| 41 | 2001-12-08 | 2002-03-08 | 30 |  | 0 | 0% | 1
| 42 | 2001-12-08 | 2002-03-08 | 30 |  | 0 | 0% | 1
| 43 | 2001-12-10 | 2002-03-10 | 30 |  | 0 | 0% | 1
| 44 | 2001-12-09 | 2002-03-09 | 30 |  | 0 | 0% | 1
| 45 | 2001-12-08 | 2002-03-08 | 30 |  | 0 | 0% | 1
| 46 | 2001-12-11 | 2002-03-11 | 30 |  | 0 | 0% | 1
| 47 | 2001-12-08 | 2002-03-08 | 30 |  | 0 | 0% | 1
|  |  |  | Average | #DIV/0! |  |  | 17
|  |  |  | Weighted Average | #DIV/0!
IM - II - 90 WTG
EXHIBIT O-1
| TURBINE NO. | ACCEPTANCE | 90 Days | Days in Mo. > 90 Days from Commissioning | MTD Avail for > 90 days from Commissioning |  |  | Turbines Included
| 1 | 2001-11-20 | 2002-02-18 | 30 |  | 0 | 0% | 1
| 2 | 2001-11-21 | 2002-02-19 | 30 |  | 0 | 0% | 1
| 3 | 2001-11-20 | 2002-02-18 | 30 |  | 0 | 0% | 1
| 4 | 2001-11-20 | 2002-02-18 | 30 |  | 0 | 0% | 1
| 5 | 2001-11-20 | 2002-02-18 | 30 |  | 0 | 0% | 1
| 7 | 2001-11-23 | 2002-02-21 | 30 |  | 0 | 0% | 1
| 8 | 2001-11-23 | 2002-02-21 | 30 |  | 0 | 0% | 1
| 9 | 2001-11-21 | 2002-02-19 | 30 |  | 0 | 0% | 1
| 13 | 2001-11-20 | 2002-02-18 | 30 |  | 0 | 0% | 1
| 14 | 2001-11-21 | 2002-02-19 | 30 |  | 0 | 0% | 1
| 15 | 2001-11-24 | 2002-02-22 | 30 |  | 0 | 0% | 1
| 17 | 2001-11-17 | 2002-02-15 | 30 |  | 0 | 0% | 1
| 18 | 2001-11-21 | 2002-02-19 | 30 |  | 0 | 0% | 1
| 19 | 2001-11-21 | 2002-02-19 | 30 |  | 0 | 0% | 1
| 20 | 2001-11-21 | 2002-02-19 | 30 |  | 0 | 0% | 1
| 21 | 2001-11-17 | 2002-02-15 | 30 |  | 0 | 0% | 1
| 22 | 2001-11-18 | 2002-02-16 | 30 |  | 0 | 0% | 1
| 23 | 2001-11-19 | 2002-02-17 | 30 |  | 0 | 0% | 1
| 24 | 2001-11-18 | 2002-02-16 | 30 |  | 0 | 0% | 1
| 25 | 2001-11-18 | 2002-02-16 | 30 |  | 0 | 0% | 1
| 26 | 2001-12-01 | 2002-03-01 | 30 |  | 0 | 0% | 1
| 27 | 2001-11-30 | 2002-02-28 | 30 |  | 0 | 0% | 1
| 28 | 2001-11-19 | 2002-02-17 | 30 |  | 0 | 0% | 1
| 29 | 2001-11-20 | 2002-02-18 | 30 |  | 0 | 0% | 1
| 30 | 2001-11-19 | 2002-02-17 | 30 |  | 0 | 0% | 1
| 49 | 2001-11-27 | 2002-02-25 | 30 |  | 0 | 0% | 1
| 50 | 2001-11-22 | 2002-02-20 | 30 |  | 0 | 0% | 1
| 51 | 2001-11-22 | 2002-02-20 | 30 |  | 0 | 0% | 1
| 52 | 2001-11-22 | 2002-02-20 | 30 |  | 0 | 0% | 1
| 53 | 2001-11-25 | 2002-02-23 | 30 |  | 0 | 0% | 1
| 54 | 2001-11-25 | 2002-02-23 | 30 |  | 0 | 0% | 1
| 55 | 2001-11-27 | 2002-02-25 | 30 |  | 0 | 0% | 1
| 56 | 2001-11-26 | 2002-02-24 | 30 |  | 0 | 0% | 1
| 57 | 2001-11-27 | 2002-02-25 | 30 |  | 0 | 0% | 1
| 58 | 2001-11-25 | 2002-02-23 | 30 |  | 0 | 0% | 1
| 59 | 2001-11-26 | 2002-02-24 | 30 |  | 0 | 0% | 1
| 60 | 2001-11-23 | 2002-02-21 | 30 |  | 0 | 0% | 1
| 61 | 2001-11-23 | 2002-02-21 | 30 |  | 0 | 0% | 1
| 62 | 2001-11-24 | 2002-02-22 | 30 |  | 0 | 0% | 1
| 63 | 2001-11-24 | 2002-02-22 | 30 |  | 0 | 0% | 1
| 64 | 2001-11-28 | 2002-02-26 | 30 |  | 0 | 0% | 1
| 65 | 2001-11-29 | 2002-02-27 | 30 |  | 0 | 0% | 1
| 66 | 2001-11-30 | 2002-02-28 | 30 |  | 0 | 0% | 1
| 67 | 2001-11-29 | 2002-02-27 | 30 |  | 0 | 0% | 1
| 68 | 2001-11-28 | 2002-02-26 | 30 |  | 0 | 0% | 1
| 69 | 2001-11-30 | 2002-02-28 | 30 |  | 0 | 0% | 1
| 70 | 2001-12-02 | 2002-03-02 | 30 |  | 0 | 0% | 1
| 71 | 2001-12-02 | 2002-03-02 | 30 |  | 0 | 0% | 1
| 72 | 2001-11-23 | 2002-02-21 | 30 |  | 0 | 0% | 1
| 73 | 2001-11-25 | 2002-02-23 | 30 |  | 0 | 0% | 1
| 74 | 2001-11-24 | 2002-02-22 | 30 |  | 0 | 0% | 1
| 75 | 2001-11-25 | 2002-02-23 | 30 |  | 0 | 0% | 1
| 76 | 2001-11-25 | 2002-02-23 | 30 |  | 0 | 0% | 1
| 77 | 2001-11-24 | 2002-02-22 | 30 |  | 0 | 0% | 1
| 78 | 2001-12-05 | 2002-03-05 | 30 |  | 0 | 0% | 1
| 79 | 2001-11-29 | 2002-02-27 | 30 |  | 0 | 0% | 1
| 80 | 2001-11-29 | 2002-02-27 | 30 |  | 0 | 0% | 1
| 81 | 2001-12-05 | 2002-03-05 | 30 |  | 0 | 0% | 1
| 82 | 2001-11-29 | 2002-02-27 | 30 |  | 0 | 0% | 1
| 83 | 2001-12-02 | 2002-03-02 | 30 |  | 0 | 0% | 1
| 84 | 2001-12-03 | 2002-03-03 | 30 |  | 0 | 0% | 1
| 85 | 2001-12-06 | 2002-03-06 | 30 |  | 0 | 0% | 1
| 86 | 2001-12-04 | 2002-03-04 | 30 |  | 0 | 0% | 1
| 87 | 2001-12-03 | 2002-03-03 | 30 |  | 0 | 0% | 1
| 88 | 2001-12-04 | 2002-03-04 | 30 |  | 0 | 0% | 1
| 89 | 2001-12-04 | 2002-03-04 | 30 |  | 0 | 0% | 1
| 90 | 2001-12-02 | 2002-03-02 | 30 |  | 0 | 0% | 1
| 91 | 2001-11-29 | 2002-02-27 | 30 |  | 0 | 0% | 1
| 92 | 2001-12-08 | 2002-03-08 | 30 |  | 0 | 0% | 1
| 93 | 2001-12-04 | 2002-03-04 | 30 |  | 0 | 0% | 1
| 96 | 2001-12-01 | 2002-03-01 | 30 |  | 0 | 0% | 1
| 100 | 2001-12-01 | 2002-03-01 | 30 |  | 0 | 0% | 1
| 102 | 2001-12-02 | 2002-03-02 | 30 |  | 0 | 0% | 1
| 103 | 2001-11-29 | 2002-02-27 | 30 |  | 0 | 0% | 1
| 104 | 2001-12-03 | 2002-03-03 | 30 |  | 0 | 0% | 1
| 105 | 2001-11-28 | 2002-02-26 | 30 |  | 0 | 0% | 1
| 106 | 2001-11-29 | 2002-02-27 | 30 |  | 0 | 0% | 1
| 107 | 2001-11-29 | 2002-02-27 | 30 |  | 0 | 0% | 1
| 108 | 2001-12-02 | 2002-03-02 | 30 |  | 0 | 0% | 1
| 109 | 2001-12-03 | 2002-03-03 | 30 |  | 0 | 0% | 1
| 113 | 2001-12-02 | 2002-03-02 | 30 |  | 0 | 0% | 1
| 114 | 2001-11-21 | 2002-02-19 | 30 |  | 0 | 0% | 1
| 115 | 2001-11-27 | 2002-02-25 | 30 |  | 0 | 0% | 1
| 116 | 2001-11-26 | 2002-02-24 | 30 |  | 0 | 0% | 1
| 117 | 2001-12-04 | 2002-03-04 | 30 |  | 0 | 0% | 1
| 118 | 2001-12-03 | 2002-03-03 | 30 |  | 0 | 0% | 1
| 119 | 2001-12-03 | 2002-03-03 | 30 |  | 0 | 0% | 1
| 120 | 2001-12-04 | 2002-03-04 | 30 |  | 0 | 0% | 1
| 121 | 2001-12-03 | 2002-03-03 | 30 |  | 0 | 0% | 1
| 122 | 2001-12-03 | 2002-03-03 | 30 |  | 0 | 0% | 1
|  |  |  | Average | #DIV/0! |  |  | 90
|  |  |  | Weighted Average | #DIV/0!