| MINUTES OF MEETING |  | Date: |  | 27-05-2025 | Time: | 11:00 |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Location: |  | MS Teams Meeting |  |  |  |
| Reference Number: | mom_value | Subject: |  | 126th Progress Meeting HSR Study (P2103) |  |  |  |
| Attendees |  |  |  |  |  |  |  |
| No. | Name |  | Title |  |  | Unit/Organization |  |
|  | Mr. Adam Fernandes |  | Project Commercial Manager |  |  | ERL |  |
|  | Mr. Adriaan Wolmhuter |  | Engineering Manager |  |  | ERL |  |
|  | Mr. Michel Gerges |  | Project Control |  |  | ERL |  |
|  | Mr. Babry Harish |  | Engineering Lead system |  |  | ERL |  |
|  | Mr. Shajahan Shameem |  | Stakeholder Manager |  |  | ERL |  |
|  | Mr. Didier Leperou |  | Executive Director |  |  | ERL |  |
|  | Mr. Esmaeil Ghahremani |  | Project Director |  |  | PMC |  |
|  | Mr. Atef Salem |  | Design Coordinator |  |  | PMC |  |
|  | Mr. Matvey Klopov |  | Alignment and Track Engineer |  |  | PMC |  |
|  | Dr. Reza Mohammadi |  | Transport Planning Manager |  |  | PMC |  |
|  | Ms. Shruti Shetty |  | Project Controller |  |  | PMC |  |
|  | Mr. Karthik Sambandam |  | MEP & Utility Lead |  |  | PMC |  |
|  | Mr. Jafar Bagheri |  | Tendering/ Systems Design Review Manager |  |  | PMC |  |
|  | Mr. Fouad Antoine |  | Tendering/ Civil Design Review Manager |  |  | PMC |  |
|  | Mr. Jean-Philippe Lavallee |  | Railway O&M expert |  |  | PMC |  |
|  | Mayank Sharma |  | Interface/Sys Assurance Manager |  |  | PMC |  |
|  | Mr. Javier Valero |  | Project Director |  |  | SEI |  |
|  | Ms. Cristina Baleia |  | Alignment Expert |  |  | SEI |  |
|  | Ms. Sandra Alcalde |  | Project Controls Expert |  |  | SEI |  |
|  | Ms. Asimina Kanellaidi |  | Commercial/Contracts Manager |  |  | SEI |  |
|  | Mr. Saeed Hussien |  | Stakeholder Manager |  |  | SEI |  |
|  | Mr. Pedro Quadros |  | Deputy Project Director |  |  | SEI |  |
|  | Ms. Vicky Chou |  | Civil Engineer/Procurement Coordinator |  |  | SEI |  |
|  | Ms. Mónica Lopez |  | Headquarters Project Coordinator |  |  | SEI |  |
|  | Mr. Pablo Fernández |  | Engineering Manager - Architecture |  |  | SEI |  |
|  | Mr. Martin Thomas |  | Transport Planning Expert |  |  | SEI |  |
|  | Mr. Jorge Tuda |  | TIS Manager |  |  | SEI |  |
|  | Mr. Rui Brito |  | Civil Procurement Lead |  |  | SEI |  |
|  | Mr. Alejandro Varon |  | Procurement Lead |  |  | SEI |  |
|  | Mr. Ahmed Elnajjar |  | Geotechnical Engineer |  |  | SEI |  |
|  | Mr. Erlantz Osa |  | Geotechnical Engineer |  |  | SEI |  |
|  | Mr. Stefan Ljungberg |  | Alignment Expert |  |  | SEI |  |
|  | Mr. Toni Castro |  | Engineering Manager - Systems |  |  | SEI |  |
|  | Mr. Iñaki Catalan |  | Engineering Manager – Civil |  |  | SEI |  |
|  | Mr. Kamaleldin Khaled |  | Stakeholder Engineer |  |  | SEI |  |
|  | Mr. Mirza Ibrshrahim |  | MEP(FLS) Expert |  |  | SEI |  |
|  | Mr. Martin Moreno |  | MEP Engineer |  |  | SEI |  |
|  | Mr. Mohamed Allam |  | Interface and Integration |  |  | SEI |  |
| Apologies |  |  |  |  |  |  |  |
|  | Mr. Ahmed Alriyami | Right of Way Lead |  |  |  | ERL |  |
|  | Mr. Mohd Hourani | Stakeholder Manager |  |  |  | ERL |  |
|  | Ms. Fatima Alhouti | Technical Coordinator Engineer |  |  |  | ERL |  |
|  | Mr. Tarun Kumar | Catenary and Third Rail Expert |  |  |  | ERL |  |
|  | Mr. Kushal Jain | Systems |  |  |  | ERL |  |
|  | Mr. Ibrahim Sheikh |  |  |  |  | ERL |  |
|  | Mr. Djamel Attoui | Systems Director |  |  |  | ERL |  |
|  | Mr. Stephen Bennett | Transport Planning Expert |  |  |  | ERL |  |
|  | Mr. Abdulla Alebri | Civil Engineer Graduate |  |  |  | ERL |  |
|  | Mr. Ali Almheiri | Civil Engineer Graduate |  |  |  | ERL |  |
|  | Mr. Abdulaziz Alholy | Stations Design Expert |  |  |  | ERL |  |
|  | Mr. Yousef Kakish | Stakeholder lead |  |  |  | ERL |  |
|  | Ms. Fatima Alhouti | Senior Right of Way Engineer |  |  |  | ERL |  |
|  | Mr. Khalid Belhaj | System Assurance Expert |  |  |  | ERL |  |
|  | Mr. Ishak Hisyamizan | Interface |  |  |  | ERL |  |
|  | Mr. Mohamed Hegab | Project Schedule & Cost Expert |  |  |  | ERL |  |
|  | Mr. Almansoori Humaid | Stakeholder Manager |  |  |  | ERL |  |
|  | Mr. Mohammed Alshehhi | Chief Projects Officer |  |  |  | ERL |  |
|  | Ms. Aysha Raoof | Transport Planning Expert |  |  |  | ERL |  |
|  | Mr. Ali Al Sammarraie | Transport Planning Expert |  |  |  | ERL |  |
|  | Mr. Ghady Ghanem | Business Development |  |  |  | ERL |  |
|  | Mr. Fadi Elzouhbi | Security Manager |  |  |  | ERL |  |
|  | Mr. Martin Payne | Contract Manager |  |  |  | ERL |  |
|  | Mr. Frederic Koenig | Project Controls director |  |  |  | ERL |  |
|  | Ms. Azza AlSuwaidi | Director |  |  |  | ERL |  |
|  | Mr. Sébastien Mangeant | Executive Project Director |  |  |  | ERL |  |
|  | Mr. Alireza Amini | Cost Estimates Manager |  |  |  | PMC |  |
|  | Mr. Laurent Perocheau | Engineering Lead - Systems |  |  |  | PMC |  |
|  | Mr. Ghazi Faisal | Stakeholder Manager |  |  |  | PMC |  |
|  | Ms. Mery Delgado Palomo | System Engineer |  |  |  | PMC |  |
|  | Mr. Purnesh Kulkarni | PMO Officer |  |  |  | PMC |  |
|  | Mr. Milen KOCEV | PMO |  |  |  | PMC |  |
|  | Mr. Soheil Mohammadkhani Shali | Engineering Lead – Civil |  |  |  | PMC |  |
|  | Ms. Nuria Torres | Roadways Expert |  |  |  | SEI |  |
|  | Mr. Jose Manuel Martin | Systems Coordinator |  |  |  | SEI |  |
|  | Mr. Ivan Quintana | MEP Engineer |  |  |  | SEI |  |
|  | Mr. Andres Moriel | Systems Assurance |  |  |  | SEI |  |
|  | Mr. Pablo Ramos |  |  |  |  | SEI |  |
|  | Ms. Angela Barba | TIS expert |  |  |  | SEI |  |
|  | Ms. Shilpa Gulati | Project Controls Engineer |  |  |  | SEI |  |
|  | Mr. Victor Perez | Project Controls Expert |  |  |  | SEI |  |
|  | Mr. Aitor Santos | Depot Expert |  |  |  | SEI |  |
| Meeting Agenda |  |  |  |  |  |  |  |
| - MANAGEMENT-STAKEHOLDER - TRANSPORT MODEL/PLANNING - PACKAGING & PROCUREMENT STRATEGY AND TENDER DOCUMENTATION - CIVIL - STATIONS - MEP - SYSTEM INTEGRATION - CAPEX - RAILWAY SYSTEMS - AOB |  |  |  |  |  |  |  |
| Comments on Previous Minutes / General |  |  |  |  |  |  |  |
| Meeting Minutes |  |  |  |  |  |  |  |
| Item | Subject | Comments / Actions |  |  |  | Action By | Due Date |
| 1. | MANAGEMENT - STAKEHOLDER | Phase 1 NOCs in Abu Dhabi: NOC#1: From Ch. 15 to Ch. 24: MCC: - MCC approval received. ITC: TIP in progress (to be discussed in separate section). NOC#2: Approved NOC#3: Approved. NOC#4: Approved. NOC#5: TRANSCO: Under review. Approval expected this week. SEI to follow up. ADDC: ER to issue an undertaking letter. Etisalat: Meeting with Etisalat to be scheduled to discuss their requirements. Al Reem: - Meeting with Bunya is planned on 29th May to discuss the utilities relocation proposal and to update the progress. - ER to issue an official letter to MODON. - Note: Bi-weekly meeting is happening with MODON/Jacobs. Some actions to be prepared by SEI. Al Saadiyat (ALDAR): - The station location has been adjusted as per ALDAR request. - Final responses have been shared with ALDAR. To follow up for their feedback. - SEI to proceed with the PE NOC submission after the final agreement. Al Jubail (LEAD): - After the meeting with LEAD TVS has been relocated outside Al Jubail Island. Elements sent to LEAD on the 7th May. - SEI/ER to follow up with LEAD. |  |  |  | SEI ER SEI Note ER SEI Note SEI Note Note SEI | 29/05/25 29/05/25 TBC 27/05/25 ASAP TBC ASAP |
|  |  | Al Ain route Al Turoush street section: - SEI shared Renders, sections, and a presentation with CDM & ALDAR on 20th May. SEI to follow up for their feedback. - The alignment team is making the amendments to the alignment to place the station platforms at ch 104+900. That is tied to the change to monotube tunnel in the adjacent section |  |  |  | SEI SEI | 30/05/25 29/05/25 |
|  |  | Dubai: - Detailed GIDD (Dr. Sauer) 2 locations: Location 1 – DEWA to review the report and confirm alignment change under the Power Station. ER to support. (to be discussed during the meeting with DEWA on 28th May). ER requests to contact Dr. Sauer and request them to prepare an estimation to carry out additional impact assessment on OHL pylons for new alignment Location 2 - ER to coordinate with RTA. Dubai South – DEWA: - Station shift requested by JAFZA has been studied and shared with ER. See alignment section. DS215 interface: - Alignment as per option 6B, replies to DM conditions and specific requirements related to construction of DS215 have been shared with ER. ER to respond to DM. Al Jaddaf: - Coordination meeting with RTA on 22nd April regarding the integration between HSR station and Metro station/roads. ER/SEI has shared the required files with RTA for their review on 25/04. Waiting RTA to accept/feedback. SEI to follow up. - Once accepted by RTA, ER to engage with DH. |  |  |  | ER ER Note ER Note | TBC TBC TBC |
|  |  | Sharjah HSR (Sharjah section): - ER has shared the updated constraints report with DTPS. - ER advised that alignment (Sharjah section) to be updated with single bore solution and the extended platform (235m) of the station. - A meeting to be scheduled with DTPS. HSR (Dubai section): - Alignment to proceed with the one presented to RTA. - SEI implemented one comment from RTA related to shifting the TVS/retrieval shaft outside Dubai Airport (shaft to be in RTA land). SEI confirmed that the permanent shaft has been shifted and both temporary and permanent shaft's location shared with ER. ER has shared with RTA. RTA to approve. SEI to follow up. |  |  |  | Note SEI ER/SEI Note SEI | TBC TBC ASAP |
|  |  | Civil Defence - Letter has been received from CD accepting the TSI for the HSR subject to some conditions. This letter shall be referred in the D&B Contract and also already included in Exh D2 doc related to Tunnel. Presentation has been shared with ER, ER has some comments, SEI to revise and reshare. |  |  |  | Note SEI | 28/05/25 |

|  |  | NOC submission Abu Dhabi: - All NOCs have been submitted through SMARTHUB portal. SEI to follow up for approval. Storm water and irrigation have been approved. - Street lighting commented by ADM. SEI has incorporated the comments and reshared with ADM. ADM has requested SEI to prepare a CRS for all disciplines. SEI to prepare. Dubai: - It has been agreed with RTA and DEWA during the meeting held on 8th May 2025, SEI to submit NOC 6, 7, 9, and 10. - NOC 7 and 9 (Launching shafts locations) have been submitted and rejected by RTA/ROW. - Meeting with DEWA is planned on 28th May to discuss the NOC strategy. | Note SEI Note Note Note | 30/05/25 |
| --- | --- | --- | --- | --- |
|  |  | Transport Infrastructure Plan (TIP) Submissions -The drawings for TIP Package 9 were submitted in CAD format to ITC FTP site, in response to request from ITC. -Comments on Packages 2 & 8 TIP drawings are being addressed and incorporated. -Package 6 TIP was submitted to ITC and shared with the road safety audit consultant company 4e. Drawings for two options of lane addition (6th lane) through Yas, submitted to ER and then to ITC. One option compliant (with 3m shoulders) showing westerly Yas Mall ramp bridge and two bridges on Al Ibreeq Street will have to be demolished, the other option showing shoulder narrowing to 1.2m where necessary to avoid any demolition. ER confirmed that we will not be doing STIP for 5 lanes. Specialist road safety auditor with rail experience not brought on board. SEI have reached out to the following organizations for ISA: Ricardo Rail, TÜV SÜD, Hill International, TÜV NORD GROUP, Rina, BUREAU VERITAS India Package 5 STIP Methodology Report under preparation. -Circulation plans for technical (on-line) buildings are WIP. | Note |  |
| - 2. | TRANSPORT MODEL / PLANNING | TIS at Stations: Abu Dhabi 14/05: Meeting with ITC Studies’ Team to present stations’ concept layouts and get preliminary feedback. SEI presented the AUH station layout and suggested proceeding using worst-case ridership assumptions, but ITC clarified that no feedback or approvals could be given until the STEAM model is finalized. ITC stated that the TISs for ADT and ADS could be done internally, but ITC would not engage on them nor review them unless they become a reality. |  |  |
|  |  | TIS at Stations: Dubai -25/05 - Second DJD Feasibility report review meeting: Plans shared with RTA Engineer to be distributed among relevant departments. FS report greenlighted for official submission though the RTA portal. - Sharjah TIS: a DTPS meeting is pending to be arranged with the Client’s full support in order to finalise the agreed in principle parameters for the Sharjah Station. - Maktoum TIS: a confirmation by the Client is required to commence the TIS taking into account the latest plot for Maktoum as requested by RTA during April 2025. | SEI Note Note | 09/06/25 |
|  |  | Ridership Modelling MMR for STEAM model submitted to ITC on 05/05. Further STEAM modelling, including recoding of Arcadis model refinements around stations pending receipt of updated STEAM model from ITC. Coordination ongoing with Rina/Transpo, Arup, on ridership, modal split, etc. Air traffic information still not received for Maktoum Airport from DAEP. | Note ER | TBC |
|  |  | Depot TIS Kick-off meeting for the depot TIS was held with ITC 20/03/2025. Submission of Methodology Report pending confirmation of depot location. | Note |  |
| - 3. | PACKAGING & PROCUREMENT STRATEGY AND TENDER DOCUMENTATION | Relevant P6 Programme (level 2): Base Scope D&B Level 2 Programme: Code 2 received on 19/11/2024. All remaining open comments are new from last revision, where all the previous comments have been closed. Under development the new Programme(s), considering the latest project configuration. Reem D&B Level 2 Programme (Intercity with Reem and Sectioning): Ongoing workshops to finalize the Key Milestones/Dates coordinated with the Programme, waiting for final agreement on Systems’ programme and complete report with PMC before EPFM submission. New changes requested 21/04/25 and 27/05/25 Narrative shared unofficially on 27/03/25, as agreed. | Note Note |  |
|  |  | Civil (Stations included): Addendum No.2 USBs have been issued officially on 02/05 to Bidders. Circulation plan to be included in Tender (Exh E). AUH & YAS & DJD drawings to be added. Evaluation criteria (draft) sent to ER for review. SLR folders to be added to upcoming TA. | Note Note ER | TBC |
|  |  | Systems: Addendum No.2: Exh D2 Track Changes files to be added to USBs. Circulation plan to be included in Tender (Exh E). AUH & YAS & DJD drawings to be added. | SEI Note | 27/05/25 |
|  |  | Enabling Works: Abu Dhabi: Package completed on 30/04. Dubai: Package completed on 28/04. | Note Note |  |
| - 4. | CIVIL | Alignment Phase 1 – submission status Section; Alignment; Civil Eng. & Track. Ph.1A; Rev. 00 Code 01 Submitted 27/11; Rev. AD Code 01 (report) Code 02 (dwg) Submitted (report) 28/01. Ph.1B; Rev. 03 Code 01 Submitted 17/04; Rev. AE Code 01 (report) Code 02 (dwg) Submitted (report) 29/01. Ph.1C; Rev. 00 Code 01 Submitted 31/01; Rev. AD UR Submitted 17/03. Ph.1D; Rev. 01 Code 01 Submitted 05/03; Rev. AD Code 02 Resubmission 25/04. Ph.1A (Reem-E12); Rev. AB Code 02 Submitted 09/04; See note (**). Ph.1C (full viaduct) Concept; Rev. 00 Code 05 Submitted 28/02. Ph.1C (Maktoum St UG); Rev. AB Code 02 Resubmission 27/06 (*); See note (**). Ph.1C (Maktoum St Elevated); Rev. AC UR Submitted 20/05. Ph.1D (Al Reef St); Rev. AB Code 02 Submitted 21/04. Notes: - Alignment drawings do not need to be resubmitted to exclude temporary site location. Site logistic and temporary site drawings already included a note to state that these drawings override the alignment drawings regarding the temporary site. - (*) Based on alignment shared with ER on 22/05, see Dubai section. - (**) Civil Engineering & Track drawings will be submitted after obtention of NOCs and approval of PE for related disciplines (code 2). Phase 1 – Reem Island/E12 Concept Alignment has been submitted (Code 1). New Reem station location by MODON shared with SEI on 06/01. Location was agreed in general in the meeting with MODON 29/01. Saadiyat Station agreed to be shifted towards lower chainage as per the request made by ALDAR in meeting of 10/03 and reflected in PE rev AB. TVS shaft to be shifted from Jubail island to Saadiyat island as requested by LEAD. To be reflected in next submission. Phase 1 - Dubai Section Dubai South sector PE development for two alignment alternatives (underground and elevated) considering a station at Maktoum Int. airport as instructed by ER. SEI has prepared different alignment options. Maktoum Station Elevated option: rev AC submitted to obtain code 5. Maktoum Station Underground option: revised alignment shared with ER on 22/05 with implementation of Option 6B and station shift as requested by JAFZA. Dubai North sector Revised alignment shared with ER on 22/05 with modification of Jaddaf tunnel south portal to minimize land acquisition requirements and tweak in Meydan around retrieval shaft location. Jaddaf Station. SEI studied modified track layout following SHA-DJD operation requirements meeting on 27/03. Sketches shared by SEI on 23/04. ER confirmed to move forward with the revised layout. PE alignment (new package) to be prepared according to these changes. Meeting required with ER to agree on the design updates required for other disciplines (i.e. utilities, roads, structures, drainage etc.). Phase 1 - AUH Delta Alignment modified in plan and profile to fit the Al Reef station and the required crossovers. Details agreed with PMC on 14/02. Assumptions report for Al Reef St: reply provided by ER/PMC. Phase 2– submission status Section; Alignment; Civil Eng. & Track. Option A – Al Ain section 1; Rev. AA Code 03 (*). Option A – Al Ain section 2; Rev. AB UR Submitted 16/05. Option B – Sharjah section 1; Rev. AB Code 02 On hold (**). Option B – Sharjah section 2; Rev. AB Code 01. Notes: - (*) Alignment P&P shared via email with PMC on 20/05 for closure of code 3 comments. - (**) Only pending comment is ROW validation which will be done after approval of the PE for other disciplines as well as after obtention of NOCs. Al Ain Abu Dhabi section: Viaduct solution along Turoush Street pending on feedback from ALDAR from renders and sections to get approval in principle of current alignment. Alignment to be updated at delta with monotube tunnel with dividing wall. Al Ain section: SEI to share revised alignment around Al Amerah to reflect station location preferred by ALDAR Alignment to be updated with monotube tunnel with dividing wall. Assumptions Report for Al Ain shared on 07/03. Reply provided by ER/PMC. Inner-city alignment: ER to reconfirm the need of the design of Mina Depot. Design on Mina Depot is on hold. Sharjah Alignment updated for monotube tunnel with dividing wall and 235m platforms at Sharjah Station shared with ER on 23/05. SEI to prepare submission based on discussion in Coordination meeting on 26/05. Meeting with ER required to agree on the update required for other disciplines. Assumptions Report for Sharjah shared on 07/03. Reply provided by ER/PMC. | Note Note Note Note Note Note Note Note Note SEI ER/SEI/PMC Note Note Note SEI SEI SEI Note ER/PMC Note SEI ER/SEI/PMC Note | 27/06/25 TBC 27/06/25 27/05/25 13/06/25 ASAP 20/06/25 28/05/25 |
|  |  | Roads All Phase 1 sections: pending comments related to NOC’s, RSA and authorities’ approval + minor technical comments (report/drawings). Option B (Extension to Sharjah) Code 3 comment on temporary road closure/diversion to be approved in principle by Authorities. Following meeting with ER, one main road affection will no longer be applicable with the alignment for the monotube tunnel with dividing wall therefore comment can be downgraded to code 2. | Note Note |  |
|  |  | Depots Abu Dhabi Depot Depot layout, presentation and renders shared with ER for meeting with Al Reef Palace. A meeting is required to agree on the alignment tweak to avoid impact on Palace assets. Dubai depot Initial package submitted (only IMF) has been superseded with current package (IMF+depot). Strategy agreed with ER/PMC. A note to be added to the IMF package when resubmitting to close it. | Note Note |  |
|  |  | Structures Reem Station Modification of current station structure to fit utility corridors in level -1. Subject to having approval in principle from MODON/Bunya. Tunnels Ground movement/utility impact assessment studies for DEWA pipelines affected by the HSR tunnels in Dubai by Dr Sauer already submitted ad shared with DEWA. GIDD Detailed design of TBM launching shafts ongoing (as per PE alignment). MTD submissions have been done. As per GIDD program, final DCP3 submissions are planned for the end of July. ER instructs that the detailed design for shaft at Ch 238 shall be revised as per alignment change shared by SEI on 22/05. SEI to inform about the GIDD Program impact. Single bore tunnel proposal already prepared by SEI for GIDD survey. A meeting is required to understand the final alignment to be considered. | SEI Note ER/PMC/SEI Note | 04/06/25 28/05/25 |
|  |  | EIA/EAD Constraint report submitted for both Abu Dhabi (including Reem) and Dubai (including Maktoum underground station) on 07/03. Meeting held by ER/PMC/SEI and the strategy to follow defined. SEI is proceeding with the works as per the agreement. Constraint report for Sharjah submitted and comments received. To be incorporated directly in EIA. TOR for Al Ain submitted. Any new change to be incorporated will impact and need to be discussed. Latest changes to be assessed and the way to progress to be discussed. Biweekly meeting requested by ER/PMC schedule for next Thursday and subsequent days. | Note Note Note Note ER/PMC/SEI ER/PMC/SEI | TBC 29/05/25 |
|  |  | Utilities Design Abu Dhabi Overall approval code 02. Utility relocation proposal around ADR Station has been prepared and updated drawings shared with ER on 21/04. Approval in principle required from Modon/Bunya to proceed. Dubai DEWA Clash Report rev AG submitted internally on 05/08/24 to ER/PMC. PE utility design for DEWA corridor section: Overall approval code 02. To be updated as per latest alignment changes. PE utility design for DUSUP corridor section: Overall approval code 02. PE utility design for DUSUP corridor section+MKT St: to be updated as per Option 6B. | Note Note Note Note SEI Note SEI |  |
|  |  | Geotechnical (borehole status – phase 1) Closed. Geotechnical (borehole status – phase 2) Abu Dhabi – Al Ain (Al Ain region): - Scope Completed (22 Boreholes). Abu Dhabi Al Ain – (Abu Dhabi Section) : - 4 Boreholes Executed out of 40 - All permits approved for 13 boreholes and Mobilisation in progress. - TPD is pending approval for 23 Boreholes. Version AH of GI proposal was submitted on 10 of March 2025. CRS with code 2 was received on 14 of March. The comment received refers to receiving Code 1 approval is subject to alignment approval. Note that the alignment is in the same place for more than 5 months and minor changes do not impact on the geotechnical work to be carried out. Anyway, SEI has started TPD permit process to mitigate delays. Dubai – Sharjah Extension: - 3 borehole siteworks have been finalised. - 5 boreholes NOCs are in progress Dubai Tunnels GIDD along with Reem Tunnels GIDD progress to be discussed at dedicated weekly meeting every Wednesday. | Note Note Note ER | ASAP |
| - 5. | STATIONS | Functional program and stations sizing review progressing: Station; Status; Date. ALL (GENERAL REPORT); Rev. AC CODE 2 (07/05); To be resubmitted once all stations sizing reports are approved. ADT; Rev. 00; CODE 1 (17/03). ADS (KHOR LAFFAN option - VIADUCT); Rev. 00; CODE 1 (17/03). YAS; Rev. AD CODE 2 (14/5); meeting for clarification required. AUH; Rev. AC CODE 2; AD version submitted 14/5. DJD; Rev. AC CODE 2; AD version submitted 16/5. AL REEM OPTION stations. ADR AL REEM (CD); Rev. 00; CODE 5 (08/03). ADS – AL REEM; Rev. 00; CODE 5 (17/03). | Note |  |
|  |  | Station design status: Station; Status; Date. ADT (OP.1). AT + ROADS drawings; Rev AB- CODE 2 ** (29/10) Rev – AE -AMENDMENT of lobby + MEP area sifted – SUBMITTED AS ADDITIONAL 22/01 – CODE 2 **; AF version submitted 23/05. AT report; Rev AC – CODE 2 ** (16/12); AD version submitted 26/05. ADS (OP.1). AT + ROADS drawings; Rev AD – CODE 2 (14/05); Minor issues to be resolved. AT report; Ver. AA - CODE 2; AB version submitted 12/05. YAS. AT + ROADS drawings; Rev. AE –review 06/05 (CODE 2); *Main pending issue is about station platforms evacuation. AT report; Rev. AB - CODE 2; AB version submitted 12/05. AUH. AT + ROADSdrawings; Rev. AD - CODE 2 ** (26/05); meeting for clarification required. AT report; Rev. AB - CODE 2 ** Rev AC (only ROADS update) submitted 29/11/24; AD version submitted 26/05. DJD – without BOCC + STATION BOX AMENDEMENT due to track cancellation to be shown in Addendum. AT + ROADS drawings; Rev. AF - SUBMITTED 03/02 according to critical comments workshops – CODE 2 **; AG version submitted 12/05. AT report; Rev. (AB) - CODE 2 ** (31/10) Rev AC – CODE 2 **; 16/12/24. AL REEM OPTION stations. ADR AT; Ver. AA (PE) - AT drawings - Sizing report - AT report; CODE 2 (07/04) CODE 2 (04/04) CODE 2 (07/04). ADS AT; Ver. AA (PE) - AT drawings - Sizing report - AT report; CODE 2 (07/04) CODE 2 (07/04) CODE 2 (07/04). SHA + MKT options + AAN STATIONS. SHA station design; Ver. AA (PE) - AT drawings - Sizing report - AT report; CODE 3 (07/04) CODE 3 (29/04) CODE 3 (29/04). MKT underground; Ver. AA (PE) - AT drawings - Sizing report - AT report; CODE 2 (07/04) CODE 2 (07/04) CODE 2 (15/04). MKT viaduct; Ver. AA (PE) - AT drawings - Sizing report - AT report; CODE 2 (07/04) CODE 2 (07/04) CODE 2 (15/04). AL AIN – TAWAN station; Ver. AA - AT drawings submitted 21/04 - Sizing report - AT report; CODE 3 (09/05) Submitted 08/05 Submitted 08/05. Tender AT documents. AAG (Architectural Aesthetic Guidelines); Ver. AE – submitted 02/04; CODE 2 (16/04) – 5 comments still open. Stations DESIGN CRITERIA; Ver. AC – CODE 2 (16/04) –12 comments still open; ver. AD submitted 26/05. Buildings TECHNICAL SPECIFICATION; Ver. AD – CODE 2 (16/04) –15 comments still open; ver. AE submitted 22/05. (**) CRS include note: “Overall CRS comments are reduced to Code 2 to enable Tender submission, but Code 3 comments remain in the register and both Code 2 and Code 3 need to be resolved ASAP.” |  |  |
| - 6. | MEP | MEP Design Status - Tunnels: Ongoing task to adapt the facilities to the new alignment and resolve pending Cod 2. Tunnel; Status; Forecast. ADT tunnel Section; Rev. AE. Cod 2; 30/05/25. YAS – AD Border Cut and Cover:; Rev. AC. Cod 2.; 30/05/25. AUH tunnel section; Rev. AD. Cod 2. Revision required for the new Alignment AUH delta.; 30/05/25. DUSUP tunnel section; Rev AB Cod 2. Considering a station at Maktoum Int. Airport.; 30/05/25. DJD tunnel section; Rev AD. Cod 2. Revision required for extension to Sharjah; 30/05/25. - Stations: Ongoing task to solve pending Cod 2. The new versions will be implemented considering the new changes of distribution. Station; Status; Forecast. ADT; Rev. AB: Cod 2.; 20/05/25. ADS; Rev. AB: Cod 2.; 20/05/25. YAS; Rev. AD: Cod 2.; 20/05/25. AUH; Rev. AD: Cod 2.; 20/05/25. DJD; Rev. AC: Cod 2.; 20/05/25. - Depots: Ongoing task to solve pending Cod 2. Depots; Status; Forecast. Shahama Depot; Rev. AD Cod 1.; Submitted on 15/05/25. IMF Dubai; Rev. AB: Cod 2:; Submitted on 15/05/25. New configuration of IMF Dubai. Comments received on 26/04/25; Submitted on 15/05/25. IMF Al Ain; Rev AA pending review; Submitted on 15/05/25. - Auxiliary Buildings: Ongoing work to adapt the facilities to the distribution modifications required to include outdoor equipment inside the buildings. Auxiliary Buildings; Status; Forecast. Rev. AD: Cod 1.; Submitted on 15/05/25. - Technical Specifications: New version was submitted to include the tender comments. Technical Specifications; Status; Forecast. MEP; Rev. AE Cod. 1; Rev 00. Submitted 13/03. Phase 1 – Reem Island/E12: - Stations MEP: - MEP ADR PE . A new revision to include the additional details required for the bidding process for the following systems: - HVAC: Critical areas unit schedules and airflow schematics will be added. - Plumbing: One GA drawing for drainage will be added. - Electrical: One LV E&B schematics will be added. - MEP ADS PE submission has been submitted on 14/03. Rev. Cod 2 received on 03/03. - A new revision to include the additional details required for the bidding process for the following systems: HVAC: Critical areas unit schedules and airflow schematics will be added. - Plumbing: One GA drawing for drainage will be added. - Electrical: One LV E&B schematics will be added. Phase 1 - Dubai Section PE development for two alignment alternatives (underground and elevated) considering a station at Maktoum Int. airport. - Tunnel MEP: - PE first submission has been submitted on 14/03. Rev. AA Cod 2 received on 03/03. - Stations MEP: Maktoum Stations, A new revision to include the additional details required for the bidding process for the following systems: - HVAC: Critical areas unit schedules and airflow schematics will be added. - Plumbing: One GA drawing for drainage will be added. - Electrical: One LV E&B schematics will be added. All the new drawings requested for the tender will be submitted on 31st May. Phase 1 – Option 2. Sharjah Section PE development for alignment considering an underground station at Sharjah. - Tunnel MEP: - PE first submission has been submitted on 19/03. Rev. AA Cod 2received on 03/03. - Sharjah Station MEP: - PE first submission has been submitted on 19/03. Rev cod 3 received on 12/04. - A new revision will be prepared for the next addendum to include the additional details required for the bidding process for the following systems: - HVAC: Critical areas unit schedules and airflow schematics will be added. - Plumbing: One GA drawing for drainage will be added. - Electrical: One LV E&B schematics will be added. New revision to be submitted on 31st May. Al Reef Variation PE first submission for alignment considering new variation of Al Reef station. - Tunnel MEP: - MEP AUH Tunnel Design according with the Alignment modifications. - PE first submission has been submitted on 14/03. Al Reef Station MEP: - MEP design for the Al Reef Station. - PE first submission has been submitted on 14/03. rev. AA Cod 2 received on 03/04. Al Ain - Tunnel MEP. PE to be submitted. - Abu Dhabi section: On going task to design the MEP disciplines (ventilation, Firefighting, Electric supply and drainage) for the alignment typology in Abu Dhabi section. - Al Ain section: PE ongoing: On going task to design the MEP disciplines (ventilation, Firefighting, Electric supply and drainage) for the alignment typology Al Ain section. - Al Ain Station MEP. PE to be submitted. - On going task to design the MEP for the new station typology in Al Ain. It has been submitted on 09/05. - Al Ain Depot. - PE first submission has been submitted on 15/04. Rev Cod. 02 has been received on 30/04. | Note SEI SEI SEI SEI SEI SEI SEI SEI SEI | 15/05/25 31/05/25 15/05/25 15/05/25 23/05/25 15/05/25 15/05/25 31/05/25 15/06/25 |
| - 7. | Si&A | SAFETY P2103-UAE-GHA-RP-04102_AD Preliminary Design Safety Case Rev. AD has been already submitted on the 26th of March. | Note |  |
|  |  | System Architecture: P2103-UAE-GER-RP-04002-AH System Architecture Diagram [SAD] has been approved (code-01) on May 23rd. Rev. 00 has been submitted on May 26th considering some minor comments on rev. AH following a meeting with ER and PMC. | Note |  |
| - 8. | CAPEX | Full CAPEX report and excel/presto models Integrated CAPEX of all sections will be delivered in a single document – under a new code, integrating all sections: - Reem to Jubail - Abu Dhabi and Dubai sections - AUH section Al Reef option - Dubai South viaduct alternative - Maktoum station tunnel base scope - Maktoum station viaduct alternative - Sharjah extension option, sections 1 and 2, including the underground station. Exhibits C1, status as follows: Exhibits C1; Status; Forecast. EW AD (based on ER Commercial review comments); Rev 04 Code 1; Submitted 25/11. Conformed Contract version sent by email on 16/04/2025. EW DU (including quantities for DUSUP corridor, and alternative alignment in Dubai, not approved by RTA); Rev 02 Code 1; Submitted 24/12. Conformed Contract version sent by email on 15/04/2025. CW AD (considering Base Scope+Alternative+Optional alignments + Sectioning, and addressing ER/PMC CRS by email); Rev AC Code 1; Issued 07/01 DRAFT Tender addendum 29/03. FINAL C1 files sent by email on 25/04/2025. Amended TC version and write-ups sent on 26/05.. CW DU (considering Base Scope+Alternative+Optional alignments + Sectioning, and addressing CRS comments); Rev AB Code 1; Issued 07/01 DRAFT Tender addendum 29/03. FINAL C1 files sent by email on 25/04/2025. Amended TC version and write-ups sent on 26/05.. Rail Systems (considering Base Scope+Alternative+Optional alignments + Sectioning, and addressing CRS* comments); Rev AC Code 3; 11/02 submitted by EPFM. TA Schedule of Rates (form A3) by email on 16/04/2025. Other forms by email on 22/04 and 06/05. Meeting with ER PQ on 13/05. Forms A1 to A5, adapted to ER PQ template, sent on 25/05. Write-up sent on 21/05.. * ER head office added as PS in Systems Package. | Note |  |
| - 9. | RAILWAY SYSTEMS | Technical Specifications (TS) and Drawings - SEI JV has updated impacted Technical Specifications due to the consideration of FRMCS as a base option for the Railway Mobile Radio (RMR) instead of GSM-R. - References across the TS and SoW have been updated. - ER meeting with TDRA to secure 900MHz and 1900 MHz bands. SEI JV to share slides | Note |  |
|  |  | Power Companies status Update: TAQA: - TS locations agreed and new applications forms shared a month ago for ER/PMC to manage. TAQA to officially confirm voltage levels and required power will be supplied. - Additional information (Phase Unbalance Study 400kV TAQA, updated SLD for TAQA...) submitted through EPFM. - MV TCs locations and power supply last version delivered Dec. 2024. DEWA: - TS locations agreed (officially submitted from ER to DEWA after agreement reached). Voltage levels and demanded power confirmed. - MV TCs locations and power supply last version delivered Dec. 2024. SEWA - TS location not agreed (Sharjah), although system configuration and requests initially presented and favourable engagement perceived. Voltage levels and demanded power presented but not confirmed. - Letter on border exemption shared on 22nd with ER, feedback received yesterday to amend it. | Note SEI | ASAP |
|  |  | Cybersecurity and Security: - Cyber Security TS version 02 came with code 1. v03 will be shared asap (GSM-R update of references). - Security Systems TS updated and shared with ER/PMC with the fencing and CCTV requirements agreed with ER Security. - STRA (ver AC) received code 2, SEI JV to resubmit addressing the comments. Slides required by Abu Dhabi Police shared yesterday with ER for action | ER/PMC ER/PMC ER/PMC | ASAP ASAP ASAP |
| - 10 | AOB | Performance Bond & Legal Form to be provided by SEI. | SEI | ASAP |
| Prepared by: |  | Vicky Chou |  |  |
| Reviewed, & approved by: |  | Javier Valero |  |  |
| Next Meeting: |  | 10/06/2025 |  |  |