| MINUTES OF MEETING |  |  |  |  |  |  |  | Date: |  | 18/02/2025 |  |  |  |  |  |  | Time: |  | 17:00-18:00 |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  |  | Location: |  | TEAMS virtual meeting |  |  |  |  |  |  |  |  |  |  |  |
| Reference Number: |  |  |  | mom_value |  |  |  | Subject: |  | Package F - SA Progress Meeting No. 11 |  |  |  |  |  |  |  |  |  |  |  |
| Attendees |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No. |  | Name |  |  |  |  |  | Title |  |  | Unit/Organization |  |  |  |  |  |  |  |  |  |  |
|  |  | Andries Laubscher |  |  |  |  | Rolling Stock Manager |  |  |  |  |  |  |  |  |  |  | Etihad Rail |  |  |  |
|  |  | Rita Ribeiro |  |  |  |  | System Assurance Engineer |  |  |  |  |  |  |  |  |  |  | Hafeet Rail |  |  |  |
|  |  | Wael Alnahdi |  |  |  |  | Rolling Stock Engineer |  |  |  |  |  |  |  |  |  |  | Hafeet Rail |  |  |  |
|  |  | Alexandros Avgerinos (Chair) |  |  |  |  | System Assurance Manager |  |  |  |  |  |  |  |  |  |  | Systra |  |  |  |
|  |  | Mayank Sharma |  |  |  |  | Requirements Expert |  |  |  |  |  |  |  |  |  |  | Systra |  |  |  |
|  |  | Imran Zaib |  |  |  |  | Rolling Stock Manager |  |  |  |  |  |  |  |  |  |  | Systra |  |  |  |
|  |  | Samir Aib |  |  |  |  | E-ISA Project Director |  |  |  |  |  |  |  |  |  |  | Bureau Veritas |  |  |  |
|  |  | Drago Repas |  |  |  |  | Project Manager |  |  |  |  |  |  |  |  |  |  | Progress Rail |  |  |  |
|  |  | Russell Kubycheck |  |  |  |  | System Assurance Manager |  |  |  |  |  |  |  |  |  |  | Progress Rail |  |  |  |
|  |  | Denis Melas |  |  |  |  | ETCS Lead |  |  |  |  |  |  |  |  |  |  | Progress Rail |  |  |  |
|  |  | Abhay Negi |  |  |  |  | Commercial & Contract Manager |  |  |  |  |  |  |  |  |  |  | Progress Rail |  |  |  |
|  |  | Ola Tannous |  |  |  |  | Safety Expert |  |  |  |  |  |  |  |  |  |  | Progress Rail |  |  |  |
|  |  | Cristina Santos |  |  |  |  | Safety Lead |  |  |  |  |  |  |  |  |  |  | Progress Rail |  |  |  |
|  |  | Hassaan Nasir |  |  |  |  | Reliability Lead |  |  |  |  |  |  |  |  |  |  | Progress Rail |  |  |  |
|  |  | Jerry Borger |  |  |  |  | C-ISA Assessor |  |  |  |  |  |  |  |  |  |  | Ricardo |  |  |  |
| Apologies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | Pedro Melim |  |  |  |  | Rail Sys. & Technology Director |  |  |  |  |  |  |  |  |  |  | Hafeet Rail |  |  |  |
|  |  | Malcolm Peart |  |  |  |  | Project Director |  |  |  |  |  |  |  |  |  |  | Systra |  |  |  |
|  |  | Sebastien Billot |  |  |  |  | Engineering Lead – SYS & RS |  |  |  |  |  |  |  |  |  |  | Systra |  |  |  |
|  |  | Wilson Sander |  |  |  |  | C-ISA Assessor |  |  |  |  |  |  |  |  |  |  | Ricardo |  |  |  |
|  |  | Mario Viggiani |  |  |  |  | Project Manager |  |  |  |  |  |  |  |  |  |  | PRS |  |  |  |
|  |  | Filippo Salotti |  |  |  |  | Product Manager |  |  |  |  |  |  |  |  |  |  | PRS |  |  |  |
| Meeting Agenda |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - Comments on Previous Minutes / General - Contractor’s SA Organisation - Design Progress - System Assurance Progress - SA Interface with Other Parties - SA Audits - Safety Notices - Requirements Management |  |  |  |  |  |  |  |  | - Configuration Management - EMC, E&B, Lightning Protection - Human Factors & Ergonomics - Fire & Life Safety - Security Management - Software Management - Verification, Testing & Acceptance - A.O.B |  |  |  |  |  |  |  |  |  |  |  |  | - Configuration Management - EMC, E&B, Lightning Protection - Human Factors & Ergonomics - Fire & Life Safety - Security Management - Software Management - Verification, Testing & Acceptance |
| Comments on Previous Minutes / General |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Item | Subject |  |  |  | Comments / Actions |  |  |  |  |  |  |  |  |  | Action By |  |  |  |  | Due Date |  |
| Meeting Minutes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Item | Subject |  |  |  |  | Comments / Actions |  |  |  |  |  |  |  |  |  | Action By |  |  |  |  | Due Date |
|  | Contractor’s SA Organisation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 1.1 | Status |  |  |  | Package F appointed Ricardo as the C-ISA for locomotives Onboard ETCS will be delivered/certified by PRS [10/12/24] The nomination of the ETCS C-ISA is still pending The SA progress meeting was conducted without the PRL SAM (due to leave) [07/01/25] RINA will be the C-ISA for PRS (onboard ETCS) [21/01/25] RINA engagement to start asap with the review of the ETCS PHA, in addition to the rest of the SA deliverables for not delaying the closure of DCP2 and the ETCS PDSC [04/02/25] RINA is already onboard and started assessing ETCS SA deliverables RINA to submit the C-ISA assessment plan. A copy to be sent to PMEC for info [18/02/25] No change for SA RINA to provide the Org Chart to prove independence from the RINA team under Package D Integration The E-ISA raised a concern regarding the independence of RINA C-ISA for the onboard ETCS and RINA C-ISA for the Pkg D works. Post meeting Note: PRL confirmed that RINA Services (assessment for the onboard) is different and independent to RINA Consulting (consultancy for Pkg D scope). |  |  |  |  |  |  |  |  | Note PRS Note |  |  |  |  |  | 24-Dec-24 Completed |  |
|  | Design Progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 2.1 | Programme |  |  |  | Design Milestone Dates DCP1; DCP2; DCP3; DCP3F. Contract; 16-Sep-24; 3-Jan-25; 2-Jun-25. Planned; 1-Dec-24; 3-Jan-25. Forecast; 17-Jan-25 28-Feb-25 21-Mar-25; 28-Feb-25 21-Mar-25. [18/02/25] Table updated, subject to Recovery Plan | Info |  |
| - 2.2 | Design Submissions Status |  |  |  | DCP0/DCP1; 26 Nov; 07 Jan; 21 Jan; 4 Feb; This meeting. Code 1; 22; 27; 31; 29; 32. Code 2; 13; 8; 8; 7; 6. Code 3; 0; 0; 1; 1; 0. Code 4; 1; 3; 1; 0; 0. Code 5; 0; 0; 0; 0; 0. Draft; 4; 2; 1; 1; 0. Under Review; 6; 5; 2; 6; 6. Total; 46; 45; 44; 44; 44. DCP2; 26 Nov; 07 Jan; 21 Jan; 4 Feb; This meeting. Code 1; 1; 14; 14; 15; 18. Code 2; 2; 7; 7; 10; 7. Code 3; 0; 0; 2; 3; 3. Code 4; 0; 2; 3; 3; 3. Code 5; 0; 0; 0; 0; 0. Draft; 33; 16; 15; 12; 10. Under Review; 9; 7; 5; 3; 5. Total; 45; 46; 46; 46; 46. [18/02/25] Tables updated | Info |  |
| - 2.3 | Design Assumptions |  |  |  | [07/01/25], [21/01/25], [04/02/25] [18/02/25] Nothing to report |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Info |  |
|  | System Assurance Progress |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 3.1 | System Assurance Deliverables |  |  |  | Document discipline codes: GAM, GCM, GEH, GER, GMS, GSE DCP0/DCP1; 10 Oct; 07 Jan; 21 Jan; 4 Feb; This meeting. Code 1; 12; 15; 16; 16; 18. Code 2; 6; 4; 4; 3; 2. Code 3; 0; 0; 1; 1; 0. Code 4; 0; 1; 0; 0; 0. Code 5; 0; 0; 0; 0; 0. Draft; 5; 2; 1; 1; 0. Under Review; 0; 1; 0; 1; 2. TOTAL; 23; 23; 22; 22; 22. DCP2; 10 Oct; 07 Jan; 21 Jan; 4 Feb; This meeting. Code 1; 1; 4; 4; 5; 6. Code 2; 6; 6; 6; 6; 7. Code 3; 2; 0; 2; 3; 3. Code 4; 0; 2; 3; 3; 3. Code 5; 0; 0; 0; 0; 0. Draft; 18; 12; 13; 11; 9. Under Review; 2; 6; 2; 2; 2. TOTAL; 29; 30; 30; 30; 30. [18/02/25] Table updated. PRL has started submitting DCP3 deliverables DSR should be finalised by next week. The DSR with an SA filter to be forwarded to E-ISA on a weekly basis. | Info |  |
| - 3.2 | Safety Issues |  |  |  | [07/01/25] DCP1 PHA was never submitted, and no workshop was scheduled. This is a major delay. Scheduled for 10-Jan-25. Yet, DCP 2 IHA/MHA was submitted without a workshop taking place, received Code 4 DCP2 Hazard Log was also submitted, received Code 4 DCP2 Design Safety Review was submitted without a workshop taking place, received Code 4 SIL Determination Report is still Code 3 due to lack of info from PRS [21/01/25] PHA workshop for the ETCS was held on 17-Jan-25. The E-ISA raised some concerns on missing hazards for the Specific application. RINA to assess the PHA and issue assessment report. Contractor to address concerns and issue PHA Rev AA report to PMEC for review [04/02/25] E-ISA raised SN0002 on the PHA workshop process. PRL to issue PHA Report and respond to the E-ISA. PRL to request a meeting with the E-ISA to review comments. [18/02/25] PHA was submitted, under PMEC review. SHA workshop held on 11-Feb-25, report to be issued 18-Feb-25 IHA workshop held on 12-Feb-25, report to be issued 19-Feb-25 subject to C-ISA review Design Safety Review meeting held on 14-Feb-25, report to be issued 19-Feb-25 subject to C-ISA review. Safety Notice SM 001 not yet responded |  |  |  |  |  |  | PRL PRL/PRS PRL/PRS |  |  |  |  |  |  |  | 10-Jan-25 Completed 28-Jan-25 6-Feb-25 Completed |  |
| - 3.3 | RAM issues |  |  |  | [07/01/25] Nothing to report [21/01/25] RAM Plan for ETCS is Code 3, a CRM was held on 21-Jan-25 to resolve open comments. To be resubmitted by 28-Jan-25 [04/02/25] RAM Plan not yet resubmitted. QRA Rev AA was submitted. PMEC to review by 11-Feb-25 [18/02/25] QRA Rev AA, is now Code 3. To be resubmitted FFA & IFA was submitted, under PMEC review |  |  |  |  |  |  | PRL PMEC |  |  |  |  |  |  |  | 28-Jan-25 11-Feb-25 |  |
| - 3.4 | Hazards Status |  |  |  | [07/01/25], [21/01/25] No hazards have been uploaded into ComplyPro [04/02/25] Hazards have been uploaded in CP, linking to CMs is pending. [18/02/25] Linking between Hazards and CMs was completed by 17-Feb-25. New training session on the hazard management process will be arranged by PMEC/Bentley for next week |  |  |  |  |  |  | Info |  |  |  |  |  |  |  |  |  |
| - 3.5 | CMs Status |  |  |  | [07/01/25], [21/01/25], [04/02/25] [18/02/25] Nothing to report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 3.6 | Safety Case Status |  |  |  | PDSC; Planned Date; Actual date; Status. Rev AA; 4-Mar-25. [07/01/25] New date to be confirmed on tomorrow’s progress meeting [21/01/25] Recovery Plan not yet submitted to PMEC, new dates to be provided by the next meeting [04/02/25] Recovery plan submitted, DCP2 to be completed by 28-Feb-25. PRL confirmed PDSC first submission date of 28-Feb-25 (including C-ISA report) This contradicts the recovery plan for closure of DCP2 by 28-Feb-25. To be further discussed [18/02/25] New date for first submission of the PDSC is 4-Mar-25 (including the GASC) | 3-Dec-24 TBC 08-Jan-25 04-Feb-25 Completed |  |
| - 3.7 | Onboard ETCS Progress (PRS) |  |  |  | Onboard Signalling is developed by PRS (ECM) in Italy [07/01/25] DSR Rev AF is now Code 2 with few comments open To be confirmed by the next meeting [21/01/25] PRS contribution to the PRL SA documents has been progressed, but the final DSR is pending approval. PMEC comments were sent to PRL on 21-Jan-25. New workshop to be held on 24-Jan-25 to finalise DSR [04/02/25] PRL and PRS deliverables were discussed in a workshop on 28-Jan-25. PRL to submit revised DSR. Ongoing. PRL/PRS discussed options to expedite closure of DCP3F in line with the project timeline. PRL to present new dates after the planned meeting with Employer on 5-Feb-25. [18/02/25] Progress is ingoing. PRL/PRS ICD is complete. Electrical schematic under discussion. The Baseline GASC certification is on schedule on the Italian project, no delay foreseen. PRL to receive certified GASC by 17-Mar-25 |  |  |  |  |  |  | PMEC PRL |  |  |  |  |  |  |  | 24-Jan-25 Completed 18-Feb-25 |  |
|  | SA Interface with Other Parties |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 4.1 | ICDs |  |  |  | Status of ICDs With Package; A; B; C; D; G; H; I2; ER Stg2. Draft; 0; 0; 0; 1; -; -; -; -. Submitted; 1; 1; 1; 2; -; -; -; -. Code 2; 0; 0; 0; 0. Code 1; 1; 1; 1; 0. [18/02/25] Table updated | Info |  |
| - 4.2 | CM Transfer |  |  |  | CMs transferred to Other Parties To Package; A/B/C; D; G; H; I1; I2; Operator. Submitted. Signed. CMs transferred from Other Parties From Package; A/B/C; D; G; H; I1; I2; Operator. Submitted. Signed. [18/02/25] Nothing to report | Info |  |
|  | SA Audits |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 5.1 | Contractor Audits |  |  |  | [07/01/25] For PRL only, planned for end of next week [21/01/25] PRL internal SA audit is scheduled for 21-Jan-25 [04/02/25] Internal PRL SA Audit conducted on 21-Jan-25. No major findings. [18/02/25] Item closed |  |  |  |  |  |  | PRL |  |  |  |  |  |  |  | TBC 17-Jan-25 21-Jan-25 Closed |  |
| - 5.2 | PMEC Audits |  |  |  | [07/01/25] Audit planned for 10-Jan-25. Notification sent to Contractor [21/01/25] PMEC SA audit was held on 10-Jan-25. Report to be issued by 24-Jan 25 [04/02/25] PMEC to issue evidence list by 7-Feb-25 [18/02/25] PMEC to issue evidence by 28-Feb-25 |  |  |  |  |  |  | Note PMEC |  |  |  |  |  |  |  | 10-Jan-25 Completed 24-Jan-25 7-Feb-25 28-Feb-25 |  |
| - 5.3 | C-ISA Audits |  |  |  | [07/01/25] To be confirmed at a later stage [21/01/25], [04/02/25], [18/02/25] The C-ISA SA audit to be held after the Detailed Design stage |  |  |  |  |  |  | Note |  |  |  |  |  |  |  |  |  |
| - 5.4 | E-ISA Audits |  |  |  | [07/01/25], [21/01/25], [04/02/25], [18/02/25] Nothing scheduled as yet |  |  |  |  |  |  | Note |  |  |  |  |  |  |  |  |  |
|  | Safety Notices |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 6.1 | C-ISA |  |  |  | SN No.; Related Document; Closed Observ.; To be responded by (party & status). 50863-150; SA Plan; 1/1; Closed. 50863-146/144; Safety Mngt Plan; 4/4; Closed. 50863-153; Safety V&V Plan; 1/1; Closed. 50863-112; HF & Ergonomics Plan; 1/1; Closed. 50863-160; SA Change Analysis; 1/1; Closed. 50863-169/ 170/172/173; Cross Acceptance Initial Ap.; 4/4; Closed. 50863-174-176; Cross Acceptance Procedure; 3/3; Closed. 50863-178; Fire Engineering Mngt Plan; 1/1; Closed. 50863-201; Assumptions Register; 1/1; Closed. 50863-202; PHA Analysis Report; 1/1; Closed. 50863-223; Safety Critical Items List (SCIL); 1/1; Closed. 50863-177; Supplier’s ISA Remit; 1/1; Closed. 50863-219 50863-220; Requirements Management Plan; 0/2; PRL C-ISA; Open. 50863-221; Safety Integrity Level (SIL) Determination Report; 1/1; Closed. 50863-222; System Assurance Audit Plan; 0/1; PRLC-ISA; Open. 50863-226/227; FFA, IFA Report; 2/2; Closed. 50863-231; SHA Report; 0/1; C-ISA; Open. [18/02/25] Table updated PRL to request RINA to provide status of assessments PRS PHA was assessed by RINA, details to be provided in the next meeting | Note |  |
| - 6.2 | E-ISA |  |  |  | SN No.; Rev; Related Document; Open Observ.; To be responded by (party & date). SN0002; 01; PHA ETCS onboard workshop; 4; PRL; 7-Feb-25 28-Feb-25. [18/02/25] Nothing to report | Note |  |
|  | Requirements Management - ComplyPro |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 7.1 | Contractual Requirements |  |  |  | [07/01/25] DCP1 Requirements Compliance Report was submitted, Code 4, document to become obsolete DCP2 Requirements Compliance Report was submitted showing minimum progress. It is Code 4 due to wrong discipline number. PMEC are reviewing the Acceptance Criteria for allocation. The Interface Register has some issues, Bentley to resolve by end of week. PRL report some issues on the evidence module. [21/01/25] Splitting of certain requirements has been completed. Bentley will upload verification criteria and other fields relating to cross acceptance. Training session was held last week. Requirements apportionment is ongoing [04/02/25] Requirements, Scope of Supply doc completed, Technical Specifications doc still in VAC stage Bentley has prepared the Derived requirements module in CP Interface hazard module to be live by 7-Feb-25 [18/02/25] For the scope document progress is 100% for allocation and VAC. For the Loco Tech Spec document progress is 50% for allocation. PMEC review is ongoing |  |  |  |  |  |  | PMEC PRL |  |  |  |  |  |  |  | 10-Jan-25 Completed 18-Feb-25 4-Mar-25 |  |
| - 7.2 | Derived Requirements |  |  |  | [07/01/25], [21/01/25], [04/02/25], [18/02/25] Nothing to report |  |  |  |  |  |  | Note |  |  |  |  |  |  |  |  |  |
|  | Configuration Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 8.1 | Submission Status |  |  |  | [07/01/25] Configuration Mngt Plan is now Code 1 [04/02/25] PRL DCP2 Configuration audit scheduled for 13-Feb-25 [18/02/25] Configuration Baseline Report Rev AA issued, PMEC to review |  |  |  |  |  |  | Note PRL |  |  |  |  |  |  |  | 20-Dec-24 Closed 13-Feb-25 |  |
|  | EMC, E&B, Lightning Protection |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 9.1 | Submission Status |  |  |  | [15/10/24] EMC Mngt Plan is Code 1 [18/02/25] EMC Risk Analysis & Risk Log submitted, under PMEC review |  |  |  |  |  |  | PRL |  |  |  |  |  |  |  | Closed |  |
|  | Human Factors & Ergonomics |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 10.1 | Submission Status |  |  |  | [07/01/25] HF & E Plan is now Code 1 [04/02/25] C-ISA safety notice closed |  |  |  |  |  |  | PRL Note |  |  |  |  |  |  |  | 13-Dec-24 Closed |  |
|  | Fire and Life Safety |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 11.1 | Submission Status |  |  |  | [07/01/25] The Fire Engineering Plan is now Code 1 [04/02/25] C-ISA safety notice closed |  |  |  |  |  |  |  | PRL Note |  |  |  |  |  |  | Closed |  |
|  | Security Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 12.1 | Submission Status |  |  |  | [07/01/25] Security Mngt Plan Rev AB is now Code 2 [21/01/25], Security Mngt Plan Rev AC to be submitted, date TBC [04/02/25], [18/02/25] No new date has been provided by PRL |  |  |  |  |  |  |  | PRL |  |  |  |  |  |  | TBC |  |
|  | Software Management |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 13.1 | Submission Status |  |  |  | [07/01/25] The Software Config Mngt Plan is now Code 1 SQAP resubmission still pending, expecting info from PRS [21/01/25] No progress on the SQAP resubmission. Ricardo/TUV Nord to assess and issue Safety Note [04/02/25] To be resubmitted by 7-Feb-25 [18/02/25] Under TUV Nord review, date to be confirmed in the next meeting |  |  |  |  |  |  | PRL |  |  |  |  |  |  |  | TBC 7-Feb-25 4-Mar-25 |  |
|  | Verification, Testing & Acceptance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 14.1 | Submission Status |  |  |  | [07/01/25] VTA Plan Rev AC is now Code 1 |  |  |  |  |  |  | PRL |  |  |  |  |  |  |  | 24-Dec-24 Closed |  |
|  | Any Other Business |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 15.1 | Absence from work |  |  |  | The next scheduled meeting is on 4-Feb-25. PRL SAM will be absent, the PRL SA progress will be reported by the Safety Expert Ola Tannous |  |  |  |  |  |  | Note |  |  |  |  |  |  |  |  |  |
| - 15.2 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 15.3 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Attachments |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| - 16.1 | Presentation |  |  |  | None |  |  |  |  |  |  |  |  |  |  |  |  |  |  | Info |  |
| Prepared by: |  |  | Alexandros Avgerinos, SAM, PMEC |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Reviewed, & approved by: |  |  | Hafeet Rail, PMEC & HAS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Next Meeting: |  |  | 04-Mar-25, 17:00 hrs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Attendance List (extracted for TEAMS)

Package F – DSR Tracker as of 14-Feb-25