Table 3.1a Timing of the different Work Packages and their components (Gantt Chart)
WPs/Tasks	YEAR 1				YEAR 2				YEAR 3				YEAR 4
WP1 – The INPUT-HEART phenomapping platform	Q1	Q2	Q3	Q4	Q1	Q2	Q3	Q4	Q1	Q2	Q3	Q4	Q1	Q2	Q3	Q4
Task 1.1: Composing a database inventory
Task 1.2: Conceptual harmonisation of the available databases
Task 1.3: Completeness of the databases and communication of the federated learning procedure
Task 1.4: A blueprint for a phenomapping platform
WP2 - Cardiac imaging phenomapping for early cardiovascular risk prediction
Task 2.1: Software for standardizing the extraction and analysis of cardiac motion/deformation data
Task 2.2: Assessment of cardiac spatiotemporal motion/deformation abnormalities using the big population data
Task 2.3: Machine learning approaches for precision cardiac phenomaps
Task 2.4: Deep phenotyping through personalized mechanistic modeling of cardiovascular physiology
WP3 – Circulating biomarkers (proteomics) for the early detection of heart disease and risk stratification
Task 3.1: Sample transfer to Olink Proteomics AB, Uppsala, Sweden
Task 3.2: Measurements of circulating biomarkers using PEA platform in the discovery and validation cohorts
Task 3.3: Integration of biomarkers profile and predictive modelling
Task 3.4: Developing a custom multiplex platform
WP4 - Machine learning for CV risk stratification and outcome prediction
Task 4.1: Exploratory phase
Task 4.2: Pre-processing of the available training data
Task 4.3: Selection of machine learning models
Task 4.4: Design of the experimental procedure, implementation of the algorithms and model comparisons
Task 4.5: Joint risk modelling
Task 4.6: Models diagnostics and improving of code of the final machine learning